## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Preparation
section | Details
checkpoint | Check Area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
checkpoint | Apply Moisture Fix if required for job
checkpoint | Disc purged material
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply prep compound
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
section | Installation
checkpoint | Confirm vinyl layout direction
checkpoint | Install as per specification - Carry out vinyl installation as per spec
checkpoint | Install coving & capping/sealant as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Tile Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required as per plan
section | Installation
checkpoint | Confirm carpet tile pattern direction/layout
checkpoint | Install carpet tiles as per specifications
checkpoint | Install trims as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL