## Sheet1
ConQA Team Notes:
Document Title: |  | CHK-12-STR-HOP-Precast Material Inspection
ITP Description: |  | HOP-Precast Material Inspection
Discipline (e.g. CIV/STR/RAIL: |  | 12-STR
Revision Number: |  | 0
Revision Date: |  | 2025-08-05
ITP created by: |  | Manwel/Cedric
ITP approved for use by: |  | Pradeep Talasila |  |  |  |  | Details
Special Notes to ConQA Team : |  | ITP available for Hopkins Road
Inspection & Test Plan - Precast Deliveries
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2025-08-04
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Delivery Details |  | Enter: Delivery Docket Number: [Free text box]: Enter:Delivery Date: [Free text box]: Enter:Element ID (s): [Free text box]: Attach: Delivery Docket and packaging Slip | Document Review Visual | Each Delivery | IP | PE/SE | This Checklist
2 | Packaging Inspection-Quantity |  | Does the number of packages/items in the delivery match that listed on the freight list and/or docket? | Visual | Each Delivery | IP | PE/SE | This Checklist
3 | Packaging Inspection-Delivery Contents |  | Have the correct precast elements been delivered? Check labels/markings, birth certificates and check actual dimensions against dwgs to make sure. Check that elements have the correct number of lifting points and hold-down brackets. | Document Review Visual | Each Delivery | IP | PE/SE | This Checklist
4 | Packaging Inspection-Birth Certificate |  | Is the delivery accompanied by Precast items Birth Certificates? Precast components are to be marked on the birth certificate. Cast date and lot are to be marked on the birth certificate. ATTACH: BIRTH CERTIFICATES | Document Review | Each Precast item | IP | PE/SE | Birth Certificate
5 | Product Verification prior to delivery | VR620.08 | Prior to delivery have the following evidence been provided: 1-Validation that the concrete strength is as per the 28-day strength in IFC (40MPa or 50MPa) 2-Validation that the precast elements are least 7 days (168 hours) old? | Document Review | Each Precast Item | IP | PE/SE | Concrete Test Reports Birth Certificate
6 | Packaging Inspection-Transport |  | Is the condition of packaging acceptable. Precast items are protected from damage during the transport. Check for cracking or damage around dunnage locations. Are the Ferrules capped with a protective cap | Visual | Each Precast item | IP | PE/SE | This Checklist
7 | Product Inspection - Markings | VR620.06 | Are markings of the element on each element and approximately 40mm high? | Visual | Each Precast item | IP | PE/SE | This Checklist
8 | Product Inspection - Reinforcement & Cast-in items | VR620.04 | 1-Has any of the projecting reinforcement been damaged? 2-Are bars as per shop drawings and within tolerance (±3 mm)? | Visual Measure | Each Precast item | IP | PE/SE | This Checklist
9 | Product Inspection - Dimensional Tolerances |  | Have the dimensions of the item been verified? 1-Validation of dimensions 2-Validation of cast-in locatios 3-Validation of Hog (if referring to beams) | Visual Measure | Each Precast item | IP | PE/SE | This Checklist
10 | Pre-Lift Inspection-Transport |  | Are the elements stacked in the correct way to allow for lifting per the approved lift plan? Check lifting points for damage to concrete or lifters. Is there safe access to lifting points and elements can be lifted without damaging the element. | Visual | Each Precast item | IP | PE/SE | This Checklist
11 | Fault IDs: |  | For each precast type delivered, check for the following: 1-Identification markings match the panel type 2-Element fabricated as per drawings 3-Cracks 4-Spalling/Damage to concrete surface 5-Exposed Reinforcement 7-Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design 8-Cast-in items incorrect or damaged inc bolts, hold-down brackets, conduits etc. | Visual | Each Precast item | IP | PE/SE | This Checklist
12.1 | Check for Faults - 1 | Item 7 on this Checklist | For Each Precast type delivered: Enter: Panel Identification:[FREE TEXT BOX]: Enter:Quantity:[FREE TEXT BOX]: Enter:Fault ID if any:[FREE TEXT BOX]: | Visual Measure | Each precast type delivered | IP | PE/SE | This Checklist
12.2 | Check for Faults - 2 | Item 7 on this Checklist | For Each Precast type delivered: Enter: Identificatio:[FREE TEXT BOX]: Enter:Quantity:[FREE TEXT BOX]: Enter:Fault ID if any:[FREE TEXT BOX]: | Visual Measure | Each precast type delivered | IP | PE/SE | This Checklist
12.3 | Check for Faults - 3 | Item 7 on this Checklist | For Each Precast type delivered: Enter: Identificatio:[FREE TEXT BOX]: Enter:Quantity:[FREE TEXT BOX]: Enter:Fault ID if any:[FREE TEXT BOX]: | Visual Measure | Each precast type delivered | IP | PE/SE | This Checklist
12.4 | Check for Faults - 4 | Item 7 on this Checklist | For Each Precast type delivered: Enter: Identificatio:[FREE TEXT BOX]: Enter:Quantity:[FREE TEXT BOX]: Enter:Fault ID if any:[FREE TEXT BOX]: | Visual Measure | Each precast type delivered | IP | PE/SE | This Checklist
12.5 | Check for Faults - 5 | Item 7 on this Checklist | For Each Precast type delivered: Enter: Identificatio:[FREE TEXT BOX]: Enter:Quantity:[FREE TEXT BOX]: Enter:Fault ID if any:[FREE TEXT BOX]: | Visual Measure | Each precast type delivered | IP | PE/SE | This Checklist
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /