## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CHK-12-STR-HOP-Precast Material Inspection | [5 empty] | CHK-12-STR-HOP-Precast Material Inspection Rev 0
section | Details
checkpoint-no-value | Referenced Documentation
label | Document Title: CHK-12-STR-HOP-Precast Material Inspection
label | ITP Description: HOP-Precast Material Inspection
label | Discipline (e.g. CIV/STR/RAIL): 12-STR
label | Revision Number: 0
label | Revision Date: 5/08/2025
label | ITP created by: Manwel/Cedric
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1 - Delivery Details
label | Acceptance Criteria - Enter: Delivery Docket Number: [Free text box]:
textbox | Enter: Delivery Date:
textbox | Enter: Element ID (s):
label | ○ Attach: Delivery Docket and packaging Slip
label | Method - Document Review, Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 2 - Packaging Inspection-Quantity
label | Acceptance Criteria - Does the number of packages/items in the delivery match that listed on the freight list and/or docket?
label | Method - Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 3 - Packaging Inspection-Delivery Contents
label | Acceptance Criteria - Have the correct precast elements been delivered? Check labels/markings, birth certificates and check actual dimensions against dwgs to make sure. Check that elements have the correct number of lifting points and hold-down brackets.
label | Method - Document Review, Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 4 - Packaging Inspection-Birth Certificate
label | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
label | ○ Precast components are to be marked on the birth certificate.
label | ○ Cast date and lot are to be marked on the birth certificate.
label | ○ ATTACH: BIRTH CERTIFICATES
label | Method - Document Review
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Birth Certificate
date | Date Completed:
checkpoint | 5 - Product Verification prior to delivery
label | Reference - VR620.08
label | Acceptance Criteria - Prior to delivery have the following evidence been provided:
label | 1 - Validation that the concrete strength is as per the 28-day strength in IFC (40MPa or 50MPa)
label | 2 - Validation that the precast elements are least 7 days (168 hours) old?
label | Method - Document Review
label | Frequency - Each Precast Item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Concrete Test Reports, Birth Certificate
date | Date Completed:
checkpoint | 6 - Packaging Inspection-Transport
label | Acceptance Criteria - Is the condition of packaging acceptable.
label | ○ Precast items are protected from damage during the transport. Check for cracking or damage around dunnage locations.
label | ○ Are the Ferrules capped with a protective cap
label | Method - Visual
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Product Inspection - Markings
label | Reference - VR620.06
label | Acceptance Criteria - Are markings of the element on each element and approximately 40mm high?
label | Method - Visual
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 8 - Product Inspection - Reinforcement & Cast-in items
label | Reference - VR620.04
label | Acceptance Criteria - 1 - Has any of the projecting reinforcement been damaged?
label | 2 - Are bars as per shop drawings and within tolerance (±3 mm)?
label | Method - Visual, Measure
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 9 - Product Inspection - Dimensional Tolerances
label | Acceptance Criteria - Have the dimensions of the item been verified?
label | 1 - Validation of dimensions
label | 2 - Validation of cast-in locatios
label | 3 - Validation of Hog (if referring to beams)
label | Method - Visual, Measure
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 10 - Pre-Lift Inspection-Transport
label | Acceptance Criteria - Are the elements stacked in the correct way to allow for lifting per the approved lift plan? Check lifting points for damage to concrete or lifters. Is there safe access to lifting points and elements can be lifted without damaging the element.
label | Method - Visual
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 11 - Fault IDs:
label | Acceptance Criteria - For each precast type delivered, check for the following:
label | 1 - Identification markings match the panel type
label | 2 - Element fabricated as per drawings
label | 3 - Cracks
label | 4 - Spalling/Damage to concrete surface
label | 5 - Exposed Reinforcement
label | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
label | 8 - Cast - in items incorrect or damaged inc bolts, hold - down brackets, conduits etc.
label | Method - Visual
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 12.1 - Check for Faults - 1
label | Reference - Item 7 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 12.2 - Check for Faults - 2
label | Reference - Item 7 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 12.3 - Check for Faults - 3
label | Reference - Item 7 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 12.4 - Check for Faults - 4
label | Reference - Item 7 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 12.5 - Check for Faults - 5
label | Reference - Item 7 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP