## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-302-CIV-CPD-Bollard Installation
ITP Number |  | 302
ITP Description: |  | CPD-Bollard Installation
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2025-07-25
ITP created by: |  | Andrew Carlini
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | Calder Park Drive LXRP
Inspection & Test Plan - Bollard Installation
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-07-25
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings S516 S517 VicRoads Section 610 VicRoads Section 630 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Materials
2.1 | Concrete | IFC Drawings | 25MPa concrete to be used as per IFC drawings. | Document Review | Each Mix | HP | SE/Site Supervisor | Supplier Certificate of Compliance
2.2 | Bollard, Chains | IFC Drawings AS41000 AS1163 S516 S517 | All Steel must comply with Australian Standards. Bollard sizes must be checked on site. | Document review Visual and Measure | All elements | HP | SE/Site Supervisor | Supplier Certificate of Compliance
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, bollard locations Offset checked against the running edge prior toinstallation of bollards. | Measure Visual | Each element | IP | Surveyor SE/PE | This ITP
4 | Construction / Installation Activities
4.1 | Excavation works | IFC Drawings | Excavation for bollard foundation must not undermine footing of existing structures. Follow asset owners guidelines for work around their service. Excavation must use Non Distructive Digging in the rail corridor | Visual |  | IP | SE/Site Supervisor | This ITP
4.2 | Ground Conditions | IFC Drawings | All bollard foundations to be inspected by the site team prior to installing the bollards. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Each bollard | IP | SE/Site Supervisor | This ITP
4.4 | Bollard Foundation | IFC Drawings | 25MPa concrete. Typical Footing: Footing dimension 650mm deep, diameter of min 350mm 140x140mm bollard to be installed 600mm deep. | Measure | Each footing | IP | SE/Site Supervisor | Concrete dockets
4.5 | Bollard Installation | IFC Drawings | Maximum post spacing to be 1650mm ctr Max. Bollard height 900mm above ground level. | Measure | Each bollard | IP | SE/Site Supervisor | This ITP Delivery Dockets
4.6 | Chain Installation | IFC Drawings | 8mm HDG Chain, with max 300mm sag 40mm hole in bollard, chain to be secured via 120x12mm HDG Hex Head Bolt | Visual | Each element | IP | SE/Site Supervisor | This ITP
5 | Post-construction / Post-installation Activities
5.1 | Bollard Alignment/Height | IFC Drawings | Bollards are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings. | Measure | Each lot | IP | SE/Site Supervisor | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /