## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-303-CIV-Permanent Cattle Fencing
ITP Description: |  | Permanent Cattle Fencing
Discipline (e.g. CIV/STR/RAIL: |  | 303-CIV
Revision Number: |  | 0
Revision Date: |  | 2025-08-05
ITP created by: |  | Andrew Carlini
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Calder Park Drive
Inspection & Test Plan - Permanent cattle Fencing
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-08-05
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | AS1657 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | SD3102 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Materials
2.1 | Concrete | IFC Drawings | 20 MPa concrete to be used as per IFC drawings. | Document Review | Each Mix | HP | SE/Site Supervisor
2.2 | Steel components including posts, wires and fittings | IFC Drawings AS1657 | All Steel must comply with Australian Standards. Steel section sizes must be checked on site. | Document review Visual and Measure | All elements | HP | SE/Site Supervisor | Supplier Certificate of Compliance
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, and fence start and end points. Offset checked against the running edge prior to installation of posts. | Visual and Measure | Each element | IP | Surveyor SE/PE | This ITP
4 | Construction / Installation Activities
4.1 | Excavation works | IFC Drawings SD3102 | Excavation completed by auger outside of service working limits. Follow asset owners guidelines for work around their service. | Visual | Each fence footing | IP | SE/Site Supervisor | This ITP
4.2 | Ground Conditions | IFC Drawings | All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Each post | IP | SE/Site Supervisor | This ITP
4.3 | Strainer Post Assemblies | IFC Drawings SD3102 | Single Strainer Assembly: Strainer Post to be 2300mm, with min 1100mm embedment into concrete footing, max height to be 1150mm above FSL. 1x Stay attached to strainer post approximately 400mm from top of post, to be 3000 to 3600mm long (As per manufacturers specification) and secured into the ground via a concrete anchor block. Double Strainer Assembly Strainer Post to be 2300mm, with min 1000mm embedment into concrete footing, max height to be 1150mm above FSL. 2x Stay's attached to strainer post approximately 400mm from top of post, to be 3000 to 3600mm long (As per manufacturers specification) and secured into the ground via a concrete anchor block. Double Strainer assembly required at intervals not exceeding 200 metres. | Measure | Each Strainer Post | IP | SE/Site Supervisor | This ITP Concrete Dockets
4.4 | Fence Post Installation | IFC Drawings SD3102 | Intermediate Posts to be 1800mm long, with Min. 650 embedment into the ground, Max. height to be 1150mm above FSL Intermediate Posts to be spaced every 6900mm, every third post 2.no Star Picket evenly spaced between Intermediate posts, 1800mm long with Min. 650 embedment into the ground, Max. height to be 1150mm above FSL. Bottom wire hole location to be located within 25 to 100mm of FSL | Measure | Each post | IP | SE/Site Supervisor | This ITP
4.3 | Fence Footing | IFC Drawings SD3102 | Footing only required at Strainer Posts. Footing dimensions 1200mm deep x 300mm diameter. 20 MPa concrete | Measure | Each footing | IP | SE/Site Supervisor | This ITP Concrete Dockets
4.5 | Wire Installation | IFC Drawings SD3102 | 2 No. 1.6dia High tensile barbed wire at the second and forth wires, 5 No. 2.5dia High tensile plain wire in all other locations. Wires are to spaced approximately 150mm apart (In accordance to SD3102). Wires shall be tightened and securely fastened to strainer posts. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips. | Visual | Each element | IP | SE/Site Supervisor | This ITP
4.6
5 | Post-construction / Post-installation Activities
5.1 | As-Built Survey | IFC Drawings | Posts are to be checked for verticality and ensure spacings do not exceed standards. | Measure | Each lot | IP | SE/Site Supervisor | This ITP
5.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /