## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-302-CIV-CPD-Bollard Installation | itp |  |  |  |  | ITP-302-CIV-CPD-Bollard Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-302-CIV-CPD-Bollard Installation
label | ITP Description: CPD-Bollard Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 25/07/2025
label | ITP created by: Andrew Carlini
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - IFC Drawings
label | ○ S516
label | ○ S517
label | ○ VicRoads Section 610
label | ○ VicRoads Section 630
section | 2. Materials
checkpoint | 2.1 - Concrete
label | Reference - IFC Drawings
label | Acceptance Criteria - 25MPa concrete to be used as per IFC drawings.
label | Method - Document Review
label | Frequency - Each Mix
label | Category - HP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Supplier Certificate of Compliance
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Bollard, Chains
label | Reference - IFC Drawings
label | ○ AS41000
label | ○ AS1163
label | ○ S516
label | ○ S517
label | Acceptance Criteria - All Steel must comply with Australian Standards.
label | ○ Bollard sizes must be checked on site.
label | Method - Document review, Visual and Measure
label | Frequency - All elements
label | Category - HP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Supplier Certificate of Compliance
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Pre-construction / Pre-installation Activities
checkpoint | 3.1 - Survey Set-out
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey to set out the following but not limited to: existing services, bollard locations
label | ○ Offset checked against the running edge prior toinstallation of bollards.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Construction / Installation Activities
checkpoint | 4.1 - Excavation works
label | Reference - IFC Drawings
label | Acceptance Criteria - Excavation for bollard foundation must not undermine footing of existing structures.
label | ○ Follow asset owners guidelines for work around their service.
label | ○ Excavation must use Non Distructive Digging in the rail corridor
label | Method - Visual
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Ground Conditions
label | Reference - IFC Drawings
label | Acceptance Criteria - All bollard foundations to be inspected by the site team prior to installing the bollards. All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | Method - Visual
label | Frequency - Each bollard
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.4 - Bollard Foundation
label | Reference - IFC Drawings
label | Acceptance Criteria - 25MPa concrete.
label | Typical Footing:
label | — Footing dimension 650mm deep, diameter of min 350mm
label | ○ 140x140mm bollard to be installed 600mm deep.
label | Method - Measure
label | Frequency - Each footing
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Concrete dockets
date | Date Completed:
checkpoint | 4.5 - Bollard Installation
label | Reference - IFC Drawings
label | Acceptance Criteria - Maximum post spacing to be 1650mm ctr
label | ○ Max. Bollard height 900mm above ground level.
label | Method - Measure
label | Frequency - Each bollard
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP, Delivery Dockets
date | Date Completed:
checkpoint | 4.6 - Chain Installation
label | Reference - IFC Drawings
label | Acceptance Criteria - 8mm HDG Chain, with max 300mm sag
label | ○ 40mm hole in bollard, chain to be secured via 120x12mm HDG Hex Head Bolt
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-construction / Post-installation Activities
checkpoint | 5.1 - Bollard Alignment/Height
label | Reference - IFC Drawings
label | Acceptance Criteria - Bollards are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | Method - Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-303-CIV-CPD-Permanent Cattle Fencing | itp |  |  |  |  | ITP-303-CIV-CPD-Permanent Cattle Fencing Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-302-CIV-CPD-Bollard Installation
label | ITP Description: CPD-Bollard Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 25/07/2025
label | ITP created by: Andrew Carlini
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - IFC Drawings
label | 1.2 - Non Dependent
label | Reference - AS1657
label | 1.3 - Non Dependent
label | Reference - SD3102
section | 2. Materials
checkpoint | 2.1 - Concrete
label | Reference - IFC Drawings
label | Acceptance Criteria - 20 MPa concrete to be used as per IFC drawings.
label | Method - Document Review
label | Frequency - Each Mix
label | Category - HP
label | Responsibility - SE/Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Steel components including posts, wires and fittings
label | Reference - IFC Drawings AS1657
label | Acceptance Criteria - All Steel must comply with Australian Standards.
label | ○ Steel section sizes must be checked on site.
label | Method - Document review, Visual and Measure
label | Frequency - All elements
label | Category - HP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Supplier Certificate of Compliance
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Pre-construction / Pre-installation Activities
checkpoint | 3.1 - Survey Set-out
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey to set out the following but not limited to: existing services, and fence start and end points.
label | ○ Offset checked against the running edge prior to installation of posts.
label | Method - Visual and Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Construction / Installation Activities
checkpoint | 4.1 - Excavation works
label | Reference - IFC Drawings SD3102
label | Acceptance Criteria - Excavation completed by auger outside of service working limits.
label | ○ Follow asset owners guidelines for work around their service.
label | Method - Visual
label | Frequency - Each fence footing
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Ground Conditions
label | Reference - IFC Drawings
label | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | Method - Visual
label | Frequency - Each post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Strainer Post Assemblies
label | Reference - IFC Drawings SD3102
label | Acceptance Criteria - Single Strainer Assembly:
label | ○ Strainer Post to be 2300mm, with min 1100mm embedment into concrete footing, max height to be 1150mm above FSL.
label | ○ 1x Stay attached to strainer post approximately 400mm from top of post, to be 3000 to 3600mm long (As per manufacturers specification) and secured into the ground via a concrete anchor block.
label | Double Strainer Assembly:
label | ○ Strainer Post to be 2300mm, with min 1000mm embedment into concrete footing, max height to be 1150mm above FSL.
label | ○ 2x Stay's attached to strainer post approximately 400mm from top of post, to be 3000 to 3600mm long (As per manufacturers specification) and secured into the ground via a concrete anchor block.
label | ○ Double Strainer assembly required at intervals not exceeding 200 metres.
label | Method - Measure
label | Frequency - Each Strainer Post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP, Concrete Dockets
date | Date Completed:
checkpoint | 4.4 - Fence Post Installation
label | Reference - IFC Drawings SD3102
label | Acceptance Criteria - Intermediate Posts to be 1800mm long, with Min. 650 embedment into the ground, Max. height to be 1150mm above FSL
label | ○ Intermediate Posts to be spaced every 6900mm, every third post
label | ○ 2.no Star Picket evenly spaced between Intermediate posts, 1800mm long with Min. 650 embedment into the ground, Max. height to be 1150mm above FSL.
label | ○ Bottom wire hole location to be located within 25 to 100mm of FSL
label | Method - Measure
label | Frequency - Each post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Fence Footing
label | Reference - IFC Drawings SD3102
label | Acceptance Criteria - Footing only required at Strainer Posts.
label | ○ Footing dimensions 1200mm deep x 300mm diameter.
label | ○ 20 MPa concrete
label | Method - Measure
label | Frequency - Each footing
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP, Concrete Dockets
date | Date Completed:
checkpoint | 4.5 - Wire Installation
label | Reference - IFC Drawings SD3102
label | Acceptance Criteria - 2 No. 1.6dia High tensile barbed wire at the second and forth wires, 5 No. 2.5dia High tensile plain wire in all other locations. Wires are to spaced approximately 150mm apart (In accordance to SD3102).
label | ○ Wires shall be tightened and securely fastened to strainer posts.
label | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-construction / Post-installation Activities
checkpoint | 5.1 - As-Built Survey
label | Reference - IFC Drawings
label | Acceptance Criteria - Posts are to be checked for verticality and ensure spacings do not exceed standards.
label | Method - Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP