## Folder Structure
Site QA
Zone | Level | Room No. | Checklist
Hotel | Lift Car
|  | Lift Car 1 | Unit Checklist
|  | Lift Car 2 | Unit Checklist
|  | Lift Car 3 | Unit Checklist
|  | Lift Car 4 | Unit Checklist
Ground Floor
|  | G.17 | Unit Checklist
|  | G.18 | Unit Checklist
|  | G.19 | Unit Checklist
|  | G.21 | Unit Checklist
Level 2
|  | 2.09 | Unit Checklist | Kitchen floor and splash back
|  | 2.1 | Unit Checklist | Entry room only
|  | 2.11 | Unit Checklist
|  | 2.18 | Unit Checklist
Level 3
|  | 302 | Unit Checklist
|  | 303 | Unit Checklist
|  | 304 | Unit Checklist
|  | 305 | Unit Checklist
|  | 306 | Unit Checklist
|  | 307 | Unit Checklist
|  | 308 | Unit Checklist
|  | 309 | Unit Checklist
|  | 310 | Unit Checklist
Level 4
|  | 402 | Unit Checklist
|  | 403 | Unit Checklist
|  | 404 | Unit Checklist
|  | 405 | Unit Checklist
|  | 406 | Unit Checklist
|  | 407 | Unit Checklist
|  | 408 | Unit Checklist
|  | 409 | Unit Checklist
|  | 410 | Unit Checklist
Level 5
|  | 502 | Unit Checklist
|  | 503 | Unit Checklist
|  | 504 | Unit Checklist
|  | 505 | Unit Checklist
|  | 506 | Unit Checklist
|  | 507 | Unit Checklist
|  | 508 | Unit Checklist
|  | 509 | Unit Checklist
|  | 510 | Unit Checklist
Level 6
|  | 602 | Unit Checklist
|  | 603 | Unit Checklist
|  | 604 | Unit Checklist
|  | 605 | Unit Checklist
|  | 606 | Unit Checklist
|  | 607 | Unit Checklist
|  | 608 | Unit Checklist
|  | 609 | Unit Checklist
|  | 610 | Unit Checklist
Level 7
|  | 702 | Unit Checklist
|  | 703 | Unit Checklist
|  | 704 | Unit Checklist
|  | 705 | Unit Checklist
|  | 706 | Unit Checklist
|  | 707 | Unit Checklist
|  | 708 | Unit Checklist
|  | 709 | Unit Checklist
|  | 710 | Unit Checklist
Level 8
|  | 802 | Unit Checklist
|  | 803 | Unit Checklist
|  | 804 | Unit Checklist
|  | 805 | Unit Checklist
|  | 806 | Unit Checklist
|  | 807 | Unit Checklist
|  | 808 | Unit Checklist
|  | 809 | Unit Checklist
|  | 810 | Unit Checklist
Level 9
|  | 902 | Unit Checklist
|  | 903 | Unit Checklist
|  | 904 | Unit Checklist
|  | 905 | Unit Checklist
|  | 906 | Unit Checklist
|  | 907 | Unit Checklist
|  | 908 | Unit Checklist
|  | 909 | Unit Checklist
|  | 910 | Unit Checklist
Level 10
|  | 1002 | Unit Checklist
|  | 1003 | Unit Checklist
|  | 1004 | Unit Checklist
|  | 1005 | Unit Checklist
|  | 1006 | Unit Checklist
|  | 1007 | Unit Checklist
|  | 1008 | Unit Checklist
|  | 1009 | Unit Checklist
|  | 1010 | Unit Checklist
Level 11
|  | 1102 | Unit Checklist
|  | 1103 | Unit Checklist
|  | 1104 | Unit Checklist
|  | 1105 | Unit Checklist
|  | 1106 | Unit Checklist
|  | 1107 | Unit Checklist
|  | 1108 | Unit Checklist
|  | 1109 | Unit Checklist
|  | 1110 | Unit Checklist
Level 12
|  | 1202 | Unit Checklist
|  | 1203 | Unit Checklist
|  | 1204 | Unit Checklist
|  | 1205 | Unit Checklist
|  | 1206 | Unit Checklist
|  | 1207 | Unit Checklist
|  | 1208 | Unit Checklist
|  | 1209 | Unit Checklist
|  | 1210 | Unit Checklist
Level 13
|  | 1302 | Unit Checklist
|  | 1303 | Unit Checklist
|  | 1304 | Unit Checklist
|  | 1305 | Unit Checklist
|  | 1306 | Unit Checklist
|  | 1307 | Unit Checklist
|  | 1308 | Unit Checklist
|  | 1309 | Unit Checklist
|  | 1310 | Unit Checklist
Level 14
|  | 1402 | Unit Checklist
|  | 1403 | Unit Checklist
|  | 1404 | Unit Checklist
|  | 1405 | Unit Checklist
|  | 1406 | Unit Checklist
|  | 1407 | Unit Checklist
|  | 1408 | Unit Checklist
|  | 1409 | Unit Checklist
|  | 1410 | Unit Checklist
Level 15
|  | 1502 | Unit Checklist
|  | 1503 | Unit Checklist
|  | 1504 | Unit Checklist
|  | 1505 | Unit Checklist
|  | 1506 | Unit Checklist
|  | 1507 | Unit Checklist
|  | 1508 | Unit Checklist
|  | 1509 | Unit Checklist
|  | 1510 | Unit Checklist
Level 15
|  | 1502 | Unit Checklist
|  | 1503 | Unit Checklist
|  | 1504 | Unit Checklist
|  | 1505 | Unit Checklist
|  | 1506 | Unit Checklist
|  | 1507 | Unit Checklist
|  | 1508 | Unit Checklist
|  | 1509 | Unit Checklist
|  | 1510 | Unit Checklist
Level 16
|  | 1602 | Unit Checklist
|  | 1603 | Unit Checklist
|  | 1604 | Unit Checklist
|  | 1605 | Unit Checklist
|  | 1606 | Unit Checklist
|  | 1607 | Unit Checklist
|  | 1608 | Unit Checklist
|  | 1609 | Unit Checklist
|  | 1610 | Unit Checklist
Level 17
|  | 1702 | Unit Checklist
|  | 1703 | Unit Checklist
|  | 1704 | Unit Checklist
|  | 1705 | Unit Checklist
|  | 1706 | Unit Checklist
|  | 1707 | Unit Checklist
|  | 1708 | Unit Checklist
|  | 1709 | Unit Checklist
|  | 1710 | Unit Checklist
Level 18
|  | 1802 | Unit Checklist
|  | 1803 | Unit Checklist
|  | 1804 | Unit Checklist
|  | 1805 | Unit Checklist
|  | 1806 | Unit Checklist
|  | 1807 | Unit Checklist
|  | 1808 | Unit Checklist
|  | 1809 | Unit Checklist
|  | 1810 | Unit Checklist
Level 19
|  | 1902 | Unit Checklist
|  | 1903 | Unit Checklist
|  | 1904 | Unit Checklist
|  | 1905 | Unit Checklist
|  | 1906 | Unit Checklist
|  | 1907 | Unit Checklist
|  | 1908 | Unit Checklist
|  | 1909 | Unit Checklist
|  | 1910 | Unit Checklist
Level 20
|  | 2002 | Unit Checklist
|  | 2003 | Unit Checklist
|  | 2004 | Unit Checklist
|  | 2005 | Unit Checklist
|  | 2006 | Unit Checklist
|  | 2007 | Unit Checklist
|  | 2008 | Unit Checklist
|  | 2009 | Unit Checklist
|  | 2010 | Unit Checklist
Level 21
|  | 2102 | Unit Checklist
|  | 2103 | Unit Checklist
|  | 2104 | Unit Checklist
|  | 2105 | Unit Checklist
|  | 2106 | Unit Checklist
|  | 2107 | Unit Checklist
|  | 2108 | Unit Checklist
|  | 2109 | Unit Checklist
|  | 2110 | Unit Checklist
Level 22
|  | 2202 | Unit Checklist
|  | 2203 | Unit Checklist
|  | 2204 | Unit Checklist
|  | 2205 | Unit Checklist
|  | 2206 | Unit Checklist
|  | 2207 | Unit Checklist
|  | 2208 | Unit Checklist
|  | 2209 | Unit Checklist
|  | 2210 | Unit Checklist
Level 23
|  | 2302 | Unit Checklist
|  | 2303 | Unit Checklist
|  | 2304 | Unit Checklist
|  | 2305 | Unit Checklist
|  | 2306 | Unit Checklist
|  | 2307 | Unit Checklist
|  | 2308 | Unit Checklist
|  | 2309 | Unit Checklist
|  | 2310 | Unit Checklist
Level 24
|  | 2402 | Unit Checklist
|  | 2403 | Unit Checklist
|  | 2404 | Unit Checklist
|  | 2405 | Unit Checklist
|  | 2406 | Unit Checklist
|  | 2407 | Unit Checklist
|  | 2408 | Unit Checklist
|  | 2409 | Unit Checklist
|  | 2410 | Unit Checklist
Level 25
|  | 2502 | Unit Checklist
|  | 2503 | Unit Checklist
|  | 2504 | Unit Checklist
|  | 2505 | Unit Checklist
|  | 2506 | Unit Checklist
|  | 2507 | Unit Checklist
|  | 2508 | Unit Checklist
|  | 2509 | Unit Checklist
|  | 2510 | Unit Checklist
Level 26
|  | 2602 | Unit Checklist
|  | 2603 | Unit Checklist
|  | 2604 | Unit Checklist
|  | 2605 | Unit Checklist
|  | 2606 | Unit Checklist
|  | 2607 | Unit Checklist
|  | 2608 | Unit Checklist
|  | 2609 | Unit Checklist
|  | 2610 | Unit Checklist
Level 27
|  | 2702 | Unit Checklist
|  | 2703 | Unit Checklist
|  | 2704 | Unit Checklist
|  | 2705 | Unit Checklist
|  | 2706 | Unit Checklist
|  | 2707 | Unit Checklist
|  | 2708 | Unit Checklist
|  | 2709 | Unit Checklist
|  | 2710 | Unit Checklist
Apartment | Level 29
|  | 2901 | Unit Checklist
|  | 2902 | Unit Checklist
|  | 2903 | Unit Checklist
Level 30
|  | 3001 | Unit Checklist
|  | 3002 | Unit Checklist
|  | 3003 | Unit Checklist
Level 31
|  | 3101 | Unit Checklist
|  | 3102 | Unit Checklist
|  | 3103 | Unit Checklist
Level 32
|  | 3201 | Unit Checklist
|  | 3202 | Unit Checklist
|  | 3203 | Unit Checklist
Level 33
|  | 3301 | Unit Checklist
|  | 3302 | Unit Checklist
|  | 3303 | Unit Checklist
Level 34
|  | 3401 | Unit Checklist
|  | 3402 | Unit Checklist
|  | 3403 | Unit Checklist
Level 35
|  | 3501 | Unit Checklist
|  | 3502 | Unit Checklist
|  | 3503 | Unit Checklist
Level 36
|  | 3601 | Unit Checklist
|  | 3602 | Unit Checklist
Level 37
|  | 3701 | Unit Checklist
|  | 3702 | Unit Checklist
Level 38
|  | 3801 | Unit Checklist
|  | 3802 | Unit Checklist
Level 39
|  | P003 | Unit Checklist
Level 40
|  | P002 | Unit Checklist
Level 41
|  | P001 | Unit Checklist

## Checklist 1- Hardflooring (2)
checklist | Unit Checklist
Section | Substrate inspection
checkpoint | Substrate has no damages or cracks
Floor grinded or free of contaminant and laitance
Section | Screed works
Checkpoint | Apply Sikadur 32 bonding agent to concrete surface (if CSP5 is not achievable)
Mix Sika T-latex and Sika screed binder as bonding slurry prior to screeding
Mix aggregate to Sika screed binder - 4:1 ratio
Screed to form fall using Sika Monotop-325N. (Less than 12mm thickness build up)
FFL confirmed and Screed to correct fall and height requirement
No lose sand on top of completed screed
Section | Tiling
Checkpoint | Setting out according to IFC construction drawing / Site confirmation
Apply Sika Primer-11W+
Installation of de-coupling membrane
Full coverage of coping stone / tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & propreitary expansion trims installed as per IFC drawings
Skirting tile installed as per IFC drawings
Section | Grout and Silicone
Checkpoint | Tiles adhesive cured and clean all adhesive residues / dust on tiles and between joints
Grout installed into all joint and properly clean
Silicon applied to a neat continuously finish
Section | Final seal
Checkpoint | Tiles cleaned and sealed
Section | Final check and Sign off
Checkpoint | Tiling Completed
Photo Taken of Completed Area
Sign off and Handover

## Checklist 2 - Wet Area
checklist | Unit Checklist
Section | Substrate inspection
checkpoint | Substrate has no damages or cracks
Floor grinded or free of contaminant and laitance
Section | Screed works
Checkpoint | Apply Sikadur 32 bonding agent to concrete surface (if CSP5 is not achievable)
Mix Sika T-latex and Sika screed binder as bonding slurry prior to screeding
Mix aggregate to Sika screed binder - 4:1 ratio
Screed to form fall using Sika Monotop-325N. (Less than 12mm thickness build up)
FFL confirmed and Screed to correct fall and height requirement
No lose sand on top of completed screed
Section | Waterproofing
Checkpoint | Apply Sika Primer-11W+
Install Sika SealTape to all corners, all expansion and construction joints
Apply 1st coat of of Sikalatic -152
Install Sika Fibre Mesh on top of fresh 1st coat Sikalastic -152
Apply 2nd coat of Sikalastic -152
Water test performed and pass
Section | Tiling
Checkpoint | Setting out according to IFC construction drawing / Site confirmation
Apply Sika Primer-11W+
Full coverage of coping stone / tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & propreitary expansion trims installed as per IFC drawings
Skirting tile installed as per IFC drawings
Section | Grout and Silicone
Checkpoint | Tiles adhesive cured and clean all adhesive residues / dust on tiles and between joints
Grout installed into all joint and properly clean
Silicon applied to a neat continuously finish
Section | Final seal
Checkpoint | Tiles cleaned and sealed
Section | Final check and Sign off
Checkpoint | Tiling Completed
Photo Taken of Completed Area
Sign off and Handover

## Checklist 3 - Screeding
checklist | Unit Checklist
Section | Substrate inspection
checkpoint | Substrate has no damages or cracks
Floor grinded or free of contaminant and laitance
Section | Screed works
Checkpoint | Apply Sikadur 32 bonding agent to concrete surface (if CSP5 is not achievable)
Mix Sika T-latex and Sika screed binder as bonding slurry prior to screeding
Mix aggregate to Sika screed binder - 4:1 ratio
Screed to form fall using Sika Monotop-325N. (Less than 12mm thickness build up)
FFL confirmed and Screed to correct fall and height requirement
No lose sand on top of completed screed