## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
67ff2845-80b4-4fa1-ac85-85c997d62be5 | checklist | Checklist 1 |  | Checklist 1
d7b6ba25-5f9e-4f81-a37f-38ba6d5870d1 | section | Substrate inspection
08e42365-41b1-4c19-b082-4bc6a9a866a1 | checkpoint | Substrate has no damages or cracks
8643d3d5-d765-4404-b3b7-64b33605dfd1 | checkpoint | Floor grinded or free of contaminant and laitance
629a7f5f-72f1-46d6-9009-0cc7ccb591a5 | section | Screed works
bbe2625a-7fdf-4ec9-b235-63acf9f5f02f | checkpoint | Apply Sikadur 32 bonding agent to concrete surface (if CSP5 is not achievable)
ce704e96-95ca-4640-9339-b76a60fe453e | checkpoint | Mix Sika T-latex and Sika screed binder as bonding slurry prior to screeding
e2162938-d138-4971-899a-aaa9cf5ac290 | checkpoint | Mix aggregate to Sika screed binder - 4:1 ratio
6c302bb6-2a2f-4464-9eaf-88f3fd3c066b | checkpoint | Screed to form fall using Sika Monotop-325N. (Less than 12mm thickness build up)
d0ce8454-6a36-459e-8225-51cb8da0d0e6 | checkpoint | FFL confirmed and Screed to correct fall and height requirement
15cf4de3-eb58-4f49-8d6b-e5deb008b180 | checkpoint | No loose sand on top of completed screed
6b41d4f0-3ae1-426d-89a8-98fbe3567140 | section | Tiling
5dab742b-f8d4-4357-b57e-209eca43c5df | checkpoint | Setting out according to IFC construction drawing / Site confirmation
a937bbc9-0bc9-4923-b792-167d662d2aed | checkpoint | Apply Sika Primer-11W+
bbf51210-442a-45f7-9654-654107cfc54d | checkpoint | Installation of de-coupling membrane
2e8c133a-ec2f-4d7c-a7ff-406d1a555dbc | checkpoint | Full coverage of coping stone / tiles with adhesive
3b0b8266-b488-4e8d-a9aa-21039aa57df2 | checkpoint | Tile lippiness checked and to acceptable standard
6901e893-d0a1-42f1-b8fa-dea65ccacf10 | checkpoint | Finishing trims & proprietary expansion trims installed as per IFC drawings
171ceeda-c9f0-4f3a-b30e-85d45897bc5d | checkpoint | Skirting tile installed as per IFC drawings
29f47ee0-a25b-481a-83ae-6b3855165f3d | section | Grout and Silicone
e1539596-7f0d-4cb1-aff1-eb62fd645d2e | checkpoint | Tiles adhesive cured and clean all adhesive residues / dust on tiles and between joints
7a8d3648-e757-4a7c-85b8-926a00af0d21 | checkpoint | Grout installed into all joint and properly clean
4b9224e5-689f-4bd6-8d5c-0640f48357a4 | checkpoint | Silicon applied to a neat continuously finish
ec1abe82-df8f-41e6-9635-729dfff10cc6 | section | Final seal
405ca9d6-e98d-43c1-a8b9-a55c7c2878a3 | checkpoint | Tiles cleaned and sealed
b2e309e3-7c4b-472c-8ed2-d4c3eca13a9e | section | Final check and Sign off
f5c60ea1-c759-4047-bb82-58268b892ac9 | checkpoint | Tiling Completed
16dc16f3-ebed-4bfb-9094-2b31a0ef9e8a | checkpoint | Photo Taken of Completed Area
ba64a647-0cac-45a4-829a-f09c9fe47048 | signoff | Sign off and Handover
9674fa07-f58b-40e7-9907-66e6564bd66a | checklist | Checklist 2 |  | Checklist 2
bf09d02a-5ba6-498f-b6b0-9691ae53627a | section | Substrate inspection
8806342e-84e4-40ec-9b2b-f997a38b679c | checkpoint | Substrate has no damages or cracks
d979c416-cf6b-489a-94a6-e1114cb104ee | checkpoint | Floor grinded or free of contaminant and laitance
9d5c629c-0e44-4678-828e-c80827511eeb | section | Screed works
7a045c02-67a0-4992-a02b-3397f71a0545 | checkpoint | Apply Sikadur 32 bonding agent to concrete surface (if CSP5 is not achievable)
f673514d-c2e6-4200-a569-ad239d437fec | checkpoint | Mix Sika T-latex and Sika screed binder as bonding slurry prior to screeding
e4e9a961-8e24-40ca-b5c5-b1c7e8bb2a55 | checkpoint | Mix aggregate to Sika screed binder - 4:1 ratio
d3a8db47-ff36-4643-882e-e0b54a9fccba | checkpoint | Screed to form fall using Sika Monotop-325N. (Less than 12mm thickness build up)
ab1d21c5-d6cd-413a-a5e8-3dd938b8e9b4 | checkpoint | FFL confirmed and Screed to correct fall and height requirement
5d80b1af-fcad-4598-813d-5d7c2a8f041a | checkpoint | No loose sand on top of completed screed
d71fb727-0ef3-485a-9126-e56eb68097b1 | section | Waterproofing
29486eff-eebc-4b48-9190-3527982c1efd | checkpoint | Apply Sika Primer-11W+
fa7fa2d0-9334-4666-8662-8b03a54cde24 | checkpoint | Install Sika SealTape to all corners, all expansion and construction joints
bca6d429-7b73-40f9-b6f0-19319b985574 | checkpoint | Apply 1st coat of of Sikalatic -152
2367f2b2-b3a1-46b2-97e2-5d3a0fef471d | checkpoint | Install Sika Fibre Mesh on top of fresh 1st coat Sikalastic -152
427896b3-9638-4efd-a7c4-6a1dd1ec9ffa | checkpoint | Apply 2nd coat of Sikalastic -152
5c611798-dec1-46ef-9c3d-9560414d0a62 | checkpoint | Water test performed and pass
5323e2e1-6d06-4b4e-a0cf-19a571ccf189 | section | Tiling
0d20c8b8-eb50-4fe3-86f1-de6878c9dd9e | checkpoint | Setting out according to IFC construction drawing / Site confirmation
0cbf98b9-dcef-400f-acb4-dec437a8cc36 | checkpoint | Apply Sika Primer-11W+
683ab09b-23ad-4297-b637-3771807e543a | checkpoint | Full coverage of coping stone / tiles with adhesive
05b06a1b-edc9-446c-9da9-083b380375c8 | checkpoint | Tile lippiness checked and to acceptable standard
2ab9beba-1197-4ed2-962e-b2b75305880c | checkpoint | Finishing trims & proprietary expansion trims installed as per IFC drawings
a8deb550-3694-464e-8839-e9228433cd67 | checkpoint | Skirting tile installed as per IFC drawings
ddf80291-eee2-4c41-9d7a-d8d3581c18d5 | section | Grout and Silicone
8fba1c89-b8c6-4e85-8239-b5c634b93b9b | checkpoint | Tiles adhesive cured and clean all adhesive residues / dust on tiles and between joints
06e3efce-9483-41ae-a4a1-608b108cc097 | checkpoint | Grout installed into all joint and properly clean
97cbb10d-29d8-4499-bfa1-14b515f9f420 | checkpoint | Silicon applied to a neat continuously finish
766b8614-a2f7-4042-b8d8-4adf92bd2a8c | section | Final seal
f18f9b95-226c-45a8-bebf-8aca2b2646d6 | checkpoint | Tiles cleaned and sealed
07338254-7204-4bb0-91ce-16f5d35ccd54 | section | Final check and Sign off
db30eaf6-8521-4da2-85fe-2c12c036a503 | checkpoint | Tiling Completed
b6960e78-0e1c-4bd7-97a4-d290ea7cc3d5 | checkpoint | Photo Taken of Completed Area
72a1866e-d065-4452-b88e-366524f35a9e | signoff | Sign off and Handover
9c799def-8cbe-4725-8c0b-e7a192a49a56 | checklist | Checklist 3 |  | Checklist 3
fa613950-3ec1-411f-8987-ec753a9a9e98 | section | Substrate inspection
b0506a90-061e-4944-a9fc-28de29ab9d82 | checkpoint | Substrate has no damages or cracks
662ddac3-dfea-4bd2-b903-2da54fc59da3 | checkpoint | Floor grinded or free of contaminant and laitance
7e77e6b7-1877-40e8-aced-99c00e3febbf | section | Screed works
ed9bc2ea-cbf2-4e04-9be6-990a0b1bacba | checkpoint | Apply Sikadur 32 bonding agent to concrete surface (if CSP5 is not achievable)
e4d0fe01-a0d8-4d52-a532-11032cf5113b | checkpoint | Mix Sika T-latex and Sika screed binder as bonding slurry prior to screeding
55d1e791-a43c-4b44-81b8-5bed221b8a6d | checkpoint | Mix aggregate to Sika screed binder - 4:1 ratio
41d108ff-1965-459b-8430-be4e50760f79 | checkpoint | Screed to form fall using Sika Monotop-325N. (Less than 12mm thickness build up)
994e33b1-4c74-448a-9ac6-577ad6110e91 | checkpoint | FFL confirmed and Screed to correct fall and height requirement
a5a8f55b-96ce-49f3-a926-36ca9634f9ab | checkpoint | No loose sand on top of completed screed