## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 5f1e3e7b-853d-40ea-b533-1f00adc718c1 |  | checklist | Scope required |  |  |  |  | Yes | Rework Checklist | 10c2adf6-2102-4cb3-8f7b-950934ef6023
checkpoint-status | 7035c62b-e296-45f4-914e-5374fcf7af17 |  | checkpoint | Pre Fire Completed and QA signed off
checkpoint-status | 80973eed-f94d-4fb6-9e0c-94028575ffce |  | checkpoint | Post Fire Reinstatement work Completed
checkpoint-status | 55cdc4ad-380d-43f0-87af-147eb78933ff |  | checkpoint | Contract Coatings Remedials Completed (Photos attached or list Aconex Field Ref #)
checkpoint-status | 73bff0a2-a55e-493f-832c-bdb002f8a7b8 |  | checkpoint | FCC Remedials Completed (Photos attached or list Aconex Field Ref #)
checklist-sectioned | 010c6b64-c925-4d30-ad10-8c7908f73af5 |  | checklist | QA - Painting |  |  |  |  | Yes | QA - Painting | 123f810b-78ea-4546-a738-c2daf0103ebb
checkpoint-group | d073c74c-0ea0-4e29-9d42-5b6569f0ff8e |  | section | Precommencment
checkpoint-status | 03b8572c-de40-4e90-b3b4-1de456704243 |  | checkpoint | Handover from Stopping crew
checkpoint-status | a261e6ae-8df9-4c74-96c3-acbca1a271f1 |  | checkpoint | Work area clean & tidy
checkpoint-status | 553a9166-2346-4c87-a81a-35265e2ca7b5 |  | checkpoint | Skirting doors & Architraves installed
checkpoint-status | 56dcb1b0-4e29-4046-92e3-1c4799ba7897 |  | checkpoint | Architrave mitres sanded flush
checkpoint-group | d0bcd248-6962-42f2-9eb3-f99f87c7cf8a |  | section | Sealer coat
checkpoint-status | 7220757c-32e9-4151-9c33-8f0f2313b16d |  | checkpoint | Apply Sealer coat to walls, ceiling & trims
checkpoint-status | 9b7f6d16-269d-43f5-b979-8e8c92630db4 |  | checkpoint | Handover back to Stopping crew for 1st QA light check surfaces for stopping defects.
checkpoint-status | 2e4dc5f3-9eb9-4ef3-8259-f77bdb796858 |  | checkpoint | Handover from Stopping crew
checkpoint-group | e7c74898-e833-415f-9ef1-d54907768d32 |  | section | First Coat
checkpoint-status | c663c7b7-d81e-4b90-923e-9e83c5c0ee62 |  | checkpoint | Apply first coat of colour to walls, Ceilings & timber trim.
checkpoint-status | 0fd1ec33-2d4a-4fbf-baa4-16e65ea474b3 |  | checkpoint | 2ND QA check surfaces for stopping defects corrected by Stopping crew
checkpoint-status | a3d7d41e-45bc-41ab-9bdb-f90f1e5b80da |  | checkpoint | Surfaces free of defects – Accept hand over from Interiors team
checkpoint-status | e0b70926-007b-42d7-a741-b2000b041def |  | checkpoint | Apply x2 topcoats to ceiling
checkpoint-status | eb22d4d9-2eb6-4abf-ad78-cfe83cac6507 |  | checkpoint | Apply 1st Coat to walls, doors & timber trim
checkpoint-group | 35ae50e5-bb10-4fa4-ae18-cf563701e2c9 |  | section | Final Coat Trims
checkpoint-status | d5919a0b-eef9-4118-8fdf-932a11ccd0e9 |  | checkpoint | Final coat timber doors, architraves, skirtings & window frames
checkpoint-status | f5851391-1cf3-47e8-a3aa-2ad82f1ffc33 |  | checkpoint | Apply final topcoat to timber doors, architraves, skirtings & window frames.
checkpoint-status | 409efc68-c8ff-4586-b788-4e6fddd7f03a |  | checkpoint | Light check walls in preparation of final coat
checkpoint-group | b9b2c3d0-ab33-4e1a-afe3-b250973d1ac0 |  | section | Final Coat Walls
checkpoint-status | a8f7d400-c21f-4e06-b4d4-58e49404ae3a |  | checkpoint | Apply final coat on walls.
checkpoint-status | 18950d79-24b3-4a44-a310-2cab75e2b48e |  | checkpoint | Notification signage in place notifying final coats have been applied.
checkpoint-status | 260eaa59-8617-4750-9efe-c1ac19b13024 |  | checkpoint | Completion check, rectify defects
label | 2446cae7-8606-5918-b2c7-16ab84ec7b2d |  | note | Touch ups / Extras identified & agreed
label | b355b555-a698-59ff-861c-7c4c81b58e3b |  | note | Touch ups/ Extras completed
checklist-flat | 614a09c2-5387-43c8-afd1-1f7fcd8e111e |  | checklist | Intumescent for Area: |  |  |  |  | Yes | QA - Intumescent Paint | 1dfe20e3-48c0-410e-af3e-74cd8a113bd2
checkpoint-status | 893e0e37-82a2-403e-a753-d752ea0debe8 |  | checkpoint | Specification & mark-up received & reviewed
checkpoint-status | cef47135-9010-42c5-b56a-3a2f6eb5c339 |  | checkpoint | Q.A. from steel fabricator received & reviewed
checkpoint-status | 0de00358-261a-4b47-907f-0c1764ef5af2 |  | checkpoint | Cleaning/washing of substrate
checkpoint-status | f8631b5c-cfa8-4c1b-af53-9b088671f1f4 |  | checkpoint | Substrate acceptable
checkpoint-status | 930f799a-c97a-4315-a833-6700ec2d8f80 |  | checkpoint | Base DFT readings on primers
checkpoint-status | 9e83510c-1c6e-4927-9e41-9b62e0a19a22 |  | checkpoint | Intumescent applied
checkpoint-status | ebe0a1b4-c0ea-4a19-93a0-c53b9fd813e0 |  | checkpoint | Dry film inspection completed
checkpoint-status | 528198fc-acf9-49af-9157-5392257092e8 |  | checkpoint | Topcoats applied in accordance with specification
checklist-flat | acf16bf3-6690-463f-be0d-2f95260b1065 |  | checklist | Exterior Painting – Linea Board |  |  |  |  | Yes | Exterior Painting – Linea Board | 6c6d2a00-6320-4409-af26-43aee6099a96
checkpoint-status | 598acc3d-57b9-4336-9696-e7b576aeeb3d |  | checkpoint | Boards installed correctly & defect free
checkpoint-status | acb41bf4-c9a0-4b45-8c58-d92c67010e1b |  | checkpoint | Silicon to joints completed & satisfactory
checkpoint-status | d605641d-ec5c-434f-aeae-150df568f9c1 |  | checkpoint | Primer coat
checkpoint-status | d6740a68-3338-4e33-922e-40f4acacffd3 |  | checkpoint | Filling & sanding
checkpoint-status | 0bc33954-86ab-4258-86ea-d9a80e83dbc5 |  | checkpoint | Spot prime
checkpoint-status | e610eab1-a26c-4d53-9968-94c78471502e |  | checkpoint | 1st topcoat
checkpoint-status | 79f6b8d0-e56b-4751-a7ce-a404f8a8dcb6 |  | checkpoint | 2nd topcoat
checklist-flat | b3a6cd26-05a5-4ad5-bdca-3e0b6be8e4e8 |  | checklist | Miscellaneous/Attach Drawings |  |  |  |  | Yes | Miscellaneous/Attach Drawings | a9637aaf-1f71-49e2-a298-86382908cc61
checkpoint-status | 1c625852-8607-4a67-b7d6-8697d8946d9c |  | checkpoint | Document Attached
checklist-flat | dd3f2e14-78ab-4b9b-bca2-310af0a2a088 |  | checklist | Variation # |  |  |  |  | Yes | Variation # | da0bcc06-3f8b-48ee-b4c7-0701d35a262e
checkpoint-status | cf50e155-6423-439f-ab06-f00bbcc56e30 |  | checkpoint | Variation completed with photos of work
text | 925806c4-b4cf-5c7a-9e24-33669f4c117a |  | textbox | Details (Level/Unit/Area)
text | 3d7554eb-6c5e-5869-b380-7774ef2ff50b |  | textbox | Hours/Minutes
checklist-flat | ccb50b26-22b8-436e-b31e-3c93257e1184 |  | checklist | QA - Interior Painting |  |  |  |  | Yes | QA - Interior Painting | e5178c1c-c96b-468c-9ec5-56f35c35466e
checkpoint-status | 99ed6a60-000e-4bf1-a83d-8dbb59923aa9 |  | checkpoint | Area accessible, substrates acceptable
checkpoint-status | e4204b86-7ac5-406a-ab45-40753df2e06d |  | checkpoint | Plaster work complete to lifting eyes, drossbachs & defects
checkpoint-status | 9a085231-5638-4fdd-8829-7ff3ff7302d5 |  | checkpoint | Stopping complete
checkpoint-status | 015c518d-12a0-4598-9c8a-ec832c646f7e |  | checkpoint | Washing complete
checkpoint-status | f89db632-4ab7-41db-b44a-9b59fb87fd27 |  | checkpoint | Approval given to paint
text | d98df7a9-fe71-58ae-b597-d172e1d9f0b2 |  | textbox | Who has given approval to paint
checkpoint-status | ce4e919e-a6e9-4a60-ad04-fdf315383d31 |  | checkpoint | Paint specifications and colour checked & correct to specification
checkpoint-status | f7362fcd-5953-4388-937c-9272adb35930 |  | checkpoint | First coat/ sealant coat completed
checkpoint-status | a03ec492-4115-4dbc-ac0d-66d8c2950244 |  | checkpoint | Light inspection completed and approved to continue
label | 5198f252-baf0-5755-b361-d6f603d59d1e |  | note | Any issues "FAIL" and document remedial work - "Pass" once completed
checkpoint-status | 7da3bc1d-9871-45a3-b0ee-7af07b6d6ea6 |  | checkpoint | General comments and photos of additional paint application
checkpoint-status | 42a9865b-e885-4c67-9531-301fb9783640 |  | checkpoint | Final coat completed, no overpainting, finish acceptable as per specification
holdpoint | 0b773e31-2639-47b1-a3c6-9131f25f54db |  | signoff | Request Signoff