## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Balcony Checklist |  |  |  |  | Yes | Balcony Checklist - Flinders Tower West | 1a5e8d56-8334-4595-a141-60271be71575
checkpoint-status |  |  | checkpoint | Internal and external caulking
checkpoint-status |  |  | checkpoint | Right and left bead
checkpoint-status |  |  | checkpoint | Glass condition
checkpoint-status |  |  | checkpoint | Slider installed (n/a if not)
checkpoint-status |  |  | checkpoint | Slider condition
checklist-sectioned |  |  | checklist | Panel installation Checklist - Flinders Tower West |  |  |  |  | Yes | Panel installation Checklist - Flinders Tower West | 652fe637-b31f-47b1-9396-534529136c1a
checkpoint-group |  |  | section | Pre-Install
checkpoint-status |  |  | checkpoint | Brackets are torqued (photos).
checkpoint-status |  |  | checkpoint | Gutter plate and sleeve installed (photos)
checkpoint-status |  |  | checkpoint | (PHOTO) BMU pin installed
checkpoint-status |  |  | checkpoint | Cladding installed to slab edge per engineers design and checked
checkpoint-status |  |  | checkpoint | (PHOTO) Cladding installed to Curtain Wall
checkpoint-status |  |  | checkpoint | Cladding fixed to panel per engineers design/instruction
checkpoint-status |  |  | checkpoint | All cladding fixing points accounted for and engaged
checkpoint-status |  |  | checkpoint | All fixings inspected and sealed per engineers design
checkpoint-status |  |  | checkpoint | (Photo) Cladding secure and in position prior to panel installed
checkpoint-status |  |  | checkpoint | Cladding checked for defects
checkpoint-status |  |  | checkpoint | Riggers checked Cladding fixings to curtain wall panel have been made per engineering and cladding is secure prior to panels being launched.
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Panel in good caulking condition
checkpoint-status |  |  | checkpoint | Protection tape in good condition
checkpoint-status |  |  | checkpoint | No defects/scratch/dents/distortion/crack All defects will be fixed in defect stage
checkpoint-status |  |  | checkpoint | Gaps between concrete and subsill subhead are sealed properly
checkpoint-status |  |  | checkpoint | Sub-sill, subhead in position, check expansion bolts are used and nuts are tightened. No changes were made during installation
checkpoint-status |  |  | checkpoint | Panel installed and fixed in position. Correct fixings are used.
checkpoint-status |  |  | checkpoint | (PHOTO) Slab edge insulation and J-hook insulation are filled and caulked properly
checkpoint-status |  |  | checkpoint | (PHOTO) Glass / panel surface in good condition
checkpoint-group |  |  | section | Post-Install
checkpoint-status |  |  | checkpoint | Check weight of panel is as per schedule and enter weight below
text | b5f03a1b-7e1d-56b9-9ae9-8e21b6434af8 |  | textbox | Panel Weight
checkpoint-status |  |  | checkpoint | Skirting and pelmet installed in position
checkpoint-status |  |  | checkpoint | Window and sliding door open and close in good condition and adjusted properly
checklist-sectioned |  |  | checklist | Panel Installation Checklist |  |  |  |  | Yes | Panel Installation Checklist - Flinders Tower West (old) | 82515df0-2095-4a1d-abfd-b37a17dda1b9
checkpoint-group |  |  | section | Pre-Install
checkpoint-status |  |  | checkpoint | Brackets are torqued (photos).
checkpoint-status |  |  | checkpoint | Gutter plate and sleeve installed (photos)
checkpoint-status |  |  | checkpoint | (PHOTO) BMU pin installed
checkpoint-status |  |  | checkpoint | Cladding installed to slab edge per engineers design and checked
checkpoint-status |  |  | checkpoint | (PHOTO) Cladding installed to Curtain Wall
checkpoint-status |  |  | checkpoint | Cladding fixed to panel per engineers design/instruction
checkpoint-status |  |  | checkpoint | All cladding fixing points accounted for and engaged
checkpoint-status |  |  | checkpoint | All fixings inspected and sealed per engineers design
checkpoint-status |  |  | checkpoint | Cladding secure and in position prior to panel installed
checkpoint-status |  |  | checkpoint | Cladding checked for defects
checkpoint-status |  |  | checkpoint | Riggers checked Cladding fixings to curtain wall panel have been made per engineering and cladding is secure prior to panels being launched.
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Panel in good caulking condition
checkpoint-status |  |  | checkpoint | Protection tape in good condition
checkpoint-status |  |  | checkpoint | No defects/scratch/dents/distortion/crack All defects will be fixed in defect stage
checkpoint-status |  |  | checkpoint | Gaps between concrete and subsill subhead are sealed properly
checkpoint-status |  |  | checkpoint | Sub-sill, subhead in position, check expansion bolts are used and nuts are tightened. No changes were made during installation
checkpoint-status |  |  | checkpoint | Panel installed and fixed in position. Correct fixings are used.
checkpoint-status |  |  | checkpoint | Slab edge insulation and J-hook insulation are filled properly (photos)
checkpoint-status |  |  | checkpoint | (PHOTO) Glass / panel surface in good condition
checkpoint-group |  |  | section | Post-Install
checkpoint-status |  |  | checkpoint | Check weight of panel is as per schedule and enter weight below
text | 31737e0f-d31e-5ef2-bb6a-3b601a88af10 |  | textbox | Panel Weight
checkpoint-status |  |  | checkpoint | Skirting installed in position
checkpoint-status |  |  | checkpoint | Window and sliding door open and close in good condition