## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Insulation | [5 empty] | Insulation Checklist (Gatehouse Roof)
section | Material Inspection
checkpoint | Insulation - R3.6 Glasswool on Medium Sarking - 130mm
checkpoint | Thermal spacer: 115mm thermal spacer
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Gatehouse Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Gatehouse Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof Penetrations Checklist (Gatehouse Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond 400mm x 400mm
checkpoint | 65mm to 125mm Dektite #3
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Gatehouse Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 100mm Dia 0.4mm colorbond
checkpoint | Pops: 100mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 100mm colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (Gatehouse Security Hut Roof)
section | Material Inspection
checkpoint | Insulation - R3.6 Glasswool on Medium Sarking - 130mm
checkpoint | Thermal spacer: 115mm thermal spacer
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Gatehouse Security Hut Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Gatehouse Security Hut Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Gatehouse Security Hut Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 100mm Dia 0.4mm colorbond
checkpoint | Pops: 100mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 100mm colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Plyboard | [5 empty] | Plyboard (Hub 1st Floor Roof)
section | Material Inspection
checkpoint | 22mm Particleboard
section | Installation
checkpoint | Minimal gaps between particle board
checkpoint | Screwed onto purlin
checkpoint | 10 screws per board for 400mm x 800mm
checkpoint | 15 screws for board for 2000mm x 800mm
checkpoint | 20 screws per board for 3600mm x 800
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (Hub 1st Floor Roof)
section | Material Inspection
checkpoint | Insulation - R3.6 Glasswool on Medium Sarking - 130mm
checkpoint | Thermal spacer: 115mm thermal spacer
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Hub 1st Floor Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Hub 1st Floor Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Hub 1st Floor Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 150mm Dia 0.4mm colorbond
checkpoint | Pops: 150mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 150mm colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (Hub Airlock Roof)
section | Material Inspection
checkpoint | Insulation - R3.6 Glasswool on Medium Sarking - 130mm
checkpoint | Thermal spacer: 115mm thermal spacer
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Hub Airlock Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Hub Airlock Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Hub Airlock Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 100mm Dia 0.4mm colorbond
checkpoint | Pops: 100mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 100mm colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (Hub Airlock Roof Canopy)
section | Material Inspection
checkpoint | Insulation - R3.6 Glasswool on Medium Sarking - 130mm
checkpoint | Thermal spacer: 115mm thermal spacer
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Hub Airlock Roof Canopy)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Hub Airlock Roof Canopy)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Hub Airlock Roof Canopy)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 100mm Dia 0.4mm colorbond
checkpoint | Pops: 100mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 100mm colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Plyboard | [5 empty] | Plyboard (Hub Main Roof)
section | Material Inspection
checkpoint | 22mm Particleboard
section | Installation
checkpoint | Minimal gaps between particle board
checkpoint | Screwed onto purlin
checkpoint | 15 screws for board for 1800mm x 800mm
checkpoint | 20 screws per board for 3600mm x 800mm
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Box Gutter Installation Checklist (Hub Main Roof)
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: 60mm
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: colorbond stainless steel
checkpoint | Gutter Flashing: Colorbond stainless steel
checkpoint | Sumps / Outlets: colorbond stainless steel 600mm x 600mm
checkpoint | Overflows: colorbond stainless steel
checkpoint | Box gutter Expansion Join - upto 1200mm
checkpoint | Material Sparation Barrier
section | Installation
checkpoint | Sump Depth adheres with AS3500:3 p.38
checkpoint | Box Gutter depth adheres with AS 3500:3 p.37
checkpoint | Gutter Brackets installed with fall as per Specification (no less than 1:200)
checkpoint | Gutter Brackets installed no greater than 750mm Centre to Centre
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Lower most part of Gutter flashing are at least 100mm off from sole of the box gutter
checkpoint | Pops are installed from underside of the sump
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (Hub Main Roof)
section | Material Inspection
checkpoint | Insulation - R3.6 Glasswool on Medium Sarking - 130mm
checkpoint | Thermal spacer: 80mm thermal spacer
checkpoint | Thermal spacer: 115mm thermal spacer
checkpoint | 18mm Packers to 80mm Spacers
checkpoint | 22mm to pulines without plyboard
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Hub Main Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
checkpoint | Material eparation barrier
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Hub Main Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Hub Main Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 150mm Dia 0.4mm colorbond
checkpoint | Pops: 150mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 150mm colorbond
checkpoint | Spreader up to 150mm Colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof Penetrations Checklist (Hub Main Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond 400mm x 400mm
checkpoint | Flashing Material: 0.61mm Colorbond 600mm x 600mm
checkpoint | Flashing Material: 0.61mm Colorbond 1000mm x 1000mm
checkpoint | C205 Outrigger penetrations
checkpoint | HatchwayPenetration 1200 x 1200
checkpoint | Backtray flashing - 1800mm
checkpoint | Dektite #3 - 65mm to 125mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Covered Training Shelter)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Roof Sarking: Medium weight Paper
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Sarking installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Covered Training Shelter)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Covered Training Shelter)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 100mm Dia 0.4mm colorbond
checkpoint | Pops: 100mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 100mm colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Bike Shed)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Roof Sarking: Medium weight Paper
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Sarking installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Bike Shed)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Bike Shed)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 100mm Dia 0.4mm colorbond
checkpoint | Pops: 100mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 100mm colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (Production Workshop - Amenities Node Roof)
section | Material Inspection
checkpoint | Insulation - R3.6 Glasswool on Medium Sarking - 130mm
checkpoint | Thermal spacer: 115mm thermal spacer
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Production Workshop - Amenities Node Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Safety Mesh Stapled
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Production Workshop - Amenities Node Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary MAX 40mm
checkpoint | Compression Flashing Fixings Max 100mm
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof Penetrations Checklist (Production Workshop - Amenities Node Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond 1800mm x 1800mm
checkpoint | 65mm to 125mm Dektite #3
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Production Workshop - Amenities Node Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 150mm Dia 0.4mm colorbond
checkpoint | Pops: 150mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 150mm colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Box Gutter Installation Checklist (Production Workshop - Canopy Roof)
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: 60mm
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: colorbond stainless steel
checkpoint | Gutter Flashing: Colorbond stainless steel
checkpoint | Sumps / Outlets: colorbond stainless steel 600mm x 600mm
checkpoint | Overflows: colorbond stainless steel
checkpoint | Box gutter Expansion Join - upto 1200mm
checkpoint | Downpipes: 150mm Dia 0.4mm colorbond
checkpoint | Pops: 150mm round 0.61mm Colorbond
checkpoint | Downpipe Clips for 150mm colorbond
checkpoint | Material Sparation Barrier
section | Installation
checkpoint | Sump Depth adheres with AS3500:3 p.38
checkpoint | Box Gutter depth adheres with AS 3500:3 p.37
checkpoint | Gutter Brackets installed with fall as per Specification (no less than 1:200)
checkpoint | Gutter Brackets installed no greater than 750mm Centre to Centre
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Lower most part of Gutter flashing are at least 100mm off from sole of the box gutter
checkpoint | Pops are installed from underside of the sump
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Production Workshop - Canopy Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Roof Saring - Proctor Wrap HTS-IT or Vapawrap Metal roof
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
checkpoint | Material separation barrier
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Metal Fascia Installation | [5 empty] | Metal Fascia Installation Checklist (Production Workshop - Canopy Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Production Workshop - Internal Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Roof Sarking: Proctor HTS-IT or VapaWrap Metal Roof
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Sarking installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Structural Works | [5 empty] | Structural Works (Production Workshop - Internal Roof)
section | Material Inspection
checkpoint | Roof Truss End Support
checkpoint | Roof Top Hat 50mm
checkpoint | Roof Truss 450mm
section | Installation
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Production Workshop - Internal Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary MAX 40mm
checkpoint | Compression Flashing Fixings Max 100mm
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Production Workshop - Inverter Store Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | 30mm Top Hat - Fixed to Precast
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Production Workshop - Inverter Store Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Hanwha Orange
checkpoint | Apron Flashings - Coolmax
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary MAX 40mm
checkpoint | Compression Flashing Fixings Max 100mm
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof Penetrations Checklist (Production Workshop - Inverter Store Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond 600mm x 600mm
checkpoint | HatchwayPenetration 1200 x 1200
checkpoint | Backtray flashing - 1800mm
checkpoint | Dektite #3 - 65mm to 125mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Production Workshop - Inverter Store Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: 125mm High Front
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 100mm Dia 0.4mm colorbond
checkpoint | Pops: 100mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 100mm colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (Production Workshop - Main Roof)
section | Material Inspection
checkpoint | Insulation - R3.6 Glasswool on Medium Sarking - 130mm
checkpoint | Thermal spacer: 115mm thermal spacer
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Production Workshop - Main Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Roof Sheets: Webglass GC 3050GSM - Kliplok profile
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
checkpoint | Protective purlin strips for Webglass GC
section | Installation
checkpoint | Staple/ clip mesh overlapped
checkpoint | 3 Screws per Clip
checkpoint | Top Hat between purlins 96mm
checkpoint | Top Hat support under backtray 25mm
checkpoint | Soaker Flashing between kliplok and webglass
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Production Workshop - Main Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Barge Capping Material: Han Wha Orange
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary MAX 40mm
checkpoint | Compression Flashing Fixings Max 100mm
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof Penetrations Checklist (Production Workshop - Main Roof)
section | Material Inspection
checkpoint | Penetration 0.61mm Colorbond - Up to 150mm x 300mm
checkpoint | Penetration 0.61mm Colorbond - Up to 1000mm x 1000mm
checkpoint | Penetration 0.61mm Colorbond - Up to 1200mm x 1200mm
checkpoint | Penetration 0.61mm Colorbond - Up to 1700mm x 1700mm
checkpoint | Hatchway Penetration 0.61mm Colorbond - Up to 1200mm x 1200mm - 2
checkpoint | Dektite #3 - 65mm to 125mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Production Workshop - Main Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 600mm Centres
checkpoint | Gutterboard support to oversized gutter
section | Installation
checkpoint | Syphonic outlets - Fix only
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation | [5 empty] | Box Gutter Installation Checklist (Production Hall - Warehouse Loading Dock)
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: 60mm
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: colorbond stainless steel
checkpoint | Gutter Flashing: Colorbond stainless steel
checkpoint | Sumps / Outlets: colorbond stainless steel 600mm x 600mm
checkpoint | Overflows: colorbond stainless steel
checkpoint | Box gutter Expansion Join - upto 1200mm
checkpoint | Downpipes: 150mm Dia 0.4mm colorbond
checkpoint | Pops: 150mm round 0.61mm Colorbond
checkpoint | Downpipe Clips for 150mm colorbond
checkpoint | Material Sparation Barrier
section | Installation
checkpoint | Sump Depth adheres with AS3500:3 p.38
checkpoint | Box Gutter depth adheres with AS 3500:3 p.37
checkpoint | Gutter Brackets installed with fall as per Specification (no less than 1:200)
checkpoint | Gutter Brackets installed no greater than 750mm Centre to Centre
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Lower most part of Gutter flashing are at least 100mm off from sole of the box gutter
checkpoint | Pops are installed from underside of the sump
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Production Hall - Warehouse Loading Dock)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Roof Sarking: Proctor Wrap HTS-IT or Fletchers Vapawrap for metal roof
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
checkpoint | Material Separation Barrier
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Sarking installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Production Hall - Warehouse Loading Dock)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material: 0.61mm Colorbond to match
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checklist | Roof Penetrations | [5 empty] | Roof Penetrations Checklist (Production Hall - Warehouse Loading Dock)
section | Material Inspection
checkpoint | Penetration: 0.61mm colorbond coolmax - Roof Brace
checkpoint | Penetration: 0.61mm colorbond coolmax - Backtry Flashing - 600mm
checkpoint | 65mm to 125mm Dektite #3
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (Production Hall - Warehouse Main Roof)
section | Material Inspection
checkpoint | Insulation - R3.6 Glasswool on Medium Sarking - 130mm
checkpoint | Thermal spacer: 115mm thermal spacer
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Production Hall - Warehouse Main Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Roof Sheets: Webglass GC 3050GSM - Kliplok profile
checkpoint | Coating Type: Colorbond Coolmax
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
checkpoint | Protective purlin strips for Webglass GC
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Top Hat between purlins 96mm
checkpoint | Top Hat support under backtray 25mm
checkpoint | Soaker Flashing between kliplok and webglass
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Production Hall - Warehouse Main Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Barge Capping Material: Han Wha Orange
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary MAX 40mm
checkpoint | Compression Flashing Fixings Max 100mm
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof Penetrations Checklist (Production Hall - Warehouse Main Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond 1600 x 1600
checkpoint | HatchwayPenetration 1200 x 1200
checkpoint | Dektite #3 - 65mm to 125mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Production Hall - Warehouse Main Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 600mm Centres
checkpoint | Gutterboard support to oversized gutter
section | Installation
checkpoint | Syphonic outlets - Fix only
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Production Hall - Warehouse Internal Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm standard colorbond Kliplok
checkpoint | Roof Sarking - Proctor Warp HTS-IT or Fletchers Vapawrap for metal roof
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Top Hat between purlins 96mm
checkpoint | Top Hat support under backtray 25mm
checkpoint | Soaker Flashing between kliplok and webglass
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Structural Works | [5 empty] | Structural Works (Production Hall - Warehouse Internal Roof)
section | Material Inspection
checkpoint | Roof Truss End Support
checkpoint | Roof Top Hat 50mm
checkpoint | Roof Truss 450mm
section | Installation
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation | [5 empty] | Insulation Checklist (Paint Shop - Roof)
section | Material Inspection
checkpoint | Insulation - R3.6 Glasswool on Medium Sarking - 130mm
checkpoint | Thermal spacer: 115mm thermal spacer
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | Insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Paint Shop - Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Roof Sheets: Webglass GC 3050GSM - Kliplok profile
checkpoint | Coating Type: Coolmax Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Profile Infill strips
checkpoint | protective purlin strips for webglass GC
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Staple mesh
checkpoint | Top Hat between purlins 96mm
checkpoint | Top Hat support under backtray 25mm
checkpoint | Soaker Flashing between kliplok and webglass
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Paint Shop - Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary MAX 40mm
checkpoint | Compression Flashing Fixings Max 100mm
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations | [5 empty] | Roof Penetrations Checklist (Paint Shop - Roof)
section | Material Inspection
checkpoint | Penetration - 0.61mm Colorbond Coolmax - Up to 1200mm x 1200mm
checkpoint | Penetration - 0.61mm Colorbond Coolmax - Up to 650mm dia
checkpoint | Penetration - 0.61mm Colorbond Coolmax - Up to 1000mm dia
checkpoint | Penetration - 0.61mm Colorbond Coolmax - Backtray Flashing - 1200mm (650 dia)
checkpoint | Penetration - 0.61mm Colorbond Coolmax - Backtray Flashing - 1500mm (1000mm dia)
checkpoint | Penetration - 0.61mm Colorbond Coolmax - Backtray Flashing - 1800mm (1200mm x 1200mm)
checkpoint | Dektite #3
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Paint Shop - Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Colorbond Coolmax
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Pops - 0.61mm Colorbond - 150mm
checkpoint | Downpipe - 0.40mm Colorbond - 150mm dia
checkpoint | Downpipe Clips (150mm)
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Paint Shop - Internal Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Roof Sarking: Proctor Wrap HTS-IT or Fletchers Vapa Wrap for metal roof
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Structural Works | [5 empty] | Structural Works (Paint Shop - Internal Roof)
section | Material Inspection
checkpoint | Roof Truss End Support
checkpoint | Roof Top Hat 50mm
checkpoint | Roof Truss 450mm
section | Installation
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Dangerous Goods Store)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Roof Sarking: Proctor Wrap HTS-IT or Fletchers Vapa Wrap for metal roof
checkpoint | Coating Type: Coolmax Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Dangerous Goods Store)
section | Material Inspection
checkpoint | Flashing Material: Colorbond Coolmax
checkpoint | Barge Capping Material: Coolmax
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary MAX 40mm
checkpoint | Compression Flashing Fixings Max 100mm
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Dangerous Goods Store)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 100mm Dia 0.4mm colorbond
checkpoint | Pops: 100mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 100mm colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation | [5 empty] | Roof Installation Checklist (Rain Water Test Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond Coolmax Kliplok/ Speed Deck Ultra
checkpoint | Roof Sarking: Proctor Wrap HTS-IT or Fletchers Vapa Wrap for metal roof or mediumweight paper
checkpoint | Coating Type: Coolmax Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 12 Gauge x 40mm Hex Head Type 17 screws
checkpoint | Infill Strips
section | Installation
checkpoint | 3 Screws per Clip
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation | [5 empty] | Flashing/Capping Installation Checklist (Rain Water Test Roof)
section | Material Inspection
checkpoint | Flashing Material: Colorbond Coolmax
checkpoint | Barge Capping Material: Coolmax
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary MAX 40mm
checkpoint | Compression Flashing Fixings Max 100mm
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Ensure Cappings have minimum 3° fall back into the roof
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation | [5 empty] | Quad Gutter Installation Checklist (Rain Water Test Roof)
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter Brackets: External 3mm Podercoated 900mm Centres
checkpoint | Gutter Flashing:
checkpoint | Downpipes: 100mm Dia 0.4mm colorbond
checkpoint | Pops: 100mm round 0.61mm Colorbond
checkpoint | 19mm Structural Plyboard to support Fascia
checkpoint | Metal Fascia support Angle (2x length of plyboard)
checkpoint | Downpipe Clips for 100mm colorbond
section | Installation
checkpoint | Plywood support to fascia
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | Size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe clips Max 2m spacing
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: