## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | GIB Installation QA |  |  |  |  | Yes | GIB Installation QA | 0789c6a4-4304-4be8-a2d0-5f33925816b1
checkpoint-group |  |  | section | Job Details
checkpoint-status |  |  | checkpoint | Area
text | b55f156c-5dea-5bb0-89e3-aa1207571c68 |  | textbox | Level:
text | a34946ad-4d17-5b9b-8e5c-a42821ea7db0 |  | textbox | Elevation:
text | 1463407b-00bd-5293-8de3-f589422282f9 |  | textbox | Between Grids:
checkpoint-status |  |  | checkpoint | Team
text | 2afc2d4a-b034-5dde-8b10-faac7dd648e8 |  | textbox | Site Supervisor:
text | a944878c-799c-5cd0-91cc-31b62154d48f |  | textbox | Site Installers:
checkpoint-status |  |  | checkpoint | Symonite drawing/detail referenced for construction
checkpoint-status |  |  | checkpoint | Product Install manuals
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Has framing been signed off and handed over by the main contractor.
label | f9b5add5-2600-524f-8c46-0de2c8eb8e77 |  | note | Note: photo document.
checkpoint-status |  |  | checkpoint | Confirm framing layout provides adequate fixing points to be able to meet the required fixing centres.
label | 97237c15-ff8f-5dd1-9de5-ad6d99ee0ea8 |  | note | Note: photo handover area
checkpoint-status |  |  | checkpoint | Confirm appropriate access has been provided.
checkpoint-status |  |  | checkpoint | Confirm GIB Weatherline board is 13mm thick
checkpoint-group |  |  | section | Sheet fixing and set out
checkpoint-status |  |  | checkpoint | Confirm correct fixings used.
label | e10f33dc-908d-5c44-95bd-5c22fb637cda |  | note | Note: 2. 41mmx6g Gib Grabber Ceramic Coated High Thread Screws for Timber
checkpoint-status |  |  | checkpoint | Confirm correct fixings set out
label | 65f2f04b-b8e3-59b4-8c66-1b869d423c0f |  | note | Note: 75mm from the corner edge. 200mm on centres for Studs 400mm centres and below. 100mm screw centres for studs more than 400mm centres
label | f3843695-00bf-5ab2-b0d6-a57139142ae1 |  | note | Minimum 12mm from bound edge
label | a9f29f28-f881-5aa1-9459-6d0691dd3abf |  | note | Minimum 18mm from cut edge
label | f5017a8d-acef-5a71-bb8b-cea1be463d1b |  | note | Maximum 58mm from the top edge (seismic gap)
checkpoint-status |  |  | checkpoint | Confirm GIB Board that is to be installed is dry.
checkpoint-status |  |  | checkpoint | Confirm Gib Weatherline joint is at the centre of studs and nogs
checkpoint-status |  |  | checkpoint | Screw head is flushed to the surface and not overdriven
checkpoint-status |  |  | checkpoint | Screws minimum 25mm distance to each other
checkpoint-status |  |  | checkpoint | Screws maximum 12 pcs per linear metre
checkpoint-status |  |  | checkpoint | Exposed edge is taped
checkpoint-status |  |  | checkpoint | Conform the panels overhang the bottom plate as per drawing
label | 07e1b61f-bdac-5392-a331-13b8e483921f |  | note | Note: Flush to bottom plate for Levels 1-2
label | ab635817-378a-517a-8a5a-aad4f7c83f8b |  | note | 15mm past bottom plate for Ground Floor
checkpoint-group |  |  | section | Penetrations
checkpoint-status |  |  | checkpoint | Confirm penetrations have been set out as per symonite elevations
checkpoint-status |  |  | checkpoint | Penetrations through GIB is to be constructed in line with Symonite drawing
checkpoint-status |  |  | checkpoint | Confirm main contactor has determined if council inspection is required prior to hand over AND Confirm main contractor has been given opportunity to coordinate council inspection.
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Confirm work area clean, tidy and all quality assurance issues resolved in this area.
label | 48f18430-fe7f-5384-b7cd-27514e6215e5 |  | note | Note: photo area
checkpoint-status |  |  | checkpoint | Confirm main contractor has inspected area prior to hand over.
checkpoint-status |  |  | checkpoint | Confirm written communication stating main contractor has accepted has been received.
checklist-sectioned |  |  | checklist | Proclima Underlay Installation QA |  |  |  |  | Yes | Proclima Underlay Installation QA | 0f5f9ef4-b04c-48d3-b905-2bba1eb88163
checkpoint-group |  |  | section | DETAILS
checkpoint-status |  |  | checkpoint | Project details
text | a8e2b22b-f253-5c94-be9e-161f17545e7c |  | textbox | Project Name:
text | dcd4d15d-67f4-533d-bbee-a313010d8c10 |  | textbox | Address:
text | d5eceec3-8c18-56b4-978c-57e8ce2525a4 |  | textbox | Level/Area:
select | 5c63db20-9739-5cb2-9002-4fb17115e24a |  | dropdown | Rigid wall underlay (RWU) and/or Roof Sarking (RS) type: | Fibre Cement, Ply, OSB, SIP, CLT, Glass faced Gypsum, Other
text | 8501914a-413b-5a00-92d5-eb5110db79dc |  | textbox | Specify if other:
text | 0eb9899e-8638-5fc1-967d-e220431345ac |  | textbox | RWU/RS thickness: |  |  | mm
checkpoint-group |  |  | section | RIGID WALL UNDERLAY / ROOF SARKING
checkpoint-status |  |  | checkpoint | Check the RWU or RS has been installed in accordance with the Architects drawings
checkpoint-status |  |  | checkpoint | Check the RWU or RS has been installed as per manufacturers guidelines
checkpoint-status |  |  | checkpoint | Check there are no fixings or sharp objects protruding from the RWU or RS
checkpoint-status |  |  | checkpoint | Check RWU or RS is dry & free of contaminants before applying the ADHERO
checkpoint-status |  |  | checkpoint | Brush, wipe or vacuum the RWU or RS surface to remove any loose pieces, dust, dirt or other material that may be present, before applying the ADHERO
checkpoint-group |  |  | section | HORIZONTAL INSTALLATION
checkpoint-status |  |  | checkpoint | Line the internal & external corners of the RWU with a vertical 400mm wide strip of ADHERO, with min 150mm overlap on either side (option)
checkpoint-status |  |  | checkpoint | Remove the 250mm release paper from the back of the ADHERO, and apply to RWU at a pre-marked height. Apply pressure using a PRESSFIX XL or rubber roller
checkpoint-status |  |  | checkpoint | Remove the 2nd release paper, smooth down from centre of sheet, working outwards and applying pressure with a PRESSFIX XL or 150mm hard rubber roller
checkpoint-status |  |  | checkpoint | Overlap ADHERO sheets in a shingle fashion working upwards. Observe sheet markings for 150mm overlap to all sheets, and to the edges of the RWU
checkpoint-status |  |  | checkpoint | Work all air bubbles in ADHERO to sheet edge, and flatten all creases. (See 2.5b) Seal ADHERO to foundation surfaces with 5mm bead of ORCON sealant
checkpoint-group |  |  | section | VERTICAL INSTALLATION
checkpoint-status |  |  | checkpoint | Remove both release papers from back of ADHERO and adhere from top down, following a pre marked vertical line
checkpoint-status |  |  | checkpoint | Overlap sheets by 150mm min at vertical joins, and to the bottom edge of the RWU
checkpoint-status |  |  | checkpoint | Firmly press ADHERO evenly across the sheet using PRESSFIX XL or rubber roller Work all air bubbles in ADHERO to sheet edge, and flatten all creases where possible
checkpoint-status |  |  | checkpoint | Apply TESCON EXTORA 60mm tape to 100mm either side of any creases that terminate at the sheet edge or vertical overlap
checkpoint-group |  |  | section | OTHER PENETRATIONS THROUGH ADHERO
checkpoint-status |  |  | checkpoint | Use ROFLEX grommets and TESCON EXTORA 60 tape to seal all pipe penetrations made through the ADHERO. Refer to the ROFLEX installation guide
checkpoint-status |  |  | checkpoint | Use KAFLEX grommets and TESCON EXTORA 60 tape to seal all round cable penetrations made through the ADHERO. Refer to the KAFLEX installation guide
checkpoint-status |  |  | checkpoint | Use TESCON EXTORA 60 tape to seal all other penetrations made through the ADHERO that are not possible to seal with ROFLEX or KAFLEX grommets
checkpoint-status |  |  | checkpoint | Repair all cuts and tears in ADHERO with TESCON EXTORA 100 tape, to a minimum 50mm past the edges of the damaged area.
checkpoint-status |  |  | checkpoint | Repair larger holes in ADHERO with another piece of ADHERO, allowing for min 150mm cover past the damaged area on all sides. Then apply EXTORA 60mm tape across the top and sides of the ADHERO patch
checkpoint-status |  |  | checkpoint | Seal screw penetrations through ADHERO from cladding attachments with TESCON NAIDECK butyl tape or EXTOSEAL sill tape. Discuss with the cladding/roofing installer before handing over areas to be clad.
checkpoint-group |  |  | section | CLADDING OVER THE ADHERO
checkpoint-status |  |  | checkpoint | If ADHERO is fully exposed during construction (ie not protected by shrinkwrap), record the 1st day of its exposure (or installation) here
text | 7a8be502-e13e-5235-aaf9-fb97ace60c6b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Record the last day of possible exposure (180 days or 6 months after installation) Ensure cladding or temporary covering of the ADHERO is in place by this date
text | fb92314f-a9ef-5bed-a2b1-f62109123685 |  | textbox | Date:
checkpoint-group |  |  | section | Signoff
checkpoint-status |  |  | checkpoint | Installer name and signature
text | a4f39f28-8552-5122-a031-6110219944a4 |  | textbox | Name:
holdpoint |  |  | signoff | Insert signature
checklist-sectioned |  |  | checklist | Hook and Pin System QA |  |  |  |  | Yes | Hook and Pin System QA | 77d26d5b-628d-4edc-82c4-878aa62388ce
checkpoint-group |  |  | section | Job Details
checkpoint-status |  |  | checkpoint | Area
text | 84c1fcea-54a0-5590-a007-e0c64f126f61 |  | textbox | Level:
text | c68c82e8-2144-50fd-9b40-d96ac5cd9eab |  | textbox | Elevation:
text | eef2e0a3-9cf0-5fbc-b1a3-17d78b9f69b8 |  | textbox | Between Grids:
checkpoint-status |  |  | checkpoint | Team
text | 8b73d4f0-6a4a-59fb-8df2-418ff11c8cb8 |  | textbox | Site Supervisor:
text | 2097c53f-c682-59c5-ae86-e60808d06752 |  | textbox | Site Installers:
checkpoint-status |  |  | checkpoint | Symonite drawing/detail referenced for construction
checkpoint-status |  |  | checkpoint | Product Install manuals
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Siderise and Insulation QA been completed?
label | 4b781057-3085-5656-b053-c622617881cd |  | note | Note: photo document.
checkpoint-group |  |  | section | F Brackets
checkpoint-status |  |  | checkpoint | Location in accordance to drawing
checkpoint-status |  |  | checkpoint | Blue butyl pad with butyl tape present
checkpoint-status |  |  | checkpoint | Screw size is as per drawing and on the timber studs
checkpoint-status |  |  | checkpoint | Adjacent lengths must be tightly butted
checkpoint-group |  |  | section | T-Rail
checkpoint-status |  |  | checkpoint | Screwed to the F-bracket as per drawing
checkpoint-status |  |  | checkpoint | Plumb and Straight
checkpoint-status |  |  | checkpoint | Not damaged or bent
checkpoint-status |  |  | checkpoint | Expansion joining if needed, minimum 4 mm
checkpoint-group |  |  | section | Panels
checkpoint-status |  |  | checkpoint | Hanging pin aligned and fixed to rail as per drawing
checkpoint-status |  |  | checkpoint | Panel seating perfectly onto the hanging pin. Plumb and straight
checkpoint-status |  |  | checkpoint | Panel secured properly
label | 42883a18-35e8-58bf-b857-509c5ff1e5eb |  | note | Note: photo area
checkpoint-status |  |  | checkpoint | Confirm main contractor has inspected area prior to hand over.
checkpoint-status |  |  | checkpoint | Confirm written communication stating main contractor has accepted has been received.
checklist-sectioned |  |  | checklist | Insulation and Siderise QA |  |  |  |  | Yes | Insulation and Siderise QA | a3e98abe-09de-4b1a-a5e7-34b3af324892
checkpoint-group |  |  | section | Job Details
checkpoint-status |  |  | checkpoint | Area
text | 9cf9a277-7a54-58d8-a87d-8af61b9a5f58 |  | textbox | Level:
text | c1b27350-ce82-5da0-b099-00702f302d7d |  | textbox | Elevation:
text | 951cdbc1-4988-5246-b7dc-495eaa5acda6 |  | textbox | Between Grids:
checkpoint-status |  |  | checkpoint | Team
text | 285e5fe3-e075-5af9-8ca1-09df4d962ebf |  | textbox | Site Supervisor:
text | c9228479-d3f2-54c8-965d-cc4371c226bc |  | textbox | Site Installers:
checkpoint-status |  |  | checkpoint | Symonite drawing/detail referenced for construction
checkpoint-status |  |  | checkpoint | Product Install manuals
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Has building wrap been completed and QA been signed of by Main contractor.
label | 8a781828-4621-5475-9409-ea78fbd849ae |  | note | Note: photo document.
checkpoint-group |  |  | section | Siderise RH50-30/30 + RV90/60 Horizontal Cavity Barrier
checkpoint-status |  |  | checkpoint | Location in accordance to drawing
checkpoint-status |  |  | checkpoint | 1mm Thick Siderise SS support bracket at 400mm centres
checkpoint-status |  |  | checkpoint | Fixing is along centre line of the strip
checkpoint-status |  |  | checkpoint | Adjacent lengths must be tightly butted
checkpoint-status |  |  | checkpoint | Ensure label side is facing out into cavity
checkpoint-status |  |  | checkpoint | Siderise tape is applied properly top and bottom
label | cd97a432-1923-5773-8b2c-2896e55c1c95 |  | note | Note: photo completed area
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Impaler Pins with butyl pad screws to the timber beam at least 2 every insolation board. Min 5 impalers each board
checkpoint-status |  |  | checkpoint | Thickness of the insulation used is correct. 100mm at the wall.
checkpoint-status |  |  | checkpoint | Adjacent lengths must be tightly butted
checkpoint-status |  |  | checkpoint | Beads, clips, installed
checkpoint-group |  |  | section | HILTI CFS-SP SIL FIRESTOP JOINT SPRAY
checkpoint-status |  |  | checkpoint | Applied on the back of the spandrel panels
checkpoint-status |  |  | checkpoint | Minimum 2mm wet thickness
checkpoint-status |  |  | checkpoint | Overlapping minimum 13mm onto adjacent assemblies
label | 3621647a-964a-53d3-986f-98fbd2ac3b73 |  | note | Note: photo area
checkpoint-status |  |  | checkpoint | Confirm main contractor has inspected area prior to hand over.
checkpoint-status |  |  | checkpoint | Confirm written communication stating main contractor has accepted has been received.
checklist-sectioned |  |  | checklist | Windows, Doors, Louvers and Curtain Wall QA |  |  |  |  | Yes | Windows, Doors, Louvers and Curtain Wall QA | eb824446-35cf-40be-9f6f-3b91344d2803
checkpoint-group |  |  | section | Job Details
checkpoint-status |  |  | checkpoint | Area
text | a1968a60-4a19-574c-b44f-4bb7c90a8bd8 |  | textbox | Level:
text | 42f173bd-b3ae-566a-86f6-0ed6bbd89b06 |  | textbox | Elevation:
text | e133f48e-0086-5c3a-8a02-feb817fb8631 |  | textbox | Between Grids:
checkpoint-status |  |  | checkpoint | Team
text | 2ce5a48f-41fa-57f5-b13b-32bd2b9b57e4 |  | textbox | Site Supervisor:
text | fac60612-88b9-5a26-a025-d33dae243192 |  | textbox | Site Installers:
checkpoint-status |  |  | checkpoint | Symonite drawing/detail referenced for construction
checkpoint-status |  |  | checkpoint | Product Install manuals
checkpoint-group |  |  | section | Pre-start
checkpoint-status |  |  | checkpoint | Has building wrap been completed and QA been signed of by Main contractor.
label | de32856a-53b4-5cb4-b30e-3a368401c82a |  | note | Note: photo document.
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Check the dimension and squareness
checkpoint-status |  |  | checkpoint | Confirm Tescon Extoseal and separator is applied to window opening Application Guide.
checkpoint-status |  |  | checkpoint | Screws along frames with weatherseal at the head of each screws
checkpoint-status |  |  | checkpoint | Head and Sill Flashing as per drawing and in good condition
checkpoint-status |  |  | checkpoint | Silicon applied properly and on the right thickness. Minimum 10mm
checkpoint-status |  |  | checkpoint | Protection tape is applied
label | 5662db50-fe0d-5773-a38e-3b30b6eb1d79 |  | note | Note: photo completed membrane area (including penetration in present)
checkpoint-group |  |  | section | Glass
checkpoint-status |  |  | checkpoint | Glass without scratch, chip and permanent damage
checkpoint-status |  |  | checkpoint | Glass measurement, thickness, type, and colour according to shop drawing
checkpoint-status |  |  | checkpoint | Setting blocks and gasket installed properly
checkpoint-status |  |  | checkpoint | Beads, clips, installed
checkpoint-status |  |  | checkpoint | Confirm main contractor has been given opportunity to inspect the area.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Confirm work area clean, tidy and all quality assurance issues resolved in this area.
label | e43995ea-c82c-5ac8-b8ee-e964740c553d |  | note | Note: photo area
checkpoint-status |  |  | checkpoint | Confirm main contractor has inspected area prior to hand over.
checkpoint-status |  |  | checkpoint | Confirm written communication stating main contractor has accepted has been received.