## Resources
type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist | In Situ: |  |  |  |  | Yes | In Situ Concrete Pour Checklist | 7ff23fb8-fd3f-448a-8614-f743e3a54c8c
section | Job Details
checkpoint | Information
textbox | Wall No
textbox | Pour Location
textbox | Placer
textbox | Pour Date
textbox | Job Number
textbox | Concrete Strength
textbox | Slump Required
textbox | Admixtures
textbox | Max Aggregate Size
textbox | Wall type / Finish
checkpoint | Tests required
button | Cylinders | YES, NO
button | Slump | YES, NO
tickbox | Drawing Check
tickbox | Checked architectural drawings and details
tickbox | Checked structural drawings and details
tickbox | Pre-Construction Approvals
tickbox | Client/Engineer Inspection completed
tickbox | Starter bars check location level, laps
section | Pre Pour
checkpoint | Pre Pour Inspection
tickbox | Formwork - check location, alignment, dimensions, plumb
tickbox | Formwork - bracing, support, form ties, release agents
tickbox | Formwork - check position of fillets, chamfers
tickbox | Location match as per pour plan
tickbox | Final survey point / levels check
tickbox | Final clean out prior to pour
checkpoint | Hold Down Bolts
tickbox | Position correct
tickbox | Surveyed date
checkpoint | Cast in items
tickbox | Block outs - size, location
tickbox | Floor starters - size, location
tickbox | Drossbach starters - size, location
checkpoint | Set downs
tickbox | Positions match arch plans
tickbox | Depths correct
tickbox | Braced adequately
checkpoint | Pre pour discussion points
tickbox | Emergency evacuation point discussed
tickbox | Pour Methodology discussed & confirmed
tickbox | Concrete pump locations discussed & confirmed
tickbox | Clear right of way for concrete trucks to deliver
tickbox | Turning circle for concrete trucks to be discussed & agreed
tickbox | Morning prestart location & time to be confirmed
note | Note All sections are to be completed prior to pouring concrete
checkpoint | Concrete Dockets Attached/Sent
textbox | Start Time
textbox | Finish Time
textbox | Weather
textbox | Pour Volume
textbox | Rejected / Waste
checkpoint | Final Approvals
tickbox | FWL Company Foreman
tickbox | Main Contractor Rep
tickbox | FWL Company Project Manager
section | Post Pour
checkpoint | Post Pour Checks
tickbox | Strip formwork
tickbox | Repairs and patching
tickbox | Notes
textbox | Non-compliance
textbox | Action required
textbox | Comments
checkpoint | Final Approvals
tickbox | FWL Company Foreman
tickbox | Main Contractor Rep
tickbox | FWL Company Project Manager
checklist | Remedial: |  |  |  |  | Yes | Remedial Checklist | 947a6e1d-5b45-4ab2-a683-00ad10341bc8
section | Job Details
checkpoint | Information
textbox | Building No
textbox | Pour Location
textbox | Placer
textbox | Pour Date
textbox | Job Number
textbox | Concrete Strength
textbox | Slump Required
textbox | Admixtures
textbox | Max Aggregate Size
textbox | Finish
checkpoint | Tests required
button | Cylinders | YES, NO
button | Slump | YES, NO
checkpoint | Drawing Check
tickbox | Checked architectural drawings and details
tickbox | Checked structural drawings and details
checkpoint | Pre-Construction Approvals
tickbox | Foundation inspection completed
tickbox | In ground drainage completed and tested (see drainage check sheet QA)
tickbox | In ground services completed and tested
tickbox | Starter bars check location level, laps
section | Pre Pour
checkpoint | Pre Pour Inspection
tickbox | Formwork - check location, alignment, dimensions, plumb
tickbox | Formwork - bracing, support, form ties, release agents
tickbox | Formwork - check position of fillets, chamfers
checkpoint | Rebates
tickbox | Positions match arch plans
tickbox | Depths correct
checkpoint | Cast in items
tickbox | Block outs - size, location
tickbox | Floor starters - size, location
tickbox | Drossbach starters - size, location
checkpoint | Set downs
tickbox | Positions match arch plans
tickbox | Depths correct
tickbox | Braced adequately
tickbox | Pre pour plan match up completed
checkpoint | Hold Down Bolts /Shear Keys
tickbox | Position correct
tickbox | Surveyed date
checkpoint | Stop Ends
tickbox | Construction joints braced sufficiently Tied Top & Bottom
tickbox | Location match as per pour plan
tickbox | Correct pours around mesh, adequate supervision required regarding concrete installation and vibration
tickbox | Construction joints, control joints
tickbox | Final survey point / levels check
tickbox | Final clean out prior to pour
checkpoint | Pre pour discussion points
tickbox | Emergency evacuation point discussed
tickbox | Pour Methodology discussed & confirmed
tickbox | Concrete pump locations discussed & confirmed
tickbox | Clear right of way for concrete trucks to deliver
tickbox | Turning circle for concrete trucks to be discussed & agreed
tickbox | Morning prestart location & time to be confirmed
checkpoint | FWL Sign Off
tickbox | Will Puketapu
tickbox | Regan Howley
tickbox | Other Site Supervisor
note | Note All sections are to be completed prior to pouring concrete
checkpoint | Concrete Dockets Attached/Sent
textbox | Start Time
textbox | Finish Time
textbox | Weather
textbox | Pour Volume
textbox | Rejected / Waste
section | Post Pour
checkpoint | Post Pour Checks
tickbox | Concrete curing procedures in place
tickbox | Confirm saw cut
tickbox | Strip formwork
tickbox | Repairs and patching
tickbox | Floor height QA completed
tickbox | Notes
textbox | Non-compliance
textbox | Action required
checkpoint | Post Pour Actions
tickbox | Saw cuts completed
tickbox | Precast panels starters marked out
checkpoint | Final Approvals
tickbox | FWL Company Foreman
tickbox | Main Contractor Rep
tickbox | FWL Company Project Manager
checklist | Concrete Pour Checklist |  |  |  |  | Yes | Concrete Pour Checklist | cdc66c7a-0ceb-49cc-b7ab-47ad871e9c82
section | Job Details
checkpoint | Information
textbox | Pour Location
textbox | Placer
textbox | Pour Date
textbox | Concrete Strength
textbox | Slump Required
textbox | Admixtures (if requested for VO purposes)
textbox | Finish
textbox | Tests ordered
textbox | Curing type required
section | Pre Pour
checkpoint | Pre Pour Inspection
tickbox | Formwork - check location, alignment, dimensions, plumb
tickbox | Formwork - bracing, support, form ties, release agents
tickbox | Formwork - check position of fillets, chamfers
checkpoint | Rebates
tickbox | Positions match arch plans
tickbox | Depths correct
checkpoint | Set downs
tickbox | Positions match arch plans
tickbox | Depths correct
tickbox | Braced adequately
tickbox | Pre pour plan match up completed
checkpoint | Items needing checking
tickbox | HD Bolts Position
textbox | Final survey date
tickbox | Share Keys installed
tickbox | Block starters installed
tickbox | Panel starters installed
tickbox | Dross bach's installed
checkpoint | Stop Ends
tickbox | Construction joints braced sufficiently Tied Top & Bottom
tickbox | Location match as per pour plan
tickbox | Correct pours around mesh, adequate supervision required regarding concrete installation and vibration
tickbox | Construction joints, control joints
tickbox | Final survey point / levels check
tickbox | Final clean out prior to pour
button | Are these stop ends a variation? | YES, NO
checkpoint | M2 installed
checkpoint | Pre pour discussion points
tickbox | Emergency evacuation point discussed
tickbox | Pour Methodology discussed & confirmed
tickbox | Concrete pump locations discussed & confirmed
tickbox | Clear right of way for concrete trucks to deliver
tickbox | Turning circle for concrete trucks to be discussed & agreed
tickbox | Morning prestart location & time to be confirmed
checkpoint | Concrete pour final details/checks
tickbox | Curing organised
tickbox | Concrete cutter organised
textbox | Start Time
textbox | Finish Time
textbox | Weather
textbox | Pour Volume
textbox | Rejected / Waste
section | Post Pour
checkpoint | Post Pour Checks
tickbox | Concrete curing procedures in place
tickbox | Confirm saw cut
tickbox | Mark saw cuts before water curing begins
tickbox | Concrete height check
textbox | Formwork strip date
tickbox | Hiab booked for pick up
tickbox | Strip formwork
tickbox | Repairs and patching
tickbox | Floor height QA completed
checkpoint | Concrete Dockets Attached/Sent
checkpoint | Notes
textbox | Non-compliance
textbox | Action required
checkpoint | Post Pour Actions
tickbox | Saw cuts completed
tickbox | Curing completed
tickbox | Height check completed
tickbox | Precast panels starters marked out