## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - Pavement Rehabilitation |  |  |  |  | Yes | ITP - Pavement Rehabilitation | 10693694-4aa3-4027-87b2-74fd2c18ef06
checkpoint-group |  |  | section | 1.0 PRECONSTRUCTION HOLD POINTS
checkpoint-status |  |  | checkpoint | 1.1 Agree QA Requirements
label | 4909e7a8-e300-5f79-96f3-aa958bcdc564 |  | note | SPECIFICATION REFERENCE: ITP
label | e2c7bef1-e029-5b6e-975a-328ed88bd150 |  | note | TEST REQUIRED: Check pricing and ITPs & notify Westlink of any difference in understanding of specification requirements
label | dd2f68b0-5d5e-581a-9ee4-bcaef48165e4 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Review ITP and confirm minimum quality requirements are understood prior to construction handover meeting.
label | 67226033-4394-56c3-895d-7eb9d3e5ba61 |  | note | TASK ASSIGNED TO: Construction Project Manager
label | 19f6b3c5-78ef-5363-a25d-cd76176d0a70 |  | note | ACCEPTANCE CRITERIA: Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.2 Confirm nominated project manager, supervisor, foreman, finishing grader operator
label | 3c8a4285-1ddb-5dc9-8cf7-4077a4d8d8ef |  | note | SPECIFICATION REFERENCE: NTP
label | 1e817c77-df16-5ed8-bb83-18d00a964eff |  | note | TEST REQUIRED: Meeting
label | 352f51c8-fe45-59fd-85a9-6e817380aa0e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 24 hours notice prior to construction handover meeting.
label | c4b2077e-eab0-5902-a1ab-214b82869c94 |  | note | TASK ASSIGNED TO: Construction Project Manager
label | 9431cdf8-9217-57c3-9bb0-5da6da4fc192 |  | note | ACCEPTANCE CRITERIA: Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.3 Submit resident letter for approval
label | 111c1924-3835-5629-a2ba-76d8688a7473 |  | note | SPECIFICATION REFERENCE: NTP
label | 9638de78-8424-5006-937f-9fb5f72a5973 |  | note | TEST REQUIRED: Submit letter to Delivery Manager for review and approval
label | 484b60bd-eaf6-5003-8dc0-2a579be1989e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 48 hours prior to letter box drop
label | 6519e648-0098-5efa-82b7-b20e4d85b34e |  | note | TASK ASSIGNED TO: Construction Project Manager
label | a5e651ba-3054-57bf-94cb-bd6304d8dfbf |  | note | ACCEPTANCE CRITERIA: Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.4 Construction Handover Meeting
label | 356883a5-6f01-5293-9765-bb9c623a2eb4 |  | note | SPECIFICATION REFERENCE: NTP
label | 667e7f13-90e3-5c08-8c2d-33a9d05cf2a1 |  | note | TEST REQUIRED: Meeting
label | d97a8747-0466-5da5-af7c-5f339bc057f2 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Minimum 48 hours prior to planned commencement of physical works.
label | e86824cf-aa5d-59ac-89e8-ea68c60dbc14 |  | note | TASK ASSIGNED TO: Construction Project Manager
label | 47c28e58-2b63-57ae-9514-1778dd738619 |  | note | ACCEPTANCE CRITERIA: Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.5 Physical works Programme
label | e77f84e9-e56b-519e-8133-ffbebf09f66c |  | note | SPECIFICATION REFERENCE: Physical works Programme to be uploaded to WestLink Sharepoint site, emailed to WestLink Delivery Manager and start and end dates to by updated in RAMM Contractor prior to physical works.
label | d15ae509-0a30-5a84-9822-785cb3d05e54 |  | note | TEST REQUIRED: NTP
label | 10d4ee0d-7a06-5d79-9764-9f262e693e78 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Minimum 10 working days prior to commencement of physical works.
label | 6b4605ac-187c-530d-89df-3fd3518f44af |  | note | TASK ASSIGNED TO: Construction Project Manager
label | 63107b9c-3437-5df7-99cb-319d90e5bc9f |  | note | ACCEPTANCE CRITERIA: Confirmation received by Delivery Manager by scheduled task timing
checkpoint-group |  |  | section | 2.0 SUBGRADE CONSTRUCTION (WIDENING AND UNDERCUT AREAS)
checkpoint-status |  |  | checkpoint | 2.1 Formation
label | 926a71bd-ada4-5e3a-9929-62beae58adae |  | note | SPECIFICATION REFERENCE: TNZ F/1 11.2.1
label | 625e38da-2af0-5855-a655-7d9a2bc6a26d |  | note | TEST REQUIRED: 3m straight edge
label | 9ab714c5-b350-5f90-a769-fc45ab61b65e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 20m centres alternate lanes - 57 tests (undercut areas additional)
label | 62ff475a-e6fb-5527-bc6c-cbe4feace498 |  | note | TASK ASSIGNED TO: Pavement subcontractor quality representative
label | 7bbdc01d-532a-53d6-903e-c7d7b9f734f3 |  | note | MEASURING DEVICES OR METHOD: 3m straight edge, tape measure
label | e4d48d78-8a01-57e8-8429-5c58071a28d3 |  | note | ACCEPTANCE CRITERIA: +/- 30mm
label | 95b6f46c-2614-572c-9c9b-a25ececb45f4 |  | note | QUALITY DOCUMENTATION: Inspection checklist
checkpoint-status |  |  | checkpoint | 2.2 Finished Level
label | cd096726-20f8-5c3f-9b7e-e77541d111f0 |  | note | SPECIFICATION REFERENCE: TNZ F/1 11.2.2
label | 22377324-cf45-5507-a544-54615998c033 |  | note | TEST REQUIRED: String line or approved alternative
label | c3176dbf-3e00-59b1-bd43-88353f16404f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 20m centres alternate lanes - 57 tests (undercut areas additional)
label | 6f7ec489-65be-5d42-892a-ec05caf06e56 |  | note | TASK ASSIGNED TO: Pavement subcontractor quality representative
label | e534e8fc-c37b-56d1-ac0e-abd35e88bc62 |  | note | MEASURING DEVICES OR METHOD: Stringline, tape measure
label | bd8d2ea7-8567-5a13-97ef-8f517e0e9d63 |  | note | ACCEPTANCE CRITERIA: +0mm / -30mm
label | e43108ab-c931-562e-9b7d-c916567c9a1d |  | note | QUALITY DOCUMENTATION: Inspection checklist
checkpoint-status |  |  | checkpoint | 2.3 Bearing strength
label | 5ba1d971-e928-5a29-841f-486c7b3f9558 |  | note | SPECIFICATION REFERENCE: Design
label | d13e6666-40cd-5d1d-9bb3-f35a5b1bbd9d |  | note | TEST REQUIRED: Inferred CBR
label | 7003a0fd-d93c-5eb2-af2b-cef8dfbc7dc6 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 20m centres alternate lanes - 57 tests (undercut areas additional)
label | df176773-a415-505f-96bd-da486d486e46 |  | note | TASK ASSIGNED TO: Pavement subcontractor quality representative
label | c1b3e8ff-f2fc-54a1-a48b-16f30e5ebbdc |  | note | MEASURING DEVICES OR METHOD: Scala penetrometer to NZS 4402 : 1988, Test 6.5.2. Inferred CBR from Austroads Pavement Design Manual 2004
label | c5a5b77a-e51a-538a-8331-a0f8bd00e7a3 |  | note | ACCEPTANCE CRITERIA: CBR ? 4
label | f571688e-ed23-57ed-8378-ac9bd10ae18c |  | note | QUALITY DOCUMENTATION: Inspection checklist
checkpoint-group |  |  | section | 3.0 SUBBASE MATERIAL TESTING
checkpoint-status |  |  | checkpoint | 3.1 Particle size distribution
label | ee74af8c-f9b5-5f51-9306-eb19292f1e26 |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | 288dd900-fadd-5966-9fbf-f1f9150c75a5 |  | note | TEST REQUIRED: Wet sieving test
label | a5563246-9b1c-5379-abbf-d1120aa5e8cb |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 sample per 1000m3 - 1 tests (1 test on same sample as MDD/OMC curve)
label | 87a42e6c-12d9-5e02-86b5-c6e9ce142270 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | bd331755-363a-5ae9-afdc-9d743f60ce21 |  | note | MEASURING DEVICES OR METHOD: NZS4407 4407 : 1991, Test 3.8.1
label | 8b3e417f-f843-5b58-93ae-b00b7bbe857c |  | note | ACCEPTANCE CRITERIA: 100% passing 63mm 55 – 80% passing 37.5mm 35 – 65% passing 19mm 20 – 50% passing 9.5mm 10 – 35% passing 4.75mm 2 – 20% passing 1.18mm ?6% passing 75micron
label | 9f601189-6d99-5d5c-a9f2-e63008abca31 |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 3.2 Sand equivalent
label | 5462fc4d-e38d-58c8-b44a-ef8fd25a4362 |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | 53e49327-c6ed-53c0-9e7c-e74fe2648584 |  | note | TEST REQUIRED: Sand equivalent
label | bd606d3f-350b-5caf-b334-21e898ef54f2 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 sample per 1000m3 - 1 tests
label | d14ff086-1157-538a-a14a-b3afc1a6d3f6 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 04c3f27b-d4ca-56f0-8a98-fa3556880fe7 |  | note | MEASURING DEVICES OR METHOD: NZS4407 : 1991, Test 3.6
label | 2a479ee9-0b9f-5539-8a99-3ea08788c103 |  | note | ACCEPTANCE CRITERIA: ? 25
label | 218e97ba-7825-5626-b2e6-450173a7803b |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 3.3 Crushing Strength
label | 9d403231-561d-5629-bb79-958a6d55b44f |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | 4052083e-98bc-5003-b1e9-3acdcabaab5a |  | note | TEST REQUIRED: Crushing Resistance Test
label | b2924580-e013-5687-ab6a-a4bf9b2e3ca6 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 sample per 1000m3 - 1 tests
label | 8649dd57-c69e-55d1-9904-ebc8bd3af200 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 7e9a5f47-3adf-589d-8888-23820c781471 |  | note | MEASURING DEVICES OR METHOD: NZS 4407 : 1991, Test 3.10
label | 8da085c6-076c-536a-bce1-8b2c23045411 |  | note | ACCEPTANCE CRITERIA: <10% fines passing 2.36mm under 110 KN load
label | af355666-a8aa-5ec0-bf7d-b0615d80694e |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 3.4 Soaked CBR
label | c0e33d1f-6700-5070-b487-60bc66264cd5 |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | dc2fa231-2ddd-578d-8308-35f9f5df7890 |  | note | TEST REQUIRED: Remoulded soaked CBR
label | f08a45c9-96f9-529d-abed-7e312cdd0365 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 sample per 1000m3 - 1 tests
label | c1e927b0-9de5-5e5d-8856-f7433417424f |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | bae2e1c1-fc2c-5821-a9ad-87a32c1749df |  | note | MEASURING DEVICES OR METHOD: Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
label | 2d575fe8-9931-5873-8250-968dcc7cdec9 |  | note | ACCEPTANCE CRITERIA: ? 80%
label | 89481adf-4016-5109-b90f-b0437f1f858e |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 3.5 Determination of MDD & OWC
label | dc5b5821-791d-5efa-89b5-d935c538b67b |  | note | SPECIFICATION REFERENCE: TNZ B/2 7.5, WBOPDC DC 2009, Cert 1E
label | e0972a3a-6f1a-5f6d-a635-1cb3ecaca0a7 |  | note | TEST REQUIRED: 5 point compaction curve
label | 5b011bc9-b3d7-5d29-8d21-b8ba1171fecf |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS:
label | 28248565-b151-5d2c-89a3-b15ab8a2470c |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | ad892f93-38f4-5c30-9553-0e896d25f2c2 |  | note | MEASURING DEVICES OR METHOD: NZS 4402 : 1986, Test 4.1.3
label | cc364818-6558-5685-ae66-90f89bcfb587 |  | note | ACCEPTANCE CRITERIA: report value only
label | 767aed7c-cb32-59f1-ae4b-c489ac1fe3fa |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 3.6 Weathering Quality
label | 9c31a76d-51cc-53b2-a7a5-60018e78d43e |  | note | SPECIFICATION REFERENCE: Design
label | d9667a26-6b64-54ab-bd7a-e122938b7fa2 |  | note | TEST REQUIRED: Weathering Quality Index Test
label | 6338d72b-498c-5f0e-a078-605da4537d81 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test per 10,000m3 (min 1 test) - 1 tests
label | bf5e60ce-938a-59e2-82a8-8eb1c49fc6dc |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | f495cf1a-36a3-50d3-b6bf-84092a76a51c |  | note | MEASURING DEVICES OR METHOD: NZS 4407 : 1991, Test 3.11
label | 5d7a0878-0d2e-58dd-b33c-909e211448dc |  | note | ACCEPTANCE CRITERIA: AA, AB, AC, BA, BB or CA
label | 9df169b1-1d99-5592-ae3e-c0027c12e58d |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 3.7 Solid Density
label | 0bc46822-daa1-5bf6-b140-f2aef10bcad2 |  | note | SPECIFICATION REFERENCE: TNZ B/2 7.5
label | 1f50c685-5d6d-5c8c-878b-f47d80263bd6 |  | note | TEST REQUIRED: Solid Density
label | 819d021a-d9ab-5e21-a36b-26f37c36920f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test per 10,000m3 (min 1 test) - 1 tests
label | 1ad0250a-99af-5cd6-8aea-50abf23669bc |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | fb0c0203-5ce1-5898-8639-33d0858e7553 |  | note | MEASURING DEVICES OR METHOD: NZS 4407 : 1991, Test 3.7
label | 2d37a6d4-1267-57e2-a961-37c9d430daf4 |  | note | ACCEPTANCE CRITERIA: report value only
label | c7e0beac-71b5-58c2-9a21-18b544a7472f |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-group |  |  | section | 4.0 SUBBASE LAYER CONSTRUCTION
checkpoint-status |  |  | checkpoint | 4.1 Finished Level
label | 5b0e79e8-0923-597b-b1b6-c3d16655e778 |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | 28d487af-59ef-58ed-b981-ce0a0e2932e4 |  | note | TEST REQUIRED: String line or approved alternative
label | 7cdc979a-135e-5624-90b6-e7dadd327288 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: centreline and edge of seal at 20m intervals - 129 Tests
label | 87e71a5b-1e5a-5770-bade-53c5b40f50fd |  | note | TASK ASSIGNED TO: Pavement subcontractor quality representative
label | 6a025cb4-a581-52c3-84f5-f590c6a47a39 |  | note | MEASURING DEVICES OR METHOD: Stringline, tape measure
label | 9ef164b3-1bc4-5bea-be51-fb527c7671a5 |  | note | ACCEPTANCE CRITERIA: +5mm / -25mm
label | 551ed695-a00c-5875-9326-b4e742605f3f |  | note | QUALITY DOCUMENTATION: Inspection checklist
checkpoint-status |  |  | checkpoint | 4.2 Compaction
label | 4ef156ea-73fd-5360-9ccf-f754b2f4bb55 |  | note | SPECIFICATION REFERENCE: TNZ B/2 7.6
label | 9cfbc18a-51c5-5f3b-b2d9-2efd34245041 |  | note | TEST REQUIRED: NDM - - testing limited to areas where subbase is at full depth
label | 6a4ccfcd-7992-5c6f-a6ac-0972b6755c19 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: min 5 tests per lot (max lot size = 1,000 m2) - 9 tests
label | 1e890173-49b7-5d56-a2ad-2022ac67ec99 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 8012b710-9b91-5f65-818e-78af0d228c0c |  | note | MEASURING DEVICES OR METHOD: NDM
label | 0877a206-9764-5913-85a5-611493a283f4 |  | note | ACCEPTANCE CRITERIA: Mean ? 95% MDD, Min ? 92%, Total voids ? 20%
label | 1e2e0e36-45cc-52bb-87bc-9d68b2276347 |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-group |  |  | section | 5.0 BASECOURSE LAYER MATERIAL TESTING - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | 5.1 Particle size distribution
label | c16697f8-b54d-5b2c-98a0-3ef926cac2e4 |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | d3156b66-4485-59c2-ad19-84fa3d3aeb31 |  | note | TEST REQUIRED: Wet sieving test
label | fa06c5db-98a8-5f8b-9e5c-1fc339902891 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 sample per 1000m3 - 1 tests (1 test on same sample as MDD/OMC curve)
label | 8b6e4eb8-ced1-53a6-9490-bdf8e03fa7a0 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 2e012a32-2407-580a-b09f-6ee940e86707 |  | note | MEASURING DEVICES OR METHOD: NZS4407 4407 : 1991, Test 3.8.1
label | 2674ad04-c744-5bcb-b6b8-b631ea1d28c9 |  | note | ACCEPTANCE CRITERIA: 100% passing 37.5mm 66 - 81% passing 19mm 43 - 57 passing 9.5mm 28 - 43 passing 4.75mm 19 - 33 passing 2.36mm 12 - 25 passing 1.18mm 7 - 19 passing 600µm 3 - 14 passing 300µm 0 - 10 passing 150µm 0 - 7 passing 75µm
label | a662af93-a0c4-5857-856c-f74644f3e466 |  | note | QUALITY DOCUMENTATION: IANZ Report
checkpoint-status |  |  | checkpoint | 5.2 Determination of MDD & OWC
label | 6666e4bb-5fc0-5849-8118-22dc8d30542f |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | 72d03668-15d5-5f5f-a445-c1973fa2bf51 |  | note | TEST REQUIRED: 5 point compaction curve
label | 79b5fd11-97bb-5f1a-9897-6ebda289b837 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test
label | 884cdecf-c653-5892-a498-5eb86f6e2f27 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | c67f2dfa-f4eb-5b00-b94f-96a8dcac2c9b |  | note | MEASURING DEVICES OR METHOD: NZS 4402 : 1986, Test 4.1.3
label | 233cd49a-b6e5-5144-ad1b-08e23c408966 |  | note | ACCEPTANCE CRITERIA: report value only
label | 37d9f2fa-8fa6-5266-8587-ddbb9fbce376 |  | note | QUALITY DOCUMENTATION: IANZ Report
checkpoint-status |  |  | checkpoint | 5.3 Crushing Strength
label | 886cb533-dc04-5d90-b18f-db9529f6b1ef |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | f83d8838-1dff-58ff-ac17-f9f060a0d162 |  | note | TEST REQUIRED: Crushing Resistance Test
label | 200b313e-e3bf-5173-ad2e-df8c6870b649 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 sample per 1000m3 - 1 tests
label | 5956cae8-3c29-585c-b84a-351121a71862 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 43498c1d-d7f4-55f9-9b08-15cde5615770 |  | note | MEASURING DEVICES OR METHOD: NZS 4407 : 1991, Test 3.10
label | 7760e646-7347-58e6-bfa1-bc4f49017c1e |  | note | ACCEPTANCE CRITERIA: <10% fines passing 2.36mm under 130 KN load
label | 62196167-fd32-54cb-8185-44d69c053ab8 |  | note | QUALITY DOCUMENTATION: IANZ Report
checkpoint-status |  |  | checkpoint | 5.4 Sand equivalent
label | 8e6f0843-f8c7-5679-9be9-609604e6b31a |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | d6a83970-81d0-5711-b793-a7f1c271e9a6 |  | note | TEST REQUIRED: Sand equivalent
label | 60115fda-e94e-5961-89a8-430cf3ad5721 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 sample per 1000m3 - 1 tests
label | 658a41cf-9952-5419-98aa-53f63f5fabd4 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 44183d7f-4e37-5742-82f6-bd98a55f0613 |  | note | MEASURING DEVICES OR METHOD: NZS4407 : 1991, Test 3.6
label | a50cb9c5-8750-518a-9c1b-617df6ae8e72 |  | note | ACCEPTANCE CRITERIA: ? 40
label | 3b037dd1-3bbf-52a1-baba-1e2bb8d2d179 |  | note | QUALITY DOCUMENTATION: IANZ Report
checkpoint-status |  |  | checkpoint | 5.5 Weathering Quality
label | ddec8d68-e192-5239-b3be-1b27155d01b6 |  | note | SPECIFICATION REFERENCE: TNZ M/4 3.3.2
label | 90d9337b-3520-51ef-bc2c-eb1c3d7f9199 |  | note | TEST REQUIRED: Weathering Quality Index Test
label | 3db2bda9-3517-58cf-9b67-f979a75878a2 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 0acfb604-af3a-5163-8035-31eb9dca04d7 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | e485edb1-c33f-5ab9-ba5b-3bf47e360d16 |  | note | MEASURING DEVICES OR METHOD: NZS 4407 : 1991, Test 3.11
label | a5fdfb57-6bd7-5314-8028-8d148ec3e31f |  | note | ACCEPTANCE CRITERIA: AA, AB, AC, BA, BB or CA
label | 0658f5bd-aa23-5961-90ff-84b2e59157e0 |  | note | QUALITY DOCUMENTATION: IANZ Report
checkpoint-status |  |  | checkpoint | 5.6 Solid Density
label | 0af23c22-a075-50ef-8115-08dabd7fedc7 |  | note | SPECIFICATION REFERENCE: TNZ B/2 7.5
label | 8d1dadd7-15f1-57d9-9a8b-ee7ce722d823 |  | note | TEST REQUIRED: Solid Density
label | 3f694ed9-01d5-57cb-88f2-dfc3da614cef |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test per 10,000m3 (min 1 per source) - 1 tests
label | ed96880d-d166-58fd-9433-1aabc316846b |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 19093ce8-fc63-5242-8fcf-35dfc0311a66 |  | note | MEASURING DEVICES OR METHOD: NZS 4407 : 1991, Test 3.7
label | 11d72245-f636-5ead-b9c2-553e52dd79bd |  | note | ACCEPTANCE CRITERIA: report value only
label | 04926c1c-a453-5cef-9429-70fd3f96d803 |  | note | QUALITY DOCUMENTATION: IANZ Report
checkpoint-group |  |  | section | 6.0 BASECOURSE LAYER CONSTRUCTION - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | 6.1 Formation
label | 123b4e83-257f-5b6c-9e6f-23251db1549d |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | 87e540bb-a786-53f2-be99-2b00d1251a30 |  | note | TEST REQUIRED: 3m straight edge
label | 9b4d1f0e-0682-550f-ad8e-e183da555069 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 20m centres each side - 94 Tests
label | 3b922bf3-5cb2-5db3-a9d5-b6e0708c07e2 |  | note | TASK ASSIGNED TO: Pavement subcontractor quality representative
label | cdba94de-a9a3-54ec-84b7-8b4719c19246 |  | note | MEASURING DEVICES OR METHOD: 3m straight edge, tape measure
label | 5d225620-46d2-530e-8718-92d21f8667d7 |  | note | ACCEPTANCE CRITERIA: +/- 10mm
label | 41cf8158-5ccb-525c-b3a9-79e933ddf114 |  | note | QUALITY DOCUMENTATION: Inspection checklist
checkpoint-status |  |  | checkpoint | 6.2 Finished Level
label | 316045ff-5f80-5481-a278-6500bef2cd60 |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | 1b3e0470-85d6-5750-92ec-072f84c2a38a |  | note | TEST REQUIRED: String line
label | fddeeb20-9fb3-582d-a07d-76586a1e43f3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: centreline and edge of seal at 20m intervals - 129 Tests
label | f0396688-16e5-5db3-a1a1-f3419fef5861 |  | note | TASK ASSIGNED TO: Pavement subcontractor quality representative
label | 9fd91430-4e3d-5b0e-b19c-4b4eff2725d3 |  | note | MEASURING DEVICES OR METHOD: Stringline, tape measure
label | 9c986fd3-372f-5717-806a-c4b9a1705f1d |  | note | ACCEPTANCE CRITERIA: +15mm / -5mm
label | 0c74c19f-5798-55d1-8543-d9c0325714a8 |  | note | QUALITY DOCUMENTATION: Inspection checklist
checkpoint-status |  |  | checkpoint | 6.3 Plateau Density Test
label | 5b5f3e54-63c7-577c-a882-7b4fa0c24666 |  | note | SPECIFICATION REFERENCE: TNZ B/2 7.5 (b)
label | f404f40e-b73a-5cf8-8617-8390b783ef4c |  | note | TEST REQUIRED: Plateau Density Test
label | cc9474d7-c6f1-557e-9d1d-e790959a95ca |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test minimum
label | 5ca51340-290d-5f0c-a1bc-d036fc32fb74 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | d7e1ee33-d06f-5cf0-95aa-6cbdd89ca1a4 |  | note | MEASURING DEVICES OR METHOD: NDM
label | 62df9322-7e7d-52af-9092-3892c29a1008 |  | note | ACCEPTANCE CRITERIA: report value only
label | 3dac8c45-9d08-5087-9795-aa5653f09928 |  | note | QUALITY DOCUMENTATION: IANZ Report
checkpoint-status |  |  | checkpoint | 6.4 Compaction
label | 85be0e86-33f1-5fc9-b782-041fe2b95e80 |  | note | SPECIFICATION REFERENCE: TNZ B/2 7.6
label | bd7055bd-0865-5ab8-9638-6dae5cf2ba3d |  | note | TEST REQUIRED: NDM
label | 8ef4e0a8-5887-5c84-89a2-3a209ed0527c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: min 5 tests per lot (max lot size = 1,000 m2) - 20 tests
label | 313551d1-ef95-58f0-9987-574663ccee54 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 4f2e8b20-c0d0-55f8-abfd-afb949ed765a |  | note | MEASURING DEVICES OR METHOD: NDM
label | 9833d075-4782-55fb-9a13-d0775d222b8c |  | note | ACCEPTANCE CRITERIA: Mean ? 98% MDD, Min ? 95%, Total voids ? 20%
label | 5d6abaf1-21a5-50f1-9bfa-465fd738de36 |  | note | QUALITY DOCUMENTATION: IANZ Report
checkpoint-status |  |  | checkpoint | 6.5 Compaction - Feather Edge
label | 189ca583-83ae-5038-af89-30fd7ae757a1 |  | note | SPECIFICATION REFERENCE: TNZ B/2 8
label | a769e4ff-3f80-56d2-8c6c-15381aa04460 |  | note | TEST REQUIRED: Visual Inspection
label | 4a91d74f-ce5d-5a85-8092-b695395051ee |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Inspect full length each side
label | 685547fd-d8a5-5616-b179-fd1db34b0720 |  | note | TASK ASSIGNED TO: Pavement subcontractor quality representative
label | 07fcc644-258b-5085-a7e3-a497afb18985 |  | note | MEASURING DEVICES OR METHOD: truck with 4 tonne wheel load
label | a0080081-f573-5218-a764-5d5491976d70 |  | note | ACCEPTANCE CRITERIA: the surface shall be able to withstand a moving wheel load of up to 4 tonnes without displacement
label | c0468080-b874-5579-9d63-5a1838296b74 |  | note | QUALITY DOCUMENTATION: Inspection checklist
checkpoint-status |  |  | checkpoint | 6.6 Degree of Saturation
label | 05ac2d71-47ea-58ca-bd6c-f84ee82150a6 |  | note | SPECIFICATION REFERENCE: WBOPDC DC 2009, Cert 1E
label | 9f9fa8bc-ce02-538c-8fdb-95ca6aadad5f |  | note | TEST REQUIRED: NDM
label | 0d9f6331-912c-5e04-a91d-deac00b904a8 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: min 5 tests per lot (max lot size = 1,000m2) - 20 tests
label | 15099881-0df7-514d-ab41-fa17ab11dd43 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | f7386ca6-395f-5981-b0d5-70feb84f21cb |  | note | MEASURING DEVICES OR METHOD: NDM
label | d8feda9d-642c-5474-8c95-f8ff1e471f44 |  | note | ACCEPTANCE CRITERIA: < 60% (or 80% on consultation with the pavement designer)
label | 40602ef8-3dfd-5781-893c-01eaaceadddc |  | note | QUALITY DOCUMENTATION: IANZ Report
checkpoint-status |  |  | checkpoint | 6.7 Surface Finish
label | 1a96c69c-dc5a-5840-9c53-5dab13db6e49 |  | note | SPECIFICATION REFERENCE: TNZ B/2 7.8
label | 7d1e6c22-3f7d-5a2a-a8ef-2faadde2b43d |  | note | TEST REQUIRED: Visual Inspection
label | 664813bb-d070-5f11-b796-e1516187b8ff |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | 6157da78-c49a-59ff-94bd-25e88d6ba544 |  | note | TASK ASSIGNED TO: Pavement subcontractor quality representative
label | bb898439-be92-5ea1-8507-82c50cc7933a |  | note | MEASURING DEVICES OR METHOD: Stiff bristled broom, camera, eye
label | 1dac8fca-5e8e-584f-93ce-3539f16368ae |  | note | ACCEPTANCE CRITERIA: The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which; • The large aggregate is • exposed to the surface; • held in place with a matrix of smaller aggregates • The smaller aggregate is held firmly in place by fine material; • The matrix does not displace under normal trafficking or sweeping. The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 97b128e3-8512-555f-af0d-062300efafa8 |  | note | QUALITY DOCUMENTATION: Inspection checklist and photographs supplied electronically.
checkpoint-status |  |  | checkpoint | 6.8 Ride Quality
label | e7200c52-b7e3-5c39-861b-2d50b3c23852 |  | note | SPECIFICATION REFERENCE: Internal measure
label | fbddfa0a-590b-56a5-ad87-dcc112e77e34 |  | note | TEST REQUIRED: Ride quality test to AG:AM/T002
label | b6d52c2a-6544-5866-bfd6-13c3eedfe6f5 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Within 12 months of first coat seal
label | 8c457508-7197-5f31-bb10-c176387934c7 |  | note | TASK ASSIGNED TO: Either by pavement subcontractor or by Westlink Asset Management team from latest HSD survey
label | 05a49c51-f7f2-54a8-a7c3-13481feba4e8 |  | note | MEASURING DEVICES OR METHOD: inertial laser profiler or response-type roughness meter
label | afa9b228-2128-5d51-b4c3-414d73dec662 |  | note | ACCEPTANCE CRITERIA: no 100m moving average > 60 counts
label | 6dbcfe99-d6a1-5144-82aa-1cfeae03209c |  | note | QUALITY DOCUMENTATION: Certified test report
checkpoint-group |  |  | section | 7.0 BITUMEN - TO GAIN APPROVAL
checkpoint-status |  |  | checkpoint | 7.1 Penetration
label | 683eb3ef-a5e1-5161-a8ed-27e33c03a75a |  | note | SPECIFICATION REFERENCE: TNZ M/1 Table 1
label | f2b83eac-8aff-5600-b74e-ec4e62a7c4b2 |  | note | TEST REQUIRED: Penetration at 25°C, 100g, five seconds
label | f5f677e3-4660-57c6-a667-6e7c6e844a6f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test
label | 330f93d0-29f1-58c1-aee2-0a5e4a9441b6 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | c9bd2da5-7798-5e96-9efd-cdb0144b2ebe |  | note | MEASURING DEVICES OR METHOD: ASTM D5
label | ff9663be-7891-5766-947c-117186211dc6 |  | note | ACCEPTANCE CRITERIA: Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | 2ab31d57-6421-5875-99cc-62d3d110e80e |  | note | QUALITY DOCUMENTATION: Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 7.2 Viscosity
label | fff85a2a-ce65-5a2b-9c0f-7f1fa84abc65 |  | note | SPECIFICATION REFERENCE: TNZ M/1 Table 1
label | 5ec40d90-4c27-59b3-a481-10aeaaf27a72 |  | note | TEST REQUIRED: Viscosity PaS at 60°C
label | 0f655cd1-2dd2-5cbe-88b2-c7ad22e58bce |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test
label | a6d85025-20e6-50ea-a3bd-8cca4b2c2395 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | cf2838e1-9eb8-52b6-b466-5254c6c18f20 |  | note | MEASURING DEVICES OR METHOD: AS 2341.2 or ASM D2171
label | e1c233e6-de39-5eed-8af9-158d8086b60a |  | note | ACCEPTANCE CRITERIA: Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | e0134b48-9490-549b-a9db-e6a0bd03ef95 |  | note | QUALITY DOCUMENTATION: Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 7.3
label | ee32b03e-c017-5801-96ff-0fac2fed2721 |  | note | SPECIFICATION REFERENCE: TNZ M/1 Table 1
label | 46ae9ae5-a14b-571c-ba2f-fc6e401530f2 |  | note | TEST REQUIRED: Viscosity mm2/s at 135°C
label | 0c4ea221-42d6-5d0d-a1ab-143a880ca258 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test
label | e757039a-a49e-5ac2-80a4-4ddf9a18100c |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | a25354b2-556c-5fe2-9f05-dde91156999f |  | note | MEASURING DEVICES OR METHOD: AS 2341.3 or ASM D2170
label | e709c3f5-5e6d-55b7-9c19-5dc50f6a604e |  | note | ACCEPTANCE CRITERIA: Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | c2787e3e-afd1-5cde-95f5-4cf953ac39c2 |  | note | QUALITY DOCUMENTATION: Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 7.4 Flash Point
label | 39901730-f668-513a-975d-db747d26c172 |  | note | SPECIFICATION REFERENCE: TNZ M/1 Table 1
label | b5977828-29e9-5ec2-8da8-843e3d9c2836 |  | note | TEST REQUIRED: Flash point (Cleveland open cup), °C
label | 9d4d57e1-c812-50ce-ba5b-abadf7e3c04f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test
label | d4c26c4d-e241-58df-b152-33a4600bd7b6 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | eba90f13-ae9a-5827-a250-4f46876d24d4 |  | note | MEASURING DEVICES OR METHOD: ASTM D92
label | d18cab7f-cea5-5a9e-9be9-39d081f18214 |  | note | ACCEPTANCE CRITERIA: Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | c8c25572-57d7-58c9-b6e0-5250470a0a65 |  | note | QUALITY DOCUMENTATION: Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 7.5 Solubility
label | 4a6b7797-faae-55d9-ad47-70230acd5f95 |  | note | SPECIFICATION REFERENCE: TNZ M/1 Table 1
label | b7a840c3-acd5-52a5-b52d-52de4c718a7a |  | note | TEST REQUIRED: Solubility in Trichloroethylene, % or Solubility in Toluene, %
label | 772d61fa-25d0-56fc-a10a-521aed7e99b2 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test
label | c14e15dc-44ba-5fe7-ae73-c1aec7b152da |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | beced6d2-d139-5d8e-a8ae-e81f41913407 |  | note | MEASURING DEVICES OR METHOD: ASTM D2042, AS 2341.8
label | a55a1d78-f1cf-57dd-893c-2269d99512c4 |  | note | ACCEPTANCE CRITERIA: Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | 2d5986ae-31a7-5347-898d-1922d83c74bb |  | note | QUALITY DOCUMENTATION: Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 7.6 Rolling Thin Film
label | f8b93dc2-dd35-5c17-b8da-604531968ce9 |  | note | SPECIFICATION REFERENCE: TNZ M/1 Table 1
label | 40bf65a7-dbe6-5d62-a074-3d8f9a6602bc |  | note | TEST REQUIRED: Rolling Thin Film Oven Test
label | 75554527-27dd-5d0a-af6b-aad2fa14e742 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test
label | 13f29353-83a1-512a-9e7d-554e618c4a19 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 788677f2-4b82-5311-bec1-566b58723fba |  | note | MEASURING DEVICES OR METHOD: ASTM D2872 or AS 2341.10
label | 1392cf74-ea28-5459-b4bb-73e35ed199ab |  | note | QUALITY DOCUMENTATION: Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 7.7 Penetration
label | dde0dcc9-411d-599c-adb5-962caffe19eb |  | note | SPECIFICATION REFERENCE: TNZ M/1 Table 1
label | df332b33-d9bf-5cf2-b327-992408856f25 |  | note | TEST REQUIRED: Penetration of residue, at 25°C, 100g, five seconds, % of original
label | 9bfbe6da-f808-55df-9c2a-07876ba5629a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test
label | 9b3b7390-9cac-54bd-aaa1-b093d05a3591 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 56929acd-47f3-576e-bc0f-402b04ff59ee |  | note | MEASURING DEVICES OR METHOD: ASTM D5
label | 3fb29dfc-b6ff-5821-8351-63c76f8968db |  | note | ACCEPTANCE CRITERIA: Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | c3db1af4-3888-5dfd-8bbb-0a3240922ef2 |  | note | QUALITY DOCUMENTATION: Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 7.8 Ductility
label | a3c0070b-127c-552d-886a-fd4db02d113e |  | note | SPECIFICATION REFERENCE: TNZ M/1 Table 1
label | 9471b601-f67c-5fa0-8c8f-2d6c441367c9 |  | note | TEST REQUIRED: Ductility of residue, at 25°C, (metres)
label | 3f53d4e7-0b9a-5e32-9144-03700f6f5355 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 1 test
label | b2bb91b4-7d97-5eb5-a35e-32da96802fe3 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 3e39d94a-b5ec-5d29-ab08-d36084bb7b2b |  | note | MEASURING DEVICES OR METHOD: ASTM D113
label | df71c620-3093-51ad-b55a-a1c459455929 |  | note | ACCEPTANCE CRITERIA: Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | 72c62e5b-1410-51fb-a41f-4944eda5a68a |  | note | QUALITY DOCUMENTATION: Letter of compliance from NZTA
checkpoint-group |  |  | section | 8.0 SEALING CHIP MATERIAL TESTING
checkpoint-status |  |  | checkpoint | 8.1 Crushing Strength
label | 31e82815-addc-5e2f-9b17-f07843f97248 |  | note | SPECIFICATION REFERENCE: TNZ M/6 3.2
label | 583421f6-8286-51fd-9d96-a751358f7a67 |  | note | TEST REQUIRED: Crushing Resistance Test
label | 1eee9b61-d97a-58d0-9dba-fd2b8a8f3156 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 0b7d6ff6-6ac3-5bbf-890c-eb516fedc82f |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | b139f8ce-ad8e-514e-a8cf-62bc75dab6c1 |  | note | MEASURING DEVICES OR METHOD: NZS 4407:1991, Test 3.10
label | 044cd976-23ad-5d99-b3d7-6bd5494f8297 |  | note | ACCEPTANCE CRITERIA: <10% fines passing 2.36mm under 230 KN load
label | 5bbd6f8a-cf58-564f-81fe-82ef331b6c46 |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 8.2 Weathering Quality
label | 1e445c35-c555-5d1c-90ba-4db402b8991c |  | note | SPECIFICATION REFERENCE: TNZ M/6 3.3
label | 552c3468-6cdc-5d1c-8a91-d065828a2f6f |  | note | TEST REQUIRED: Weathering Quality Index Test
label | c6ba46fd-5b6a-5342-9133-627909e131a1 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | c1493066-b447-5e2c-87b0-8c6cccb5ce8b |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 0c5d96d4-e5b3-50fc-af1e-4af8d524029f |  | note | MEASURING DEVICES OR METHOD: NZS 4407:1991, Test 3.11
label | 96862149-392a-59c9-b409-6ed5f2cfc476 |  | note | ACCEPTANCE CRITERIA: AA or BA
label | 075fc9f4-dcf8-5d47-8130-e6028ded1910 |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 8.3 Weak Particles Test
label | 4b1adae7-7098-501c-aed0-d40886fe54fd |  | note | SPECIFICATION REFERENCE: TNZ M/6 3.4
label | ed7eaa2f-50f5-50b8-95cb-8c4c8b4aa7da |  | note | TEST REQUIRED: Australian Weak Particles Test
label | b031bcf2-368d-5501-a748-0eda8d1234aa |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Only undertaken in cases of dispute
label | f21ec117-e660-5a80-a5be-5340b02764fe |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 1c90bee3-45e4-50bc-b946-829f835bf168 |  | note | MEASURING DEVICES OR METHOD: AS 1141.32-1995
label | e4845c04-d507-5d64-9268-aac09f6e2ed8 |  | note | ACCEPTANCE CRITERIA: Maximum of 1%
label | aa762bbb-7756-56e2-9461-ce1947605423 |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 8.4 Cleanliness
label | 050085bc-eaea-57f3-b299-01a6c53f7c3d |  | note | SPECIFICATION REFERENCE: TNZ M/6 4.1.1
label | 57b42821-6924-58cc-ab32-8ceb72f953c9 |  | note | TEST REQUIRED: Cleanliness Test
label | 63807785-6764-599f-9df9-b39d9c99a758 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | bcde709f-e982-5ddb-bbbf-a84f84f0af67 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | c642642a-2acb-58d4-8cd4-3bde8be32c18 |  | note | MEASURING DEVICES OR METHOD: NZS 4407:1991, Test 3.9
label | 9634720b-7902-5317-bba3-35f654c06a66 |  | note | ACCEPTANCE CRITERIA: Grade 2 - 89 min Grade 3 - 87 min Grade 4 - 85 min
label | dbb575d0-3e8a-548b-a2b9-8089225ed623 |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 8.5 Size & Shape
label | c1511884-2be2-5c65-a81e-1cc4232fa8e6 |  | note | SPECIFICATION REFERENCE: TNZ M/6 4.1.2
label | fb4c00c1-aef9-53c4-850b-0402841b9154 |  | note | TEST REQUIRED: Size & Shape
label | 4cb56129-74b0-56ae-a9c2-5b5b31ad3f43 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | e4d165a4-f56e-506b-a261-0ecb66480cdc |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 6c32a65a-9acd-55bb-9e8c-92f1cfa3233c |  | note | MEASURING DEVICES OR METHOD: NZS 4407:1991, Test 3.13
label | abe8cc29-9d17-5822-ba65-ae357bb9f33e |  | note | ACCEPTANCE CRITERIA: Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD 1.1% passing 4.75mm
label | 832fa4b9-369e-5b25-a0e0-018c895856fc |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 8.6 Broken Faces
label | 131962a8-922d-58f7-9e9b-321f35e44d2a |  | note | SPECIFICATION REFERENCE: TNZ M/6 4.1.2
label | 0ca74b77-45a4-526a-8be6-02e46f4364b6 |  | note | TEST REQUIRED: Broken Faces Test
label | d170108a-603c-5278-a01a-9ca17a08dd02 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 9ec6b95d-febd-54ef-809a-f2fef7cc5cfe |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | d328c9f8-10fe-5604-a634-b1c34d4cf8f4 |  | note | MEASURING DEVICES OR METHOD: NZS 4407:1991, Test 3.14
label | 10eb68a4-51fd-5936-8c60-4be068458d03 |  | note | ACCEPTANCE CRITERIA: 98% with minimum two broken faces
label | c5088eb9-616e-51da-b8cd-7a5895da9ccc |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 8.7 Grading
label | 4c75e03a-00d4-5503-8974-acfb1564a0d4 |  | note | SPECIFICATION REFERENCE: TNZ M/6 4.2.2
label | e8b5d429-355c-5314-a4be-df2a82b34c33 |  | note | TEST REQUIRED: Grading
label | e226abad-a51f-5c65-a339-f8c3a299724b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 0f2ce6fd-4dd4-537a-8a5c-f00725f50a0b |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | 6943c72f-1598-56a6-bb6a-bf18f3f37d80 |  | note | MEASURING DEVICES OR METHOD: NZS 4407:1991, Test 3.8
label | 940b196e-2894-5404-860a-50019a067a20 |  | note | ACCEPTANCE CRITERIA: Grade 5 100% passing 13.2mm 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300µm Grade 6 100% passing 9.5mm 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300µm
label | 1b782af5-5064-5e9e-97b1-4fd427f85f59 |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-status |  |  | checkpoint | 8.8 Cleanliness
label | 2f7933af-676d-5c99-aa99-dc4924d13f01 |  | note | SPECIFICATION REFERENCE: TNZ M/6 4.2.3
label | 942629d3-43f2-5fd6-a8c8-97465ed5b396 |  | note | TEST REQUIRED: Cleanliness Test
label | 75817131-e706-5ee3-94e4-03a9dc6c26c3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 4ea8b990-82aa-5b08-9d70-a95285d0f509 |  | note | TASK ASSIGNED TO: IANZ accredited laboratory
label | b06cef68-94b1-520c-86bc-aef4380860c1 |  | note | MEASURING DEVICES OR METHOD: NZS 4407:1991, Test 3.9
label | c07e1519-bf50-5b46-a037-b999dfdae627 |  | note | ACCEPTANCE CRITERIA: Report Value Only
label | 4378d524-3f25-559d-8a65-f8a41a344a73 |  | note | QUALITY DOCUMENTATION: IANZ Test report
checkpoint-group |  |  | section | 9.0 SEAL DESIGN
checkpoint-status |  |  | checkpoint | 9.1 Seal design
label | 7332a086-59c2-5b8f-9960-63001c6c2d8d |  | note | SPECIFICATION REFERENCE: TNZ P/3
label | 3fab5224-8394-5e51-b680-1fd2d3ffa4b2 |  | note | TEST REQUIRED: Seal design
label | 1384aae6-bd60-5214-8cd3-53ef1b592a6f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: 2 weeks prior to sealing
label | 924e0e99-10f3-5f34-86df-1abfff536967 |  | note | TASK ASSIGNED TO: Contractor's Quality Manager
label | cec6778a-ea24-5bdb-a032-e00cbd97746c |  | note | MEASURING DEVICES OR METHOD: report only
label | 7ace36d6-2688-5a1c-b286-1cc60226f85c |  | note | ACCEPTANCE CRITERIA: report only
label | 4d6ba846-398a-59d8-bd2f-ef95947e25ba |  | note | QUALITY DOCUMENTATION: Seal design
checkpoint-group |  |  | section | 10.0 SEALING RECORDS
checkpoint-status |  |  | checkpoint | 10.1 Pre-seal inspection
label | 3b9874b0-4fad-525f-ad89-4979a540ae17 |  | note | SPECIFICATION REFERENCE: Client request
label | d6e7d6f6-56ab-534b-aed9-672a16665a87 |  | note | TEST REQUIRED: Visual inspection
label | 683fc000-6e34-5dc9-a592-45d16c5cfc65 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: On day of seal. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | 23c06c4a-ac73-5b77-9037-2bb0f7d63c4b |  | note | TASK ASSIGNED TO: Contractor's Quality Manager
label | 7d1ef50b-0013-524c-9eb9-22cc38760d25 |  | note | MEASURING DEVICES OR METHOD: eye, camera, broom
label | e044194d-e131-5dbf-993b-1d1c1bf8e871 |  | note | ACCEPTANCE CRITERIA: The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which; • The large aggregate is • exposed to the surface; • held in place with a matrix of smaller aggregates • The smaller aggregate is held firmly in place by fine material; • The matrix does not displace under normal trafficking or sweeping. The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 3932de8a-5e2e-5d46-b820-e34a11632937 |  | note | QUALITY DOCUMENTATION: Inspection checklist and photographs supplied electronically.
checkpoint-status |  |  | checkpoint | 10.2 Blend sheet
label | b87450fc-9cce-5886-8c47-37e4ab3d6350 |  | note | SPECIFICATION REFERENCE: Client request
label | 754ba473-e4ae-5846-be28-ba09dec222b2 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: On day of seal
label | 646b2af4-90e8-50e8-85d0-60df70a9f35c |  | note | TASK ASSIGNED TO: Bitumen blending facility
label | 2f048bd7-b82a-5478-842c-f6ea58f7da23 |  | note | ACCEPTANCE CRITERIA: Report value only
label | 5b4dc2d2-78d6-5cea-a6d0-d6941bb3aab2 |  | note | QUALITY DOCUMENTATION: Blend sheet
checkpoint-status |  |  | checkpoint | 10.3 Spray sheets
label | 92171b4e-66d2-5778-bb8d-4ab23adecf88 |  | note | SPECIFICATION REFERENCE: Client request
label | 086b5df2-5591-5787-ac04-9418e1e2014e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS: On day of seal
label | fb95b95f-899a-59e8-994d-1f790b88e09e |  | note | TASK ASSIGNED TO: Sealing Manager
label | a8bbe7b2-18c8-56ec-bd60-c4be8534d8c9 |  | note | ACCEPTANCE CRITERIA: Report value only
label | 6adfc558-394f-5fb3-999f-0e08e8343b69 |  | note | QUALITY DOCUMENTATION: Spray sheets
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | d8086cb5-0188-5df7-82f8-e43e60cd902c |  | textbox | Contractor's Rep Name:
text | 37120512-fec6-5959-aaa0-34872e71c771 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Te Matai Rd 3 13.70-14.38 |  |  |  |  | Yes | SYS - ITP - Te Matai Rd 3 13.70-14.38 (old version) | 2d72db13-4fab-4b6c-9f8e-ebdeee74ad1e
checkpoint-group |  |  | section | 1.0 - PRECONSTRUCTION HOLD POINTS
checkpoint-status |  |  | checkpoint | 1.1 - Agree QA Requirements
label | 016b2b97-2a39-53c3-a39d-272201ab7627 |  | note | SPECIFICATION REFERENCE- ITP
label | de675db7-7034-50c4-885c-8a4d1e2dac89 |  | note | TEST REQUIRED - Check pricing and ITPs & notify Westlink of any difference in understanding of specification requirements
label | 787efb5f-4952-5023-9fa1-642b4c69d3f8 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Review ITP and confirm minimum quality requirements are understood prior to construction handover meeting.
label | 3278d572-1347-58d5-a69b-0fdfd0beb314 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 0551714d-57f3-5e10-aa1e-5382ef2e77b5 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.2 - Confirm nominated project manager, supervisor, foreman, finishing grader operator
label | ec5a6585-7328-5461-9b1e-f149d8380172 |  | note | SPECIFICATION REFERENCE- NTP
label | 43dfed4c-e855-5f33-afff-f2ef9428d961 |  | note | TEST REQUIRED - Meeting
label | cc2ce9c2-86de-5c0b-ae5f-5a9a95e1103e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 24 hours notice prior to construction handover meeting.
label | e75cf25e-00cc-5b81-b314-a288653cf035 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | b736909b-e939-5bb7-af6b-c70a035f1177 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.3 - Submit resident letter for approval
label | 8abd57aa-e11d-5115-9f26-f3be739e8a06 |  | note | SPECIFICATION REFERENCE- NTP
label | c412a540-a02c-50ab-943f-7d8ab9342d57 |  | note | TEST REQUIRED - Submit letter to Delivery Manager for review and approval
label | c3cc48f0-3449-5f9a-8545-5c767cbf1aca |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 48 hours prior to letter box drop
label | d17c6ab2-6522-5d7b-975a-b8fb735d642e |  | note | TASK ASSIGNED TO - Construction Project Manager
checkpoint-status |  |  | checkpoint | 1.4 - Construction Handover Meeting
label | 1567dfa1-5c33-5149-b794-19dead2763d6 |  | note | SPECIFICATION REFERENCE- NTP
label | 7285d996-65f3-58cd-8c90-fc0df45f5c6f |  | note | TEST REQUIRED - Meeting
label | 38c12216-08ad-56d1-ac37-a8ed96c8f558 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 48 hours prior to planned commencement of physical works.
label | a70caf41-2c46-5b55-b37e-4a9767ddb1f5 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 712bb03c-b040-5b35-95a0-bfc63b116443 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.5 - Physical works Programme
label | b67b1be7-1564-5a35-a108-5bdc870fea81 |  | note | SPECIFICATION REFERENCE- NTP
label | 44f2bf8a-6b9e-54d7-9832-ad7bdee5da51 |  | note | TEST REQUIRED - Physical works Programme to be uploaded to WestLink Sharepoint site, emailed to WestLink Delivery Manager and start and end dates to by updated in RAMM Contractor prior to physical works.
label | ecf8aaef-9249-5995-a18d-fa7bcd8cb1b1 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 10 working days prior to commencement of physical works.
label | 8115eda3-3a55-58d5-a807-aaad223a0d26 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | c0a59481-ca1b-5679-a08c-5a535effa7bd |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-group |  |  | section | 2.0 - SUBGRADE CONSTRUCTION (WIDENING AND UNDERCUT AREAS)
checkpoint-status |  |  | checkpoint | 2.1 - Formation
label | 1e7e11bd-f418-5d76-bf91-dfbb170482a1 |  | note | SPECIFICATION REFERENCE- TNZ F/1 11.2.1
label | 52a4a7a1-c878-569d-a900-3d287bc65375 |  | note | TEST REQUIRED - 3m straight edge
label | cc8297c8-bada-5814-a11f-43e287905095 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres alternate lanes - 140 Tests (undercut areas additional)
label | d7a2ee9b-35bc-5a56-abdc-2902ef3b2ee7 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | de2bbdfb-d4d6-5300-9138-817b62cda625 |  | note | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | 838d8385-aa56-58db-879b-e52ba4d7afeb |  | note | ACCEPTANCE CRITERIA - +/- 30mm
label | 77b378c8-d624-5d88-9629-a4ee81c9bb19 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 2.2 - Finished Level
label | 03b6b330-fe15-5782-80bf-46b791ef0594 |  | note | SPECIFICATION REFERENCE- TNZ F/1 11.2.2
label | b8a19bd5-bc4c-541b-b82f-265d497e5f21 |  | note | TEST REQUIRED - String line or approved alternative
label | 9163abbb-6c78-5bf8-b28b-53b0cc347c4f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres alternate lanes - 140 Tests (undercut areas additional)
label | 2cd01c68-0d0b-5697-b3ac-6ff7d0160658 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 0d461daf-32a5-533e-8481-ad3f1eb01000 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | eecded6d-857d-5db0-bca1-fd406736a323 |  | note | ACCEPTANCE CRITERIA - +0mm / -30mm
label | 4d041552-9584-59b5-94aa-d0fb370cc6ff |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 2.3 - Bearing strength
label | cf0edd1d-616c-502a-b1b6-bb67970bb371 |  | note | SPECIFICATION REFERENCE- Design
label | 988b311a-fcd4-5956-947e-7d389c6ae011 |  | note | TEST REQUIRED - Inferred CBR
label | d37c9502-9303-5a1e-b6e2-f28d4b0e97c0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres alternate lanes - 140 Tests (undercut areas additional)
label | 6db3c4fc-9f8b-550d-8839-6a6c195b95b2 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | b6217ac5-fd51-595d-95f5-47feea1ff297 |  | note | MEASURING DEVICES OR METHOD - Scala penetrometer to NZS 4402 : 1988, Test 6.5.2. Inferred CBR from Austroads Pavement Design Manual 2004
label | 91aa0904-e4c9-5011-a758-109b2a8cdc0b |  | note | ACCEPTANCE CRITERIA - CBR e 4
label | da8ec9bd-26a6-5110-99ba-c8d2b8a15540 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 2.4 - Compaction (Provisional)
label | b81d98e3-0adb-5be9-8b6c-87b846ef6edc |  | note | SPECIFICATION REFERENCE- TNZ F/1 10.5.1
label | d5897503-c783-545b-9643-61394bca7e8c |  | note | TEST REQUIRED - Proof Roll
label | 44ff6b79-da8b-547f-9532-b1df873f2fff |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 100% coverage (Provisional - where subgrade improvement material has been used)
label | 402fbe91-8204-5ae7-a4f6-dee2003b3024 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 3e9e691f-6ef8-53fb-bf2f-0aadb576bfd5 |  | note | MEASURING DEVICES OR METHOD - smooth wheel roller with min loading 6259 kg/m width
label | 84414898-a120-5398-815a-38bdce6a88fc |  | note | ACCEPTANCE CRITERIA - d 5mm
label | ad27731e-20e5-52b3-a75b-780eb965af13 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-group |  |  | section | 3.0 - SUBGRADE IMPROVEMENT MATERIAL TESTING (FOR SUBGRADE IMPROVEMENT MATERIAL IN UNDERCUTS)
checkpoint-status |  |  | checkpoint | 3.1 - Particle size distribution
label | e00cf082-4aab-56bf-b861-e23bca827590 |  | note | SPECIFICATION REFERENCE- Design
label | e27a612e-f470-5f98-bfba-c726e8a2cd27 |  | note | TEST REQUIRED - Wet sieving test
label | b5f646d4-f203-5618-bd20-69a478cc7fa3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - minimum 1 test
label | e0f646ff-cf2e-570e-ae5a-3fa6eb5cef33 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 6b4ab2f4-ff2f-5195-9e25-2512e15f7ffc |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.8.1
label | e51a3cad-4c0c-5c60-bd1d-f982b633e14b |  | note | ACCEPTANCE CRITERIA - 100% passing 75mm
label | 86b3bb3c-6879-5e9d-98ac-78cb7425440d |  | note | 8 - 50% passing 4.75mm
label | 33d5e165-a63a-5b5e-aa09-a1b10b8936d7 |  | note | 8 - 50% passing 425µm
label | ccd87a38-f4d9-5451-8349-4f4f79a1d1c9 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 3.2 - Soaked CBR
label | 09d58a06-56e9-5f9c-84cc-da9bd8717d56 |  | note | SPECIFICATION REFERENCE- Design
label | bc7d7c43-d0dd-5d2b-9507-89e562341c74 |  | note | TEST REQUIRED - Remoulded soaked CBR
label | 72e5c5b1-e7d5-52cd-bcff-ba3bf0174911 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - minimum 1 test
label | 1e3682f0-91c1-5f71-a330-46fa53e4089c |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | cb0e9673-f910-5626-9c0b-a1d14adfc290 |  | note | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.1 at OMC. CBR testing to NZS 4407 : 1991 Test 3.15
label | a71a6272-f7c0-5f94-8382-e695fe6d3405 |  | note | ACCEPTANCE CRITERIA - e 15%
label | 7cf7e8b8-3b3b-5302-a85a-eca22e30f50f |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 3.3 - Determination of MDD & OWC
label | c31ef450-e093-5913-9720-fbea83e200af |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.5
label | 1a384ba0-dbd8-53dd-baf8-1a30a0037a90 |  | note | TEST REQUIRED - 5 point compaction curve
label | 8cbd91f2-a82a-525a-8f77-3dd8f6c0f2f5 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | eada77f4-8ff2-5b38-8d27-8afd0312d1b7 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 0e3ee232-fd5f-5b73-8ae0-ab33bed9fd9a |  | note | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.1 (Standard)
label | 75e2960a-5f8f-5661-b12f-5f904b83c238 |  | note | ACCEPTANCE CRITERIA - report value only
label | 47d4d36f-4a42-5f74-8f4f-c2eee7823361 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | 4.0 - SUBGRADE IMPROVEMENT LAYER (S.I.L) CONSTRUCTION
checkpoint-status |  |  | checkpoint | 4.1 - Formation
label | 1869d5ec-dbd7-5b2f-8477-6ace80cfc54f |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.7
label | 0926e7b1-3d06-5520-88a0-2d9f577638d9 |  | note | TEST REQUIRED - 3m straight edge or approved equivalent
label | 29a57735-6483-58ac-bdcd-d35aa6306d32 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 140 Tests
label | 3a7b3f0a-f590-5e00-afb9-6280ef9110db |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | fa440475-9f5a-527c-b950-e714172c26f1 |  | note | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | dd53858d-93cb-5412-9ef1-a873dffbad8f |  | note | ACCEPTANCE CRITERIA - report value only
label | af7b9bc3-42e3-570e-8578-252616caf4b6 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 4.2 - Compaction
label | 90826c02-2b71-53a6-8db1-068346b335c3 |  | note | SPECIFICATION REFERENCE- TNZ F/1 10.5.1
label | 467609cc-cdd3-573d-9767-4a4e44dd6ae0 |  | note | TEST REQUIRED - Proof Roll
label | 0db3dfb2-81c6-5276-9d1b-40276db7a79f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 100% coverage (Provisional - where subgrade improvement material has been used)
label | 50958fcd-1c3b-54a4-9cd9-8a367bacd93b |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | e53cc2e9-b84b-53ce-84a0-1cb085a6b0c3 |  | note | MEASURING DEVICES OR METHOD - smooth wheel roller with min loading 6259 kg/m width
label | 3fa2da22-3afa-564b-ba0a-c6aa82ce2b6c |  | note | ACCEPTANCE CRITERIA - d 5mm
label | de21cbc2-6cb6-53ab-91f4-01b7da26e385 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-group |  |  | section | SUBGRADE IMPROVEMENT LAYER (S.I.L) CONSTRUCTION
checkpoint-status |  |  | checkpoint | 4.3 - Bearing strength
label | 819212a2-b7f6-57fc-824d-f09fad43e3e5 |  | note | SPECIFICATION REFERENCE - Design
label | d05b5015-e10f-5fa3-877b-a9f5c6336a0b |  | note | TEST REQUIRED - Inferred CBR, (or in-situ CBR)
label | c07856ac-3a43-53f9-a818-1dff2c8e795e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 140 Tests (undercut areas additional)
label | 2f384273-854e-5982-b4fd-6c3e8cb41490 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 0ef9737d-5c4e-5d38-9186-ec1ccd4e4728 |  | note | MEASURING DEVICES OR METHOD - Scala penetrometer to NZS 4402 : 1988, Test 6.5.2. Inferred CBR from Austroads Pavement Design Manual 2004. Or In-situ CBR
label | 46d04978-5846-5925-acfd-566399fbc95a |  | note | ACCEPTANCE CRITERIA - CBR ≥ 15
label | ed605cfd-3670-5515-a4d7-eb65f47e229d |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 4.4 - Finished Level
label | e71f029b-a492-5ded-9c10-014dea88dad3 |  | note | SPECIFICATION REFERENCE - TNZ B/2 5.1
label | 738160e0-07cd-554e-a2a3-dd45b63688ef |  | note | TEST REQUIRED - String line or equivalent
label | 94a9cc25-08cb-525e-b52e-4357fccea997 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 140 Tests
label | 61c3596d-2135-55c2-aba4-3225cfa1e1dd |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 66f9c10e-ea53-59c0-ad8a-7cf9d6306a8a |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | 557ff906-0dd0-5028-946a-907ecd1e5766 |  | note | ACCEPTANCE CRITERIA - +5mm / -25mm
label | b335079b-f383-5c52-94c7-22fc31368602 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-group |  |  | section | 5.0 SUBBASE MATERIAL TESTING
checkpoint-status |  |  | checkpoint | 5.1 - Particle size distribution
label | e195baa0-39d0-55e3-bf3a-9146bedbbb26 |  | note | SPECIFICATION REFERENCE - WBOPDC DC 2009, Cert 1E
label | 6e8fa868-c2ad-5766-9585-f2351f26b421 |  | note | TEST REQUIRED - Wet sieving test
label | 33de82f7-bad1-58b8-8022-5f45571b057b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 sample per 1000m3 - 2 tests (1 test on same sample as MDD/OMC curve)
label | a727c172-4c25-5e04-8151-9638f9956721 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | b2f61428-b676-5161-9203-5186b131b091 |  | note | MEASURING DEVICES OR METHOD - NZS4407 4407 : 1991, Test 3.8.1
label | c8ff8669-fbe2-5639-a847-fd476ada2dab |  | note | ACCEPTANCE CRITERIA - 100% passing 63mm
label | b4fdb9c6-e61f-5284-b4c0-fc5ea96abce0 |  | note | 55 – 80% passing 37.5mm
label | 8b737d7f-74bd-59ca-9d88-ab517825fc62 |  | note | 35 – 65% passing 19mm
label | 9d5fe04b-950d-5f92-9e57-f70dac1da1b6 |  | note | 20 – 50% passing 9.5mm
label | fd4b3d19-f98c-55b8-837e-e83275e05aa4 |  | note | 10 – 35% passing 4.75mm
label | 4067722b-0811-594b-9eb7-73bbcb5735f3 |  | note | 2 – 20% passing 1.18mm
label | 8f5c6ad0-a900-56ee-b421-25a37f9db31d |  | note | ≤6% passing 75micron
label | 48e503ff-4c8d-5a89-aa7b-b97cec2ef343 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.2 - Sand equivalent
label | 64cf2505-383c-594a-9ea7-923d8b132130 |  | note | SPECIFICATION REFERENCE - WBOPDC DC 2009, Cert 1E
label | 4c740ff3-a259-52c4-8507-6d72852da11d |  | note | TEST REQUIRED - Sand equivalent
label | a9f1d065-22d3-5681-b108-fe0ceec118ec |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 sample per 1000m3 - 2 tests
label | bf75092e-fc0c-5cbe-a4c9-07c2d073b858 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | ae9cca44-e440-593e-ba48-a31696965ba8 |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | abdf5374-7fe8-5c25-b697-f0e302bd516c |  | note | ACCEPTANCE CRITERIA - ≥ 25
label | f5c92dac-1b25-5a24-a857-8a0052b7f536 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.3 - Crushing Strength
label | 2a8451b2-5f9a-5c7e-9be8-feddd5691762 |  | note | SPECIFICATION REFERENCE - WBOPDC DC 2009, Cert 1E
label | 6fd6c23c-f799-589f-85cb-782e3546a8c4 |  | note | TEST REQUIRED - Crushing Resistance Test
label | e20bacbd-1dc8-5204-8f27-626a7cf68c5f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 sample per 1000m3 - 2 tests
label | 59218cb9-0810-524a-b2f4-1d24b9274789 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 13816811-8c62-592f-95fd-85ead2707080 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.10
label | e26afc0b-6ae1-52c6-82dc-3607d3f46bea |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 110 KN load
label | 27835d37-0ef5-55be-886f-0d032fed1245 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.4 - Soaked CBR
label | eccd0744-f618-5455-b11e-4b0d4966cc92 |  | note | SPECIFICATION REFERENCE - WBOPDC DC 2009, Cert 1E
label | 05335474-086e-561b-9cca-0f1654e3a506 |  | note | TEST REQUIRED - Remoulded soaked CBR
label | 48bd0b23-dcf7-5757-ab07-c2ecedd0e692 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 sample per 1000m3 - 2 tests
label | 2e1bf41f-0bc8-5893-b23f-004b284687ea |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 43c30688-36b0-5d65-9bcc-52be7a8e49e4 |  | note | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
label | aefdd4fd-7b1e-5cca-b195-e3594716fbbb |  | note | ACCEPTANCE CRITERIA - ≥ 80%
label | e2755a59-9562-5dfe-b00f-dbef8eb8e632 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.5 - Determination of MDD & OWC
label | 553119cb-adbc-51b6-a0e8-dd179b5ea9ff |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5, WBOPDC DC 2009, Cert 1E
label | f7b1ac1c-b4d9-5229-b8f7-9154d946d6d9 |  | note | TEST REQUIRED - 5 point compaction curve
label | 55d94e1f-fb26-56bc-a361-f53a6fae4c00 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 67de74e9-d3cf-5290-934e-c279373e158d |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | aa06b46e-1e70-549e-8be9-cbbb5c579ed5 |  | note | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.3
label | 32d8fb77-487a-58e2-b10d-7813f6eef55a |  | note | ACCEPTANCE CRITERIA - report value only
label | 739a7bdb-3e34-510c-a385-d791ea00be0f |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.7 - Weathering Quality
label | d4dbc948-b267-59a1-9a06-71e68c132866 |  | note | SPECIFICATION REFERENCE - Design
label | 7603fcd2-8907-5070-815d-076996ca0426 |  | note | TEST REQUIRED - Weathering Quality Index Test
label | 24b87728-215f-56c4-8141-f5aae43cb8b6 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 test) - 1 tests
label | 566a1b76-126a-51f8-af7e-f6d4e3b211f2 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e2d54287-2eaa-5f67-8685-64459d78ae2d |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.11
label | 7b89ff12-3be2-597d-8904-c9e42293e4e8 |  | note | ACCEPTANCE CRITERIA - AA, AB, AC, BA, BB or CA
label | 9760da5f-113b-510b-a3d7-68936c55ece6 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.8 - Solid Density
label | 5359a966-b7d1-541a-839a-65bc015c49e2 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | 1dfb2b41-0ea4-5282-aa60-4f4d956808eb |  | note | TEST REQUIRED - Solid Density
label | 6f4c827b-94b0-534f-8ff3-09609f9b6c51 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 test) - 1 tests
label | 0ca51501-2bbe-56f0-8e02-6666bb39d70f |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 21ee1b03-2cb9-50c3-84d3-9ca58492aef3 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.7
label | 707bb9ad-7e6a-5584-99df-7acd49d93396 |  | note | ACCEPTANCE CRITERIA - report value only
label | c30375ed-561a-56df-a18d-992e75982a2b |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | 6.0 SUBBASE LAYER CONSTRUCTION
checkpoint-status |  |  | checkpoint | 6.1 - Finished Level
label | 2acaa520-3d48-5a13-9573-bedb18110391 |  | note | SPECIFICATION REFERENCE - WBOPDC DC 2009, Cert 1E
label | a3bf643d-7300-5fc9-8f71-f9a6c22f765f |  | note | TEST REQUIRED - String line or approved alternative
label | 670e0984-30bf-5290-aadc-4e3311b80f2b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 140 Tests
label | 1139d5f3-e872-5ccc-aed8-23971da014e8 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 75021d42-9602-5cf9-aa66-8baf0568bc7d |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | 6674d8e8-e2f6-5941-a0a2-799201d4f5ce |  | note | ACCEPTANCE CRITERIA - +5mm / -25mm
label | 4a2f85df-6b5f-56eb-b85d-382200bddc1c |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 6.2 - Compaction
label | fbe22621-08e6-529d-81a2-c12770d2609f |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.6
label | 2f1e114a-c0c8-55f4-be1c-7911c257dd7a |  | note | TEST REQUIRED - NDM - testing limited to areas where subbase is at full depth
label | 36271ef9-8e7f-5875-8feb-b378132ce754 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 19 tests
label | 9508f4cc-8301-592e-97c0-18f905855661 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 1ede54d9-f0cc-5a50-afac-34bb9757cb04 |  | note | MEASURING DEVICES OR METHOD - NDM
label | 45f61480-fef5-52a0-8940-fbc0a88a38f1 |  | note | ACCEPTANCE CRITERIA - Mean ≥ 95% MDD, Min ≥ 92%, Total voids ≤ 20%
label | 9703ab11-bb52-5b8b-b34a-b2a5e1b957be |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | 7.0 BASECOURSE LAYER MATERIAL TESTING - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | 7.1 - Crushing Strength
label | 2a83f051-bd8b-5048-a320-d347c26e9834 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.1
label | 3ab6c099-f83e-5669-a9bd-8f5c27d1a971 |  | note | TEST REQUIRED - Crushing Resistance Test
label | 0bfb301e-82bc-53ec-a118-d60792a47183 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | fc85fae2-36af-5857-a1d6-cb24f6bf7464 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 4570146e-e3b8-5439-b134-a87d45d7b362 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.10
label | f27e0bcd-f4e4-5e1a-b2ff-2990d9b6ef40 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 130 KN load
label | 14c9b406-b9c2-5402-916b-a4d1052d7595 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.2 - Weathering Quality
label | 376bf9ef-1689-52a4-8ecd-8b8e09efb465 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.2
label | c2cdae7d-0e49-58e9-bff0-c11c014bda02 |  | note | TEST REQUIRED - Weathering Quality Index Test
label | e0783723-221f-57de-954c-86cfa2c9f333 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | b390c8e0-60ee-5cf6-be0d-9a730377d1bf |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e1dbebbc-0b65-548f-987b-f38b42382f00 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.11
label | 7b34e344-509f-5519-911e-3841093b63f3 |  | note | ACCEPTANCE CRITERIA - AA, AB, AC, BA, BB or CA
label | 7c0d8c32-2536-5a5a-9df5-31104449eddc |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.3 - Soaked CBR
label | b0065006-ecd4-58fc-9086-664ee8b65392 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.3
label | f23bb223-d381-5d6a-9680-678f7849760d |  | note | TEST REQUIRED - Remoulded soaked CBR
label | b6a113f2-35cb-5e4b-a5fd-3899e93cbbdf |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | dc624d93-757a-5bec-889e-2818b3ed88bf |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 662d2e50-e5b1-507a-992a-b8eff3c7adb8 |  | note | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
label | 40333aa9-9125-5e13-97fb-33c875c7be6f |  | note | ACCEPTANCE CRITERIA - ≥ 80%
label | 53cebaf2-51db-51e9-9e64-f80856e690db |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.4 - Sand equivalent
label | e3b4ba7b-7cbd-5095-bdfe-cceaf31e1571 |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.1.1
label | d8dfb2f8-b554-523a-9cc1-c7dcc8c21dee |  | note | TEST REQUIRED - Sand equivalent
label | 02c0328f-ed10-5d30-93cc-4772a9c88dee |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400-1500m3=3 tests; 1500-4000m3=4 tests; >4000m3=1 test/1000m3
label | 7c088d5a-d696-5e4d-b7f2-6adf03e44874 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 802d78eb-7477-5628-8c96-6290a50a6ab3 |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | 522ef9b5-db35-5c90-a43d-26753d459f22 |  | note | ACCEPTANCE CRITERIA - ≥ 40
label | 212e4a26-5c1a-5a53-9ebd-7fe7c5827d4b |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.5 - Broken Faces Content
label | b59584e2-6f65-5d5b-adef-ca425851a7af |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.2
label | 7af67208-1b4b-516a-ae43-be6868ffeb97 |  | note | TEST REQUIRED - Broken face content
label | e988885e-090e-5638-88ea-fa65e290dce8 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS -
label | 7ebf2f04-5e0d-5f82-95de-502229a47d1a |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e36d3539-cb4e-5ffe-8823-76b31e789d9a |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.14
label | dde4fc97-a26c-56de-876d-9a22bf473a8e |  | note | ACCEPTANCE CRITERIA - ≥ 70%
label | 608149e3-17a6-57e5-b351-4b132168ae73 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.6 - Particle size distribution
label | 2df7d472-0bc1-510a-b6d7-d85efe5b82cb |  | note | SPECIFICATION REFERENCE - Design
label | 60330c33-4e72-52e7-bf8f-116348849433 |  | note | TEST REQUIRED - Wet sieving test
label | 31c4adfa-61e6-53d0-9c30-16602a468c0d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS -
label | dd8c1e94-6ca8-50b7-b15d-c46fab3491c0 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | a2f2f85a-2211-5dc3-914f-0fa02aac2340 |  | note | MEASURING DEVICES OR METHOD - NZS4407 4407 : 1991, Test 3.8.1
label | 54f376dc-bc65-58d0-981c-290d858346a9 |  | note | ACCEPTANCE CRITERIA - 100% passing 37.5mm
label | dcdb6ca4-f6ae-5267-88aa-3a8142b688e1 |  | note | 66 - 81% passing 19mm
label | d6e8578a-2f30-5efb-a76c-1fb79b11a971 |  | note | 43 - 57 passing 9.5mm
label | bc994788-e62d-5104-8226-6bd8e069c9bc |  | note | 28 - 43 passing 4.75mm
label | 41b646b2-5019-551f-b57f-0c8b3ac284b7 |  | note | 19 - 33 passing 2.36mm
label | 66a08be2-48fb-5f0b-bbf5-eb0631541610 |  | note | 12 - 25 passing 1.18mm
label | b9df1a3c-4397-530b-bf79-84e7a5ff4566 |  | note | 7 - 19 passing 600µm
label | b3b34ccc-cf0b-599b-9bb8-28eadbe60434 |  | note | 3 - 14 passing 300µm
label | 0c7f4852-4956-541d-a278-efe3829df05f |  | note | 0 - 10 passing 150µm
label | 21e90c49-f4df-5742-8df6-1ced45183abf |  | note | 0 - 7 passing 75µm
label | 4a7f6559-0867-5379-8690-0c37e6f8d45a |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.7 - Solid Density
label | 4a790268-ac81-500a-97f3-7d3091469572 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | bd74b2f2-8128-505d-91af-7afb1650b237 |  | note | TEST REQUIRED - Solid Density
label | 694b5b45-2f03-59a5-92af-7852d0522948 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 2 tests
label | c46971fe-9b3b-5aea-a8d7-ae7412342c08 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | b7e19a33-757a-5347-8f79-34836648d91c |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.7
label | c7a9982e-b2dd-5b37-a519-a5a67620aad0 |  | note | ACCEPTANCE CRITERIA - report value only
label | 5e6a1aa5-eb3d-5a2c-bc63-b9468ad1188a |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.8 - Determination of MDD & OWC
label | f73830db-6511-5340-b08b-68b818a8d8a4 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | f316f878-4898-59f1-94c8-75e492385a30 |  | note | TEST REQUIRED - 5 point compaction curve
label | d8df106a-2483-5ca6-b08d-f976c3338ea1 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 2 tests
label | e5960e73-9009-5874-82e4-a6547641474a |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | c04911a1-7255-5e2f-999a-164472f7e1db |  | note | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.3
label | 3b9148c8-bdcd-5aaa-86ef-9011a6c8e333 |  | note | ACCEPTANCE CRITERIA - report value only
label | 3a58bff9-25fa-5e21-ac9c-e3e4bfbedb4c |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-group |  |  | section | 8.0 BASECOURSE LAYER CONSTRUCTION - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | 8.1 - Formation
label | b4263e53-0946-54a7-9b14-b364eaf187b0 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.7
label | 99e7c972-3eec-5b0e-ab2f-11f2e98dec73 |  | note | TEST REQUIRED - 3m straight edge
label | 269c1c0d-00cf-5a40-a0d8-be64a345ef2a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 140 Tests
label | 816c6c92-fe98-5c46-86e2-1a82b1a6f5da |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | bf2825fd-f711-5ed8-94e4-58b2d8e6cfa7 |  | note | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | 1177c3cb-9704-5c1d-ac99-166a2c7d748f |  | note | ACCEPTANCE CRITERIA - +/- 10mm
label | 19e7c326-81cd-58ba-89c2-f7b77e0004ef |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 8.2 - Finished Level
label | b8a28c1b-e95f-592a-921f-c6c1a5adc25b |  | note | SPECIFICATION REFERENCE - TNZ B/2 5.1
label | 0faade13-2a58-5c9b-8177-2970a6c2a84b |  | note | TEST REQUIRED - String line
label | ea54bbdb-8600-5b2d-bec5-3d32a525223e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - centreline and edge of seal at 20m intervals - 209 Tests
label | 19c37156-48c5-527a-ae93-b23ab8d824d2 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 788bad71-0d0a-5afe-8923-adee630fa416 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | a00f1702-aa24-5181-aa3f-5ae5d2a19774 |  | note | ACCEPTANCE CRITERIA - +15mm / -5mm
label | cffd0ba9-dea3-54bb-8dc7-3de34d8043fc |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 8.3 - Plateau Density Test
label | 3bb2e4b8-4eca-5834-ae2b-9fcf05cc4a7a |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5 (b)
label | 24e686d0-5870-5d34-b2db-b7ce2be8a81e |  | note | TEST REQUIRED - Plateau Density Test
label | b8aaff63-ee56-53af-8e25-99c5ba752c2b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test minimum
label | 867e91af-4af3-5d08-9bf3-d3199651b924 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | bf89cb89-f70c-5483-92e9-bdebab16b968 |  | note | MEASURING DEVICES OR METHOD - NDM
label | ac9566e3-d2c6-5ddf-96d2-c2ae50a51dcc |  | note | ACCEPTANCE CRITERIA - report value only
label | 9c6bb38a-36b6-52ab-b22b-34f7a9b9ca09 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 8.4 - Compaction
label | 224962f7-a78f-5519-89fe-e51f5a807bfc |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.6
label | 0f4268e4-b9b5-595e-a14d-c75a3b62b00c |  | note | TEST REQUIRED - NDM
label | 2eeffa5e-de2d-56f9-acff-c9902df83203 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 60 tests
label | 73871479-20a6-556a-8898-2b2e7951c004 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 60426331-3bad-54a3-a6c8-cddf727bffcb |  | note | MEASURING DEVICES OR METHOD - NDM
label | db581bb0-6d08-5076-a21b-fda4d5552f74 |  | note | ACCEPTANCE CRITERIA - Mean ≥ 98% MDD, Min ≥ 95%, Total voids ≤ 20%
label | a12815cb-94bb-55d8-8a34-4898eb2f9203 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 8.5 - Compaction - Feather Edge
label | 672a32d0-06ee-53d1-81df-cd1603d0c34e |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.1 and 8
label | 879bd9fc-e3df-5015-8e80-14cfca0741a8 |  | note | TEST REQUIRED - Visual Inspection
label | 1d70b873-95b2-52fb-81d4-b0f040e230a7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Inspect full length each side
label | 9fc9c81b-7ae7-5266-a373-b55ca4959995 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 12a4688c-e94f-59ad-a895-d44d744daed0 |  | note | MEASURING DEVICES OR METHOD - eye and truck with 4 tonne wheel load.
label | 2743abf8-64a2-578f-a964-eb9503b45837 |  | note | ACCEPTANCE CRITERIA - the aggregate in the feather edge shall not be segregated and the surface shall be able to withstand a moving wheel load of up to 4 tonnes without displacement
label | 11fecb5a-9cce-5eb8-8a24-7bcce72943d6 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 8.7 - Surface Finish
label | 6731f801-753a-598b-8ff4-9ba52844b1fb |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | 84eb0b6c-11b0-562a-abab-373a1fe9535c |  | note | TEST REQUIRED - Visual Inspection
label | fa3a1c47-cb09-5eef-808f-f931a7a4bb1b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | 39f72b24-680b-5fd1-b46e-c2ed89915ec5 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | ffececa7-d7f0-50ca-b097-34cc646d1c45 |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | a6b7d689-5db3-5c23-b4fd-c76a91c80a77 |  | note | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | 011d3113-54e3-5dd4-90a5-69dbb430a668 |  | note | • The large aggregate is
label | 0cc76eae-b8d6-5fdf-9cc1-5f5ecb79f424 |  | note | • exposed to the surface;
label | 710e1007-c1b9-5e19-9adc-62a04cfdf5cf |  | note | • held in place with a matrix of smaller aggregates
label | e8d86300-9030-5424-a2fa-b7de8269f4ab |  | note | • The smaller aggregate is held firmly in place by fine material;
label | b3b48600-a9af-5d6b-8920-910446d6af01 |  | note | • The matrix does not displace under normal trafficking or sweeping.
label | a1e47bfb-69d5-5ffc-8daf-4af62883cdd2 |  | note | The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 1f4224ff-d25c-5405-805e-9dc16042bce2 |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-status |  |  | checkpoint | 8.8 - Ride Quality
label | 4f5799fc-240f-588b-98f3-016f724d67e2 |  | note | SPECIFICATION REFERENCE - Internal measure
label | 77427bb3-b91d-5df5-9e22-bb8cf5e73370 |  | note | TEST REQUIRED - Ride quality test to AG:AM/T002
label | 5451c4cd-e1ef-5b58-8c5c-f84f6f594ef7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to first coat seal
label | 864d76f4-bffd-5b60-8448-38ac935acffa |  | note | TASK ASSIGNED TO - Pavement subcontractor
label | c3efad85-cfd4-5a03-ac44-b9e11bf583b8 |  | note | MEASURING DEVICES OR METHOD - inertial laser profiler or response-type roughness meter
label | 4444cb54-3f84-5b56-9ed3-2f9806caaec4 |  | note | ACCEPTANCE CRITERIA - no 100m moving average > 60 counts
label | 72649eda-3beb-59f5-a297-ee7a825c5a94 |  | note | QUALITY DOCUMENTATION - Certified test report
checkpoint-group |  |  | section | 9.0 BITUMEN - TO GAIN APPROVAL
checkpoint-status |  |  | checkpoint | 9.1 - Penetration
label | e1e30ad9-d124-5cc4-a83f-5641ac587ab3 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 1ae58ec8-2b36-580e-b25e-67cf863a5375 |  | note | TEST REQUIRED - Penetration at 25°C, 100g, five seconds
label | cf4fd39d-ec90-5672-90d7-2f8f33c310e9 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | c8be7fdc-b87d-5881-a321-d617e4007eee |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e33e9e1e-4535-5ca9-a86c-fcce9a1be7ac |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | 905cd629-41f9-5f90-a995-b68ccff4b11d |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | a964917b-61d3-54e9-be83-1952e9138527 |  | note | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 9.2 - Viscosity
label | 66c08235-ccc4-5fed-b4be-e738080cb5fc |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 97c9279f-09fc-5f1a-bc50-1b3f9f9797ac |  | note | TEST REQUIRED - Viscosity PaS at 60°C
label | 579e7855-0565-5182-84e7-141fe07eed37 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | e9bae646-21a9-568b-b48f-5c52c844d818 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 68e707ce-f616-52ce-b040-ff705cdb9893 |  | note | MEASURING DEVICES OR METHOD - AS 2341.2 or ASM D2171
label | ffd984c2-deee-55c7-bc4e-8f2b24b32613 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 9.3 - Viscosity
label | 7fee384c-e34d-5ebf-ac59-eb01b0f7c081 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | a237455f-cf89-5d6f-8280-645a176a173f |  | note | TEST REQUIRED - Viscosity mm2/s at 135°C
label | 3e9ab280-127e-59d8-b1be-7b8ae848280e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | a2af9c90-dbd3-5aaf-a404-e9f4f1c018ef |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 928cb53c-942e-5653-937e-a6a241172b2c |  | note | MEASURING DEVICES OR METHOD - AS 2341.3 or ASM D2170
label | 75c4cd3d-f5b6-5977-9642-6d16b095c03a |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 9.4 - Flash Point
label | 5ac235ca-c830-560f-9697-03196d7bfd59 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 8ef0010f-f8a0-5b04-a63b-417800c8cdb4 |  | note | TEST REQUIRED - Flash point (Cleveland open cup), °C
label | a769f353-493c-5822-ae0f-347f21128bf3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 7500d1d9-9e61-500b-a8b3-85e94ada895e |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 464492ee-70f9-54b2-9da6-c3d2f418b835 |  | note | MEASURING DEVICES OR METHOD - ASTM D92
label | 88a0d824-0049-56d9-a8a1-df777d169df3 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 9.5 - Solubility
label | 682721b6-a4cc-583e-a4ba-772995c4dc15 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 7dc6744e-b351-536e-a914-119404831d06 |  | note | TEST REQUIRED - Solubility in Trichloroethylene, % or Solubility in Toluene, %
label | 2cd95a85-0976-5137-b2db-c321497d1683 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | c90e8662-04ea-52c2-a90c-0127e5f249e4 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 804ec64f-d741-55c8-93ae-f892a781dab9 |  | note | MEASURING DEVICES OR METHOD - ASTM D2042, AS 2341.8
label | cb5ea45d-0419-5306-ac49-e0cb9aa18d27 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 9.6 - Rolling Thin Film
label | 7fae8604-dae6-58c6-bf9c-5893f3d9a340 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 1011bcb5-4efe-56ff-b560-3f5aeccf1b01 |  | note | TEST REQUIRED - Rolling Thin Film Oven Test
label | 93c2bb0a-022c-5dd8-99c7-4598198eab26 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | b3fde56d-a9f7-5ef6-8cb6-536a52e6b184 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | a2def034-6315-5029-a754-981adec88567 |  | note | MEASURING DEVICES OR METHOD - ASTM D2872 or AS 2341.10
checkpoint-status |  |  | checkpoint | 9.7 - Penetration
label | 2705684c-33b0-56c1-abd5-c76ab6ab2f86 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | c95e7333-12bf-558c-b6d8-ed5d4d278593 |  | note | TEST REQUIRED - Penetration of residue, at 25°C, 100g, five seconds, % of original
label | 192083e3-991e-5046-9157-7a6bcfac0931 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | bfee0a3f-3288-5873-987c-31c75f3f4380 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 410221ce-ed33-503d-9497-7710e5cbd172 |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | c301bc19-4bb1-5577-ba5d-afa4978bdc3b |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 9.8 - Ductility
label | fba4fdd5-8132-5970-8687-1364c5110007 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 087bfb30-3b10-5d5c-bf9f-b47acc049df1 |  | note | TEST REQUIRED - Ductility of residue, at 25°C, (metres)
label | 1e607d2a-940c-5d40-9aed-eb48e28df9be |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 5a0acc39-73ca-5710-9087-2277918017a6 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | b625f545-19f3-5f61-8efe-6232387a70af |  | note | MEASURING DEVICES OR METHOD - ASTM D113
label | 84978892-8623-5cb1-a7ce-d2f9b59ae536 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-group |  |  | section | 10.0 SEALING CHIP MATERIAL TESTING
checkpoint-status |  |  | checkpoint | 10.1 - Crushing Strength
label | eab839c7-7f0a-5bb6-aa1d-c311db95720b |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.2
label | affc64de-1610-5362-b0f3-393ac8db5207 |  | note | TEST REQUIRED - Crushing Resistance Test
label | 1995267f-ea9a-5982-b0e7-b49cb74ded51 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | b20c29df-d40d-5b9d-a1f1-ae4002e55fb1 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 3f5a5c3a-24d4-58dc-9041-6a587ea583c1 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.10
label | ca2672d5-a1e3-5d3f-96df-6c2f365f95b9 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 230 KN load
label | f3a4f6f5-c16e-5882-9311-ed067d54364d |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 10.2 - Weathering Quality
label | 533401ed-3b51-5879-be47-825e350645df |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.3
label | d598f71b-5074-5c09-8c8a-8bbc3af19574 |  | note | TEST REQUIRED - Weathering Quality Index Test
label | b9166a76-2ee7-531f-ad37-8b15b1bb3390 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 9399a433-c322-5ab0-b2e2-78caf74859e2 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d655c081-3846-532f-90db-7f66fd953590 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.11
label | ce17d85e-b13d-539b-ac11-0b646534bf9c |  | note | ACCEPTANCE CRITERIA - AA or BA
label | bfbc5e50-3cb5-563f-95ef-63b5a9632fb1 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 10.3 - Weak Particles Test
label | 74d0eb42-c842-53e9-9e18-10cab9539058 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.4
label | ee45d9b6-eca3-5784-a03f-d7cfbac22456 |  | note | TEST REQUIRED - Australian Weak Particles Test
label | f91c5431-9620-5930-bed2-9b71d745157c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Only undertaken in cases of dispute
label | 1191e8a0-c8c8-5c50-a0e3-5697c550364a |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | f06893e1-52e7-5039-b3f5-88bd9169f608 |  | note | MEASURING DEVICES OR METHOD - AS 1141.32-1995
label | a0778bc4-86fa-5611-8508-c007b1b97240 |  | note | ACCEPTANCE CRITERIA - Maximum of 1%
label | 89fd6fa7-f821-52b2-a9fc-462e6fe3e86d |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 10.4 - Cleanliness
label | 5392a3ec-87c6-5d13-a163-571eb29a99f3 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.1
label | d22cd792-a87e-5e0f-a21f-b0147b8a5c3e |  | note | TEST REQUIRED - Cleanliness Test
label | 62d7c4f3-4aa5-54f5-9c45-fceaab2625f0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | cea0eae7-95f1-5b7e-b28e-dfbb95e23246 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 7a70c97f-94fd-50e1-b4de-70333290dc2d |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | 7807c115-c7f7-5749-8de6-17b964b0b180 |  | note | ACCEPTANCE CRITERIA - Grade 2 - 89 min Grade 3 - 87 min Grade 4 - 85 min
label | d9a6c34e-b6f2-57ff-ba85-d0c9ad680d6d |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 10.5 - Size & Shape
label | 89ae5068-6178-5d98-80d1-997ec4dd2de4 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | d9905826-72b7-53f0-ac5b-49f6c3cdc0f0 |  | note | TEST REQUIRED - Size & Shape
label | 0e56ee16-9dbe-587c-aea4-5dde8d2b092f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | ae2fa25e-9be1-50ce-8783-c5aedb38e2ec |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d7da5d8f-5cff-5cdf-a3d4-326ddb0e0d3d |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.13
label | 92dfc895-a255-586f-930e-0f8bda7477f6 |  | note | ACCEPTANCE CRITERIA - Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD 1.1% passing 4.75mm
label | 729f79cd-436a-5d53-8f7e-7f0ef9a0b9af |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 10.6 - Broken Faces
label | b29f3215-5500-5766-baa4-7bae61434f1e |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | 20607081-7702-528e-9a39-d23c51e3eb33 |  | note | TEST REQUIRED - Broken Faces Test
label | ff678fa9-c3d9-539f-9f5e-4c69b9021b2f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | ada283a9-1172-5977-98ed-cb09b4b32be5 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 688e7bef-1984-5bb4-a0e4-5eefa2f05d55 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.14
label | c30dcdb6-f494-5ef0-a4c9-feda810fb445 |  | note | ACCEPTANCE CRITERIA - 98% with minimum two broken faces
label | 855567fc-3bc1-500c-aa64-e948eec98c1b |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 10.7 - Grading
label | 99d7fb53-0f43-5f54-a169-6205d0543c38 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.2.2
label | 8c249b58-0c25-5106-9668-c268fada6578 |  | note | TEST REQUIRED - Grading
label | 1ac89992-6a55-5fd5-9757-9d1b66d7f849 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | eb8cf60a-159f-567a-aaae-c76091cb638d |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | cda564db-0145-5413-9f81-eef84e319faf |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.8
label | a2f7a178-b33b-5ba0-9b72-8ad5fce833ad |  | note | ACCEPTANCE CRITERIA - Grade 5
label | bd97b480-e4af-5fca-bffb-f99cb7116bc7 |  | note | 100% passing 13.2mm
label | 64973afb-8c63-5ec7-9c62-74227fdcc79d |  | note | 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300µm
label | 0ea9474e-e156-5df9-bf72-2b7199cf6444 |  | note | Grade 6
label | 30132b7b-a54a-5987-abd7-1445a54769dc |  | note | 100% passing 9.5mm
label | 9acf551e-9c39-5b68-a8de-ce7c6567af96 |  | note | 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300µm
label | 4ad4673c-213a-5b84-b7f4-cf4d3c121bb9 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 10.8 - Cleanliness
label | c646a295-6fcd-5593-99a4-1e03bdd19c5b |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.2.3
label | 6df74939-5733-5b4b-9514-43dadaf8f41c |  | note | TEST REQUIRED - Cleanliness Test
label | 86a6eab5-c629-50fb-a8c6-42c48124efb9 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of
label | db195f0b-e39d-5fa4-8cb4-dbf077d99fab |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 0473e8ee-68d5-5906-9dc1-71771d5f5930 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | c8c38b09-cc8c-5efd-a0b5-b3a3f5e76d5e |  | note | ACCEPTANCE CRITERIA - Report Value Only
label | c39a8896-8569-59a1-a5e8-fd4f2c33bb4a |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | 11.0 SEAL DESIGN
checkpoint-status |  |  | checkpoint | 11.1 - Seal design
label | 6d10575d-c8c3-5dd6-8d18-c70143cde26f |  | note | SPECIFICATION REFERENCE - TNZ P/3
label | 097a6393-75fb-5328-8ca0-a5ff84e6dac9 |  | note | TEST REQUIRED - Seal design
label | 0fed73f3-2852-5303-b547-f148bd03a4de |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks prior to sealing
label | 77ceb748-bb65-5f69-ba2b-918db72e5a58 |  | note | TASK ASSIGNED TO - Contractor's Quality Manager
label | a15f9abf-e649-50da-9cbe-0f3f79512662 |  | note | MEASURING DEVICES OR METHOD - report only
label | b65a7905-4bb2-5c65-bfcb-4d8f66f2ca22 |  | note | ACCEPTANCE CRITERIA - report only
label | a681ba20-5aa7-5bb4-9831-d7270761c22e |  | note | QUALITY DOCUMENTATION - Seal design
checkpoint-group |  |  | section | 12.0 SEALING RECORDS
checkpoint-status |  |  | checkpoint | 12.1 - Pre-seal inspection
label | 128f0b6b-5ec7-50f1-8262-b4356cd19a95 |  | note | SPECIFICATION REFERENCE - Client request
label | 241afc51-13de-5afb-81c6-332186d55f1d |  | note | TEST REQUIRED - Visual inspection
label | e92921bc-af84-5593-aef6-146c5c8ca580 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | 8c89d595-d303-55e0-980c-b8761683b262 |  | note | TASK ASSIGNED TO - Contractor's Quality Manager
label | ebc1fefc-87bd-52f3-bee3-a24df3ea1957 |  | note | MEASURING DEVICES OR METHOD - eye, camera, broom
label | 1a02f37f-3e2c-5064-8995-946b998ff804 |  | note | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | 44626672-054a-59b4-9659-75bf35847ead |  | note | • The large aggregate is
label | 4f25bd09-04e4-582e-83bf-80a53d1f3d7e |  | note | • exposed to the surface;
label | 43e372a5-ef84-5170-8fee-567c72ff4432 |  | note | • held in place with a matrix of smaller aggregates
label | cb6a4920-faec-577d-a792-a973330ee617 |  | note | • The smaller aggregate is held firmly in place by fine material;
label | bd8ef3be-0675-53b1-88d9-9387f5d8f222 |  | note | • The matrix does not displace under normal trafficking or sweeping.
label | 3ec638ff-c31a-5acc-a681-e5c3c858ca14 |  | note | The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 709379d2-a5f0-560c-9b30-a434c74445b1 |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-status |  |  | checkpoint | 12.2 - Blend sheet
label | 33ee4c93-c311-527c-bff4-c0914031f0a2 |  | note | SPECIFICATION REFERENCE - Client request
label | ac282528-a655-5841-b0c6-8c4db115472a |  | note | TEST REQUIRED -
label | 033096fd-2fc6-58da-90af-a99a48f7a3e0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | e93fba30-3abc-552e-8dda-70b8b7462737 |  | note | TASK ASSIGNED TO - Bitumen blending facility
label | 5cae6409-2272-5208-b91d-59b10af4e69a |  | note | ACCEPTANCE CRITERIA - Report value only
label | fd1ad56a-4e44-554f-ad93-d71349ef0210 |  | note | QUALITY DOCUMENTATION - Blend sheet
checkpoint-status |  |  | checkpoint | 12.3 - Spray sheets
label | 1f0d0dae-f24e-55b1-a787-0e1df0d47ba7 |  | note | SPECIFICATION REFERENCE - Client request
label | ea6af27d-d478-5dad-b864-0cda7eba05d0 |  | note | TEST REQUIRED -
label | 1ba3ba95-f7b4-5108-a2f7-c657ec190f88 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | 995b8b32-9910-55e5-a4dc-712b93c8356c |  | note | TASK ASSIGNED TO - Sealing Manager
label | b4f812d3-a802-59e9-b8f5-2651dd4402a9 |  | note | ACCEPTANCE CRITERIA - Report value only
label | 7a52f10d-ff4f-5a84-8c18-59d5d569ca31 |  | note | QUALITY DOCUMENTATION - Spray sheets
checklist-sectioned |  |  | checklist | ITP - No 3 Rd 2.58-4.073 |  |  |  |  | Yes | ITP - No 3 Rd 2.58-4.073 | 479a3b56-27c9-4752-844c-fe43e52bcac7
checkpoint-group |  |  | section | 1.0 - PRECONSTRUCTION HOLD POINTS
checkpoint-status |  |  | checkpoint | 1.1 - Agree QA Requirements
label | c42e9361-cf1b-5c9f-b328-9ab6b64f1057 |  | note | SPECIFICATION REFERENCE- ITP
label | 804cf9de-5283-5345-b36a-8d958cffb773 |  | note | TEST REQUIRED - Check pricing and ITPs & notify Westlink of any difference in understanding of tender pricing
label | 7105c0af-0718-553f-be82-a05d3a0b7ce4 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Review ITP and confirm minimum quality requirements are understood prior to construction handover meeting.
label | 21531601-1424-55cf-b119-d717ebf5ee8e |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 0c867ed5-48a4-554c-9caa-6b45ce803e75 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.2 - Confirm Pricing for Additional Items
label | 809b50e5-ae83-5b70-ad2f-9b1b356a5aff |  | note | SPECIFICATION REFERENCE- NTP
label | c77d0031-c64a-5560-9486-77885d6773c4 |  | note | TEST REQUIRED - Pricing for additional items to be submitted to Design Project Manager and approved
label | 5751feae-7079-5d15-bacc-8e3e252df256 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to construction handover meeting.
label | 3650b0c3-8ff8-5bcc-b1ba-3dd68c296c01 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 6ec6ea3c-c052-5fab-b30f-f3a184cb2b07 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.3 - Construction Handover Meeting
label | d7e9b545-c8e4-50d0-bc0c-3c00e34e3a93 |  | note | SPECIFICATION REFERENCE- NTP
label | 6bbfe7ed-71a8-5c48-80c4-67b18a2ca70d |  | note | TEST REQUIRED - Meeting
label | f6e50a53-e411-5c31-ad66-da7aba7ba3fb |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 2 weeks prior to commencement of physical works.
label | 0e96c7ec-50ff-5d25-9334-c846bb6c8596 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 20341d8f-7038-5f69-905b-b004cd4b2640 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.4 - Physical works Programme
label | c7c8ff2d-4781-58e1-87dd-2d919060993b |  | note | SPECIFICATION REFERENCE- NTP
label | 57618015-9db5-56da-8953-efe2b230ad40 |  | note | TEST REQUIRED - Physical works Programme to be uploaded to WestLink Sharepoint site, emailed to Delivery Manager and start and end dates to by updated in RAMM Contractor prior to physical works.
label | 4c207c69-e563-5d9a-adac-7555d495e972 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 10 working days prior to commencement of physical works.
label | da6ddc71-7602-5f85-8fc9-3889f5c6b732 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 3e1833b0-3d09-5105-830c-a200dda062f0 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.5 - Quantity Review
label | 4a76001d-4ff9-5642-9ddf-62402cd554f9 |  | note | SPECIFICATION REFERENCE- NTP
label | 1631d5c3-1686-56b9-b454-4691e5ee6127 |  | note | TEST REQUIRED - Confirm construction set-out and drawings align with quantities provided in schedule of quantities
label | fd6197ac-01fd-5058-bb0a-59cfca43ac1a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - After construction set-out, prior to commencement of physical works.
label | 666d0e62-ab05-5abf-b29c-2853c73a61ea |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 4dcc89c1-34a1-5a8b-b439-3b17aedcd7f8 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.6 - Existing Pavement Walkover
label | cd111aa6-de43-544d-8002-34bc81f85c0a |  | note | SPECIFICATION REFERENCE- NTP
label | 12489345-ce8f-51a0-ae54-b0f30151adf8 |  | note | TEST REQUIRED - Visual Inspection of existing pavement
label | 66c73384-f139-5870-94ff-2d323e3997e3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to ripping seal construction. Site walkover between WestLink Delivery Manager and Construction Project Manager to identify and agree any isolated treatments required in existing pavement to normalise strength.
label | 3d26d9da-a2fd-5b39-84f6-c9f507ae0259 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | e878e9a9-781a-5264-b068-3f60e14c5ed8 |  | note | MEASURING DEVICES OR METHOD - Eye, spray paint, mark-up on drawings
label | 0f26d3a4-0655-53db-8a2e-30c2345e9d58 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
label | 1fc731de-8550-5dbd-88bc-f79b5b5e3911 |  | note | QUALITY DOCUMENTATION - Mark-up on drawings
checkpoint-group |  |  | section | 2.0 - SUBGRADE INSPECTION
checkpoint-status |  |  | checkpoint | 2.1 - Bearing strength
label | a79156e8-a84f-57a4-a66b-b5b00c2fd658 |  | note | SPECIFICATION REFERENCE- Design
label | e66da1f2-30dd-56cc-ba44-9cde3225e646 |  | note | TEST REQUIRED - Inferred CBR
label | d4ec84b8-ea96-5838-9222-538ae28bc682 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres in seal widening areas where subgrade is exposed by topsoil strip
label | f9cbf1d2-af2f-54ee-99dd-c04522a47ecf |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 2446a740-8e45-5707-af33-73ace2aab1d0 |  | note | MEASURING DEVICES OR METHOD - Scala penetrometer to NZS 4402 : 1988, Test 6.5.2. Inferred CBR from Austroads Pavement Design Manual 2004
label | d82a4824-7d2e-5266-bcd0-2dbc4cb67d05 |  | note | ACCEPTANCE CRITERIA - CBR ≥ 4
label | 2df181ed-253b-5cce-a823-ebff2ca73548 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 2.2 - Compaction (Provisional)
label | 37e905f0-00a5-5ff9-af2e-c2941da7ce25 |  | note | SPECIFICATION REFERENCE- TNZ F/1 10.5.1
label | a41f7fd6-4c25-55fd-835d-e86f39abfd04 |  | note | TEST REQUIRED - Proof Roll
label | a6565de6-5174-56d7-bc3d-bc9cbfc24e6c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 100% coverage (Provisional - where subgrade improvement material has been used)
label | 747a5cf7-9835-5c47-8fff-3002a550d3e0 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 66754c85-3031-5d47-b1ce-7ffe416a6215 |  | note | MEASURING DEVICES OR METHOD - Smooth wheel roller with min loading 6259 kg/m width or large miller
label | fd5a8110-9d4d-5974-beeb-81326d589c58 |  | note | ACCEPTANCE CRITERIA - ≤ 5mm
label | 3f8a5fb2-6d5f-5135-9780-ef1fcfb493ea |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-group |  |  | section | 3.0 - LOWER SUBBASE MATERIAL TESTING
checkpoint-status |  |  | checkpoint | 3.1 - Particle size distribution
label | b13c32be-18fa-5328-8e12-376dfed98fe7 |  | note | SPECIFICATION REFERENCE- Design
label | c53a146e-36e9-5ba5-b46c-18bd96a58c93 |  | note | TEST REQUIRED - Wet sieving test
label | 1d2fa652-45df-57c6-ab85-02bdbed65b41 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - minimum 1 test (on same sample as MDD/OMC curve)
label | c7d1e217-ec6a-539d-b36c-86e49e5a3697 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | cc22e80e-ac69-5bec-9acf-61df9b9faccd |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.8.1
label | e8d91c30-dfd6-598d-8c6a-094086052b98 |  | note | ACCEPTANCE CRITERIA - 100% passing 75mm
label | c57de50c-f648-5ed5-b7ef-d59ff71d19da |  | note | 8 - 50% passing 4.75mm
label | 87dc3982-9f26-5ee3-94c1-491e53f768de |  | note | 8 - 50% passing 425µm
label | 22bc4947-d5da-5f76-a1c2-0c3b85fc832d |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 3.2 - Soaked CBR
label | 5f1d2185-135c-5080-964d-342301c36b8e |  | note | SPECIFICATION REFERENCE- Design
label | e9e9f9ab-2ed5-554d-9cbb-2ff268240f89 |  | note | TEST REQUIRED - Remoulded soaked CBR
label | 57795400-1d19-53db-8ea0-3d61c71e370a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - minimum 1 test
label | 4b4f3200-8108-50fd-b722-2b6789e7a6ba |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 665079a6-4f42-5de4-8b84-6fce73ff4b49 |  | note | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.1 at OMC. CBR testing to NZS 4407 : 1991 Test 3.15
label | 7dfce3ed-ee76-5cb5-a0f2-a05b88e33421 |  | note | ACCEPTANCE CRITERIA - ≥ 15%
label | b32f83d2-d214-5003-9bf9-0bd2c968edf8 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 3.3 - Sand equivalent
label | 395bbace-64c6-57a3-b878-1b59c569e5d4 |  | note | SPECIFICATION REFERENCE- Design
label | adf62abe-434e-53ce-a84a-434064eb3ca0 |  | note | TEST REQUIRED - Sand equivalent
label | 2092c7d3-e678-514d-a9f1-f10e1daeaf55 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 sample per 500m3 - 3 tests
label | f58ec8e4-0cba-52ff-a590-591faedbed44 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 6ba89fd2-342f-5878-87e2-46cbbb89f3ac |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | 1f81b2db-e026-50b5-b8b9-b76432f187c0 |  | note | ACCEPTANCE CRITERIA - ≥ 25 (unless agreed otherwise with Paul Anderson)
label | 4d5596dc-512f-51ac-a913-20fa49943bf6 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 3.4 - Determination of MDD & OWC
label | 4ba914d8-6c84-5b7b-bd52-6e19eed00ba2 |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.5
label | cf2b7263-dcdc-5063-9ddc-3e8ab0830479 |  | note | TEST REQUIRED - 5 point compaction curve
label | 7d1497b0-44c0-51f3-8c56-7009b1b49308 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | a784378d-dd7b-5445-9d22-9394ccfcac3c |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 68c1e1b1-a923-57a7-815a-42b6a2a57bc9 |  | note | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.1 (Standard)
label | a0dd9b1f-6cd1-56be-b7b8-f254131c58e2 |  | note | ACCEPTANCE CRITERIA - report value only
label | aff2114f-eb71-56f1-9ee3-43b83d198ea7 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | 4.0 - LOWER SUBBASE LAYER CONSTRUCTION
checkpoint-status |  |  | checkpoint | 4.1 - Formation
label | 464a08d9-4e34-5156-8969-0c50fba47410 |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.7
label | 7b4019d0-0b8d-5bd3-90f7-62a798416d96 |  | note | TEST REQUIRED - 3m straight edge or approved equivalent
label | 697c51d1-b21c-5628-9c5e-a7749372b716 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 149 Tests
label | 1460f776-b722-54dd-9de1-f218b31c8dbb |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | bc4d0ed7-d104-5198-9c08-26a8efa85791 |  | note | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | 46c2aa38-7076-573a-876b-91302c9cf8e0 |  | note | ACCEPTANCE CRITERIA - +/- 10mm
label | e7c74e55-5949-51ea-b878-369a65c82ed2 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 4.2 - Finished Level
label | d5762e84-74d5-5509-a165-d5c0da93f87e |  | note | SPECIFICATION REFERENCE- TNZ B/2 5.1
label | 95e929ad-d97f-52fd-87b4-53b73b4649fa |  | note | TEST REQUIRED - String line or equivalent
label | ac78cade-c705-5e62-a642-341ef9b4beff |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 149 Tests
label | c048e3ff-f484-557d-935c-e45bcbdcfe3b |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | f12affbb-bb40-5690-b6e9-bd7f32dd216f |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | c3f45e5c-a0ed-5443-8bd5-27ca356fe006 |  | note | ACCEPTANCE CRITERIA - +5mm / -25mm
label | 2ef4b4c7-4ed2-509b-9b25-06469e9b715d |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 4.3 - Compaction
label | 7aed140f-0a44-5114-a05d-7dfe0e373899 |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.6
label | 93e65c83-abd8-559b-aab5-6c106dcc2c61 |  | note | TEST REQUIRED - NDM
label | 0954e6a1-47f6-5583-8555-99eb2b4b9f0c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 20 tests
label | a56d3a98-1e8a-536a-8d91-e48ed44770d0 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 3ebe8e22-d76a-552b-85e0-95dcb1077497 |  | note | MEASURING DEVICES OR METHOD - NDM
label | 27719408-ae86-5340-b15e-95dffa6fc0ae |  | note | ACCEPTANCE CRITERIA - Mean ≥ 95% MDD, Min ≥ 92%, Total voids ≤ 20%
label | 44f2a597-083b-57c3-a2df-02bd79523bdd |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | 5.0 - UPPER SUBBASE MATERIAL TESTING
checkpoint-status |  |  | checkpoint | 5.1 - Crushing Strength
label | 01951ca1-3da8-569b-b852-b61d5b9c8faa |  | note | SPECIFICATION REFERENCE- Design
label | 393ff89c-e6c8-570e-9675-20b95de25158 |  | note | TEST REQUIRED - Crushing Resistance Test
label | 4fc84080-5252-5fcd-84db-56b2e26301af |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 test) - 1 tests
label | 7d6321f2-0d19-5f0b-b652-b0c89e3b2190 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 485bb192-4ebe-5170-accd-011da10618a2 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.10
label | 4d76c3aa-76cc-5f0f-8250-dcb2e86d3680 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 110 KN load
label | 333b30d6-5415-5cc8-ba97-122f651d77ed |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.2 - Weathering Quality
label | 5189d880-b313-5f19-8b37-e75b4094b388 |  | note | SPECIFICATION REFERENCE- Design
label | 08358906-7e1b-5da5-b5c1-144b6fbb39fa |  | note | TEST REQUIRED - Weathering Quality Index Test
label | 863c86c8-61fe-58c1-9151-8b4d9e1e5997 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 test) - 1 tests
label | c054f2ae-eebc-5438-b888-9582baf4f3ea |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 8cdee123-3ece-5a94-8290-367639c68e78 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.11
label | 48fa904d-ff1b-51fa-80a6-7ee0b98b70d1 |  | note | ACCEPTANCE CRITERIA - AA, AB, AC, BA, BB or CA
label | 593aa920-d761-53a3-ac87-7441c8e93eed |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.3 - Soaked CBR
label | 86d8ec04-f767-5893-b9dd-6a87c0b5d326 |  | note | SPECIFICATION REFERENCE- Design
label | 7f2331df-5286-5f24-bde5-8be995c5f2ac |  | note | TEST REQUIRED - Remoulded soaked CBR
label | 06de0ac2-1d73-5880-b1b2-c96283905df7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 sample per 500m3 - 3 tests
label | f3793696-2ddc-58f6-b28e-0997c1d1899c |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | a699164b-bad0-508a-ac78-73e3148a2582 |  | note | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
label | 96b7b7b3-79b7-5756-aa84-1f342ec63d26 |  | note | ACCEPTANCE CRITERIA - ≥ 80%
label | 7a3e59ed-0057-5fa4-a7f7-d9f0200603a8 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.4 - Sand equivalent
label | 504e7054-2386-57ab-9e38-ee7dfa2a5aab |  | note | SPECIFICATION REFERENCE- WBOPDC DC 2009
label | b4106a84-5133-5962-8d08-fbca071acb1c |  | note | TEST REQUIRED - String line or equivalent
label | 71f6b5fa-e461-5e1f-918a-c93f55caffda |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 sample per 500m3 - 3 tests
label | e9e7a9c5-21e6-5743-87e5-c11468d76d58 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d2b55d28-689a-5273-a8ee-a7b229fbc1d4 |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | 0cfed389-c900-5803-9db4-c2cf7a95b47e |  | note | ACCEPTANCE CRITERIA - ≥ 40 (unless agreed otherwise with Paul Anderson)
label | 5ef5b32b-1708-5835-a04b-130463844a96 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.5 - Particle size distribution
label | 3ea707af-f07a-5fd6-8630-fd30cc2afdbd |  | note | SPECIFICATION REFERENCE- Design
label | 3426fcab-904d-57f1-b047-4fa875f70cb2 |  | note | TEST REQUIRED - Wet sieving test
label | 0696ef6f-3051-591b-9979-60441f7c5fcd |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 sample per 500m3 - 3 tests (1 test on same sample as MDD/OMC curve)
label | ea8bb513-6ad7-548e-b4a2-3d0a98c69853 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 9abe0ff0-242a-5983-b14b-4a7b106b2e99 |  | note | MEASURING DEVICES OR METHOD - NZS4407 4407 : 1991, Test 3.8.1
label | 7775b233-4f99-5ec0-9437-df270b8c4902 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.6 - Solid Density
label | a617d3eb-d18e-58d8-bac8-cb4b69f61a0f |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.5
label | 95103a3d-6913-5868-a38b-c22aa00d3a3f |  | note | TEST REQUIRED - Solid Density
label | 4fb2d75d-2148-5892-93bc-f791dddcf637 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 79ee65fa-e7c6-5ced-86b9-03a815b2a47d |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | b05afaef-c726-54df-8c56-ad99f5b62b9e |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.7
label | a065f4bf-af6e-5805-a07b-3fb7884d1b3c |  | note | ACCEPTANCE CRITERIA - report value only
label | a790922e-d823-5f06-9a74-1efb19dc2944 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 5.7 - Determination of MDD & OWC
label | c13b21c8-500f-50f2-be0e-551f7894bff5 |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.5
label | 4d419cc3-3979-5a35-9eeb-6362d791434a |  | note | TEST REQUIRED - 5 point compaction curve
label | 357299ad-7d6e-5032-b022-22e628a075f5 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | f643f314-b54d-5b0d-99de-c3d60ea315f4 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 3b518a37-a872-5b1c-b751-1399154ad581 |  | note | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.3
label | 81542545-dcac-5752-899e-86f4d8f77575 |  | note | ACCEPTANCE CRITERIA - report value only
label | 2532ee39-9a5f-5cbf-bd19-f22859e9da02 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | 6.0 - UPPER SUBBASE LAYER CONSTRUCTION
checkpoint-status |  |  | checkpoint | 6.1 - Formation
label | b7387601-2254-5a48-bdea-54797fea8536 |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.7
label | 9b5c641f-b834-5d6d-8544-fbeccf788006 |  | note | TEST REQUIRED - 3m straight edge or approved equivalent
label | 7f4a0b9b-e894-5672-b7f1-9d17661145b0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 149 Tests
label | 5ed2760f-8b3d-5e0a-9b82-74b9e5e283d2 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 23d53a25-2289-5840-8b18-0f9caf8365ab |  | note | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | 2bb12334-ae80-5ca4-8e6c-1f0aeeb0feea |  | note | ACCEPTANCE CRITERIA - +/- 10mm
label | e691c174-3b32-513b-af7a-e1ad247efc38 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 6.2 - Finished Level
label | f1a003c3-c888-5509-a47d-ad1c06512b7a |  | note | SPECIFICATION REFERENCE- TNZ B/2 5.1
label | 46f21402-031b-5d25-8a6a-c1a8c84c66d5 |  | note | TEST REQUIRED - String line or equivalent
label | 16a672df-412a-576c-abb2-be95e758f1d9 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 149 Tests
label | ab18aaf6-7919-56d4-89ab-4cbd654c034c |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 329f48d8-495b-5411-bebc-131c6148d806 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | a5485781-2045-58af-8501-5ac57d151b05 |  | note | ACCEPTANCE CRITERIA - +5mm / -25mm
label | 8b45d419-a7ca-5a99-81b9-b5449e4b3356 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 6.3 - Compaction
label | 30d352de-5182-545f-84ca-3c7cb4e17d6b |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.6
label | 450d9347-701f-5b3d-a0a8-5951f1c55cdf |  | note | TEST REQUIRED - NDM
label | 91f93453-d238-56a5-ba41-c5bccc098b28 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 20 tests
label | 9562fb70-e940-5365-96f0-c0b4855ab4f3 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 01738b80-7a97-58ce-a3f5-617d4bbd98b2 |  | note | MEASURING DEVICES OR METHOD - NDM
label | b3608704-4483-5bd8-982b-77b7a3dce91c |  | note | ACCEPTANCE CRITERIA - Mean ≥ 95% MDD, Min ≥ 92%, Total voids ≤ 20%
label | 26397396-26d9-598d-8bae-8d44c7b56697 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | 7.0 - BASECOURSE LAYER MATERIAL TESTING - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | 7.1 - Crushing Strength
label | 322297ab-cb2b-5c6a-9a69-f2298c682be3 |  | note | SPECIFICATION REFERENCE- TNZ M/4 3.3.1
label | 89cfa024-a964-5312-a828-82b045faab09 |  | note | TEST REQUIRED - Crushing Resistance Test
label | 5355cea9-b0d4-51b4-8725-09549a49b35a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 8f915c90-25ec-5611-b468-d6c6b7080e6a |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | bc82af5e-e486-5b49-92ee-95ec7a6bf2e9 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.10
label | 1ce43333-5ac5-5223-a66d-9781e1fcdef1 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 130 KN load
label | 781a2725-6b93-578e-a2f3-b6e248bd4488 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.2 - Weathering Quality
label | a7f0af16-1766-5648-8afe-93efc534c655 |  | note | SPECIFICATION REFERENCE- TNZ M/4 3.3.2
label | eb0e531c-93c9-5276-b276-9d3aa628d714 |  | note | TEST REQUIRED - Weathering Quality Index Test
label | f40d8168-bc3a-5f1a-812a-af1b90ffad75 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 72070847-ae5b-566c-bc65-1a7e73329a70 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | be83480d-52df-5ad8-9166-0893572606cf |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.11
label | 7d648518-6076-539b-bbf4-5944154b778a |  | note | ACCEPTANCE CRITERIA - AA, AB, AC, BA, BB or CA
label | 9715f8a4-d98b-55ba-b681-0e198f20ce21 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.3 - Soaked CBR
label | 23fab5fe-4e20-5a93-ab72-bd48f17871b7 |  | note | SPECIFICATION REFERENCE- TNZ M/4 3.3.3
label | cf7b9352-339d-551e-b47b-27ffffde0848 |  | note | TEST REQUIRED - Remoulded soaked CBR
label | 489fb3d2-77ee-5c44-be65-3b9dac99c3c7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 67f8c4e6-7f8a-570a-aa50-ee39cac64ce3 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e0a9857f-204b-50db-91ac-4ad35344730f |  | note | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
label | b02f990f-5700-5ed5-b9de-873fd0be0461 |  | note | ACCEPTANCE CRITERIA - ≥ 80%
label | 906d35a3-98d7-58f9-80b5-804b1f36cfe8 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.4 - Sand equivalent
label | efb9c4ca-1182-55d7-80da-03b9040e4e7e |  | note | SPECIFICATION REFERENCE- TNZ M/4 4.2.1.1
label | d58b2993-de86-527b-af62-b878ec86f3af |  | note | TEST REQUIRED - Sand equivalent
label | 39ed6615-835e-54e8-a73a-53315bbe8b00 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | 019ae727-5a32-5808-9837-2e7d249f009e |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | c798586f-5eed-5028-9362-2ae7c3d86298 |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | 295a0a1b-813b-57dd-956c-088e550e9e7a |  | note | ACCEPTANCE CRITERIA - ≥ 40
label | 46f209ea-06d4-5ee5-9d7b-c0f2c97d240d |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.5 - Broken Faces Content
label | 3daf9c80-5c68-58e0-be84-9c09f5de0518 |  | note | SPECIFICATION REFERENCE- TNZ M/4 4.2.2
label | cb581073-11d6-5881-99d3-6e24fff32dfc |  | note | TEST REQUIRED - Broken face content
label | 975f3016-b1a7-5db4-bce7-43efa16e39c3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS -
label | b7b1402a-c19f-55ea-9ff0-6b8944a5f1a9 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 28dda8ab-6317-577f-8107-e3f513bb1d26 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.14
label | 43de2b4d-dee4-5331-93d3-0454190e3035 |  | note | ACCEPTANCE CRITERIA - ≥ 70%
label | 9e14b34b-feb9-5e6f-b1fa-de065427a29b |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.6 - Particle size distribution
label | 0e3e009c-ff6d-5f65-9218-70b8cb75195e |  | note | SPECIFICATION REFERENCE- Design
label | f23edffc-1125-5091-9609-c5b9adec4a6a |  | note | TEST REQUIRED - Wet sieving test
label | f82cf155-1204-5979-90f7-1b95be1f6708 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS -
label | 6d63ed4e-ae03-5913-a1d9-b3555cd32fbc |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 217cb60a-6332-5110-b41b-c4c232c54f19 |  | note | MEASURING DEVICES OR METHOD - NZS4407 4407 : 1991, Test 3.8.1
label | cd527f85-4775-5e9e-a177-6122baf4eb4c |  | note | ACCEPTANCE CRITERIA - 100% passing 37.5mm
label | b1be180c-3e7c-5534-940c-df2ba94d4cf9 |  | note | 66 - 81% passing 19mm
label | a3fef190-8ae0-534e-b373-215fa777e641 |  | note | 43 - 57 passing 9.5mm
label | d0730c55-9bb4-5027-9403-8040703c62e9 |  | note | 28 - 43 passing 4.75mm
label | 95b2040e-5435-551b-ad03-a1f4b0b53416 |  | note | 19 - 33 passing 2.36mm
label | 8e396889-581a-5fbb-8bb5-6f2dde6945e7 |  | note | 12 - 25 passing 1.18mm
label | 4416fb68-786b-5ed4-9ef8-91c95bcc8998 |  | note | 7 - 19 passing 600µm
label | f6ac667b-a0d5-5595-9d8b-49469be5ef6f |  | note | 3 - 14 passing 300µm
label | 54b8093d-2e30-5164-b524-f704e5ae3bbf |  | note | 0 - 10 passing 150µm
label | ce4f7be4-a977-54eb-906c-95cfedb33263 |  | note | 0 - 7 passing 75µm
label | b7c5e871-e813-518d-bb29-95ac2d9777f6 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.7 - Solid Density
label | af711ffe-97df-58f8-9070-b795045ed9fc |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.5
label | 41c5ee2f-aa76-5d89-9aa0-7a036a03b8a4 |  | note | TEST REQUIRED - Solid Density
label | 75b88d94-612d-5342-baac-9eaa8a471608 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 3 tests
label | a3c35914-2c10-55ad-afad-e015eaf37826 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | b9e33d3e-2f79-5fe9-a18b-f866e0311469 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.7
label | 83d72515-e039-5d27-8c29-12309e51d6f1 |  | note | ACCEPTANCE CRITERIA - report value only
label | 629b1c55-07a6-53e7-95a6-b664da5d3326 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 7.8 - Determination of MDD & OWC
label | 5e5b2b08-dc95-559d-b227-7e46b393fbc2 |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.5
label | fcbef630-fae7-594b-b45a-864fb8c87d41 |  | note | TEST REQUIRED - 5 point compaction curve
label | 2909b9eb-50dd-5eee-b12c-fafd5a880aa6 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 3 tests
label | a37bb2ea-e5e4-52e6-8e0a-5f77d16ec6b6 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | b1f14fbf-1119-5ba5-a626-8310ee5dd80a |  | note | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.3
label | 16aad7c9-6b9e-519b-b363-667ce51f7e19 |  | note | ACCEPTANCE CRITERIA - report value only
label | ac7eb6fc-0219-5358-9c4c-10efabe3b252 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-group |  |  | section | 8.0 - MILLED SURFACE CONSTRUCTION (IN TIE IN AREAS)
checkpoint-status |  |  | checkpoint | 8.1 - Finished Level
label | 1d57dd5a-68f9-5151-9eeb-e51802141b3f |  | note | SPECIFICATION REFERENCE- TNZ F/1 11.2.2
label | 08c70a3a-2595-5ebf-945c-149061dcdb51 |  | note | TEST REQUIRED - String line or equivalent
label | 64771058-7924-56b1-980a-5e3c4fd49a84 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 149 tests
label | 815038a2-49e1-540b-ab5f-a31148dc3e6f |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 81abac41-afed-56d6-84af-f81025a24679 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | 67dc3bee-63ab-5f93-98e1-58afe413dc03 |  | note | ACCEPTANCE CRITERIA - +0mm / -30mm
label | 8408028c-f18a-5c88-b43a-fdf8caa41876 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-group |  |  | section | 9.0 - BASECOURSE LAYER CONSTRUCTION - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | 9.1 - Formation
label | b2ec11b8-533d-56a6-ade7-3ea912f4474d |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.7
label | 8e1e673e-4463-5c55-aa65-0170bef64874 |  | note | TEST REQUIRED - 3m straight edge or approved equivalent
label | ea741b64-8b90-5015-9143-d5f93c6c8de0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 149 Tests
label | 8ae5370d-f016-5f7a-b232-498421a239ab |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 6aa38a88-c994-557a-800f-912f7a20a340 |  | note | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | cf2807cf-35d8-5bcd-bd37-68667d9965f5 |  | note | ACCEPTANCE CRITERIA - +/- 10mm
label | c89bec0a-8e60-5fd0-820e-97ba93a60b5b |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 9.2 - Finished Level
label | 59a0b7d0-2657-5d17-ab5e-31120bff6e8a |  | note | SPECIFICATION REFERENCE- TNZ B/2 5.1
label | bbf9c3da-78df-5ea1-8e94-10d7012e25ac |  | note | TEST REQUIRED - String line or equivalent
label | db0f98f0-5dc2-5aef-83d7-7b0d715e0a0b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 149 Tests
label | f1290135-400e-5bb1-b517-b8f6ba20ddb2 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | c82a938d-42c7-5b93-ab80-a94b06f84500 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | 90485f25-f123-5d5a-b9e4-205473b957c2 |  | note | ACCEPTANCE CRITERIA - +15mm / -5mm
label | d28e6770-732a-5fc9-845a-fa579120c01c |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 9.3 - Plateau Density Test
label | 3c6d4b5f-6608-5d61-8808-559499a85b96 |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.5 (b)
label | 6e96c993-356e-5172-b9d1-c7c73af0d825 |  | note | TEST REQUIRED - Plateau Density Test
label | e9263598-9a72-5c14-a213-6cd56d7e4f95 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test minimum
label | 508ba34c-7842-5880-a1c6-7b1c70780045 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 1be08e4f-bde2-53d8-8508-4fc8e11e207f |  | note | MEASURING DEVICES OR METHOD - NDM
label | 1147a276-8a92-5590-9304-4670f723650a |  | note | ACCEPTANCE CRITERIA - report value only
label | 2b12b983-452e-553a-bd13-afc3e2eea019 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 9.4 - Compaction
label | cc13ba4d-9505-503a-8a25-6746c7226a3e |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.6
label | e33be522-6f8a-52cd-bcfc-b3bfcb9f40fd |  | note | TEST REQUIRED - NDM
label | 4680b91d-e745-5808-b7b7-5a5759f13cbe |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 58 tests
label | 9eae6416-88eb-579c-9c3d-bff5b04b801e |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | ca1ce37b-ad7e-50a5-b2a4-5e4b592598c8 |  | note | MEASURING DEVICES OR METHOD - NDM
label | 10304702-6650-5c16-9321-614e81aea5f5 |  | note | ACCEPTANCE CRITERIA - Mean ≥ 98% MDD, Min ≥ 95%, Total voids ≤ 20%
label | 0b3498ba-7bfb-550f-a7ef-a2f73aa2b8d9 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 9.5 - Degree of Saturation
label | 8825ddcb-231d-5125-8fbd-83b6b2ff20d4 |  | note | SPECIFICATION REFERENCE- TNZ B/2 12
label | b9fe2d0e-42b2-5629-951f-58ef414d8941 |  | note | TEST REQUIRED - NDM
label | 19e9b88c-7652-5018-af91-465031d63ca7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 58 tests
label | 8a233cc2-68b0-5f07-aac8-53391b666944 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 94a6fc9c-b947-5988-b076-71dd0197fffc |  | note | MEASURING DEVICES OR METHOD - NDM
label | f3155d2a-1c7a-51e8-9dea-3c1a11d34896 |  | note | ACCEPTANCE CRITERIA - < 60% (or 80% on consultation with the pavement designer)
label | 6b8da8fb-0f0a-516e-b91c-105abba88d70 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 9.6 - Surface Finish
label | b28d13a1-c655-5044-a770-82e8303cc4d7 |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.8
label | 882a98fe-f5e4-5375-8f54-f002493bd118 |  | note | TEST REQUIRED - Visual Inspection
label | 9480b668-d874-5578-9e01-f825f693fa37 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | 31d11157-3c28-5679-9dfc-22612535fac3 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | f1154e15-17b5-5541-b22e-35052eddf3a5 |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | ef6adb9c-03c6-5fcf-8563-d200539df0a3 |  | note | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | fa54d31f-852b-5716-bb36-2062b709e446 |  | note | • The large aggregate is
label | d2affd46-b054-562d-bb73-8774de50008d |  | note | • exposed to the surface;
label | ea6beec9-7beb-5c76-8e97-860408ae448f |  | note | • held in place with a matrix of smaller aggregates
label | 64132665-ab37-5cae-a09f-085e0cf6eda7 |  | note | • The smaller aggregate is held firmly in place by fine material;
label | e68707e0-caf8-5add-83e6-fb87569a6e26 |  | note | • The matrix does not displace under normal trafficking or sweeping.
label | f1445fc6-d516-55e6-bfc7-1e950dd552da |  | note | The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | e007d6c3-4387-5467-9c32-3e7378137cf2 |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-status |  |  | checkpoint | 9.7 - Ride Quality
label | fadbbeb3-a1aa-582d-8b23-9a9239d949b7 |  | note | SPECIFICATION REFERENCE- Internal measure
label | 7d93f2f4-a1bb-5845-8666-18b882ccd19f |  | note | TEST REQUIRED - Ride quality test to AG:AM/T002
label | 3c82f3b7-79cf-5f0e-a2b3-93c693cfdb83 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Within 12 months of first coat seal
label | 6c862659-8660-55e0-baae-bfd2fe336167 |  | note | TASK ASSIGNED TO - Either by pavement subcontractor or by Westlink Asset Management team from latest HSD survey
label | 3a8b8d99-e788-5109-b7e9-09397e7508c0 |  | note | MEASURING DEVICES OR METHOD - inertial laser profiler or response-type roughness meter
label | adb5789f-7d89-5b5d-ab11-35d7be4be16a |  | note | ACCEPTANCE CRITERIA - no 100m moving average > 60 counts
label | 2199749d-9909-5f27-8447-45caeec8679d |  | note | QUALITY DOCUMENTATION - Certified test report
checkpoint-group |  |  | section | 10.0 - BITUMEN - TO GAIN APPROVAL
checkpoint-status |  |  | checkpoint | 10.1 - Penetration
label | ed882c1d-78cc-553b-8416-143bac6fc035 |  | note | SPECIFICATION REFERENCE- TNZ M/1 Table 1
label | 3bdd9387-8d51-5ecb-9fa9-fb3dc8fcdf33 |  | note | TEST REQUIRED - Penetration at 25°C, 100g, five seconds
label | 83ebc970-a1ca-51e5-8647-638eddbceef8 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 5b2efc8b-a3fc-5c63-ad0b-e4eaf2ea9c47 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | f3912cb7-8563-584d-b12b-58851ad0c19e |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | 8a832480-4c0f-5a0e-bbf0-e89777499608 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | d186816a-5654-51b3-ad9f-2f53a507641f |  | note | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 10.2 - Viscosity
label | 522d44b4-f421-54f5-b895-564f9d2caec8 |  | note | SPECIFICATION REFERENCE- TNZ M/1 Table 1
label | 8de15ff2-2b87-5347-b635-8526f175415a |  | note | TEST REQUIRED - Viscosity PaS at 60°C
label | 0868a3b7-cea6-5db6-af1f-32b50b61e108 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 539c9330-f399-59c3-83ba-bbaca96dc692 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 2094f04c-8ff2-534c-9633-27c55228b0d8 |  | note | MEASURING DEVICES OR METHOD - AS 2341.2 or ASM D2171
label | 7e67a404-b508-552e-ad6f-6b5458370b7f |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 10.3 - Viscosity
label | a696070b-2772-5390-ba73-d4cf133874ef |  | note | SPECIFICATION REFERENCE- TNZ M/1 Table 1
label | a26e9c45-7611-53c9-a320-7e16b7f23d94 |  | note | TEST REQUIRED - Viscosity mm2/s at 135°C
label | 3a8ac235-eb59-507f-88ee-009495007478 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 573e93d9-f76b-5a01-bab2-8a9d0a9f82de |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 4da54837-c263-5c41-9eea-ba7141a46214 |  | note | MEASURING DEVICES OR METHOD - AS 2341.3 or ASM D2170
label | f7e95678-c38f-56cd-9d0a-17cf7af79589 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 10.4 - Flash Point
label | 6dfcd996-9e7f-5367-be0d-f81587505270 |  | note | SPECIFICATION REFERENCE- TNZ M/1 Table 1
label | be6686ef-87f3-54b1-9901-3134f765807e |  | note | TEST REQUIRED - Flash point (Cleveland open cup), °C
label | 84e5f863-6b59-50f1-86b4-db01b2b86f35 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 08c8e4fc-859d-51eb-8324-f7a244322138 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 76019237-a256-5cb2-8dbe-eb82940ea38c |  | note | MEASURING DEVICES OR METHOD - ASTM D92
label | a82126db-7663-51e0-bdac-b3020e962fab |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 10.5 - Solubility
label | f2928db2-a40c-59c7-9aa1-248caf16a440 |  | note | SPECIFICATION REFERENCE- TNZ M/1 Table 1
label | 032d7d8a-5fa8-5194-aba0-35618dd2de60 |  | note | TEST REQUIRED - Trichloroethylene, % or
label | 3a263d39-37e2-5cd7-b4b9-6ae86fa1d7bb |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 3d9f5770-9976-55bf-a0a4-e5ee3766a249 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 07e2e386-fe87-5b63-b10c-a9dae56dcc3d |  | note | MEASURING DEVICES OR METHOD - ASTM D2042, AS 2341.8
label | 68b7763a-f9f7-5ec5-b2c7-236fcf033074 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 10.6 - Rolling Thin Film
label | e3377ca5-1d4b-5d3d-9c3f-4ee1cb68fd18 |  | note | SPECIFICATION REFERENCE- TNZ M/1 Table 1
label | 75cbe301-2d94-573c-8550-6e5b1974bb13 |  | note | TEST REQUIRED - Rolling Thin Film Oven Test
label | 0b00425f-4f12-5676-9508-996a3ce91248 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | cfe16c0e-cb23-5a6f-82cd-28b830270db6 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | acf928a6-8677-5cd6-bf2a-0ece713219bd |  | note | MEASURING DEVICES OR METHOD - ASTM D2872 or AS 2341.10
checkpoint-status |  |  | checkpoint | 10.7 - Penetration
label | 40eaf3f8-b3a3-5c5c-936d-818d3ce07c9c |  | note | SPECIFICATION REFERENCE- TNZ M/1 Table 1
label | a08be111-242a-576a-8a91-26d32e915530 |  | note | TEST REQUIRED - Penetration of residue, at 25°C, 100g, five seconds, % of original
label | 2146c7e2-e55c-53ca-b5f1-a3058cf4b2bc |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | bc3bba93-caff-5058-840b-9e1d8187f298 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 0035ed80-2fc0-5908-a1c5-94e166ff472a |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | 202f9dee-3264-5ed6-b1b9-90b3bc2ee44a |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 10.8 - Ductility
label | f33ae713-bd47-5545-8204-5a4868b2d615 |  | note | SPECIFICATION REFERENCE- TNZ M/1 Table 1
label | 33825743-68d8-5803-b2e4-9572e0a49f3a |  | note | TEST REQUIRED - Ductility of residue, at 25°C, (metres)
label | 75133eab-abfe-5f51-85b1-94bbf59fe42a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 03dd81bf-7ef5-51b1-af0b-b3d7167b5a1b |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 1321d70c-5a15-5753-9e83-ebae923958e8 |  | note | MEASURING DEVICES OR METHOD - ASTM D113
label | f520d6b4-a2ae-5c69-a7ab-54d10e6171b2 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-group |  |  | section | 11.0 - SEALING CHIP MATERIAL TESTING
checkpoint-status |  |  | checkpoint | 11.1 - Crushing Strength
label | 885835b2-a062-574a-acef-d4ebd21918f6 |  | note | SPECIFICATION REFERENCE- TNZ M/6 3.2
label | 7e031b06-ab1f-5931-8674-49af293ef964 |  | note | TEST REQUIRED - Crushing Resistance Test
label | 1769ee1b-7554-5109-ad3b-181a6e933009 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality
label | e489a3b2-ac88-56e9-bfbc-c0c40573f7df |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | b96cfbf5-4c28-5549-841e-b4ff883b78f8 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.10
label | 8a2c3f51-d289-58cb-8c29-5dfe56bbbdc3 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 230 KN load
label | cfc0dd3b-0feb-52bc-b4f5-daa1655f5cbf |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 11.2 - Weathering Quality
label | 957e98b2-6dcd-5380-89c6-c479dbbef465 |  | note | SPECIFICATION REFERENCE- TNZ M/6 3.3
label | f135e3a0-54d0-53d8-9021-b6296e86e5ba |  | note | TEST REQUIRED - Weathering Quality Index Test
label | 9fd24389-11ae-5158-9733-55a60c41792e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | c14b059b-4ae2-56f2-99ff-72f034fa9bdd |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 1e9f8500-4cb8-5b7d-aeba-e01d46efabfe |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.11
label | 5b7aedbe-5c75-5dac-a452-5946fb694390 |  | note | ACCEPTANCE CRITERIA - AA or BA
label | 1b9be637-2753-559b-907a-7afa9101798a |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 11.3 - Weak Particles Test
label | d9788e99-28ea-55cd-b9ce-8ef90fa6f7c9 |  | note | SPECIFICATION REFERENCE- TNZ M/6 3.4
label | 6eee4ce8-c5e0-5ec5-8582-40e7b97d0926 |  | note | TEST REQUIRED - Australian Weak Particles Test
label | 0493a0ac-af9c-5e3c-ba0f-06a083c0e45f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Only undertaken in cases of dispute
label | ae4a2cce-2ef1-53a5-97e7-ef1145375e79 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 7a99aade-7a2c-5d72-ada3-32e600ad3f66 |  | note | MEASURING DEVICES OR METHOD - AS 1141.32-1995
label | 40cc25c3-6a6a-52e5-8854-a9df370b3e81 |  | note | ACCEPTANCE CRITERIA - Maximum of 1%
label | 499e730c-fe2d-5a24-86b4-82abe26397ac |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 11.4 - Polished Stone Value
label | 9975743b-b56a-5ca2-9e96-6cdf84c11bcb |  | note | SPECIFICATION REFERENCE- TNZ M/6 3.5
label | 189e30ac-8733-5cda-bde0-b1176fc2e9bd |  | note | TEST REQUIRED - Polished Stone Value Test
label | 00d9cb5f-b98e-5b5a-8c9f-97107c5bcf87 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality
label | 19cefba3-9337-57d8-b097-0d998a25b00d |  | note | TASK ASSIGNED TO - Accredited PSV Testing Agency
label | f8df21e2-bd33-5494-a6de-4e371c77e141 |  | note | MEASURING DEVICES OR METHOD - BS 812: Part 114
label | a30e0a78-7476-579a-a632-39cb652ee70a |  | note | ACCEPTANCE CRITERIA - PSV Required = 43
label | 19f6ba5e-d81a-5319-9642-b31b8f2030f3 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 11.5 - Cleanliness
label | 7d7ab4b3-54e5-5151-93bd-6d9b7a0c0a87 |  | note | SPECIFICATION REFERENCE- TNZ M/6 4.1.1
label | 88469ada-dc54-5dea-a5b4-fdf6359899eb |  | note | TEST REQUIRED - Cleanliness Test
label | f8576e3d-dbb1-52a9-be92-7d372bb75b4b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 82f9affe-df18-56e3-aa15-403c748e82fe |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d65ca5bb-3dfd-55b3-849c-3d2ecb18a144 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | dd5d79b7-97c1-533a-9ea6-f76bfc73c1d9 |  | note | ACCEPTANCE CRITERIA - Grade 2 - 89 min
label | 1c36bedc-a15e-58e6-b435-2e5a48f24294 |  | note | Grade 3 - 87 min
label | 3b1737bd-0023-5a14-a9a3-78da8b520a1c |  | note | Grade 4 - 85 min
label | 78639aa6-85a0-5cce-a372-89ee4e1bd11d |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 11.6 - Size & Shape
label | 040ff09c-2a7e-51b1-9be9-93a06a4fb780 |  | note | SPECIFICATION REFERENCE- TNZ M/6 4.1.2
label | 1934e9a9-38c2-5593-a44d-5bab516104f1 |  | note | TEST REQUIRED - Size & Shape
label | 61a2021e-34bf-55b1-ad66-a35abd88948d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 79387c0f-f4cd-5975-9db8-333bcf13359e |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 7d3131ae-0f42-5468-b6a2-241fb1e7c857 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.13
label | 94e10034-e7d3-5ca5-9119-12add2f19806 |  | note | ACCEPTANCE CRITERIA - Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD
label | a4ab65a8-72d6-52d9-9253-9a1076638043 |  | note | Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD
label | 13696f60-f7f3-5e92-8db9-2ae2ede5d704 |  | note | Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD
label | 791ab553-7c4a-51c3-a792-bb6721e85a47 |  | note | 1.1% passing 4.75mm
label | 66d0a3c1-240e-503f-851f-08daa5eb22fb |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 11.7 - Broken Faces
label | 9116099e-7651-5a49-bafe-8048a784ba5c |  | note | SPECIFICATION REFERENCE- TNZ M/6 4.1.2
label | 50a1f4b7-06cf-5fb8-8c75-6c087f7b250f |  | note | TEST REQUIRED - Broken Faces Test
label | 3b96537b-82da-5a81-95b4-b86af985ab2a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 0f28699f-895e-5605-9b69-189f58e15b96 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 23f84006-dee0-53c4-b36f-5b5387654344 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.14
label | ad510466-6f4d-50bd-a88a-f6fd9dedf8cb |  | note | ACCEPTANCE CRITERIA - 98% with minimum two broken faces
label | 1a1d0a8f-8391-542a-987c-dbbc9759fe58 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 11.8 - Grading
label | dab18718-e952-5527-8d3f-93530e25d7f9 |  | note | SPECIFICATION REFERENCE- TNZ M/6 4.2.2
label | 8823c5bd-ba17-5032-ae31-59f07af490e1 |  | note | TEST REQUIRED - Grading
label | 3e38b256-5281-5332-ac03-95c4bbca8375 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 9178d770-4ac1-5c57-8043-d4c39c7080bb |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 8e4cfb8b-b1b3-57d9-9024-c1f80c8d59af |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.8
label | 95c5871b-742a-5a7b-a592-a864e2e76cfa |  | note | ACCEPTANCE CRITERIA - Grade 5
label | dc44a5bd-411f-5334-9bcf-0e63d483c486 |  | note | 100% passing 13.2mm
label | ad170ddc-d77a-56e5-b6cc-518c4090148c |  | note | 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300µm
label | f30a8d6c-7537-590d-89c6-c77f98bc3f54 |  | note | Grade 6
label | 06e036d3-dd36-504a-bcf3-10e40bb75241 |  | note | 100% passing 9.5mm
label | fc3adb2a-38db-53ce-906f-5bf5efd21355 |  | note | 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300µm
label | a7ba12fe-7679-5df9-a0e3-7ec0d1d4b147 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 11.9 - Cleanliness
label | f355f3e0-95e2-53db-b452-aa4782fdc0db |  | note | SPECIFICATION REFERENCE- TNZ M/6 4.2.3
label | 1c7858f6-bad7-5149-b955-44515379a3e6 |  | note | TEST REQUIRED - Cleanliness Test
label | c4b2a8fa-6f8b-5168-bc68-74d1d0349476 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality
label | 86780b9c-9ecf-56c9-8c6d-4eebbedbb546 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | de4fb7ad-c82f-5e73-859a-531f02e7a3a6 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | 81f0fbc4-439b-5a1f-a3a7-59ca29566d7f |  | note | ACCEPTANCE CRITERIA - Report Value Only
label | 9638639b-eb67-5892-aad2-5d2669725209 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | 12.0 - SEAL DESIGN
checkpoint-status |  |  | checkpoint | 12.1 - Seal design
label | 20ab68a6-b31a-5d43-b3d7-2dcc2b7f66fd |  | note | SPECIFICATION REFERENCE- TNZ P/3
label | 81acd97e-701d-5b5f-a6ab-33119c99ea36 |  | note | TEST REQUIRED - Seal design
label | 7eb99ae6-b7e1-5d31-b3e0-0f3892e02d03 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | 447ee3a4-3656-50fa-8a49-c177cfbf4c82 |  | note | TASK ASSIGNED TO - Contractor's Quality Manager
label | 0531543c-2022-5e87-902a-5432674a5397 |  | note | MEASURING DEVICES OR METHOD - report only
label | e740488d-7308-5b93-8f83-584e30bb3699 |  | note | ACCEPTANCE CRITERIA - report only
label | b28f10ef-7efd-5963-a967-92ef8bfd59ab |  | note | QUALITY DOCUMENTATION - Seal design
checkpoint-status |  |  | checkpoint | 12.2 - Seal design approval
label | 4a13df98-ca6a-5ffd-b30d-7c1ab1c16520 |  | note | SPECIFICATION REFERENCE- Internal measure
label | 956ede86-81be-547a-b1eb-2cfa70b2d497 |  | note | TEST REQUIRED - Internal verification
label | fced4712-56a2-5f6c-9ab4-41e50c61443c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | b38bd927-f70e-5d0b-afef-b2ffbf0bebd4 |  | note | TASK ASSIGNED TO - Downer Surfacing Expert
label | 611ffaa6-1584-5528-a45d-ce0d48d02f9c |  | note | MEASURING DEVICES OR METHOD - report only
label | 374b7297-5889-59fb-94c5-e5709f7e7206 |  | note | ACCEPTANCE CRITERIA - report only
label | 1627414f-1488-58c5-ac9b-886f3d761d11 |  | note | QUALITY DOCUMENTATION - Email from Downer surfacing expert confirming that the treatment selection and seal design has been reviewed to confirm it is fit for purpose
checkpoint-status |  |  | checkpoint | 12.3 - Surface Finish
label | 276c8c79-73d4-591d-807c-f1f5a9a28a30 |  | note | SPECIFICATION REFERENCE- TNZ B/2 7.8
label | ce81a0f8-7d86-5615-b29e-645992adb00d |  | note | TEST REQUIRED - Visual Inspection
label | d8144d51-845c-53d8-950b-02411475bb62 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | a531dc2b-79f3-579e-bd9b-57d6bc99c8ae |  | note | TASK ASSIGNED TO - Sealing subcontractor quality representative
label | 9dcfe007-31e1-560b-a35d-cf3da359f647 |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | e4663460-987c-5dbd-82fb-cc5a1a33369f |  | note | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | e5ca68c6-5271-54ff-8414-cafdaa31ee2e |  | note | • The large aggregate is
label | 7a4fe414-9ca7-5435-97f1-ed6e94dd3869 |  | note | • exposed to the surface;
label | c7704a85-af82-58c2-a39a-51f2a1206b76 |  | note | • held in place with a matrix of smaller aggregates
label | 97787168-86e1-58e1-82a3-e4b3fcedbf92 |  | note | • The smaller aggregate is held firmly in place by fine material;
label | f4e4a7c7-b4a8-5365-bfe7-3284dd2c4b61 |  | note | • The matrix does not displace under normal trafficking or sweeping.
label | c8d6412e-0d47-529c-9d96-43c22567e033 |  | note | The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | c97a50dd-e63f-5252-94d7-04e4b3ac1c21 |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-group |  |  | section | 13.0 - SEALING RECORDS
checkpoint-status |  |  | checkpoint | 13.1 - Blend sheet
label | c6671cf5-6dd7-57a2-9688-382fd2c60845 |  | note | SPECIFICATION REFERENCE- Client request
label | b75dc4c6-0426-55ee-b4bb-22fb5b651126 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | d94b8756-7650-5d77-babe-458d7c87e5db |  | note | TASK ASSIGNED TO - Bitumen blending facility
label | 166932f5-80fa-5bb3-ba6d-09f4d5269c95 |  | note | ACCEPTANCE CRITERIA - Report value only
label | b2d4106b-1d29-5a8b-ad5e-9c4d7aabeed0 |  | note | QUALITY DOCUMENTATION - Blend sheet
checkpoint-status |  |  | checkpoint | 13.2 - Spray sheets
label | abb29ec0-7eba-5753-acb0-f72675c653d6 |  | note | SPECIFICATION REFERENCE- Client request
label | e0702ac2-8983-5545-b5d4-2bdc2feeacae |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | 903d300a-4a4d-592b-8b7a-18174478b968 |  | note | TASK ASSIGNED TO - Sealing Manager
label | 379f8fa2-7988-5cb0-a70f-d52174c2d5cf |  | note | ACCEPTANCE CRITERIA - Report value only
label | cfdbe38a-e9a8-5685-a77b-9b80a976ad59 |  | note | QUALITY DOCUMENTATION - Spray sheets
checklist-sectioned |  |  | checklist | ITP - Maniatutu Rd 1.400-1.940 |  |  |  |  | Yes | ITP - Maniatutu Rd 1.400-1.940 | 74b735c9-0d8b-4167-8909-0749321b57da
checkpoint-group |  |  | section | PRECONSTRUCTION HOLD POINTS
checkpoint-status |  |  | checkpoint | Agree QA Requirements
label | 33e365c7-a8fd-5b17-b094-f21d349fe56b |  | note | SPECIFICATION REFERENCE - ITP
label | 4e39ffd6-95de-5405-91af-85a84338c566 |  | note | TEST REQUIRED - Check pricing and ITPs & notify Westlink of any difference in understanding of tender pricing
label | 5e231916-2296-51a9-8576-4bcf4525c03a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Review ITP and confirm minimum quality requirements are understood prior to construction handover meeting.
label | 38adab9b-df07-518f-a19d-2a3920889252 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | b80d4316-7dd8-515f-be89-bf2238d31f08 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Confirm Pricing for Additional Items
label | 65845d02-576a-5ecb-9e0d-f82751d6bbd7 |  | note | SPECIFICATION REFERENCE - NTP
label | bca639cd-87f2-5f40-b309-8191e5781967 |  | note | TEST REQUIRED - Pricing for additional items to be submitted to Design Project Manager and approved
label | a2c48b28-8c6d-554c-861e-af8851ca2391 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to construction handover meeting.
label | 23d63199-dbc6-56c6-8126-2200df16bcac |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 50b292a8-a665-5fde-be76-6e8c0bb2f5c1 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Construction Handover Meeting
label | 183ba916-984e-57e2-8469-0b8e06917e8e |  | note | SPECIFICATION REFERENCE - NTP
label | 654fc4a0-140a-530d-99bc-af51eaee25ca |  | note | TEST REQUIRED - Meeting
label | ae2f0d91-20a0-5b39-88fa-2e3565d32c47 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 2 weeks prior to commencement of physical works.
label | bb079ef1-7283-5456-a650-eba9dbb9b74e |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 1fcec003-64f1-554f-9193-20f7e8058f20 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Physical works Programme
label | d87d676b-258d-58f0-92ad-393fa4f042b5 |  | note | SPECIFICATION REFERENCE - NTP
label | d2b30489-1223-5584-bafb-d0d362503f2f |  | note | TEST REQUIRED - Physical works Programme to be uploaded to WestLink Sharepoint site, emailed to Bryan Crean and start and end dates to by updated in RAMM Contractor prior to physical works.
label | 6de7e2c4-95b6-5520-a3f9-9e9903cefe6b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 10 working days prior to commencement of physical works.
label | acf1298c-e39f-5c3b-8543-948e8aac1142 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | f6337f0f-487a-5b7d-ac69-8ca10c6bcac3 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Quantity Review
label | 436601f1-7656-5eb8-a4ca-20590e30acad |  | note | SPECIFICATION REFERENCE - NTP
label | fbafa0a7-3a3c-578d-aefe-61d5f97ed0bd |  | note | TEST REQUIRED - Confirm construction set-out and drawings align with quantities provided in schedule of quantities
label | 257ae5f5-0eb2-5884-b992-ff6ab63e59f5 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - After construction set-out, prior to commencement of physical works.
label | 93f0353c-79fb-5385-b609-dd03d349d6fb |  | note | TASK ASSIGNED TO - Construction Project Manager
label | ef7149e4-c248-54d4-a5e9-32c83d84283f |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Existing Pavement Walkover
label | 5b76a2ee-2772-5c3f-b213-43de28f0d4ec |  | note | SPECIFICATION REFERENCE - NTP
label | 097997d9-743e-5d68-834b-6c664ec2d410 |  | note | TEST REQUIRED - Visual Inspection of existing pavement
label | 7c04bfe9-5baf-5215-b089-6815588ff45e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to ripping seal construction. Site walkover between WestLink Delivery Manager and Construction Project Manager to identify and agree any isolated treatments required in existing pavement to normalise strength. Min 24hr notice to be given prior to inspection.
label | a2a10c27-0842-59ad-a71e-d5ae32ea9588 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 90b77f02-c11c-5e32-acbd-5bc6ee84254e |  | note | MEASURING DEVICES OR METHOD - Eye, spray paint, mark-up on drawings
label | 5aa71f39-5869-5c79-99e4-d581e0343951 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
label | d6907204-457b-5c33-89ed-e5ac6e5cc66d |  | note | QUALITY DOCUMENTATION - Mark-up on drawings
checkpoint-group |  |  | section | MILLED SURFACE CONSTRUCTION (IN TIE IN AREAS)
checkpoint-status |  |  | checkpoint | Finished Level
label | c7d05350-2d9c-583a-b51b-bcb9e9bb2dec |  | note | SPECIFICATION REFERENCE - TNZ F/1 11.2.2
label | 1dfff371-695c-540e-8599-d2f3adec0a96 |  | note | TEST REQUIRED - String line or equivalent
label | 483bdbe5-5d3d-5427-a265-67810c4529ba |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side, min 3 measurements across lane = 147 Measurements
label | c282f421-66a4-5a79-af9d-324f59aa4d60 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | f336fd92-5fd2-5380-83ae-687903006842 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | 07dfda69-d121-5bff-a407-1cf37d869626 |  | note | ACCEPTANCE CRITERIA - +0mm / -30mm
label | dcc97e56-02e1-5c1a-9984-73455ffe01b3 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Finished Level (post milled)
label | b5f05f1c-41c7-5cfe-817d-e6f6eb46464d |  | note | TEST REQUIRED - Visual inspection of milled surface
label | b48430ec-a87a-57e5-9d7a-5ae7838e34cd |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Site walkover between WestLink Delivery Manager and Construction Project Manager to ensure milled surface acceptability and compliance. Min 24hr notice to be given prior to
label | 62ad0dd2-acd5-5f67-bcf6-6526155ea144 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 622b49e2-ebfd-59b3-ac79-3f9688fd7bdd |  | note | MEASURING DEVICES OR METHOD - Visual inspection
label | 6fdbf04f-4ffd-5f10-a11f-895fb0b51f38 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager
label | 57d8179d-2330-54b7-93a5-884e99ae0dc3 |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied
checkpoint-status |  |  | checkpoint | Compaction
label | 539f172a-31dc-56f2-a16c-347c10bafede |  | note | SPECIFICATION REFERENCE - TNZ F/1 10.5.1
label | b63eab59-25da-531a-b032-8cbabf0e1fe0 |  | note | TEST REQUIRED - Proof Roll
label | 8ed6321b-b7bf-557b-b114-22856504edaa |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 100% coverage
label | 350510da-c2fc-5e94-ba06-5bc4e6fbc8cb |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | ea8456bc-e92e-555b-8a44-b91d8f30e095 |  | note | MEASURING DEVICES OR METHOD - Smooth wheel roller with min loading 6259 kg/m width or large miller
label | 0644346a-3683-59cf-854d-65f47ef7b3de |  | note | ACCEPTANCE CRITERIA - ≤ 5mm
label | dc951cb9-d9b2-56b0-a210-a08e9a878f13 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-group |  |  | section | BASECOURSE LAYER MATERIAL TESTING - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | Crushing Strength
label | ac4fc90b-3bcd-546e-a13b-f1cbce7fa965 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.1
label | c33e589a-a6e5-5d34-8445-5de8bff97130 |  | note | TEST REQUIRED - Crushing Resistance Test
label | 56d3f7cd-7906-5a87-8b06-3d64845e4a3c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 49f17d6f-6c60-5401-b827-d59f218075cf |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | dea6af01-d9d2-5356-a5bb-070c9a882471 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.10
label | 94f1e84d-7162-58c7-973a-e9e576ecefc5 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 130 KN load
label | 60b12ddb-7b60-56a2-bd5c-bae7dd04f43c |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Weathering Quality
label | f0a978c8-5a94-5d52-b59f-992c00e45aba |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.2
label | 0fdb1813-7c75-5e8f-b364-4d3f17ee55ff |  | note | TEST REQUIRED - Weathering Quality Index Test
label | fd34d80c-e988-5828-9f32-eddee862940d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 7758d8c1-9c97-5e5e-83a7-0f2618fa2198 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 20c85e59-2672-5f07-bc72-247a49f9a308 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.11
label | 62633567-c908-5ec5-9d58-4f95b6c3bc74 |  | note | ACCEPTANCE CRITERIA - AA, AB, AC, BA, BB or CA
label | c1c4b976-5acb-567d-92c2-f5d58c5b9f12 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Soaked CBR
label | 11951c51-369c-5790-ab67-b6116cc2e63c |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.3
label | 042646bd-98cb-55d9-a98c-ab91b0986f1f |  | note | TEST REQUIRED - Remoulded soaked CBR
label | 682dece9-3cf5-554d-9f91-495cdb10a10c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 440ca391-8b69-5aab-9d57-7dc9792c746c |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 92e52671-c7b3-599c-bc28-fdd3581b326c |  | note | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
label | 25154a55-ca90-57bc-997e-3344bee57bd4 |  | note | ACCEPTANCE CRITERIA - ≥ 80%
label | ddebf539-eaf5-52d6-a585-929ccdd701b2 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Sand equivalent
label | 64f3d532-091c-5e6e-a862-ea2459c1b284 |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.1.1
label | 703f0ae2-bbb7-5818-98a1-88d88e93b514 |  | note | TEST REQUIRED - Sand equivalent
label | 6344c4f6-a8f0-5122-a283-294af8985fe6 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | a594c5ee-8941-52a3-bb5d-1e9defcb6d0e |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | c711bac0-7249-50f0-bd95-c97bc737ae06 |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | e2586a13-8ade-51a5-adee-f4a054050067 |  | note | ACCEPTANCE CRITERIA - ≥ 40
label | 1536aa81-b1bc-56af-8265-54f4f51bcb3f |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Broken Faces Content
label | 932d703a-c36c-54d8-bf45-07a2b0e36cd0 |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.2
label | 98ae04b4-46a2-524a-bdda-1507c7ba7d94 |  | note | TEST REQUIRED - Broken face content
label | 0ab28b56-ee02-55bd-8757-14d53cf504c1 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | 8e40a7e9-0943-5fe4-9d02-a70c34b4de72 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | f7cc5225-bebe-598d-b0a1-4cbd0b356728 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.14
label | 720a50bd-4e7b-5905-b1cc-39d1535a9e06 |  | note | ACCEPTANCE CRITERIA - ≥ 70%
label | ad786b72-7c22-5fe6-96f0-dd169068c07d |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Particle size distribution
label | 762eac72-c1a5-5f8a-8453-84b79c26cb9f |  | note | SPECIFICATION REFERENCE - Design
label | d2575e43-9e6c-533a-bb18-52a569a70f47 |  | note | TEST REQUIRED - Wet sieving test
label | 15a54006-9f1d-51cc-8d52-f85b6b15089d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | a6edc56f-b7bc-596b-8cbb-1d292515a936 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | f742b385-5204-577d-8af9-75464842f03c |  | note | MEASURING DEVICES OR METHOD - NZS4407 4407 : 1991, Test 3.8.1
label | fcdbd489-6477-576c-a97d-66d72e6aa059 |  | note | ACCEPTANCE CRITERIA - 100% passing 37.5mm
label | 2b897177-8f89-5795-8346-e14836168145 |  | note | 66 - 81% passing 19mm
label | f641ed07-c032-59d1-b1c4-eb6432c63109 |  | note | 43 - 57 passing 9.5mm
label | 17071e45-afd1-5211-b718-416214cb1d98 |  | note | 28 - 43 passing 4.75mm
label | 9e0785c2-f6f5-51d5-9e6c-376a4c5f956c |  | note | 19 - 33 passing 2.36mm
label | 0b76beaf-693f-56a1-93f1-de55f89c4c51 |  | note | 12 - 25 passing 1.18mm
label | 62ea89d0-fdf2-52b4-8ecb-7e0cf3e08de1 |  | note | 7 - 19 passing 600µm
label | b408e269-04a6-52bd-9344-033526b243f6 |  | note | 3 - 14 passing 300µm
label | 9b462066-70b5-5a8e-b0ec-2f814cde5e7a |  | note | 0 - 10 passing 150µm
label | d8bf7931-d1d5-5ea5-9d90-3aa189e89c7b |  | note | 0 - 7 passing 75µm
label | 58e32e6a-c9c5-5fd9-8ed0-3ee584684170 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Solid Density
label | 9d795b62-4ad6-59a5-8f26-e1a7a3345022 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | bdba4bf1-927a-565d-8104-140027fafd00 |  | note | TEST REQUIRED - Solid Density
label | a7dcd788-b8b4-58a3-b16a-1bd43956a54e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 2 tests
label | fd379e74-c959-5c65-ba6b-1f556dc4062d |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d0e55d43-b744-5d97-a269-b98ca77cac95 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.7
label | 027f19f1-2a75-5ce3-850d-e53e39d2768d |  | note | ACCEPTANCE CRITERIA - report value only
label | adc177e8-e4b0-52cc-bf6b-00294b126d3a |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Determination of MDD & OWC
label | e1699f4c-9f61-5132-98b5-226f6719a5c8 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | 63773eb7-91fa-5dcc-a268-b36acc323266 |  | note | TEST REQUIRED - 5 point compaction curve
label | 650638e7-42a4-5aa6-92cc-b871e10b275f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 2 tests
label | 656d0838-df0e-51bf-a591-f5b1e289863c |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 8044eda1-abc4-5bc6-ac6b-ce660fe987e5 |  | note | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.3
label | 97dbe39b-f41c-5b53-b46e-5b1960bd5975 |  | note | ACCEPTANCE CRITERIA - report value only
label | 496b7f42-e627-515a-a82e-8a9072751775 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-group |  |  | section | BASECOURSE LAYER CONSTRUCTION - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | Formation
label | 6126043e-3942-5bd9-a0e9-bd54bb65a430 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.7
label | 37508ccf-7db4-5ab2-a6f8-c53932c4fdb8 |  | note | TEST REQUIRED - 3m straight edge or approved equivalent
label | 590fa8b3-80da-5e9f-b0d4-8a60645fea43 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 50 Tests
label | bb8d44e0-6793-500d-aaa7-f74606c2697d |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 6f64d042-47b3-5832-b5a0-4661007d4712 |  | note | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | 1ea91e10-4827-5f04-a6b2-76a6b790b6e2 |  | note | ACCEPTANCE CRITERIA - +/- 10mm
label | f583471a-1621-5cc4-bce8-8fb2c7e212e4 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Finished Level
label | a972e4fb-5303-5fac-9ab9-d86a3cce749d |  | note | SPECIFICATION REFERENCE - TNZ B/2 5.1
label | 5d240868-b9b7-595a-a294-21f28508b592 |  | note | TEST REQUIRED - String line or equivalent
label | 26a3a68d-c16d-53cd-9cee-7f0d16f00cdb |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 50 Tests
label | 1b506ca3-600c-5bb6-b1aa-60178823797a |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 192f4d9b-ed46-572f-b568-44d6a46b778a |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | dfc81355-d295-56da-976f-5585b978c79b |  | note | ACCEPTANCE CRITERIA - +15mm / -5mm
label | b7bad1de-3268-5cb3-bcb6-a72295aefb6b |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Plateau Density Test
label | 6b3992b7-5d14-5108-bb64-0f9e48430823 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5 (b)
label | bc933da3-c021-5393-a435-8360a4bb3d24 |  | note | TEST REQUIRED - Plateau Density Test
label | c1d0e277-1f60-5c73-8c17-fc114424b75f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test minimum
label | 8af7c6f1-33dc-5d58-bd60-c4ba932ea066 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e19e4a70-3673-5d84-94e0-5bf0beeaccc0 |  | note | MEASURING DEVICES OR METHOD - NDM
label | 14f53432-4bde-5d6f-aea3-baa45196d129 |  | note | ACCEPTANCE CRITERIA - report value only
label | 7ae84537-7170-5e35-afbc-082decceb84c |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Compaction
label | 5ec92c60-44ee-5ea3-8bd5-77e570c9803b |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.6
label | e3d16417-9bdc-5a4c-b313-4d4e3ac898f4 |  | note | TEST REQUIRED - NDM
label | ce584fb4-53f1-5721-a4a9-ae1fc5445015 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 19 tests
label | 2cc7a5eb-1887-50b9-9e71-2fac24abd47f |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e8223f4b-dd73-5118-922d-4aa5bf1d43e2 |  | note | MEASURING DEVICES OR METHOD - NDM
label | efa5dbd7-76c5-5c60-92fa-f17b9aae8cd0 |  | note | ACCEPTANCE CRITERIA - Mean ≥ 98% MDD, Min ≥ 95%, Total voids ≤ 20%
label | e1986627-76b7-5c5d-ac48-a70071bed37e |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Degree of Saturation
label | 7ce1a803-0e33-533b-8423-253461e26f29 |  | note | SPECIFICATION REFERENCE - TNZ B/2 12
label | 898923f9-6cfd-575b-9840-ef5b2d848a09 |  | note | TEST REQUIRED - NDM
label | 80d10fa3-8ed1-5c33-9061-2f8b1570a615 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 19 tests
label | b1035554-5914-54a8-b424-72c05052ed28 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 7ccc9378-917f-53df-9de5-dffd807016ea |  | note | MEASURING DEVICES OR METHOD - NDM
label | c21637ea-bdbd-5716-a43a-1093b113bd2b |  | note | ACCEPTANCE CRITERIA - < 60% (or 80% on consultation with the pavement designer)
label | 68824bea-1f07-509b-9a0c-26e7cd2b0776 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Surface Finish
label | e6152828-950e-5fb8-92c5-20ebac063651 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | 0eaa224c-16da-52a3-b161-2a25e963e852 |  | note | TEST REQUIRED - Visual Inspection
label | dacb4309-2947-58a8-972b-c2b05a3c51f8 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale. Min 24hr notice to be given prior to inspection.
label | d5129daf-6a72-5a55-bdd7-c0737febe806 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 131d6b0f-21d1-5019-ab6c-9b7901a1fecc |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | 066664b5-ab4d-5f4d-8796-911b290d3d0b |  | note | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | 55fcd928-d40a-50ac-8976-df083878a76b |  | note | • The large aggregate is
label | 170f695f-dd47-53d4-95f6-53a56b5bef32 |  | note | • exposed to the surface;
label | 7ac136e4-64aa-5053-9dd7-793901127f8a |  | note | • held in place with a matrix of smaller aggregates
label | 7013f2ba-5b1c-572f-a661-3d4bdad79f45 |  | note | • The smaller aggregate is held firmly in place by fine material;
label | 8a123513-ed41-5685-951b-da10055ff40e |  | note | • The matrix does not displace under normal trafficking or sweeping.
label | 6653a15c-74c1-5084-9c32-9ad121d248a0 |  | note | The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 05f79a90-d993-53d8-ad05-0f3a4386b7fa |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-status |  |  | checkpoint | Ride Quality
label | d5af5b0b-9c23-57c0-94a4-0761a2c448e1 |  | note | SPECIFICATION REFERENCE - Internal measure
label | 226135fb-b6a4-5a7a-8f76-d7bb4ddb9150 |  | note | TEST REQUIRED - Ride quality test to AG:AM/T002
label | 1e1b9af8-7e87-5ed8-b301-7f97ec075d87 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Within 12 months of first coat seal
label | e753e5b3-8d41-5e2f-84be-c212b0a73695 |  | note | TASK ASSIGNED TO - Either by pavement subcontractor or by Westlink Asset Management team from latest HSD survey
label | 36d881c9-b31e-5810-bcec-cfd2be41eb25 |  | note | MEASURING DEVICES OR METHOD - inertial laser profiler or response-type roughness meter
label | 90f2be8e-5b0f-529a-bb62-c12a3245d055 |  | note | ACCEPTANCE CRITERIA - no 100m moving average > 60 counts
label | f03435e3-47f5-5c85-ac7d-04249dec9750 |  | note | QUALITY DOCUMENTATION - Certified test report
checkpoint-group |  |  | section | BITUMEN - TO GAIN APPROVAL
checkpoint-status |  |  | checkpoint | Penetration
label | 2904c1d6-c679-5c7a-b258-8fbd93c22ad8 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 03642d06-2f5c-5486-8269-316eadff7544 |  | note | TEST REQUIRED - Penetration at 25°C, 100g, five seconds
label | 0e5710c3-245f-5088-abee-c7e0b1068c7d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 9111e84e-7961-55c5-ba74-46c88574bcd0 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e2f45cc8-8097-5462-9d62-d40fbbe1765d |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | 1b54725a-7674-553a-a75e-4a44363b2f3c |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Viscosity
label | d7dad656-303f-5b22-9a4f-6e25e3f1d1f6 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | b303d6eb-751d-5b5a-869a-eeeb5f4e6c91 |  | note | TEST REQUIRED - Viscosity PaS at 60°C
label | c59f6013-f6e5-5c8b-a3ba-9b6ac5c41efc |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 9bbf56d0-cc5d-5cee-b1de-c4529cc1a9a6 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | ed969439-28dd-51a1-8d81-88eab948e036 |  | note | MEASURING DEVICES OR METHOD - AS 2341.2 or ASM D2171
label | ebfbd455-5e43-5ea2-8a92-3940e143f772 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Viscosity.
label | 2b26b5e5-b699-538e-bb6c-ae2d289c0002 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 5ada89f5-2606-5cf0-88b7-2dd0c69ae54c |  | note | TEST REQUIRED - Viscosity mm2/s at 135°C
label | c87b7e88-7db4-5c3c-bc17-9ed3e4fbeb48 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | bda28e83-019e-5b7b-bb2e-17817ad3792f |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 71745c7e-d413-563d-aeb6-d69582c2f077 |  | note | MEASURING DEVICES OR METHOD - AS 2341.3 or ASM D2170
label | 6a18714b-d32c-56a7-a4f6-20764e937b29 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Flash Point
label | e8c5f3de-3170-555c-b76c-563c94dd39a2 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 0af6343e-f872-5e94-96f3-a189fc50f305 |  | note | TEST REQUIRED - Flash point (Cleveland open cup), °C
label | ff2f2e67-ec59-5ef5-b393-23fc716c60fd |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | e5c7a5f7-ea8a-5142-9085-3ea033975187 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 3551d639-5262-5369-aeaf-8b50b5f0fc24 |  | note | MEASURING DEVICES OR METHOD - ASTM D92
label | 733f66cf-0f99-5b11-8eb1-cdb10b6abcaa |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Solubility
label | b357c149-dcdd-58fd-a574-55d8daba4eec |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 1550b4fd-034b-546b-afc4-726e686ea3f1 |  | note | TEST REQUIRED - Solubility in Trichloroethylene, % or Solubility in Toluene, %
label | a5d05921-7230-5e2b-a003-9bd1ee6fc373 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | acd3fb3e-dfe9-5c4f-a320-19d67049bc83 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 92a73ee3-6762-53df-bece-bcc912138e18 |  | note | MEASURING DEVICES OR METHOD - ASTM D2042, AS 2341.8
label | c7344c78-44e8-5ad0-8f98-0edb4bc7e199 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | 99b621f2-57ca-5fae-bb6b-d2de00a5fb36 |  | note | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | Rolling Thin Film
label | 4794f850-7773-516d-96e7-a94dc6afb87e |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | f117b077-72d7-5408-a73b-5a1d1f6ab9f7 |  | note | TEST REQUIRED - Rolling Thin Film Oven Test
label | 2c30c7ca-a6c8-567b-9eaa-47273faf9202 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 9c93f6bf-e2fa-570b-b2b0-746dcb7f8b9b |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e2fe3264-3aa1-5499-a8a8-3c3a76e0fd8e |  | note | MEASURING DEVICES OR METHOD - ASTM D2872 or AS 2341.10
label | f9892379-b497-5ce1-8b5a-b533a874a5eb |  | note | ACCEPTANCE CRITERIA -
checkpoint-status |  |  | checkpoint | Penetration
label | 86b2f88d-8a3f-569a-88f8-5d4cc4f0bd54 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | f5d9a329-b468-57d2-8792-7dbd9b5d767b |  | note | TEST REQUIRED - Penetration of residue, at 25°C, 100g, five seconds, % of original
label | 8a56bdb3-371d-5b04-a022-5cabaf83f776 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 4092d47c-2de8-5aaa-85d6-e21c4d20dccd |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 7a13d8a7-fc75-5278-8296-0a6faea26ce1 |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | 5cd0fa17-6e7a-52a9-8b85-16dbb0fe1775 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Ductility
label | 2593abf8-f5e4-5aaf-b887-f1360aac508d |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 876bb1e9-07a7-58f7-8d20-1b3c3716663e |  | note | TEST REQUIRED - Ductility of residue, at 25°C, (metres)
label | d5242646-ba7e-5be2-a866-fa43a353647a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 37827ad3-44e1-50b0-94cc-ab6ef9b1a8f4 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | c537b4d1-4068-51dc-a3cf-42b07600bcc4 |  | note | MEASURING DEVICES OR METHOD - ASTM D113
label | 873a4426-3fc0-50ef-8d0d-140336b232ab |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-group |  |  | section | SEALING CHIP MATERIAL TESTING
checkpoint-status |  |  | checkpoint | Crushing Strength
label | d7d30248-4e0c-5280-ba61-59a4719bc157 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.2
label | dfd0c8b1-9ced-583c-bf4b-5b19e735075f |  | note | TEST REQUIRED - Crushing Resistance Test
label | dbd2d253-e32f-54bd-8293-0e317cd420d1 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality
label | 84bd4793-4879-5e24-8e6d-33e44686c6eb |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d88ae974-28d5-5620-b584-79fd5bec796f |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.10
label | fbab4ebd-5e17-5fde-88c8-34edda29c180 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 230 KN load
label | ae2277fc-7abd-53ed-9717-c8313b746edc |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Weak Particles Test
label | b0a070c1-9c42-5638-98a5-c037e3227a04 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.4
label | 0e6b52c2-fb62-5f4f-8629-b22b19f14ea1 |  | note | TEST REQUIRED - Australian Weak Particles Test
label | 9f4c57a5-74d4-5573-bbb0-b7f7b9ba9478 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Only undertaken in cases of dispute
label | 452de40c-84ba-5940-80d0-aeced78d8e12 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 11676fae-e7ad-5adf-9003-dfecf7ef2397 |  | note | MEASURING DEVICES OR METHOD - AS 1141.32-1995
label | 525e2344-abf1-56ce-902a-53ed4ae8d250 |  | note | ACCEPTANCE CRITERIA - Maximum of 1%
label | 8ebebd2a-474e-5eba-a202-070afb73212e |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Polished Stone Value
label | b77abb37-5bac-5442-9d20-ad28661ed927 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.5
label | 11c1644c-d6a4-5d4e-8b85-c1103679d365 |  | note | TEST REQUIRED - Polished Stone Value Test
label | 1c81ebef-11cf-5d71-ad45-383d5eab5568 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality
label | b77d4bb4-2726-58a6-b560-1251bd174ffd |  | note | TASK ASSIGNED TO - Accredited PSV Testing Agency
label | 2059b998-22dd-5676-8aff-e9c5a5eb13fc |  | note | MEASURING DEVICES OR METHOD - BS 812: Part 114
label | 81d94a09-6fe5-58b5-8be0-38e083b7a403 |  | note | ACCEPTANCE CRITERIA - PSV Required = 43
label | e437747b-69f0-5065-8f15-f6126ec510ba |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Cleanliness
label | 6b1d82af-d7c5-522a-aa20-74144f1c2455 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.1
label | 57df5cd4-5e20-5fcb-aa36-9a8fdbcf061b |  | note | TEST REQUIRED - Cleanliness Test
label | 332ebff3-0536-51ea-99cf-525acab64867 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | c9c25501-35b2-56f0-b7f1-5aa1cd6c7114 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 08ecabf3-e9d7-5c09-82be-87af49b5e09e |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | 42d1bbc2-3020-5584-819f-06d5a4e5800d |  | note | ACCEPTANCE CRITERIA - Grade 2 - 89 min Grade 3 - 87 min Grade 4 - 85 min
label | 60ed73b9-0e51-5fe7-9a73-d9a05057d80f |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Size & Shape
label | c07ef974-0196-5119-a84d-7ef291c00885 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | 3b1e1e49-b1b6-52c1-8fe5-c28560732e30 |  | note | TEST REQUIRED - Size & Shape
label | e5e14bad-2b88-5c68-9159-2eef470590aa |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 146e4f75-e9e0-59a8-8817-3651cffe88f8 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | fe695622-307d-5aca-9ae2-50039506ed58 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.13
label | 91d54bfd-c669-538d-be13-da9228e0a8c0 |  | note | ACCEPTANCE CRITERIA - Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD 1.1% passing 4.75mm
label | c8db856b-f895-5998-a7f5-5e7e2c4f35d3 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Broken Faces
label | 6d45f5db-3b8e-5456-886a-01c9299f62df |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | 371f8d7e-bca3-505d-9e2f-a5d09ba3bc66 |  | note | TEST REQUIRED - Broken Faces Test
label | af7562bb-d33e-53da-9605-570a039d3806 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 8db321f1-c82d-5c0a-86a3-f3af771c71e9 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 85324e91-c365-5b96-b074-99bb0feb126c |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.14
label | 2696cc55-eda9-5af3-a076-f472b2bf3c2c |  | note | ACCEPTANCE CRITERIA - 98% with minimum two broken faces
label | 11f5aa8a-1236-5feb-9f70-58bf1bc0eee8 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Grading
label | 99c19c94-980f-52a5-85b3-00f04d4f8023 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.2.2
label | 93bc5148-dd30-5729-bf1c-8ae84b97543a |  | note | TEST REQUIRED - Grading
label | eaa6d98a-648d-5ec0-913c-7ae04f984e63 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | fb68a9dd-a264-5e96-9102-72a645721954 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 2dbecd3a-292e-5eca-953d-98718e5c2caf |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.8
label | cda36424-7d31-504a-b61f-06dfbac0b699 |  | note | ACCEPTANCE CRITERIA - Grade 5
label | d26d34b8-ed18-5ee2-a343-cc0f6214f809 |  | note | 100% passing 13.2mm
label | e17111ea-2ca2-5d15-b32f-c7d30e38452c |  | note | 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300µm
label | cb810116-680e-586b-9d95-0dc21a6ee75d |  | note | Grade 6
label | 11eb390b-e9f1-5221-8c31-86049238db43 |  | note | 100% passing 9.5mm
label | c8f8665b-000f-5bd0-8140-cd3594b1c8da |  | note | 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300µm
label | 006fd3b3-57e0-52f4-8fc2-c9978d41cfc3 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | SEAL DESIGN
checkpoint-status |  |  | checkpoint | Seal design
label | 032f342f-5b22-509a-98bd-b17a8a8e26ee |  | note | SPECIFICATION REFERENCE - TNZ P/3
label | bc727b3e-9d56-5ec4-b72a-a7af4b443ea5 |  | note | TEST REQUIRED - Seal design
label | 7da50c7c-861d-5934-87d9-5c2905e1ac53 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | 47b039c4-3754-52c1-abf6-cbd4eabd656b |  | note | TASK ASSIGNED TO - Contractor's Quality Manager
label | 7c93c7d5-17c4-5ce7-be13-7e830949748c |  | note | MEASURING DEVICES OR METHOD - report only
label | dc9a0da8-ba70-59b4-ae51-573527133bf8 |  | note | ACCEPTANCE CRITERIA - report only
label | cad33099-aba2-564d-a3e7-5cb01bc40f6a |  | note | QUALITY DOCUMENTATION - Seal design
checkpoint-status |  |  | checkpoint | Seal design approval
label | fbc38492-83a8-509d-a2c5-43641379d8d5 |  | note | SPECIFICATION REFERENCE - Internal measure
label | 042621ba-6d0b-5c91-b9c2-00cf396650c8 |  | note | TEST REQUIRED - Internal verification
label | 03ee2539-a5c5-53fc-ad26-6f0ed2124f0f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | 45b331a8-fb01-54d4-a902-267cc6c723f8 |  | note | TASK ASSIGNED TO - Downer Surfacing Expert
label | edd86e46-ad7e-525f-a7f6-ea1c27694929 |  | note | MEASURING DEVICES OR METHOD - report only
label | 66f4fd6f-80f9-50d0-ac3d-bd737455495c |  | note | ACCEPTANCE CRITERIA - report only
label | c496ea64-bb18-5564-add3-38c4841ae24c |  | note | QUALITY DOCUMENTATION - Email from Downer surfacing expert confirming that the treatment selection and seal design has been reviewed to confirm it is fit for purpose
checkpoint-status |  |  | checkpoint | Surface Finish
label | fe3f0f6f-7cdf-519a-a1c7-fca09b17b715 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | 9a0dacf6-e874-5ecd-9b1c-004caf56531b |  | note | TEST REQUIRED - Visual Inspection
label | c577782a-a63c-5c60-a032-f19280868db0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | 2a63f237-188e-5b55-aa2c-dd557f8021fe |  | note | TASK ASSIGNED TO - Sealing subcontractor quality representative
label | acf08b77-238e-5ed1-bc87-caa17a799c8e |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | 9fad67b6-d6bc-5700-982d-d9711e7a24d9 |  | note | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | c6162adc-0fb0-593e-a151-a9458eae12db |  | note | • The large aggregate is
label | 62439b68-9b0b-5a3b-9739-d8acc8d1c338 |  | note | • exposed to the surface;
label | f38470a8-1fac-53e2-8def-b232ad110d3d |  | note | • held in place with a matrix of smaller aggregates
label | 3f357835-81d8-530e-937c-bc14713b8deb |  | note | • The smaller aggregate is held firmly in place by fine material;
label | 395a8925-9019-51d3-aff6-1674628b6c33 |  | note | • The matrix does not displace under normal trafficking or sweeping.
label | 28b66855-4c43-5549-beb2-fcc7b10e9a9f |  | note | The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 76679acc-1f5d-5806-b954-2b4a12dab2de |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-group |  |  | section | SEALING RECORDS
checkpoint-status |  |  | checkpoint | Blend sheet
label | 48313a62-eaab-52c4-afec-092c0d8ec2fc |  | note | SPECIFICATION REFERENCE - Client request
label | 57b8ec36-4edf-506a-90e4-5080f8b85a07 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | 906c21ee-9ddc-5247-b93f-1f466f103256 |  | note | TASK ASSIGNED TO - Bitumen blending facility
label | b851e5f5-58ae-5313-96ca-f43511b3ecf2 |  | note | ACCEPTANCE CRITERIA - Report value only
label | 5c30e215-fea6-53b3-8e2b-c48eb0ac630a |  | note | QUALITY DOCUMENTATION - Blend sheet
checkpoint-status |  |  | checkpoint | Spray sheets
label | c0501df1-8bde-5b47-afaf-f1b14f4452f1 |  | note | SPECIFICATION REFERENCE - Client request
label | 2322e5a5-6f5e-51cf-9ae1-f1a8e5116623 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | 6a662bba-5732-5fab-9c26-1e804f96c629 |  | note | TASK ASSIGNED TO - Sealing Manager
label | 101e8d34-1dd6-5a41-8d17-911f956c0e09 |  | note | ACCEPTANCE CRITERIA - Report value only
label | 339fe251-a259-526b-aa7f-caa79168a579 |  | note | QUALITY DOCUMENTATION - Spray sheets
checklist-sectioned |  |  | checklist | ITP - McPhail Rd RP 0.00 -1.57 |  |  |  |  | Yes | ITP - McPhail Rd RP 0.00 -1.57 | 811c0acf-cb5d-4ddb-b97b-d57960da7012
checkpoint-group |  |  | section | PRECONSTRUCTION HOLD POINTS
checkpoint-status |  |  | checkpoint | Agree QA Requirements
label | ef3b11ab-7f08-5fae-a753-500f433ca6a1 |  | note | SPECIFICATION REFERENCE - ITP
label | 46c04bea-7638-5ae6-a8e9-f8be5ba40a32 |  | note | TEST REQUIRED - Check pricing and ITPs & notify Westlink of any difference in understanding of tender pricing
label | 787ae964-0fd3-54ae-8e55-e7c79a8f3236 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Review ITP and confirm minimum quality requirements are understood prior to construction handover meeting.
label | 2a6618be-1a63-5ef6-96d7-056aed00c71f |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 10b1835c-b126-57d3-9dcc-f575f5d40bde |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Confirm Pricing for Additional Items
label | 63a15989-8e9c-58a1-90e2-5d4b188e57a6 |  | note | SPECIFICATION REFERENCE - NTP
label | bbeea194-b458-593e-8327-0518da4b11e8 |  | note | TEST REQUIRED - Pricing for additional items to be submitted to Design Project Manager and approved
label | 942763a0-4c02-5770-afd3-914fe90725c9 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to construction handover meeting.
label | 90773ec9-7707-59b4-b91d-1bcf7c244b19 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 4ac8f1d8-d6f8-5ae0-b51a-9da8cd8a0fe9 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Construction Handover Meeting
label | 2d638cf3-d4c6-5a2f-9d7b-0090ab1b8b14 |  | note | SPECIFICATION REFERENCE - NTP
label | cebd68d0-569e-598a-960f-2e855841cd2c |  | note | TEST REQUIRED - Meeting
label | f30ec8a9-a6b4-5756-b7a5-e679e28a50cc |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 2 weeks prior to commencement of physical works.
label | f0f68dac-5662-5fb5-9435-108f58e298e5 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 94a4d078-7d32-59e8-b98f-94d2f6170619 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Physical works Programme
label | d66c73fe-8812-5fde-a3eb-b9fe1fe59de5 |  | note | SPECIFICATION REFERENCE - NTP
label | a2f370dc-a861-543d-b2fe-cbf18696fee0 |  | note | TEST REQUIRED - Physical works Programme to be uploaded to WestLink Sharepoint site, emailed to Bryan Crean and start and end dates to by updated in RAMM Contractor prior to physical works.
label | 2d59fe07-6ba3-58b6-b52a-c85a867319f0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 10 working days prior to commencement of physical works.
label | 6231d287-83e9-5363-b846-fe0504e05d4d |  | note | TASK ASSIGNED TO - Construction Project Manager
label | efda6f05-034f-5450-bf22-e76ab5bdee22 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Quantity Review
label | 0daef9e0-dc88-5bdb-bdc0-78a9d6242541 |  | note | SPECIFICATION REFERENCE - NTP
label | da2e4ebe-8f5e-57f2-9f7e-1ac699e5f438 |  | note | TEST REQUIRED - Confirm construction set-out and drawings align with quantities provided in schedule of quantities
label | 43e9fa52-b6ef-52be-a91e-af811d5551ed |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - After construction set-out, prior to commencement of physical works.
label | 7418afab-4352-55d0-9782-06ae3fac59b2 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 7843f8ff-7eb3-58ac-b08c-5de0c4892961 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Existing Pavement Walkover
label | f83e1f00-27f3-5934-9d12-d4fa62689fd4 |  | note | SPECIFICATION REFERENCE - NTP
label | 5b238066-b1ce-5790-aa84-b4f0c3af00ac |  | note | TEST REQUIRED - Visual Inspection of existing pavement
label | 33012ae1-29f8-558a-9d11-177924065170 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to ripping seal construction. Site walkover between WestLink Delivery Manager and Construction Project Manager to identify and agree any isolated treatments required in existing pavement to normalise strength.
label | 5c10f4b3-a900-5099-b201-525cab5efa74 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | faab6b16-e519-5708-b23a-4d9f9fb65108 |  | note | MEASURING DEVICES OR METHOD - Eye, spray paint, mark-up on drawings
label | 204e6ce5-ec13-5427-a9b8-cab22a5fbdaf |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
label | 418cdd1c-bac3-5da9-aa9d-3181667102cf |  | note | QUALITY DOCUMENTATION - Mark-up on drawings
checkpoint-group |  |  | section | MILLED SURFACE CONSTRUCTION
checkpoint-status |  |  | checkpoint | Finished Level
label | c69f657d-f0eb-5b56-8b2c-da8b61e520e8 |  | note | SPECIFICATION REFERENCE - TNZ F/1 11.2.2
label | 22458bcf-254b-5a06-9213-e6996960d32e |  | note | TEST REQUIRED - String line or equivalent
label | ae9d2e92-4254-5a7f-a572-8747c16f49b3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side, min 3 measurements across lane = 16 Measurements
label | 28e8c64b-576b-5f38-b40d-adce8b98c9c0 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 1cbaea50-baa2-554b-bfd5-404738003792 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | 41fdc3ad-43de-5436-a328-e4b12c74b7f9 |  | note | ACCEPTANCE CRITERIA - +0mm / -30mm
label | a9dcd5f9-bfa6-5485-aead-099f86cd51b2 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Finished Level (post milled)
label | f6813b29-b930-5c4e-8204-a414b2faf28b |  | note | TEST REQUIRED - Visual inspection of milled surface
label | 69dc3907-77a5-54d9-847b-65ad05cfea2d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Site walkover between WestLink Delivery Manager and Construction Project Manager to ensure milled surface acceptability and compliance. Min 24hr notice to be given prior to
label | 7fdcfb90-136a-5dbd-8856-35c71c57e29e |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 74bbe22a-a9f7-5956-9665-8f239b2b1ace |  | note | MEASURING DEVICES OR METHOD - Visual inspection
label | 121e759a-0797-5483-9fe8-86c4878c7590 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager
label | 90e6a82a-052b-5c84-8d00-090fad64cbf8 |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied
checkpoint-status |  |  | checkpoint | Compaction
label | 69ab8459-5466-5752-964c-9a6092d08dcc |  | note | SPECIFICATION REFERENCE - TNZ F/1 10.5.1
label | 869dda63-f1db-5cb6-9018-9ecf0c10c357 |  | note | TEST REQUIRED - Proof Roll
label | 94949452-df5c-5723-bd38-dd4df83d68db |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 100% coverage
label | e4263e82-86f6-568d-89d2-44b2f8134425 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 3390ffa6-2c92-593f-a38e-785effc0ff7b |  | note | MEASURING DEVICES OR METHOD - Smooth wheel roller with min loading 6259 kg/m width or large miller
label | 3306be23-8fc7-531e-89fd-ae55c695879a |  | note | ACCEPTANCE CRITERIA - ≤ 5mm
label | 30f802b6-334b-52c2-9f29-7c8a324d49c8 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-group |  |  | section | BASECOURSE LAYER MATERIAL TESTING - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | Crushing Strength
label | 76716e7e-10e1-50fa-91bb-c78817b50f1d |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.1
label | 65936193-d613-5ba8-8e8e-4a8cf19b56f9 |  | note | TEST REQUIRED - Crushing Resistance Test
label | b6dea933-1f48-59b0-bc39-36c973b26e9a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 5e6fb305-fa81-53f5-bff2-7b8fde9fbfb1 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 2aaa6af9-6378-540a-b3cc-7c14cc5d4d8c |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.10
label | 4114113c-3129-5df7-9f9c-8af12d9fea23 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 130 KN load
label | 1ea645ef-26cb-5b94-a6d7-899f229b6239 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Weathering Quality
label | cad32d79-0bb7-558b-b0e2-577be8e8b446 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.2
label | 8aa4fd5f-8d5c-5506-952b-aec07812bf2c |  | note | TEST REQUIRED - Weathering Quality Index Test
label | 9596f174-f1e0-5a88-a1cd-b7d81004b763 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | b098bb50-8a9b-554e-96e6-fefbc708b62c |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 68b1e0e6-5a1a-55bd-9dd3-7679b90dd318 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.11
label | 1b133149-c7de-5c19-bb48-38e4cd158c61 |  | note | ACCEPTANCE CRITERIA - AA, AB, AC, BA, BB or CA
label | 945db9c5-90a7-5416-8edf-b838b2625506 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Soaked CBR
label | fc506e37-49e0-5937-8372-559986dd6676 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.3
label | 71e60993-9090-5c69-b483-e7ec7a5e2118 |  | note | TEST REQUIRED - Remoulded soaked CBR
label | 46ff793c-43c4-5923-8e7d-b9da7f9416fd |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | c1f61630-7a73-51c6-82ca-7556c3c5f070 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 147e5e3b-8106-533a-bf2f-5519adc9ec87 |  | note | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
label | f59fa7d9-556b-5f53-84e4-9b05e45f09a9 |  | note | ACCEPTANCE CRITERIA - ≥ 80%
label | 0157fc8d-d42c-540e-a9e1-635c1083c378 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Sand equivalent
label | 0a09b38e-55c9-5de0-99cd-19e848e6299c |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.1.1
label | ea425fcc-a3b3-5333-b656-9ff98abbb312 |  | note | TEST REQUIRED - Sand equivalent
label | d7f734af-b1af-5b46-8902-f778c07a98ce |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | 32fd9028-612f-5ca2-91db-2f10b00d8905 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 4d0e0dcc-f7a5-598e-a30b-88ae134d80e1 |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | 05a99bc9-ccb0-51cf-83b0-8037c1b46b7d |  | note | ACCEPTANCE CRITERIA - ≥ 40
label | 9aafe0b8-a8be-565c-9687-2b6e66058049 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Broken Faces Content
label | b32c94c3-672a-5683-8cd7-062551751efa |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.2
label | 64633d0f-99e7-5197-9365-982eb2f85d63 |  | note | TEST REQUIRED - Broken face content
label | 4869b1d9-2f9d-5e80-a477-dcda90af9db7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | b984a440-f4b2-50a6-8e2e-9ce178e00200 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 64d8ef2e-c738-57e4-bdc1-ac2b62da7410 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.14
label | 4fd22cb2-c732-5935-8240-f1658b21b336 |  | note | ACCEPTANCE CRITERIA - ≥ 70%
label | 9e0342c8-9e70-5db4-84c4-d2c67e4848fe |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Particle size distribution
label | d39a404a-2327-5864-84c4-1a38a1492304 |  | note | SPECIFICATION REFERENCE - Design
label | 96fe1f22-6e34-5f35-af5a-2b05928b2b72 |  | note | TEST REQUIRED - Wet sieving test
label | 36f3dd00-9c01-5557-ac7c-193fdc1a0880 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | d74627c7-344e-5f6d-bddb-7a0473b81542 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 79fff6db-c3ba-58ce-a3e7-a88c95ca0300 |  | note | MEASURING DEVICES OR METHOD - NZS4407 4407 : 1991, Test 3.8.1
label | 7dde348f-4e82-53c5-88fe-1d356d4c4c49 |  | note | ACCEPTANCE CRITERIA - 100% passing 37.5mm
label | c769d633-dc1b-5df8-affa-1f46e9133af8 |  | note | 66 - 81% passing 19mm
label | 928172b9-c328-5d41-9326-736252d53695 |  | note | 43 - 57 passing 9.5mm
label | 2f3655e7-1ec3-5822-b5fa-388539d5c9e4 |  | note | 28 - 43 passing 4.75mm
label | ed321cd2-02b1-5b55-ac8f-3107f22d5c71 |  | note | 19 - 33 passing 2.36mm
label | c28c695c-6da8-5d7f-83f7-7107b34b8424 |  | note | 12 - 25 passing 1.18mm
label | f7576868-2ef9-550b-bc43-8ab6090acf1e |  | note | 7 - 19 passing 600µm
label | 5476fcfa-a312-5622-b086-b859d4e658a7 |  | note | 3 - 14 passing 300µm
label | 4a4e0962-84bf-5888-9662-61653d5cafc8 |  | note | 0 - 10 passing 150µm
label | 83d13b96-383f-5983-9343-4c09aca50ae4 |  | note | 0 - 7 passing 75µm
label | ee0fa43f-93ef-5fd5-a2e0-a21deed2ff7e |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Solid Density
label | 6f97052f-d5c0-50b4-ba29-5209b3c3f29c |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | 684ec51a-24a3-5533-8262-fd75a2df264b |  | note | TEST REQUIRED - Solid Density
label | 43c14d00-414f-5a53-84e8-fe54d727b7a3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | ce5daa1c-7051-5038-ab75-5b98a1b3be01 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 11f72d28-ce5d-5a37-9425-491c780be11b |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.7
label | 506b3184-fd56-53a6-b7b6-ebcbae6f2c0a |  | note | ACCEPTANCE CRITERIA - report value only
label | b0f8d7de-06c4-577d-96c9-1991c7f7f124 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Determination of MDD & OWC
label | e3476580-044f-5cc8-8590-a60e90268ab8 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | 30340778-7864-5b6b-a366-7543cd637aa0 |  | note | TEST REQUIRED - 5 point compaction curve
label | 1192872e-dc64-54f7-9f69-d3b2bee5b2a7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | 471dcb4c-9c4d-5412-a728-313c55810ec7 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 8f96e45c-789f-5a7b-8d35-91140c50e395 |  | note | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.3
label | 2b594562-4f5f-5b5b-9449-8a1114feca88 |  | note | ACCEPTANCE CRITERIA - report value only
label | 07716531-67df-5d33-82ea-e196c962723b |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-group |  |  | section | BASECOURSE LAYER CONSTRUCTION - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | Formation
label | 1bed0737-6c76-54ec-9cfe-eaeac2824284 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.7
label | d196f301-623d-5122-bc49-117942fc6ded |  | note | TEST REQUIRED - 3m straight edge or approved equivalent
label | 3a283aff-4c37-5ed2-b8df-be5a915b2104 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 16 Tests
label | 154ae0c3-cadc-5390-995a-678945a9446d |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 06de8f83-c74f-520d-a95d-46ab8011aed8 |  | note | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | 8360ecb9-6960-5272-bfab-723023f1d20c |  | note | ACCEPTANCE CRITERIA - +/- 10mm
label | 8dbca8e0-4ce7-5d54-ba06-acd9a3576791 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Finished Level
label | e9672bd8-f77e-58eb-9098-4f2c058f562e |  | note | SPECIFICATION REFERENCE - TNZ B/2 5.1
label | 2682435c-ff60-5aa6-b840-89d7ade1b027 |  | note | TEST REQUIRED - String line or equivalent
label | 8c5e2bf4-8bc0-5fe6-8851-6bdb57eed755 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 16 Tests
label | 218c0fb5-d327-5f10-b9d5-e972aa1ade64 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 074331f2-f524-53b2-877e-8e983361f4a1 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | 61197051-f51d-58d1-8233-580d35d158d8 |  | note | ACCEPTANCE CRITERIA - +15mm / -5mm
label | 0c81bdf9-49c0-5921-b505-31bcb7453785 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Plateau Density Test
label | 2558ec9f-70fc-5719-9470-a93ee3629877 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5 (b)
label | 0cccabf8-6964-515f-af13-b13a4268e7bc |  | note | TEST REQUIRED - Plateau Density Test
label | 7faf4f3f-bbee-5213-a4b4-a1220db26e9d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test minimum
label | 0c3f17ee-f98c-5b6e-b2bf-9ca4f711b682 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 1147fbb8-6bc6-54ca-9b3f-f242cb959ce9 |  | note | MEASURING DEVICES OR METHOD - NDM
label | ac11c302-5d02-59e6-b6f3-d38fc6b193c5 |  | note | ACCEPTANCE CRITERIA - report value only
label | 00d07808-59e1-5b4f-92ae-0707d87d30aa |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Compaction
label | 8a5cff5b-50c8-529c-a14d-8b6f33b50408 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.6
label | 07920f2a-3847-54ae-bec3-0dd05caaabf7 |  | note | TEST REQUIRED - NDM
label | 07f2152f-3f95-555e-915c-78f8500b9d37 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 16 tests (Every 20m, alternating wheelpath)
label | 9aa1516d-2cc7-582f-aaee-38411603ceca |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 2886b2a9-65c1-5d8f-a33e-428bffa1fdbc |  | note | MEASURING DEVICES OR METHOD - NDM
label | c13363d2-1095-568e-ac7e-0a60a575ada4 |  | note | ACCEPTANCE CRITERIA - Mean ≥ 98% MDD, Min ≥ 95%, Total voids ≤ 20%
label | 46b14b8f-18c7-582a-b754-18c8fd443383 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Degree of Saturation
label | 2d2b91f5-56ca-5358-8d29-adc47c7e081a |  | note | SPECIFICATION REFERENCE - TNZ B/2 12
label | ab3f65e7-395f-5915-b6d4-4518758dba25 |  | note | TEST REQUIRED - NDM
label | e1f1ed4e-1c95-57e3-9503-1efca7bfb27f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 16 tests (Every 20m, alternating wheelpath)
label | 39a97a11-9018-55db-89cb-450f44f8a436 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 5c8ec55f-8546-53ea-be65-5934eb95214c |  | note | MEASURING DEVICES OR METHOD - NDM
label | bdf2daa8-746d-594d-a4fa-6bdf75090732 |  | note | ACCEPTANCE CRITERIA - < 60% (or 80% on consultation with the pavement designer)
label | 76b1457d-4b41-5450-9ff8-5847c0dc79a8 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Surface Finish
label | 8fc17b58-b938-59fd-b8b7-da22e5fbc746 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | 82100fd1-1feb-5968-a17a-df09def3a858 |  | note | TEST REQUIRED - Visual Inspection
label | 7916a6df-59a8-50f2-9e12-76f79c85177d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 20m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | 748a310f-01fa-551f-bf36-84306c5b49e3 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 71a447f5-de34-5a76-a28b-52727d1d4f77 |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | 8d9b6c61-1dfa-5e11-ac0c-523bc6463962 |  | note | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | 5f9043c0-1e12-50ac-adb1-e6bbb0a23a5e |  | note | • The large aggregate is
label | db492d80-7bec-5c35-b755-9c038de3ee79 |  | note | • exposed to the surface;
label | 88f93815-335a-59f6-a035-09932045f855 |  | note | • held in place with a matrix of smaller aggregates
label | cd2ae2d1-e9e8-51ec-9a28-a4a73aacbc95 |  | note | • The smaller aggregate is held firmly in place by fine material;
label | 0eb239cc-3991-5c2a-b645-40d3b35c0f43 |  | note | • The matrix does not displace under normal trafficking or sweeping.
label | fc9b2b80-e8af-5477-b6b9-f3e9817c9cc0 |  | note | The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 9bd284eb-ef9f-5503-a78a-31515b8844b7 |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-status |  |  | checkpoint | Ride Quality
label | af2ff1ee-024f-502e-9db4-f168f933b243 |  | note | SPECIFICATION REFERENCE - Internal measure
label | b99cb621-ba49-5a17-a4db-7034e0deb578 |  | note | TEST REQUIRED - Ride quality test to AG:AM/T002
label | 82a47ea4-6277-5501-a8cd-a5db0e9b45ed |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Within 12 months of first coat seal
label | df56f4bb-4a35-5467-b11b-21e652a46150 |  | note | TASK ASSIGNED TO - Either by pavement subcontractor or by Westlink Asset Management team from latest HSD survey
label | c717f04e-9a42-54ae-9ee4-f411f5c15956 |  | note | MEASURING DEVICES OR METHOD - inertial laser profiler or response-type roughness meter
label | 2c77df1d-f361-521f-9c75-7da40fefcdfc |  | note | ACCEPTANCE CRITERIA - no 100m moving average > 60 counts
label | 106168d3-b181-57a0-8fd1-b36127dabfdc |  | note | QUALITY DOCUMENTATION - Certified test report
checkpoint-group |  |  | section | BITUMEN - TO GAIN APPROVAL
checkpoint-status |  |  | checkpoint | Penetration
label | 9f356bc7-676c-5190-8f26-5b294b996f5e |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 52c7614f-ff4c-54b1-9ac9-b8e19303ab77 |  | note | TEST REQUIRED - Penetration at 25°C, 100g, five seconds
label | 40969ac1-64a7-5a1a-80b9-9ade7f65e9e1 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | d850a77f-c40b-5fcc-a1d1-cf06ed0fd21b |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 5942d06b-cd95-5d00-8966-60ae14e95664 |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | e1865cf7-8d47-5d48-90a0-b7db4fd14c89 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | 86ecbb29-1c37-5fa0-9132-57692a48cd7a |  | note | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | Viscosity
label | cf094ab1-04e2-553f-8832-58e7155387af |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 9dac4f50-0a60-59d9-a99b-b18b6e215aeb |  | note | TEST REQUIRED - Viscosity PaS at 60°C
label | 6e67ca87-0ba1-5798-9719-ede52a7cf2c4 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | bad7c0ed-da27-5c97-9d97-58968b6ce3cd |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 5675a358-0e12-5134-819d-c2cda4515826 |  | note | MEASURING DEVICES OR METHOD - AS 2341.2 or ASM D2171
label | c645a384-033f-50a0-981c-09bec5024e92 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Viscosity.
label | 8517ef56-3fa7-55e0-80b6-b54b2666fd52 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 5d343957-97cd-5c19-badc-b16fca4f1db3 |  | note | TEST REQUIRED - Viscosity mm2/s at 135°C
label | 02f42210-31fc-5eca-bac6-4a93087c8d27 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 79a58262-5ef1-5a2a-a587-d1ad4d7f8502 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 988f935f-b564-5092-a9fe-4790576a2fe8 |  | note | MEASURING DEVICES OR METHOD - AS 2341.3 or ASM D2170
label | b7711db4-e5ed-5bd4-83a0-fa7657d1b74e |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Flash Point
label | d542b4d6-50ea-59aa-ba4c-4d6bb82c3570 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 2b9e35f4-89c9-5f57-935e-97eadb91a2b4 |  | note | TEST REQUIRED - Flash point (Cleveland open cup), °C
label | cd462fdb-583d-5327-a24e-5f3eff0c56d6 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 403df3b4-503f-53ce-98ba-9be8414d081a |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | af0fc06a-0626-5144-88ee-11c2560b3ea6 |  | note | MEASURING DEVICES OR METHOD - ASTM D92
label | 9bcc3b42-860a-51cd-84fc-d631fc5a2513 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Solubility
label | 2f02d44e-dda0-5e18-bf3a-d020969d6fb1 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 6325d96a-f847-54fa-aaa9-4c699cc09048 |  | note | TEST REQUIRED - Solubility in Trichloroethylene, % or Solubility in Toluene, %
label | c2aa0271-9101-5b58-9789-baec42939f80 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | eb3b17ce-14f4-5c16-90dd-0901933ac518 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | c100312c-aa6f-5f46-9005-ef8d1153b232 |  | note | MEASURING DEVICES OR METHOD - ASTM D2042, AS 2341.8
label | 8ae41114-710e-5be3-8e19-7e32d3c43877 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Rolling Thin Film
label | bfb57104-d660-527c-9172-a042714ce1b2 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | b38cd233-c0b2-52a2-97ac-eb92e927629c |  | note | TEST REQUIRED - Rolling Thin Film Oven Test
label | c4d155eb-fcce-54e5-931a-ccdc26cb2c7d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | a0cc3884-8e9f-565e-ab23-7579f6f785ed |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 3421959d-6231-5aa0-9d3b-0d6415c5c085 |  | note | MEASURING DEVICES OR METHOD - ASTM D2872 or AS 2341.10
checkpoint-status |  |  | checkpoint | Penetration
label | 65dbc617-884e-51e8-8c51-26562b317098 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 9ce37b18-cd36-5cf0-89d4-0ed3a41357fd |  | note | TEST REQUIRED - Penetration of residue, at 25°C, 100g, five seconds, % of original
label | 590a3b91-137f-55ce-9950-6ca3315b3b16 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 3ba2a25f-bb95-5c9e-a55f-b1b8d867115d |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e9f9ab5b-e1b4-5f90-b979-5d03eeff60d7 |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | 89301b73-3794-5ed4-b4d3-4015e650c534 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Ductility
label | cfeffa46-4e26-5e64-afd9-6c5b27192b0c |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 0351b090-bc06-5869-a7fb-aaf5d28aaea4 |  | note | TEST REQUIRED - Ductility of residue, at 25°C, (metres)
label | 358244ab-3343-52d8-be31-11d76a643aae |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 857b5048-7bd9-57d5-8f33-cd73b1264375 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 434b23df-d31e-5615-9dda-8ddb2df82c49 |  | note | MEASURING DEVICES OR METHOD - ASTM D113
label | 587231c1-0536-5b02-9eb2-1a180cebb703 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-group |  |  | section | SEALING CHIP MATERIAL TESTING
checkpoint-status |  |  | checkpoint | Crushing Strength
label | 8db181f1-042a-5b54-a125-df269a8b6894 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.2
label | ca095887-0e9b-5232-8dc7-4385db516f12 |  | note | TEST REQUIRED - Crushing Resistance Test
label | 781e1971-602a-53f4-a274-55e3deeaf2a0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance
label | 87247279-9645-536e-8c83-b9d07e1d1bea |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 51729cf6-c632-5d31-bb45-e46773cdeefc |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.10
label | c0d02a22-c1cd-5157-abc6-ba4c09f08b6a |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 230 KN load
label | 5ee95013-6d83-5b66-b286-023b5d903e5a |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Weathering Quality
label | 2d702319-b089-52da-877c-6d048831bebe |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.3
label | ffdb0321-c889-5ca6-88f7-43f2b8d8e08d |  | note | TEST REQUIRED - Weathering Quality Index Test
label | bf04531a-e5a5-58c6-b6b9-11661456a8c0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 2339b912-86d0-5d0a-baae-a18311e9e3bb |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 54d29f95-c4c8-57b8-8486-5511d2a1cb8f |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.11
label | eab4604d-4aa9-5cdd-98fa-e35ae6120a61 |  | note | ACCEPTANCE CRITERIA - AA or BA
label | 959206bc-d6d5-5f30-8831-f5e26f47acee |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Weak Particles Test
label | 8a69793c-e761-5415-89e5-1daae343d7bd |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.4
label | 07bfc464-c987-5aff-84f5-14869bc47fc6 |  | note | TEST REQUIRED - Australian Weak Particles Test
label | b0c7a6d6-c594-5e38-a379-0981b3966d8b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Only undertaken in cases of dispute
label | 1fc9921e-658e-5e14-adbe-c752751c7be1 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 6d090da5-344c-5c6b-aa04-05ceb47f9474 |  | note | MEASURING DEVICES OR METHOD - AS 1141.32-1995
label | 900cee64-bcfc-50af-a764-907f47df174e |  | note | ACCEPTANCE CRITERIA - Maximum of 1%
label | 588be001-db42-5053-ab44-ea1a64a764fc |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Polished Stone Value
label | a550bed9-35fc-5476-bce7-51c68c634d4c |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.5
label | 1241077e-af61-593e-bde2-a86c070bbe9e |  | note | TEST REQUIRED - Polished Stone Value Test
label | 2c694e06-0823-5fda-891b-d78909e2d2f9 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance
label | d54f3d88-c4d3-5340-a3df-e3d32c78228c |  | note | TASK ASSIGNED TO - Accredited PSV Testing Agency
label | b4b7e404-dc93-5768-9e7d-ec9787f99325 |  | note | MEASURING DEVICES OR METHOD - BS 812: Part 114
label | 0740f853-4ee1-5075-95fb-78b681dd5b01 |  | note | ACCEPTANCE CRITERIA - PSV Required = 43
label | c8734408-0653-59d5-97c6-4c6e8a34731f |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Cleanliness
label | 85bd3aeb-6589-5c5e-bc40-5bf952b29db6 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.1
label | 67f8c011-34fe-5acc-8889-05cb6600fe36 |  | note | TEST REQUIRED - Cleanliness Test
label | 6e39b0e3-42db-5623-95df-7b79fa3cf919 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 43864342-7baf-58ee-9574-3e9261d89439 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | cfc67bd7-9651-5fc4-939d-38645c76a187 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | da1ef947-3f80-51a9-840f-c36cd7ef6618 |  | note | ACCEPTANCE CRITERIA - Grade 2 - 89 min Grade 3 - 87 min Grade 4 - 85 min
label | 3d0ab43f-be81-5227-93e6-3ba8693930ee |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Size & Shape
label | 5d67564b-0f82-510a-9165-8ebc8b6f05f4 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | f2f87c1f-436b-5c0c-b0e8-2eff3c2e18e5 |  | note | TEST REQUIRED - Size & Shape
label | 0a0adb4a-259a-577f-8b2b-fdb8f35d9606 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 8ae8fb56-829d-50e2-b1d2-1765bd6daeaf |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 3ce6bd09-cf08-5bc6-8043-6948c5efe7a7 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.13
label | 321307c2-adcf-548d-903c-f018a6ade291 |  | note | ACCEPTANCE CRITERIA - Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD 1.1% passing 4.75mm
label | e7dd0f43-abc0-56f9-b3fd-396ee26320d0 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Broken Faces
label | 595eb7d7-75ae-5993-8fd0-05aa64f4d96a |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | 195c96e2-a17e-5c03-96a9-cea194cf0f09 |  | note | TEST REQUIRED - Broken Faces Test
label | 56d9da76-aca4-596a-8893-e59ed11f38d5 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 31744b50-4ece-549f-bc61-1df8bad61e10 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | eef3c3d2-06ad-519e-97aa-4940124d461c |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.14
label | c1ded9ca-82d9-5729-8db9-0ff9f4845c4e |  | note | ACCEPTANCE CRITERIA - 98% with minimum two broken faces
label | 065d5bce-34e6-5146-aa2f-d79893e0af23 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Grading
label | f3e63c48-554a-52f3-8c88-0be104bc0363 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.2.2
label | f89a55b4-c28f-5096-936d-584c7ad5a664 |  | note | TEST REQUIRED - Grading
label | 40319333-b455-5883-bc8f-b6d55552ea79 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 3f0b72fa-097c-5efc-ad3a-0c85d453f8aa |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 8d0026f4-c55d-5c5e-93b7-e17fc80457c2 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.8
label | 6c44b002-242b-563e-9035-dde46cae279a |  | note | ACCEPTANCE CRITERIA - Grade 5
label | cca6fd99-60df-5b75-a5b8-6776411f029f |  | note | 100% passing 13.2mm
label | 7024f0d5-d76c-5cae-bcce-241f992f869c |  | note | 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300µm
label | 2f72dbd1-1efd-5ecc-8569-7e5e964f7dfe |  | note | Grade 6
label | 4b1c0533-33f8-5ee9-9bc3-28a683cada9f |  | note | 100% passing 9.5mm
label | e384bdbf-d705-5021-90e5-273e13e5bc3c |  | note | 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300µm
label | 29c090dd-f216-5515-bf26-a42b57c0c9b7 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Cleanliness
label | a87d28d5-9421-5d31-a07d-0234350f6e14 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.2.3
label | b7fb2385-d962-5a36-a469-68d4e8416022 |  | note | TEST REQUIRED - Cleanliness Test
label | 78a4ca65-2fe6-5c2c-a715-9bd16ee9cb25 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance
label | d6aa6ac1-4205-5f79-8f83-3f1f819ac173 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d929a0da-493b-53d7-9c38-9564b2315cf7 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | 03294e9c-f6f5-57bf-aaab-e51410325dfe |  | note | ACCEPTANCE CRITERIA - Report Value Only
label | 1b2867be-b433-599e-87c3-97cc167d74fc |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | SEAL DESIGN
checkpoint-status |  |  | checkpoint | Seal design
label | 484c7846-c1f3-5791-9ac6-19efdabf2f9b |  | note | SPECIFICATION REFERENCE - TNZ P/3
label | 5e1dea57-9d80-5d7e-99f4-d8368d5f66af |  | note | TEST REQUIRED - Seal design
label | 97d5ac8e-8169-542d-9584-84768d155566 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | 5914a030-d001-5836-a55e-abe163de9c7f |  | note | TASK ASSIGNED TO - Contractor's Quality Manager
label | 95be4ad0-8490-5bcd-a8f5-c9ab9fd5f3a1 |  | note | MEASURING DEVICES OR METHOD - report only
label | 4784f313-fa7e-5334-a967-c901eb9ab52a |  | note | ACCEPTANCE CRITERIA - report only
label | a57404d5-0aa6-5862-a441-65235d8155f2 |  | note | QUALITY DOCUMENTATION - Seal design
checkpoint-status |  |  | checkpoint | Seal design approval
label | 971a8b88-6579-55b5-ba20-8e9b87b89f1e |  | note | SPECIFICATION REFERENCE - Internal measure
label | e18f1e79-b993-58fa-b59e-47ccf75f0c94 |  | note | TEST REQUIRED - Internal verification
label | fb650e45-a74e-5305-b29c-11dcc8aa93f3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | eec63063-9243-5b20-ac77-5355585e2009 |  | note | TASK ASSIGNED TO - Downer Surfacing Expert
label | 95db4a96-3b36-5e2c-ab23-b665515b10b6 |  | note | MEASURING DEVICES OR METHOD - report only
label | 9750ea77-b902-5840-b1ae-016bcea969ec |  | note | ACCEPTANCE CRITERIA - report only
label | 8e850999-b74f-573a-80c8-20fea8cafdbe |  | note | QUALITY DOCUMENTATION - Email from Downer surfacing expert confirming that the treatment selection and seal design has been reviewed to confirm it is fit for purpose
checkpoint-status |  |  | checkpoint | Surface Finish
label | 6fd246d4-3b7e-552f-bce0-babf446f78c9 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | 39dd2586-df4b-5c20-ae9e-a8a884c4654c |  | note | TEST REQUIRED - Visual Inspection
label | 479b0414-12dd-5cfa-b108-a42eb7c70133 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | c3d65b06-7c60-5a4d-bec4-45ce32dfc535 |  | note | TASK ASSIGNED TO - Sealing subcontractor quality representative
label | f7b3d77d-15aa-53ef-9664-3e929a7c960a |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | 3472e234-a415-570d-bb77-00ca4abaf7e5 |  | note | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | c54077c5-511e-5b0a-b7da-1b8ba9f7fc91 |  | note | • The large aggregate is
label | 75d25113-c8a1-5158-8997-341183a74ab1 |  | note | • exposed to the surface;
label | e3708ce8-cb57-5384-96d1-fa12ec45c624 |  | note | • held in place with a matrix of smaller aggregates
label | 95ab8f03-854b-5f48-84cf-4e3bff96ce3e |  | note | • The smaller aggregate is held firmly in place by fine material;
label | ed8beee9-6cde-51f2-93e0-6b5828cc3d72 |  | note | • The matrix does not displace under normal trafficking or sweeping.
label | f376d14a-d81d-5416-b053-ef4948b5c041 |  | note | The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 1e87e9f7-5d7e-541e-8aec-10cc67ad1817 |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-group |  |  | section | SEALING RECORDS
checkpoint-status |  |  | checkpoint | Blend sheet
label | f93221a7-5eed-51a6-a599-3a09cbfc66b4 |  | note | SPECIFICATION REFERENCE - Client request
label | 00a57cac-ffa6-5a7a-a535-5ad4d30d6b7b |  | note | TEST REQUIRED - Documentation
label | 8eb9545d-e9bf-54a1-a954-022b0092e4ad |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | 039eba6c-7299-5092-89bd-b3e1b2302967 |  | note | TASK ASSIGNED TO - Bitumen blending facility
label | 9048f2b8-ca52-5c63-9188-949a2a8420dd |  | note | ACCEPTANCE CRITERIA - Report value only
label | e97b465d-a418-5b0d-a6ca-93a0c64e66bb |  | note | QUALITY DOCUMENTATION - Blend sheet
checkpoint-status |  |  | checkpoint | Spray sheets
label | ae2175bc-673a-59cc-a6f0-431c97699338 |  | note | SPECIFICATION REFERENCE - Client request
label | 4c9b29b9-5308-581a-9583-d99d89448019 |  | note | TEST REQUIRED - Documentation
label | 0d7b7465-9543-5a1c-93ee-e02710e5879d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | 8fce432f-0f9f-5155-a3c7-07a1b59a36e1 |  | note | TASK ASSIGNED TO - Sealing Manager
label | 3c9ee1b0-5039-5d55-b45a-1131c51779ac |  | note | ACCEPTANCE CRITERIA - Report value only
label | bd59d9c2-3b37-5b4e-aa3a-2d615d956d68 |  | note | QUALITY DOCUMENTATION - Spray sheets including asbuilt of seal area
checklist-sectioned |  |  | checklist | ITP - Jocelyn Street 0.07-0.218 |  |  |  |  | Yes | ITP - Jocelyn Street 0.07-0.218 | 8ec5b069-5776-494e-99de-7da0fd13a429
checkpoint-group |  |  | section | PRECONSTRUCTION HOLD POINTS
checkpoint-status |  |  | checkpoint | Agree QA Requirements
label | a3379f75-aa99-5438-8f13-41e27516d5d7 |  | note | SPECIFICATION REFERENCE - ITP
label | 7efbee55-2887-5c42-9970-c88e8a784c02 |  | note | TEST REQUIRED - Check pricing and ITPs & notify Westlink of any difference in understanding of tender pricing
label | c965daef-c6cc-54d2-a3c0-e6e815d10147 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Review ITP and confirm minimum quality requirements are understood prior to construction handover meeting.
label | 8397cab9-c0b0-5738-9009-94349c000c96 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | e978ae09-d665-52a3-a343-8b0443af5c9f |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Confirm Pricing for Additional Items
label | 10e5d301-887c-57e8-a2ed-906a5688b3d5 |  | note | SPECIFICATION REFERENCE - NTP
label | 2eed3dc2-b8df-5234-8649-26767c1e8287 |  | note | TEST REQUIRED - Pricing for additional items to be submitted to Design Project Manager and approved
label | 127f697b-f88b-5952-af2b-99c34d50eb40 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to construction handover meeting.
label | 38d41ddd-a384-544a-b80a-19323ab03434 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | e693ab7c-d9e1-580e-8edc-c8f13f6bf211 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Construction Handover Meeting
label | ffdac8f9-5c3b-58d7-8b6c-08e088b3b8ad |  | note | SPECIFICATION REFERENCE - NTP
label | c96983e2-583a-5cd5-95ca-72a788073e7c |  | note | TEST REQUIRED - Meeting
label | fe7763cc-9622-5d9d-b3c7-a8f431c6ce19 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 2 weeks prior to commencement of physical works.
label | 7f2c124b-20a6-57d1-8464-f4dc00629489 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 3f465790-9409-549e-b336-5c8a94c0dee4 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Physical works Programme
label | 2677c686-985f-557e-9e8c-5dcd5a5b632c |  | note | SPECIFICATION REFERENCE - NTP
label | 48425636-304a-58c8-ba89-b601b867d580 |  | note | TEST REQUIRED - Physical works Programme to be uploaded to WestLink Sharepoint site, emailed to Bryan Crean and start and end dates to by updated in RAMM Contractor prior to physical works.
label | d8fe7ccb-d2e9-5d0b-b0f8-f3864ff8bdce |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 10 working days prior to commencement of physical works.
label | cde5948b-c240-58d6-baf2-64f608b269d5 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 21a8f3d7-ab83-5119-aa1f-039ba6e58381 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Quantity Review
label | 7bf8d75d-07aa-5f47-8e69-6e73374baca0 |  | note | SPECIFICATION REFERENCE - NTP
label | 02b577cb-3cc5-5230-8102-a63f30df909a |  | note | TEST REQUIRED - Confirm construction set-out and drawings align with quantities provided in schedule of quantities
label | ebde4962-2eaa-5250-9466-7352c479b769 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - After construction set-out, prior to commencement of physical works.
label | c75d7e90-5b52-5146-85d1-33d3ea87a8ae |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 1b78b31a-ca83-5ece-9b10-e78fb4967fdb |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Existing Pavement Walkover
label | c8b2108b-a66c-5e4c-aa45-72634b8e0e10 |  | note | SPECIFICATION REFERENCE - NTP
label | 1a373598-fbc2-58c4-8ac4-73391434f7d4 |  | note | TEST REQUIRED - Visual Inspection of existing pavement
label | 937e4975-f907-58c8-bdc6-46969fbd1ed0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to ripping seal construction. Site walkover between WestLink Delivery Manager and Construction Project Manager to identify and agree any isolated treatments required in existing pavement to normalise strength.
label | f4eea2b3-9663-539d-918f-20c67686900a |  | note | TASK ASSIGNED TO - Construction Project Manager
label | c482ddf7-0a9a-5491-9a18-64024bc9259c |  | note | MEASURING DEVICES OR METHOD - Eye, spray paint, mark-up on drawings
label | 4f08e6a1-a322-5f6f-a62e-e97c5b643f18 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
label | a033d7f3-5d6d-5b12-a02e-eed5c1820249 |  | note | QUALITY DOCUMENTATION - Mark-up on drawings
checkpoint-group |  |  | section | MILLED SURFACE CONSTRUCTION (IN TIE IN AREAS)
checkpoint-status |  |  | checkpoint | Finished Level
label | b2ec7404-d251-5cf8-ad09-85c4b761eba3 |  | note | SPECIFICATION REFERENCE - TNZ F/1 11.2.2
label | db32cf8d-eea8-5197-a0d4-4ad014d89334 |  | note | TEST REQUIRED - String line or equivalent
label | 0ae72417-880c-53f7-8ac1-38a326a36f46 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side, min 3 measurements across lane = 44 Measurements
label | 93904549-9d6a-5138-bd5f-6aa23f9cece6 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 6a6684a7-37e4-53ab-8008-cce91460bda6 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | 62736048-95ab-5863-b679-7abf722db4a4 |  | note | ACCEPTANCE CRITERIA - +0mm / -30mm
label | f00d7ec7-5b7d-5a0b-ad89-20e9f6405977 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Finished Level (post milled)
label | 88a346af-25ef-5d87-b71b-709ffce46629 |  | note | SPECIFICATION REFERENCE -
label | 059eb8b5-b0cc-5129-8f65-ce62dbdcc08f |  | note | TEST REQUIRED - Visual inspection of mille surface
label | 3c8a6fc7-2676-5b16-a06c-60be56b1b48d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Site walkover between WestLink Delivery Manager and Construction Project Manager to ensure milled surface acceptability and compliance. Min 24hr notice to be given prior to
label | 149bbfeb-da3b-5ee1-85ef-3920d78df7c2 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 2617ebec-dc76-53c9-9402-adad72ab3545 |  | note | MEASURING DEVICES OR METHOD - Visual inspection
label | 23f0a741-9f6f-5866-9d73-37db08344183 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager
label | dd564225-2409-5ec3-9824-6f0ee03e775b |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied
checkpoint-status |  |  | checkpoint | Compaction (Provisional)
label | 5078ba62-8cfd-5ec5-830a-d528583e442d |  | note | SPECIFICATION REFERENCE - TNZ F/1 10.5.1
label | 6de50ef9-ff11-5762-af0a-416c9ef1bc58 |  | note | TEST REQUIRED - Proof Roll
label | 85fbea68-d05e-5f49-9b5d-868c490f363b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 100% coverage
label | 7eaa948d-f772-5dfe-a7ea-72842f4dc57c |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | faec096d-f779-5577-a382-5609751093b0 |  | note | MEASURING DEVICES OR METHOD - Smooth wheel roller with min loading 6259 kg/m width or large miller
label | 577147cb-c41d-5960-a962-1a4c02b7c20e |  | note | ACCEPTANCE CRITERIA - ≤ 5mm
label | 19004621-6bde-5fc4-a59e-c3f9b71a9ab7 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-group |  |  | section | BASECOURSE LAYER MATERIAL TESTING - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | Crushing Strength
label | 63d02016-a6f9-5463-800c-5245db26db0f |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.1
label | d85ca3d0-ad26-527b-ad87-36d07b3281c4 |  | note | TEST REQUIRED - Crushing Resistance Test
label | fbc6535e-430c-5882-9672-a3b245c29454 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 85a88e23-5577-507b-8be0-7d36a029c836 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 4b3d3d9a-969d-5cf7-9091-f4d29b5f09da |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.10
label | c9cc5885-24b5-588d-8716-60fc3a722f22 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 130 KN load
label | df7a7827-acba-5a6d-93c3-350457fdc38f |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Weathering Quality
label | e50e707b-b3c0-5b69-a729-68a517e0e88e |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.2
label | 1fc110a5-4bb4-5eed-b376-17c18a5fdb8d |  | note | TEST REQUIRED - Weathering Quality Index Test
label | 7e12a0a7-b54d-53b9-9396-bf157c832eba |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 457662c5-bca7-564f-8db3-e0260d8bc7e5 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | abd876a4-d498-5e6c-9a73-eb65897f5343 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.11
label | c428f48b-cecd-5857-9cc2-7d23cfefd4e4 |  | note | ACCEPTANCE CRITERIA - AA, AB, AC, BA, BB or CA
label | 5e9b688e-8e9c-56b6-97e1-baa43556ee66 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Soaked CBR
label | 42788dff-9185-5876-91c1-36906cf80de3 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.3
label | 58f6d3be-5cb1-54c2-8f0b-0c23c9fa9edf |  | note | TEST REQUIRED - Remoulded soaked CBR
label | 61d39b81-cc63-549c-b15f-e6dc85f849b0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 82ab6419-986a-5c99-8e70-80a605900e9b |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | fcac5ec2-34a9-53bd-a503-69c02c4c785a |  | note | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
label | 1da90aed-b6f5-5486-ae56-87a52d0e2876 |  | note | ACCEPTANCE CRITERIA - ≥ 80%
label | be9034fc-4a25-59c9-8a86-f527d604b11f |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Sand equivalent
label | e95f17c8-0d67-5633-9388-de5846a4c400 |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.1.1
label | 20bbe632-8898-52c3-9d5a-89583e7bce78 |  | note | TEST REQUIRED - Sand equivalent
label | 604148af-478b-58b7-a477-7636bd239c0c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | aaea2ef0-92ff-5540-bf11-f82749bd82f2 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | b2bfac5c-7b96-5d62-9816-bceaea29f411 |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | 2c0d2011-61fd-5c0b-bcf9-40228e7d1f54 |  | note | ACCEPTANCE CRITERIA - ≥ 40
label | 646dc46c-63a9-567e-bf96-8dd13d748ccf |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Broken Faces Content
label | f0e9a905-be31-5e9a-aebc-68620ff9f526 |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.2
label | cd372072-fb3a-5f46-86ab-36eb76845563 |  | note | TEST REQUIRED - Broken face content
label | a9f52eb3-246e-5e7c-aed6-a2ac6f61fd0c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | 0816fd80-b56c-5fbd-80f9-5c89c1359dd9 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | ff46d2ef-88c9-5ec1-b801-1aa94caf4f65 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.14
label | f1a10696-f2d2-5394-bcbd-446aaa4310fa |  | note | ACCEPTANCE CRITERIA - ≥ 70%
label | 0bbd982c-2954-5bbb-b663-aea6564e1710 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Particle size distribution
label | 7ba22ea2-0472-58ca-9c72-adca39fa9b7f |  | note | SPECIFICATION REFERENCE - Design
label | 17de55ee-9d73-5709-9704-db1e35d7723b |  | note | TEST REQUIRED - Wet sieving test
label | da39bc44-0a07-54cf-aa37-7cb1d31be2f9 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | 71d57496-6ac2-5012-b209-40fe30ede10c |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 80c2acf6-9a17-5f61-9dd7-fa1e1ae3c87e |  | note | MEASURING DEVICES OR METHOD - NZS4407 4407 : 1991, Test 3.8.1
label | c55b0d0c-aef5-5de4-8543-78d2fc03ca46 |  | note | ACCEPTANCE CRITERIA - 100% passing 37.5mm
label | 3e474aa3-d4ff-5fca-ae01-1fd9e3701b5b |  | note | 66 - 81% passing 19mm
label | 89ecf326-4c1d-56d0-8b96-8a48e1c90cef |  | note | 43 - 57 passing 9.5mm
label | 038d354e-4d9a-5c9b-ab43-fcf07040b990 |  | note | 28 - 43 passing 4.75mm
label | 95e38cef-3f38-545d-b7e1-ddd29d1a51f0 |  | note | 19 - 33 passing 2.36mm
label | 1c84f176-b127-593f-9f0c-5d24d212362f |  | note | 12 - 25 passing 1.18mm
label | c34a141c-30b4-5d81-a335-8954ec3bd14d |  | note | 7 - 19 passing 600µm
label | 017c8649-7798-5e32-96e6-f334a67b5d11 |  | note | 3 - 14 passing 300µm
label | a30d0e26-0abd-5551-91ef-f80a70c4287c |  | note | 0 - 10 passing 150µm
label | a6a7527f-762e-5f54-93ce-eb0a1aa46120 |  | note | 0 - 7 passing 75µm
label | 9265137a-3970-5f2f-aa7c-0dbe99563f84 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Solid Density
label | 9b0c4e29-5ec0-5919-97c3-436ab658a703 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | befb0574-3daf-5eb6-89ac-4b9e550bea71 |  | note | TEST REQUIRED - Solid Density
label | 072f0710-482e-5cb0-8d5e-b539d6321bb1 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | 923b0cc7-6327-562a-a2f8-b4389c4a4448 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | f39f4ace-0037-5956-a2ad-3b51c73f2118 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.7
label | b395ca03-b648-5160-9371-a1d7de5f0f74 |  | note | ACCEPTANCE CRITERIA - report value only
label | bb6f0441-cad3-5af7-a014-1d97ea53213e |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Determination of MDD & OWC
label | 6f1ef763-aecc-54cf-b552-37d452c75931 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | 64025173-0d14-5fcf-bcab-3ae4b2bc3179 |  | note | TEST REQUIRED - 5 point compaction curve
label | b04e73f1-b5be-5bb9-876d-6439edb0483f |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | e488ec7c-131d-59fd-8893-7620f575d95c |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 40bcbd51-53fd-5f1b-8d55-8f293f70ba30 |  | note | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.3
label | a801583b-b9c1-57b7-821a-0c08ce2cbdc2 |  | note | ACCEPTANCE CRITERIA - report value only
label | de3d7204-f34c-5bdc-b244-e70bf9cb70a9 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-group |  |  | section | BASECOURSE LAYER CONSTRUCTION - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | Formation
label | 293086ff-5666-5e3b-bc4f-65bf68066dda |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.7
label | b34cc57f-6a73-5207-9133-e44990391af4 |  | note | TEST REQUIRED - 3m straight edge or approved equivalent
label | 1f9d6f38-a465-5e18-9903-ee2c2239fadd |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 15 Tests
label | 8ac6e4aa-b56d-5199-884f-5f5e5666fa54 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 282beff2-1f2d-59ef-a24c-13e650ae8d0f |  | note | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | 0b9e3e6e-f053-5cdb-a672-ac7d254a8887 |  | note | ACCEPTANCE CRITERIA - +/- 10mm
label | 148c681e-464e-5cfe-9006-5cbfb413e3da |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Finished Level
label | affb3c80-76f3-511e-a676-cc90e59de99e |  | note | SPECIFICATION REFERENCE - TNZ B/2 5.1
label | b230988d-122f-5f61-9aea-aae57b504d61 |  | note | TEST REQUIRED - String line or equivalent
label | 48a890cf-84d4-5a92-acf2-e74fc3519a54 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 15 Tests
label | 4000b886-cb19-57f8-968d-46fc8c3234fd |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 71ad989b-0b29-518d-9ac5-89b9a0dd8c2a |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | 0f0399cf-dc9e-549a-8c57-fdc8399d3f82 |  | note | ACCEPTANCE CRITERIA - +15mm / -5mm
label | a79c9779-f6eb-5cbe-96db-9fe2efa250cf |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Plateau Density Test
label | edd58baf-d987-5c29-82c2-b82bd1ace044 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5 (b)
label | bf21b813-1fda-5347-8c1a-19ed0e1b491a |  | note | TEST REQUIRED - Plateau Density Test
label | 4d557e22-ab5f-59d6-8858-64405d3193f8 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test minimum
label | 889b3aa3-416a-58aa-a27f-691b03eaf566 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | b2a3ab35-e3a2-560e-9c37-9611c07c830d |  | note | MEASURING DEVICES OR METHOD - NDM
label | 7d8f068d-de8d-5ac2-8c92-e31dd7033109 |  | note | ACCEPTANCE CRITERIA - report value only
label | 1a420696-7e0c-58e9-b845-3cf6bec13775 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Compaction
label | 8864ad6d-aada-57f5-8e34-deb231e0ad76 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.6
label | c8619d36-11af-523c-af4e-671c7a6c2226 |  | note | TEST REQUIRED - NDM
label | b0e9682d-47a8-5329-a0ab-139b6b5e2647 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 10 tests
label | 1ff4cd4d-04f4-57b3-bb0e-53e972779f2e |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 5ddb103c-f2d9-528a-9a40-87f48f9ae31d |  | note | MEASURING DEVICES OR METHOD - NDM
label | 0f1adec6-0cd4-5788-8db6-709fd1742e7b |  | note | ACCEPTANCE CRITERIA - Mean ≥ 98% MDD, Min ≥ 95%, Total voids ≤ 20%
label | a0df969d-0add-5b17-b06a-9084c847a905 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Compaction - Feather Edge
label | 1d264117-85bb-5453-8ca6-819fcead3c23 |  | note | SPECIFICATION REFERENCE - TNZ B/2 8
label | 6e252207-7fb2-597b-b651-c51ef635f906 |  | note | TEST REQUIRED - Visual Inspection
label | c10d0e5e-0195-52e6-a9f8-be8606c15e8a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Inspect full length each side
label | 18c5f11d-c7c5-5177-a688-f4858190dc5f |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | f0c514eb-2231-58b3-9b2e-51f182c86929 |  | note | MEASURING DEVICES OR METHOD - Truck with 4 tonne wheel load
label | 5cf0b1d2-5f29-5ace-93d8-5b1933c5cae1 |  | note | ACCEPTANCE CRITERIA - the surface shall be able to withstand a moving wheel load of up to 4 tonnes without displacement
label | 552b5a5d-101d-5f6a-a053-872e2fc4adfa |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Degree of Saturation
label | 0ff0e8af-dcdb-585e-b03d-e75929b7eb63 |  | note | SPECIFICATION REFERENCE - TNZ B/2 12
label | b89a4dd5-ca74-58af-b8da-f5a79604149b |  | note | TEST REQUIRED - NDM
label | 93f2307b-6c0b-5e13-b87f-1a16014489a6 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 10 tests
label | 1b8db291-6ba0-565e-9454-2c91721c8cad |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 83f75e4f-3807-5ac2-b000-2c334d3d5eef |  | note | MEASURING DEVICES OR METHOD - NDM
label | a9438276-40d9-5def-b2fa-4760af959188 |  | note | ACCEPTANCE CRITERIA - < 60% (or 80% on consultation with the pavement designer)
label | e4735329-cd7d-5534-93de-1fc166b5f55c |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Surface Finish
label | e49a6ba2-b7cb-5b46-b222-c1e545280258 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | 9101b704-82a0-5417-8022-866b431d9eca |  | note | TEST REQUIRED - Visual Inspection
label | c1a4a8cb-d76d-5fca-b6c1-58d4fc26108e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale. Min 24hr notice to be given prior to inspection.
label | daccfe28-7cd5-529e-9c54-b69c17f60bb5 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 38c29430-8a75-5f35-a9bc-0a528e214732 |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | b47ea232-9b59-5086-aa3f-b2784890bd8b |  | note | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | 2cc69b55-ea9d-5a43-93af-de25d100b77e |  | note | • The large aggregate is
label | e21d47a0-2f4f-54ed-8472-5903e97cbe3c |  | note | • exposed to the surface;
label | 163692f8-f6cb-5f4f-af70-be2d816cf74d |  | note | • held in place with a matrix of smaller aggregates
label | b0287cf5-77d2-5a1f-a417-e46f6f1fa7df |  | note | • The smaller aggregate is held firmly in place by fine material;
label | 8ebc3259-6653-5ca7-a42d-c2c1d58b4368 |  | note | • The matrix does not displace under normal trafficking or sweeping.
label | af8c9e57-c37d-5ce4-b06e-ffdeb818fbd6 |  | note | The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 8065beae-ab79-5dfd-b633-a52ac3c8c6a2 |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-status |  |  | checkpoint | Ride Quality
label | 20f6c476-16b0-5825-b6bf-dd36ccef69db |  | note | SPECIFICATION REFERENCE - Internal measure
label | 00de26da-e189-51e8-80c3-35b50a0f6317 |  | note | TEST REQUIRED - Ride quality test to AG:AM/T002
label | c0a2493f-291c-5230-bf77-5708a318ee17 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Within 12 months of first coat seal
label | f82a0fa7-5c5f-5619-9ab5-01ea91392b73 |  | note | TASK ASSIGNED TO - Either by pavement subcontractor or by Westlink Asset Management team from latest HSD survey
label | b73b6d47-ffa1-5768-bc2b-8854ba78875c |  | note | MEASURING DEVICES OR METHOD - inertial laser profiler or response-type roughness meter
label | 7fa4038b-bc23-5c4d-ba92-aac980c2fceb |  | note | ACCEPTANCE CRITERIA - no 100m moving average > 60 counts
label | 47a55360-f73d-5ee8-a948-9219a4fd3aa8 |  | note | QUALITY DOCUMENTATION - Certified test report
checkpoint-group |  |  | section | BITUMEN - TO GAIN APPROVAL
checkpoint-status |  |  | checkpoint | Penetration
label | b2b3e332-c030-554b-8611-56cb083fdb10 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 6fef4587-bc4b-5197-901b-ecc6a1a15638 |  | note | TEST REQUIRED - Penetration at 25°C, 100g, five seconds
label | e4da20e1-f9a5-5830-955d-fc8eab9ca7cb |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 84420aa5-ad86-5b1f-99b6-2a0710fe67ae |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | fcf091da-c448-5ddb-b364-cb74328f8949 |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | d023da5e-0726-59c9-9fe9-687a6bab378e |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Viscosity
label | b63eebcb-477e-593a-a1ae-574ff716632b |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | d2dde9cf-19a5-5d98-b058-75cad94b9379 |  | note | TEST REQUIRED - Viscosity PaS at 60°C
label | 463c4a12-de8d-542a-b686-3d27c2c88259 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | c5d9703f-668a-59f2-9865-9130aaa78c22 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | ffd0f00d-e17a-5f7a-8dfb-eceb4b929fc3 |  | note | MEASURING DEVICES OR METHOD - AS 2341.2 or ASM D2171
label | 053a45f4-2942-575b-bda9-56e26e74f79c |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Viscosity.
label | 33d7a8ef-ea32-53c7-95b0-dd30d17e8b35 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 756b71cd-c0d0-5455-82d0-844267334dc4 |  | note | TEST REQUIRED - Viscosity mm2/s at 135°C
label | 1247fa83-6287-5972-8160-df95ef24d770 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | b6b0a142-0a6f-5a17-933f-cf1860641ed5 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 574dca4d-5896-5000-8f22-0afa220a3672 |  | note | MEASURING DEVICES OR METHOD - AS 2341.3 or ASM D2170
label | 8e68e24b-2d4f-5701-afe1-e698fd834737 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Flash Point
label | 79e84aaa-606a-5301-8f6d-250c93ab9805 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 067559ca-51d8-5d8f-8415-2513f1fd19da |  | note | TEST REQUIRED - Flash point (Cleveland open cup), °C
label | 79e45a4b-2e9f-52af-a243-bd9640f57947 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | ec542240-aebc-5c39-95ec-6a3881e05367 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 7e287e6b-d367-561f-8286-07764ac842c2 |  | note | MEASURING DEVICES OR METHOD - ASTM D92
label | 3b294667-60c5-5136-bf4b-9d7db11637a3 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Solubility
label | 897f9a86-da7a-5732-bd98-1054be83d688 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | c8ad0b64-77a1-5e7f-86d1-ec8b6fbf71b4 |  | note | TEST REQUIRED - Solubility in Trichloroethylene, % or Solubility in Toluene, %
label | 3b93d6f4-d934-52ac-863e-1f970761ada3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 7c486939-a730-5921-b1f1-c6cc18a56cd3 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | ae8ba125-a047-5f4f-bd8d-f4e1e53968fb |  | note | MEASURING DEVICES OR METHOD - ASTM D2042, AS 2341.8
label | 0cf41653-f142-5e86-af79-44d3b308e2bd |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Rolling Thin Film
label | b45de410-6f6a-5ac9-a561-db09bcac1b4c |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | c3dfa1f4-fcff-5682-a1df-b9c8abaadf91 |  | note | TEST REQUIRED - Rolling Thin Film Oven Test
label | 86f9b1cd-a200-5419-b36a-ef3c3ffb4bd1 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | dd746e94-820f-5994-83c5-afda18d6e5a6 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | f964f148-5886-5b80-9976-f5144e873e7f |  | note | MEASURING DEVICES OR METHOD - ASTM D2872 or AS 2341.10
checkpoint-status |  |  | checkpoint | Penetration
label | f8557435-1da9-5de7-85ba-9b301515b9b5 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 5b02885c-5d6b-5dcb-89a5-031c72e375a2 |  | note | TEST REQUIRED - Penetration of residue, at 25°C, 100g, five seconds, % of original
label | 1efa9a00-20ec-506a-9a84-3277a495a352 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | ef95373b-8e56-5108-b39a-b025fb3bf439 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | c728b9da-446f-5ad2-895a-b775da48ab0e |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | dfcd8cfc-321b-53da-a387-997a02d8c80a |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Ductility
label | 266d2dc6-e603-59cd-995b-7aa055dd5408 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 04a227ca-2ff3-5abe-85c4-f3414a0a8c7b |  | note | TEST REQUIRED - Ductility of residue, at 25°C, (metres)
label | dacd2fc8-60d3-578d-833b-95e7bb834fc7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 79ab101f-1936-551b-be72-3ca93cb616a6 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 9d080747-7ee3-5055-a503-e893c303a503 |  | note | MEASURING DEVICES OR METHOD - ASTM D113
label | a0540146-1f27-50c2-8310-f37d5e3e7208 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-group |  |  | section | SEALING CHIP MATERIAL TESTING
checkpoint-status |  |  | checkpoint | Crushing Strength
label | c39cd4a0-4925-579a-ad9a-815bf22987ab |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.2
label | 3bfa6e13-bb2d-579e-8485-6676f9876cd5 |  | note | TEST REQUIRED - Crushing Resistance Test
label | 4eaef047-e43e-56e1-83db-43b648861040 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 8ad6f48a-a5ea-54f3-8a88-5e6b7c3b1c5e |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | c2065c66-e451-5703-9f4a-9b7c5f72145d |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.10
label | 25e8b6bb-f483-56e6-acf6-4c37b1aecae6 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 230 KN load
label | 0822850f-450f-5d0d-9aaf-b26f7bd943d1 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Weathering Quality
label | b365121b-a0aa-5ea4-a55e-62cbdc765f10 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.3
label | aa25d41b-0147-5110-ade1-01aefd211eaf |  | note | TEST REQUIRED - Weathering Quality Index Test
label | 6cdee5b8-d51e-5dfe-872c-5c6a64eb4a88 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 72776427-0755-5e98-bf4d-9227622e5f4b |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 0fdeac7a-6db8-591a-9fd1-1548f58f763f |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.11
label | 08cee2ba-6663-5bfd-9d30-69b34acfd5c4 |  | note | ACCEPTANCE CRITERIA - AA or BA
label | ef16ef8d-aeee-5445-8282-309d1dce3ba6 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Weak Particles Test
label | 305d56a6-4bec-50e1-a845-9deb4942da48 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.4
label | 1bb7bd71-8320-5d76-82ad-e00bdd7876a5 |  | note | TEST REQUIRED - Australian Weak Particles Test
label | 9016fcd3-4e17-5ecf-b310-fb2e1ca0d127 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Only undertaken in cases of dispute
label | 4e9cb343-64b9-5517-81e2-fc6672e5d5de |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | ee821552-6b0c-5316-aee3-ec664d83bbf3 |  | note | MEASURING DEVICES OR METHOD - AS 1141.32-1995
label | 596102cd-43a3-58da-8136-d6fb9a05dfac |  | note | ACCEPTANCE CRITERIA - Maximum of 1%
label | 3e463f42-40d4-5c8a-9dec-59d9532c8476 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Polished Stone Value
label | 69067725-daad-5ef6-b7bb-90593f32a238 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.5
label | bd0dcbf8-fb68-5012-8ef6-141596a191bd |  | note | TEST REQUIRED - Polished Stone Value Test
label | 6273f7cb-bf12-5a98-9267-43df83432067 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | c2e929db-30c7-5636-b917-2ea3275e8027 |  | note | TASK ASSIGNED TO - Accredited PSV Testing Agency
label | 78ee47f5-9876-51af-9061-4d48ff480d8d |  | note | MEASURING DEVICES OR METHOD - BS 812: Part 114
label | 50fd0643-87ae-5da6-8a8b-a863216da808 |  | note | ACCEPTANCE CRITERIA - PSV Required = 43
label | aed74afd-2078-58e3-b706-2037fcee6038 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Cleanliness
label | 64ec5ff3-59fb-5b46-a3d3-161739f64f8f |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.1
label | 05f11f6d-269d-56a5-b09f-44c09f6ad813 |  | note | TEST REQUIRED - Cleanliness Test
label | db7b2abc-79bd-5516-b65a-52f2a0e31020 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 8dad4d7c-1836-5ae6-b9f7-6bca614fb9ff |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 902f8f59-3dcc-54f1-9400-1967c2263c17 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | 879e4369-78c6-5c95-ba36-e88619e99406 |  | note | ACCEPTANCE CRITERIA - Grade 2 - 89 min
label | c703d5df-6980-5ed6-b435-550b082381d8 |  | note | Grade 3 - 87 min
label | 6f5dcbc4-0172-5746-963f-cf670b3eae79 |  | note | Grade 4 - 85 min
label | 0285c3dd-bf44-5055-89e9-c7e67f2a5db7 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Size & Shape
label | 2f9c51ea-ee21-5fdc-888e-a87d2f8ac9fd |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | 86181b6b-e7cb-5b37-9f8b-e994395e8d31 |  | note | TEST REQUIRED - Size & Shape
label | 8c0ad13e-016f-52b2-a269-ef6606b6ca64 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 00dd8262-96d6-5bc8-b79f-afa573387c03 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 8b897262-16a5-59b8-8af3-786a43fc7ac1 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.13
label | d47ce18d-63e3-559c-a4c5-c00d906b33f2 |  | note | ACCEPTANCE CRITERIA - Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD
label | 35617089-988f-5cc0-912a-7067894df084 |  | note | Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD
label | 7470a737-16c7-57c7-976e-879ce627e34d |  | note | Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD
label | 56aad30b-0e32-5054-b964-a72819231063 |  | note | 1.1% passing 4.75mm
label | bb404933-1f28-56c4-b893-611558781587 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Broken Faces
label | 0f4fd790-9df4-5435-bf73-6c506b618cd6 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | e0771f86-aee3-57bd-84ae-e9ed9a5aa690 |  | note | TEST REQUIRED - Broken Faces Test
label | fa4a74a4-2d00-55ee-a614-767f617cb21e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 81094a0e-6738-5b4c-94ec-c3bd9dc8063d |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d93df05d-681a-5140-81d1-1074decb08b0 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.14
label | e720cd74-0684-5d0b-ad01-e49f1f067cb8 |  | note | ACCEPTANCE CRITERIA - 98% with minimum two broken faces
label | d765769c-6331-5829-ab9a-e80d56baf2ba |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Grading
label | b6b392e4-129d-53d4-91e6-2f334e65bd6b |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.2.2
label | 2d8702f4-f01a-521f-aac3-e16efc7e61a5 |  | note | TEST REQUIRED - Grading
label | 30a2c735-e8b1-54ca-9efa-8171bbfbddc7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 871f4c63-81ad-5bf0-8118-84ccad6dfd53 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 344393e4-19ff-56c8-af41-9e39433ff11c |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.8
label | 30a1046e-a497-56e9-a54a-7760843cb320 |  | note | ACCEPTANCE CRITERIA - Grade 5
label | eacd5e79-d1e2-57a9-9268-5243137f7c72 |  | note | 100% passing 13.2mm
label | 23bd4b2a-4d01-5af2-9119-beb89c285d79 |  | note | 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300µm
label | 44e6127f-f29f-509c-b134-51d471238d40 |  | note | Grade 6
label | 5162863c-f94b-5798-a662-257565edae64 |  | note | 100% passing 9.5mm
label | 062c1cf2-c3cb-535d-abd2-91d249994b42 |  | note | 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300µm
label | f1719682-b5b9-5fb1-99be-037a64d26c4b |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Cleanliness
label | cbd58526-ee6b-5bde-87bd-0db0e94961df |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.2.3
label | acbfd3c9-2123-5812-b3f4-24c9599a6805 |  | note | TEST REQUIRED - Cleanliness Test
label | fcd1bf97-16f3-5c37-8114-f2a7ac6afb3a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 269d598f-7034-51e5-bd04-c77a17a9de8c |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 2c5d16c1-17c3-5dc3-82aa-5354e5d2a155 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | 35995de8-c6d4-55d7-84ce-67c0ccf8053e |  | note | ACCEPTANCE CRITERIA - Report Value Only
label | c6141a36-0e7f-5660-ac81-d68dbeb25147 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | SEAL DESIGN
checkpoint-status |  |  | checkpoint | Seal design
label | a06e23ea-be59-56c5-82ad-81a7a9176b4f |  | note | SPECIFICATION REFERENCE - TNZ P/3
label | a59a01ff-6483-5e2d-8767-79084315e95d |  | note | TEST REQUIRED - Seal design
label | a34410ed-23bc-562b-bff2-273d3b2ccf40 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | 23d95001-0553-5346-8c23-0acde341c73c |  | note | TASK ASSIGNED TO - Contractor's Quality Manager
label | d349afdc-53d3-5816-b6de-167d18196b58 |  | note | MEASURING DEVICES OR METHOD - report only
label | b3019548-c407-5598-b525-80b9eb9ed759 |  | note | ACCEPTANCE CRITERIA - report only
label | cd1f062e-f120-5d28-ab17-8a07cb51ea26 |  | note | QUALITY DOCUMENTATION - Seal design
checkpoint-status |  |  | checkpoint | Seal design approval
label | c22dba3a-0260-5493-bdba-6bcfbf6088ea |  | note | SPECIFICATION REFERENCE - Internal measure
label | 688dcd2d-bd23-5c16-9da2-3493f385f9b8 |  | note | TEST REQUIRED - Internal verification
label | a11bc0d6-3aa1-5747-bad3-4ccd6c19716a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | a156cb3b-e997-56bc-98d1-6bca61ae175b |  | note | TASK ASSIGNED TO - Downer Surfacing Expert
label | 70c20134-ac13-5ccb-a2c3-4af3ecb0e68b |  | note | MEASURING DEVICES OR METHOD - report only
label | 1d18af3d-7048-5633-b02f-32c220b7fe58 |  | note | ACCEPTANCE CRITERIA - report only
label | b567edd7-b7bc-58ff-a325-eaf404064e36 |  | note | QUALITY DOCUMENTATION - Email from Downer surfacing expert confirming that the treatment selection and seal design has been reviewed to confirm it is fit for purpose
checkpoint-status |  |  | checkpoint | Surface Finish
label | 92279c31-c2cb-5de7-bc6c-6115c5cd164f |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | 4edd4f10-0d92-5d47-84ac-c5170584a950 |  | note | TEST REQUIRED - Visual Inspection
label | 91962ba4-1aca-58c5-ae54-8437956e058c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | 7b90cd85-8920-5dbe-a7a3-3748c53e1e1d |  | note | TASK ASSIGNED TO - Sealing subcontractor quality representative
label | 6de3507a-abaa-531f-9819-912562665b26 |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | a20a4064-479f-5737-a4a4-cef74220a8bd |  | note | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | b3aad67f-43e5-5223-bc61-d62297e3c818 |  | note | • The large aggregate is
label | 3c85cbad-2281-5799-a156-d1fa4f7f4dbf |  | note | • exposed to the surface;
label | 4d1c9732-cdcd-5eee-a9c7-68c5ef5a46fe |  | note | • held in place with a matrix of smaller aggregates
label | b24a7181-31b3-5fa8-9ab3-fdb8bf31b6e4 |  | note | • The smaller aggregate is held firmly in place by fine material;
label | b7d3d48f-8272-5adf-9ef0-d847c27ea86b |  | note | • The matrix does not displace under normal trafficking or sweeping.
label | a8a3a529-a750-5afb-b5f5-d5a9ec97312d |  | note | The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 41f891c8-d27a-556c-a5b7-a402e54c9eb0 |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-group |  |  | section | SEALING RECORDS
checkpoint-status |  |  | checkpoint | Blend sheet
label | 9ea91803-352b-5f30-9751-46386b36c0b5 |  | note | SPECIFICATION REFERENCE - Client request
label | 5977f151-5667-5b41-bb2d-85350a27d28c |  | note | TEST REQUIRED -
label | 63c6be31-6385-562a-bcc7-8ba52c0ee182 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | 32efdff4-50aa-5606-9b6d-b46c90743a3b |  | note | TASK ASSIGNED TO - Bitumen blending facility
label | a8c48a2e-c6dd-5e0c-b4ac-7531eccf12c6 |  | note | ACCEPTANCE CRITERIA - Report value only
label | c1c4ae42-f3d3-5c76-beb2-e7969339f7fa |  | note | QUALITY DOCUMENTATION - Blend sheet
checkpoint-status |  |  | checkpoint | Spray sheets
label | 5633451a-938c-52b9-a445-65e4ac4189c6 |  | note | SPECIFICATION REFERENCE - Client request
label | 47e4777e-4515-56b6-a8f3-390b5f6f33e1 |  | note | TEST REQUIRED -
label | 7f9e0421-1c1d-5708-acc0-fa11659b57cd |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | 1d249f6f-da3b-5a48-82d3-74eda49484ad |  | note | TASK ASSIGNED TO - Sealing Manager
label | cd1a84dd-0238-5e83-8488-2b334c37dc92 |  | note | ACCEPTANCE CRITERIA - Report value only
label | 43deaeae-83ea-581e-985e-ef318d413ae1 |  | note | QUALITY DOCUMENTATION - Spray sheets
checklist-sectioned |  |  | checklist | ITP - Oropi Rd 11.430-12.010 |  |  |  |  | Yes | ITP - Oropi Rd 11.430-12.010 | 978d61bd-04a9-42f1-b0e5-32e5cb53755f
checkpoint-group |  |  | section | PRECONSTRUCTION HOLD POINTS
checkpoint-status |  |  | checkpoint | Agree QA Requirements
label | f3510af5-92af-5cd2-9379-a205107a933b |  | note | SPECIFICATION REFERENCE - ITP
label | a5f839b6-7f01-5feb-b267-55d1accaf60c |  | note | TEST REQUIRED - Check pricing and ITPs & notify Westlink of any difference in understanding of tender pricing
label | 0e47305b-d55c-577a-bac2-3d1be0aec305 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Review ITP and confirm minimum quality requirements are understood prior to construction handover meeting.
label | 5dc1dbcd-f7f8-5c83-890e-73440468a32b |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 64ba813d-8a04-55ef-a721-1b4fac5fce61 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Confirm Pricing for Additional Items
label | 6f1a2e6c-7f7b-565d-8913-fd14408ac9cd |  | note | SPECIFICATION REFERENCE - NTP
label | 33ba4edd-1b98-58b2-87d3-ec26efc4d24c |  | note | TEST REQUIRED - Pricing for additional items to be submitted to Design Project Manager and approved
label | 9a9f36bd-40a7-5869-a80b-cf794a3b1156 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to construction handover meeting.
label | 27388b56-33aa-5504-a0ea-ebbc57bb0a02 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 4c8ba2c8-6861-523c-8c87-720223217b59 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Construction Handover Meeting
label | 010ba188-08ff-5699-9c76-16037fb17e4a |  | note | SPECIFICATION REFERENCE - NTP
label | 89528fab-51d2-5175-a344-fd61eb3282e8 |  | note | TEST REQUIRED - Meeting
label | 1561834f-5079-54f8-9709-b196215367d8 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 2 weeks prior to commencement of physical works.
label | 8108ebaa-ab9e-5fb7-af29-45d6f74b7c1e |  | note | TASK ASSIGNED TO - Construction Project Manager
label | b9bb8fec-1c8c-5687-95d4-30005cc60cd0 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Physical works Programme
label | 974615ca-0042-5021-a167-13cc398898be |  | note | SPECIFICATION REFERENCE - NTP
label | 3b6850ac-0e04-573a-8a55-e1ef0056e43b |  | note | TEST REQUIRED - Minimum 10 working days prior to commencement of physical works.
label | cbf3fb80-7bc0-5e5d-9adb-b878913ee040 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 10 working days prior to commencement of physical works.
label | 379bdbcd-cf36-5aac-a8dd-ace5ce64adb5 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 28511ed9-8e17-526d-b239-88b22af19093 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Quantity Review
label | d7f5cd4e-7e33-5e99-a944-d49a6e4317a5 |  | note | SPECIFICATION REFERENCE - NTP
label | 353f6519-0cbf-5033-8bb1-cc18304086fb |  | note | TEST REQUIRED - Confirm construction set-out and drawings align with quantities provided in schedule of quantities
label | a3bad494-e7a8-5ee6-81dd-3d32fc1633f7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - After construction set-out, prior to commencement of physical works.
label | 34c6e78b-da33-5413-97c5-cf71696bb651 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 5f616653-4373-5804-b848-84a1827a0958 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | Existing Pavement Walkover
label | 9028c84f-4371-5b7c-bbd9-3bf31a0c12e1 |  | note | SPECIFICATION REFERENCE - NTP
label | 41a453b7-24fa-5d47-a925-151ca2ff6f81 |  | note | TEST REQUIRED - Visual Inspection of existing pavement
label | 08fe4834-5f4a-553a-8fea-723e7050a83d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to ripping seal construction. Site walkover between WestLink Delivery Manager and Construction Project Manager to identify and agree any isolated treatments required in
label | fb95aef0-2a62-556e-87b4-ee059465c593 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | dfbb935a-5a17-5dee-a59e-0460a24c8e94 |  | note | MEASURING DEVICES OR METHOD - Eye, spray paint, mark-up on drawings
label | 4847a248-29f0-5611-b838-8220c993e6b8 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
label | 1ddc45fa-0805-5acb-b7cc-3be4f316bf15 |  | note | QUALITY DOCUMENTATION - Mark-up on drawings
checkpoint-group |  |  | section | MILLED SURFACE CONSTRUCTION (IN TIE IN AREAS)
checkpoint-status |  |  | checkpoint | Finished Level
label | f4140075-17e8-53aa-a962-38571fe62e51 |  | note | SPECIFICATION REFERENCE - TNZ F/1 11.2.2
label | e6849c2e-418f-5bcc-b090-2c9c1c841b6c |  | note | TEST REQUIRED - String line or equivalent
label | e809616d-9223-5624-8c2e-d05b74f78ab7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side, min 3 measurements across lane
label | 8e5a3db8-fdf1-5985-97e8-fe818d3a0588 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 6ef4196d-dbbf-515c-a88f-07bed56eb7c3 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | c88c0326-81e4-5d95-ab8a-a3af7ee7277d |  | note | ACCEPTANCE CRITERIA - +0mm / -30mm
label | be9389f0-9454-559b-8051-8033f790e06a |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Finished Level (post milled)
label | 9d2f169e-2116-5ffa-8182-bada42a79ba7 |  | note | SPECIFICATION REFERENCE -
label | c217fd34-853b-564d-86f7-c0159560b496 |  | note | TEST REQUIRED - Visual inspection of milled surface
label | 5990bbd0-c057-5d35-97ba-06b2ea0edc09 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Site walkover between WestLink Delivery Manager and Construction Project Manager to ensure milled surface acceptability and compliance. Min 24hr notice to be given prior to
label | c5c02785-dbeb-58f4-878e-fd23028178b2 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 8691e8f5-9b6d-5d6f-93a2-f6a5da395056 |  | note | MEASURING DEVICES OR METHOD - Visual inspection
label | c83eb7a3-217e-5e75-88e9-8183ee11606c |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager
label | 1fb412ab-8c3f-5c68-98e2-96a7edaa47cf |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied
checkpoint-status |  |  | checkpoint | Compaction
label | 007cc4d1-e3b5-5a20-8d87-9a9f6144846f |  | note | SPECIFICATION REFERENCE - TNZ F/1 10.5.1
label | 72f681a8-b413-576a-a727-f17c5ea06477 |  | note | TEST REQUIRED - Proof Roll
label | b2ef4b00-558f-5187-b4b9-77589f842a8c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 100% coverage
label | 23e78a22-cabe-5352-b889-551fa6e44021 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | b3b95263-67a0-5975-b827-16cc6d75a444 |  | note | MEASURING DEVICES OR METHOD - Smooth wheel roller with min loading 6259 kg/m width or large miller
label | 66c9d0ad-aefc-51a4-9908-5fd3c6d85a1d |  | note | ACCEPTANCE CRITERIA - ≤ 5mm
label | ce756487-cba5-5dcc-80d2-553f4f069b40 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-group |  |  | section | BASECOURSE LAYER MATERIAL TESTING - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | Crushing Strength
label | ffcb6a94-eadc-5b01-a6fb-ef82009c7206 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.1
label | 1f69fc5c-f9ef-59c3-80e6-7db941cf5dad |  | note | TEST REQUIRED - Crushing Resistance Test
label | e87da1e6-d521-5297-b8f5-e23178da9d4d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | e2e7562a-c8df-5673-a27b-e372d9daf8ef |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | ce5c99ca-b746-501c-bc59-c792e3b0ca31 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.10
label | e33598f4-d548-5789-9834-9ab250aee6e9 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 130 KN load
label | d3dea276-3921-5c1a-81cf-6f8e456cbfb7 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Weathering Quality
label | b8771b82-9891-569f-bd52-25256f344fed |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.2
label | 9083296e-60bd-5809-9c6a-1571ad421c85 |  | note | TEST REQUIRED - Weathering Quality Index Test
label | eb317cce-ff0e-59dc-88dc-1cd46e97aa7d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 1d26584e-fc86-5e8d-bde0-d156b5aa8b12 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d2773a6b-cb9f-5f43-a40a-1d43313e1354 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.11
label | 67433e79-0c49-5cca-a40d-16dce1f93375 |  | note | ACCEPTANCE CRITERIA - AA, AB, AC, BA, BB or CA
label | 51ad4751-1040-5904-b520-69c246997147 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Soaked CBR
label | 881386e6-3d0e-58e0-a179-9f440d4eba45 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.3
label | 605e8a77-dbf7-531e-be1c-cb2502e1f73d |  | note | TEST REQUIRED - Remoulded soaked CBR
label | d0682718-c64e-550e-a32a-48a7b310a73b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 3215fcce-e103-586f-9aa3-b9153952483e |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 59e5917b-5d86-5bf7-b7c5-3115c5d00ac6 |  | note | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
label | bc854aae-a681-58ab-a3a8-b2443ff77290 |  | note | ACCEPTANCE CRITERIA - ≥ 80%
label | c594d1e8-2440-59ad-a542-7b86eedda52f |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Sand equivalent
label | 522ea5d7-2524-5897-aeee-f4a4e5d24bdf |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.1.1
label | 4998588c-c776-56e5-9746-5e64ea3b828b |  | note | TEST REQUIRED - Sand equivalent
label | 560652b0-525b-51f9-a170-a04966c7fd11 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | 70705f62-c367-57f2-a74b-dd4821be2719 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 36964cd6-bc7d-503a-85ed-2808ecd1c1cb |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | 3523f235-3931-5c16-ba66-d652a01c449b |  | note | ACCEPTANCE CRITERIA - ≥ 40
label | e2952dfd-d432-5b46-9c9b-70f8513943d9 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Broken Faces Content
label | dcef8dba-3e94-5179-85df-e937ce05fbc2 |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.2
label | 25f43a5e-45a0-5556-94b8-c0e0ef6c04d0 |  | note | TEST REQUIRED - Broken face content
label | 05ec0775-9e99-54f0-8de4-99f06d6f721e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | 5e59c56a-16ba-5a65-8d95-dbfe3d37d7c5 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d7c32d66-12f2-5246-9644-1bf40f3d521d |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.14
label | 52ea2ae9-b07e-5cc7-adaf-a9b3482b4dfe |  | note | ACCEPTANCE CRITERIA - ≥ 70%
label | cd164d8c-369b-54ca-99f2-3abe597de155 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Particle size distribution
label | 689aae00-2c3b-5b02-897d-bbf7de8ff142 |  | note | SPECIFICATION REFERENCE - Design
label | 8c1d552a-d2bd-5f78-9aee-14e8fb63f891 |  | note | TEST REQUIRED - Wet sieving test
label | 6c668e64-c84d-5275-8b07-3fcc484c3242 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | f409123e-3c2c-5929-a282-40f8e1908ecf |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 2257080e-550e-5a2c-81ab-56ca83d34cc5 |  | note | MEASURING DEVICES OR METHOD - NZS4407 4407 : 1991, Test 3.8.1
label | 9e593e6a-55bd-5535-973f-447d914f12d3 |  | note | ACCEPTANCE CRITERIA - 100% passing 37.5mm
label | f81fe2d9-28b8-5047-99e5-14b5c030dff1 |  | note | 66 - 81% passing 19mm
label | 28cdb35a-c005-57d6-9eec-f393553f6858 |  | note | 43 - 57 passing 9.5mm
label | 83b2d5f7-9860-56f6-a4c9-d6da6898a236 |  | note | 28 - 43 passing 4.75mm
label | b39a1673-01f5-5c38-bbf6-84e679d33489 |  | note | 19 - 33 passing 2.36mm
label | f22a6df9-c9f5-5a67-8e22-d6352aee7971 |  | note | 12 - 25 passing 1.18mm
label | 9fba78ed-c810-585c-a891-2cac9a51f697 |  | note | 7 - 19 passing 600µm
label | 18793e9c-c944-58fc-b066-453962ce6a5d |  | note | 3 - 14 passing 300µm
label | 43455a9e-7499-5898-bae2-c5479d8227e4 |  | note | 0 - 10 passing 150µm
label | 32647398-b105-504b-b1b4-df62f82d5118 |  | note | 0 - 7 passing 75µm
label | 240bb5ca-2c2e-5e41-9284-7d5ce0a07319 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Solid Density
label | 03caf4ed-48ac-57de-87df-378c60008927 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | e75accd7-d3f3-5945-87d2-b56501f51657 |  | note | TEST REQUIRED - Solid Density
label | 63dc5ed1-58c2-5209-a693-ffaab4972753 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | ed3a7b12-4a30-5520-820c-2554fdc733b8 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d0eb7e86-7605-5ca3-b912-9ea81caf5d72 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.7
label | aec0393a-27f7-52e4-a158-9abf88e3587b |  | note | ACCEPTANCE CRITERIA - report value only
label | e94cbfb7-23bb-573b-960a-f0e7509401bc |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Determination of MDD & OWC
label | f38f68e0-9eb7-590d-a98f-1dd77b53a053 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | df9d19b8-39e4-5b29-a94b-8598dd94fc11 |  | note | TEST REQUIRED - 5 point compaction curve
label | 28dcae3d-12bc-52b7-9241-2646f6fe247d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | 443dca5a-adb0-588e-b55f-8e280961c1bb |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | f4ae8d0f-57d2-505c-86eb-e6bd76f90e08 |  | note | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.3
label | a30fc2ee-d770-5b6d-9032-565caec80960 |  | note | ACCEPTANCE CRITERIA - report value only
label | f3abdcea-d55f-588a-b767-99663a3e8463 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-group |  |  | section | BASECOURSE LAYER CONSTRUCTION - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | Formation
label | ebcc1cf0-614e-5a56-8535-3a0bc435cf7b |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.7
label | 20480e02-3129-5fec-b208-5ad815ccc501 |  | note | TEST REQUIRED - 3m straight edge or approved equivalent
label | 5ea3272c-50bf-5a08-ba2d-2fe155d121af |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 58 Tests
label | 233b7b50-ebf6-5784-8a78-a883ca91da5f |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 1167c669-7a55-5e14-9711-d9923d66dcd5 |  | note | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | bd6cf405-343e-5dab-b0f5-fc018a72b01b |  | note | ACCEPTANCE CRITERIA -+/- 10mm
label | 3141374d-a2eb-5b80-bc58-bee4cf761c43 |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Finished Level
label | 037e6334-4228-545d-9d5d-8b759a52d36a |  | note | SPECIFICATION REFERENCE - TNZ B/2 5.1
label | 8b68e649-9a40-5df6-bb97-7a2dbb00d350 |  | note | TEST REQUIRED - String line or equivalent
label | 9c7ee0af-73ac-5f14-8ebb-36bebea2f2ed |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 58 Tests
label | 278ba032-8373-5f9b-ab3c-bdf48d87d2db |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 05372860-e303-5155-af5d-ab5ba5a747b8 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | b5add9c2-3700-51ae-a4a9-149b22c7e144 |  | note | ACCEPTANCE CRITERIA - +15mm / -5mm
label | e4625c35-0766-5f7e-a677-2273b1a4434d |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | Plateau Density Test
label | 13cb9f24-e56f-5e42-b08d-e77e202d3924 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5 (b)
label | 367d77a4-1527-5417-bc8e-b80c13d02d75 |  | note | TEST REQUIRED - Plateau Density Test
label | 361347b6-1c8a-5236-9296-60e3c6eb791d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test minimum
label | 7fd5a6c7-96c9-50fd-b0c1-b7063892c5c6 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d5e29c0d-862b-51ba-a88a-4ff93afaeb71 |  | note | MEASURING DEVICES OR METHOD - NDM
label | 3f063a50-de69-53e2-94e8-62c712da96d5 |  | note | ACCEPTANCE CRITERIA - report value only
label | 1b413757-83b7-54d9-a8e9-f0eb9d930f59 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Compaction
label | 607c426b-b559-55a2-99ad-98d2ef516a15 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.6
label | e1e42053-e17c-5d78-95d6-167451975ddc |  | note | TEST REQUIRED - NDM
label | 0b20747c-3ed5-5079-9db2-f36f462a2899 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 20 tests
label | 4bdb51b5-ea95-5235-bdad-afd84e948efb |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | fe3286b7-1718-568a-b3fc-60cd26563f41 |  | note | MEASURING DEVICES OR METHOD - NDM
label | 139deda3-760c-5100-91ab-5dd45eb851ee |  | note | ACCEPTANCE CRITERIA - Mean ≥ 98% MDD, Min ≥ 95%, Total voids ≤ 20%
label | 2f26ed37-4443-5498-a4b8-67602a17fa91 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Degree of Saturation
label | 307a7ce5-537c-536f-8dbc-a0c5cfbe189b |  | note | SPECIFICATION REFERENCE - TNZ B/2 12
label | 087f87a5-87a2-5881-929c-7d1bc63c6067 |  | note | TEST REQUIRED - NDM
label | cab6cc5b-8306-5c5a-8671-753a3cd2bd2e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 20 tests
label | 179db0c7-8826-5d49-89b2-4484c0afec68 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 7a44b8b2-de6f-5eeb-a669-276338404f35 |  | note | MEASURING DEVICES OR METHOD - NDM
label | d7cd6e5e-13cd-5983-8544-996d2e011fe9 |  | note | ACCEPTANCE CRITERIA - < 60% (or 80% on consultation with the pavement designer)
label | ed0631ca-21b5-512c-b500-5edf5a46a4d7 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | Surface Finish
label | 95e0718b-d0e1-5750-abf9-5fa6b8b89267 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | 85194aab-3ed9-5ef7-9c12-631133922bc9 |  | note | TEST REQUIRED - Visual Inspection
label | 99154760-9699-558f-b63e-fbc74cd4b48a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale. Min 24hr notice to be given prior to inspection.
label | e241b97b-4e7d-55b3-8aa4-70da17cede09 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | b06d6f8f-d6c9-5513-9769-0f7fa67dfc14 |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | 68bba51e-2c23-500d-9444-db89aa9fdf11 |  | note | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | deb62164-0e82-580a-88e2-e13a1450e922 |  | note | • The large aggregate is
label | 27b97f77-679c-51ae-9c54-dcaa8a051490 |  | note | • exposed to the surface;
label | 225c659b-2889-5b60-9e19-ffbd921a957a |  | note | • held in place with a matrix of smaller aggregates
label | 6286c18e-f3c5-5c20-bbd5-34feb54d3327 |  | note | • The smaller aggregate is held firmly in place by fine material;
label | c1b7360e-763e-5989-ac16-89289cc44e67 |  | note | • The matrix does not displace under normal trafficking or sweeping. The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 8a2ed857-3618-5cdb-afc1-716c73636239 |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-status |  |  | checkpoint | Ride Quality
label | 9aedadae-d7fe-56e3-a132-965862a5dde3 |  | note | SPECIFICATION REFERENCE - Internal measure
label | 1278928c-046b-50e9-8d5f-af4079a78c9e |  | note | TEST REQUIRED - Ride quality test to AG:AM/T002
label | 9552f98a-8e55-52b4-bf7f-0f09e84e2c1e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Within 12 months of first coat seal
label | 52c70ecf-3f31-55de-bd15-429584af31ac |  | note | TASK ASSIGNED TO - Either by pavement subcontractor or by Westlink Asset Management team from latest HSD survey
label | bf14a858-5a18-51e9-a12b-f5aefa9d978d |  | note | MEASURING DEVICES OR METHOD - inertial laser profiler or response- type roughness meter
label | bd196d0e-2a52-5f8a-9fbd-6a97b0cf106a |  | note | ACCEPTANCE CRITERIA - no 100m moving average > 60 counts
label | 2884c5a3-935c-502c-ac5c-5a03bef5cc37 |  | note | QUALITY DOCUMENTATION - Certified test report
checkpoint-group |  |  | section | BITUMEN - TO GAIN APPROVAL
checkpoint-status |  |  | checkpoint | Penetration
label | 7a2b3231-d846-5543-bd8d-a3a3063af1eb |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 3fb486cd-d53e-5f61-adef-5a3f841f70ea |  | note | TEST REQUIRED - Penetration at 25°C, 100g, five seconds
label | fee32746-fd40-5cd9-81b2-16637370054b |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 081f6307-b4a4-5077-a364-bccb681d85a4 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | a63a921e-8c40-585d-ab1c-36781008b798 |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | 113e6a8a-0461-5ee6-a861-08350e2d71ff |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | f3087faf-0139-5ac9-b87a-6c7ffc46b1eb |  | note | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | Viscosity
label | c5300416-ae4a-58ed-b612-7eb675180494 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 56c9e51d-02d4-5373-9868-6a66dedafd6b |  | note | TEST REQUIRED - Viscosity PaS at 60°C
label | f518327b-712d-5001-9ce0-401cc17bca48 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 0309bf35-7e60-57c8-ae73-9daf8e317426 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 9bcdcd1c-6a48-5827-a5f8-bdec6c58ffe8 |  | note | MEASURING DEVICES OR METHOD - AS 2341.2 or ASM D2171
label | 196e9da0-b0d2-5e1d-ad3b-a52b7a5036c3 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Viscosity.
label | 51f8fcc7-b6f7-58a8-87a8-de23bd1f916b |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 8530508b-9c4e-5550-a153-30b83b31a643 |  | note | TEST REQUIRED - Viscosity mm2/s at 135°C
label | beb17a69-8f6a-5c03-9f0a-71e757f1ea5a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 164c0bb8-bb30-533d-93b1-5c338492536f |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 160ccc37-cb54-585f-913e-7c5a4a810de8 |  | note | MEASURING DEVICES OR METHOD - AS 2341.3 or ASM D2170
label | 3504c5cf-48f9-5dc2-abe9-91bdec2af127 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade a per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Flash Point
label | 52284e71-4b5f-5adf-89f2-40781c8aaa3f |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 76d1d884-0e03-5c9f-9042-65f636291a07 |  | note | TEST REQUIRED - Flash point (Cleveland open cup), °C
label | bf95335b-3bf8-55f6-80bd-8d717eed4285 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | ab20a197-d728-5463-81f5-b4bcdd35eb86 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 1999e5e5-528d-54a9-b77b-6a61764a09e7 |  | note | MEASURING DEVICES OR METHOD - ASTM D92
label | 89d1e1f5-b5ed-597a-b596-1f37e48c3a32 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Solubility
label | a021ccea-9c86-5a49-8241-1b86e852f3c9 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 6418a3f8-00e2-504b-ba6b-d098304bcff7 |  | note | TEST REQUIRED - Solubility in Trichloroethylene, % or Solubility in Toluene, %
label | 8726c927-d9f6-5613-9dd2-e01e7d43317a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | d4b75ce5-23ce-5f0a-a74c-868b89fbd858 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 77a84233-5680-54f2-93f8-9c7d79b48833 |  | note | MEASURING DEVICES OR METHOD - ASTM D2042, AS 2341.8
label | e8a18a17-5688-5f13-bbd9-d8d5865ee129 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Rolling Thin Film
label | 9d02ccef-2f0b-5348-921d-d0db3ae0133d |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 5253ccd3-7c3a-531e-aeb4-b9f5c8910c7a |  | note | TEST REQUIRED - Rolling Thin Film Oven Test
label | 38bc53fd-323b-5f0f-800d-19cf162e2d0d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | ffdaa05b-0a42-55c1-8735-91c368d80bf2 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 6b2fe401-0a81-5daa-96cb-1c51ce4616bb |  | note | MEASURING DEVICES OR METHOD - ASTM D2872 or AS 2341.10
checkpoint-status |  |  | checkpoint | Penetration
label | c26e0057-4228-51c2-971c-6208b20e710d |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 0440e84f-03f1-52aa-92c3-1cce676e3c75 |  | note | TEST REQUIRED - Penetration of residue, at 25°C, 100g, five seconds, % of original
label | 534f49a6-8150-5d5b-b634-39f271e4e58a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | db86981d-6e00-5927-b179-947bfa7f442b |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | f9623001-8c11-52c4-922f-9710720f1d79 |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | 5c2233fe-1bef-5cc7-b458-1de63387c2ce |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | Ductility
label | f719490e-d662-5d10-8f8b-f04347bf3a12 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 62cf88c0-f783-5570-8444-cd1740352346 |  | note | TEST REQUIRED - Ductility of residue, at 25°C, (metres)
label | 682d062f-d41b-5cda-a4c2-1998594728e2 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | bca7e18d-284d-5594-aaa4-4c459943a77e |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 0aa9260f-b1ca-5069-b2ef-b8f8c812d842 |  | note | MEASURING DEVICES OR METHOD - ASTM D113
label | 768beac8-1f48-5722-8516-f3abd34e1206 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-group |  |  | section | SEALING CHIP MATERIAL TESTING
checkpoint-status |  |  | checkpoint | Crushing Strength
label | 80cbcfac-57fe-552f-9939-e40065c93e54 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.2
label | 34b61922-384a-5b2e-af4c-2f0726798370 |  | note | TEST REQUIRED - Crushing Resistanc Test
label | bb7a48cf-8f72-51eb-b4cb-d2f27aeca5e7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 510cf072-af48-55e2-9ecd-28d694140bde |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 11bc798a-cb53-57f6-a4e2-72590ccbc96f |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.10
label | ed76cb6f-1cf7-5602-9ecc-233279260bd7 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 230 KN load
label | 032cc58d-8b0c-55ca-a3d0-cae08cbb44d8 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Weathering Quality
label | 8e072a95-f099-513b-aca0-110b9524aa92 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.3
label | cf76ea40-15ec-5b2f-9234-4ff0fd3036d8 |  | note | TEST REQUIRED - Weathering Quality Index Test
label | 709c713b-4589-5cb7-9f7c-d32be9d266a7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 6e8bb76d-bb25-5517-b928-a7a83efe8763 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | c116bf9b-4eb7-5439-9f7c-076abea2129e |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.11
label | 0668c6f3-90bd-5ccd-858a-885a0dbaf100 |  | note | ACCEPTANCE CRITERIA - AA or BA
label | df6370c6-1440-56d6-bf78-0c8532e283d9 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Weak Particles Test
label | 64b8763b-96b4-5d14-aa35-383525b9638d |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.4
label | 4ca887e6-a55b-5d20-8522-274dff4029f2 |  | note | TEST REQUIRED - Australian Weak Particles Test
label | 252fc599-585e-5201-a5cb-ff97c7e74588 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Only undertaken in cases of dispute
label | 0d60d87f-1ec6-5e66-a98e-00ae59dd3126 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 6030b65c-2af7-5197-95d5-5b24f179701f |  | note | MEASURING DEVICES OR METHOD - AS 1141.32-1995
label | 8f961ce9-17e7-5568-857a-681e19bff4b6 |  | note | ACCEPTANCE CRITERIA - Maximum of 1%
label | 43fef934-3719-5a10-ad08-1113a71748ff |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Polished Stone Value
label | 79f2104a-47b8-5ff0-b790-f7955b29aa37 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.5
label | 9587aec0-3468-5655-ab6b-44d4d6439700 |  | note | TEST REQUIRED - Polished Stone Value Test
label | ed0fa46b-25c4-57b0-9d33-70ba3107bba3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | eeb7c3b3-d6a5-50a2-a04b-44634acd6d57 |  | note | TASK ASSIGNED TO - Accredited PSV Testing Agency
label | 1612e039-e72e-55a1-a16b-38beb9e01cb4 |  | note | MEASURING DEVICES OR METHOD - BS 812: Part 114
label | ad231d55-cf68-5a3c-bc7e-69cb54dde423 |  | note | ACCEPTANCE CRITERIA - PSV Required = 43
label | d88e7a87-0f7c-52ad-8427-0d280c4f7ce8 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Cleanliness
label | e0eebec9-5c0b-5516-b731-c57c2bd6a4e4 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.1
label | 74634256-fe47-56aa-a4af-01262e89e019 |  | note | TEST REQUIRED - Cleanliness Test
label | 3c503ec7-f554-5624-a4cc-cf860dc88d2a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 854a8a61-bc09-570c-9696-d4a9b2031edc |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 6a211167-070f-5a37-bf37-71a4ff308449 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | f93f0780-d29e-5d1e-a17e-9379b2bc8934 |  | note | ACCEPTANCE CRITERIA - Grade 2 - 89 min
label | ac8e3e89-2b57-5921-9ae5-3c7fe4bacedf |  | note | Grade 3 - 87 min
label | e2b0f3f4-52c2-50d6-a244-cc8926dd05dc |  | note | Grade 4 - 85 min
label | ba44b3b2-7912-541b-a1c9-8ec2c1abf2b5 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Size & Shape
label | 6f7c427f-00d0-55be-8818-08b33da41339 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | 6f844a81-bfc4-5f53-9eaa-cb6d88e7a4a7 |  | note | TEST REQUIRED - Size & Shape
label | b0d14b3b-2bf8-5514-b8da-6396daeb379d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | b9e87dfc-2095-513b-82b9-bcecb69e98e3 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 0a4e7cb8-22ad-5d1d-a6c8-9b01c4f159c1 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.13
label | 1d8c4abb-d3f0-5158-89b5-0ff3d79fa06d |  | note | ACCEPTANCE CRITERIA - Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD
label | 5d743980-88e2-50dd-af25-5a54d4e3a168 |  | note | Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD
label | ee84e16f-e29a-5e9e-8047-4b49b99258b4 |  | note | Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD
label | a2519603-331d-5244-aa15-2362ef8f41ee |  | note | 1.1% passing 4.75mm
label | becd4c7c-b3e7-51e7-9695-49938918abd8 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Broken Faces
label | ca7d764b-d996-5bb2-ab60-5ac9e3517955 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | 4ddcc812-3e0a-5b8f-b4e0-28b7022d535f |  | note | TEST REQUIRED - Broken Faces Test
label | f4be29e0-0f5e-5896-b634-f4f07de75fd2 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | c81fefc1-0d63-57c0-9b91-55afa24f2970 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | c35e5ad0-077c-57c4-95c5-715a38046cf6 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.14
label | b08b1d33-1b89-56cd-b1fa-f2929dc54a5b |  | note | ACCEPTANCE CRITERIA - 98% with minimum two broken faces
label | 3a3d12ee-fefd-5505-852b-31c856f3b7a2 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Grading
label | 126febf1-89d5-5aef-99e3-045b8f3c82ef |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.2.2
label | a781151a-3449-5a5f-bb9c-0fe6d77f2203 |  | note | TEST REQUIRED - Grading
label | f33ee07d-4faa-5867-92bf-ed736586dd99 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 8eae7aee-2660-58cb-a538-f1fe329d88bc |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e900499f-094d-529d-894d-2e3a60d1afff |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.8
label | ff7dc1e2-9baf-5ea5-b6ce-aa2b3bb9068d |  | note | ACCEPTANCE CRITERIA - Grade 5
label | c40d7158-a390-5f49-b56b-fdd69c5815ec |  | note | 100% passing 13.2mm
label | d2cff872-3f3b-594f-8b01-5d12e099a264 |  | note | 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300µm
label | 403a7ce1-0a49-5556-a537-3085536fe865 |  | note | Grade 6
label | 018514bc-19f9-5d2f-a075-149b7c2f0907 |  | note | 100% passing 9.5mm
label | 3e486126-8f5f-552b-81e3-dbea15b97944 |  | note | 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300µm
label | 927f176a-5416-5c4b-8460-d1d168abcee3 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | Cleanliness
label | 4e42b529-db36-51a6-8a36-91ca06519e0e |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.2.3
label | 57a8e071-7da5-569e-9391-f7f083315907 |  | note | TEST REQUIRED - Cleanliness Test
label | ff657c6b-3067-573f-91d7-40891b325923 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality
label | 44352891-6f46-59b5-9161-475ff512988a |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 5b93f0da-e22c-5a62-98c9-b8354661dace |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | e725675c-8051-5bc9-88e5-070af854cebc |  | note | ACCEPTANCE CRITERIA - Report Value Only
label | ab6fb2d7-df7a-529f-ac98-9f57011e3c66 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | SEAL DESIGN
checkpoint-status |  |  | checkpoint | Seal design
label | 2c0a6e1f-3626-5012-9c46-b3cfd481709d |  | note | SPECIFICATION REFERENCE - TNZ P/3
label | 1d32394b-3de9-58bf-8ccc-902e4fba9d5f |  | note | TEST REQUIRED - Seal design
label | 88013561-c177-50de-9a90-760485173081 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | ebeb08db-1503-52a3-a582-ba406f7a67d4 |  | note | TASK ASSIGNED TO - Contractor's Quality Manager
label | e7f70965-beb0-50a8-8bde-e2f9659c192e |  | note | MEASURING DEVICES OR METHOD - report only
label | c35a90b7-0891-5d1d-a2d0-b0497b67c197 |  | note | ACCEPTANCE CRITERIA - report only
label | 064dc9aa-7009-5d3a-9c21-3fb9ffc6806a |  | note | QUALITY DOCUMENTATION - Seal design
checkpoint-status |  |  | checkpoint | Seal design approval
label | 3f46f7fa-e29b-544e-a7ee-abe471b79cb4 |  | note | SPECIFICATION REFERENCE - Internal measure
label | ef948418-394c-59a9-a87d-390a7bda43cc |  | note | TEST REQUIRED - Internal verification
label | c322c5fd-bb53-5cc8-af9e-95ef9e387da6 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | d94a9699-c307-5511-b3c6-1f6efeeeb9c5 |  | note | TASK ASSIGNED TO - Downer Surfacing Expert
label | 4147912e-6533-5fa5-8d2d-360167cd3a9e |  | note | MEASURING DEVICES OR METHOD - report only
label | c99801e7-4017-5beb-8bb8-14835a261e2d |  | note | ACCEPTANCE CRITERIA - report only
label | 897a761b-a3e2-52e7-ac14-3feda16d43e9 |  | note | QUALITY DOCUMENTATION - Email from Downer surfacing expert confirming that the treatment selection and seal design has been reviewed to confirm it is fit for purpose
checkpoint-group |  |  | section | SEALING RECORDS
checkpoint-status |  |  | checkpoint | Blend sheet
label | ad007a94-1853-5531-a34a-07be7e483dc9 |  | note | SPECIFICATION REFERENCE - Client request
label | b95d628e-2f02-5d19-bcf7-209b37070027 |  | note | TEST REQUIRED -
label | be5f75a5-dfb2-5e4e-9c7a-ea5ccee05e1a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | 6f3b445f-4a78-58cb-91a5-3371ee4b93ae |  | note | TASK ASSIGNED TO - Bitumen blending facility
label | c79b466c-cf24-5484-8058-00b3bd200ddd |  | note | ACCEPTANCE CRITERIA - Report value only
label | e1571754-2793-52d7-aaa1-69b71090774b |  | note | QUALITY DOCUMENTATION - Blend sheet
checkpoint-status |  |  | checkpoint | Spray sheets
label | 18217299-6b33-5461-bb42-68ff5fca2039 |  | note | SPECIFICATION REFERENCE - Client request
label | a8453358-74d1-519e-a437-c5f661368d4a |  | note | TEST REQUIRED -
label | 63e0213a-ed14-529d-be8b-9c4c156a2697 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | c149b25d-999b-58ef-bf97-36385f56057b |  | note | TASK ASSIGNED TO - Sealing Manager
label | 306b305f-b05d-5a54-90bf-548cb5ae7bb1 |  | note | ACCEPTANCE CRITERIA - Report value only
label | d17ed9ba-f85a-52c8-b4d6-3dc050b02610 |  | note | QUALITY DOCUMENTATION - Spray sheets
checklist-sectioned |  |  | checklist | ITP - Maniatutu 0.020-0.300 | itp |  |  |  | Yes | ITP - Maniatutu 0.020-0.300 | ca5516d4-74f8-4114-a39f-b97a2cd9a29c
checkpoint-group |  |  | section | 1.0 - PRECONSTRUCTION
checkpoint-status |  |  | checkpoint | 1.1 - Agree QA Requirements
label | 6b4165cb-d809-526b-b28a-5139cf0336ff |  | note | SPECIFICATION REFERENCE - ITP
label | 042e9428-4b62-54ac-9a3d-8944dfaf42cd |  | note | TEST REQUIRED - Check pricing and ITPs & notify Westlink of any difference in understanding of tender pricing
label | 6194c4df-2252-5d6c-b863-68b2f830172c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Review ITP and confirm minimum quality requirements are understood prior to construction handover meeting.
label | fbf14cf7-5df2-5dc0-a701-feb0c5c70f0e |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 30854046-3e24-5b43-9909-2199f35501b3 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.2 - Confirm Pricing for Additional Items
label | e6d1fd12-1f36-5796-9bdc-bf3b0a29adf4 |  | note | SPECIFICATION REFERENCE - NTP
label | 2c012b37-91f7-5ad1-9afc-fe818b284d2d |  | note | TEST REQUIRED - Pricing for additional items to be submitted to Design Project Manager and approved
label | 41471ae5-3f34-5240-9343-699189130b28 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to construction handover meeting.
label | 3102862d-64a7-59ab-83ed-66e686d63756 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 3510fc3e-0461-5dc6-8a44-7f572d41670e |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.3 - Construction Handover Meeting
label | f01970eb-f9d3-5525-a332-4ffa5e0259bb |  | note | SPECIFICATION REFERENCE - NTP
label | 46963096-23c7-5eb4-8d56-bf8331832443 |  | note | TEST REQUIRED - Meeting
label | 535035b6-7977-584b-a26f-013d4c8f88d7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 2 weeks prior to commencement of physical works.
label | e5852972-26bc-57d1-9884-8c099fdf4f1a |  | note | TASK ASSIGNED TO - Construction Project Manager
label | caf5b9a2-c87a-551b-acf8-434ed376a0a9 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.4 - Physical works Programme
label | c4534218-555f-5205-9ab5-54febbe6d1a5 |  | note | SPECIFICATION REFERENCE - NTP
label | ad573948-fbec-5ef1-bde3-c11377352a35 |  | note | TEST REQUIRED - Physical works Programme to be uploaded to WestLink Sharepoint site, emailed to Bryan Crean and start and end dates to by updated in RAMM Contractor prior to physical works.
label | 1c004a4d-5354-5f0a-96fa-4627c05380a5 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 10 working days prior to commencement of physical works.
label | bf8650bf-e29e-5afd-a497-c893d1b85039 |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 1a89c81a-130b-53cc-8560-a92fe5366a27 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.5 - Quantity Review
label | df7c5927-adee-5ec5-a49f-803dc5fbc8b8 |  | note | SPECIFICATION REFERENCE - NTP
label | 4ba0dd34-80eb-5efc-a8de-d45725f56663 |  | note | TEST REQUIRED - Confirm construction set-out and drawings align with quantities provided in schedule of quantities
label | 74d565bf-f888-595d-afa3-87cd23977fb3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - After construction set-out, prior to commencement of physical works.
label | e17be456-21b9-5bf7-b4cc-abf47117ccdb |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 01a2ef17-eeb9-5023-a7fa-ffe440522d34 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint-status |  |  | checkpoint | 1.6 - Existing Pavement Walkover
label | 87cd31f6-55c8-5187-9eb5-a8d8cdd4cb3d |  | note | SPECIFICATION REFERENCE - NTP
label | e79fe622-fdfc-589e-b342-8d2918702025 |  | note | TEST REQUIRED - Visual Inspection of existing pavement
label | f7762db7-6a7e-5aa2-a3f9-a747386401d9 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS -
label | 264fa8b2-712f-5fd5-b381-aa25fc1a8a00 |  | note | • Prior to ripping seal construction. Site walkover between WestLink Delivery Manager and Construction Project Manager to identify and agree any isolated treatments required in existing pavement to normalise strength.
label | 59f7fe7e-e6eb-528e-a439-138fc2fe86b6 |  | note | • Min 24hr notice to be given prior to inspection.
label | 86ac56af-3b08-5580-8886-ab3ba218dc7b |  | note | TASK ASSIGNED TO - Construction Project Manager
label | c8c3d7aa-af5d-55cb-bfb5-41b00d9d2967 |  | note | MEASURING DEVICES OR METHOD - Eye, spray paint, mark-up on drawings
label | d288dcce-89c5-516e-a822-555d8f364978 |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
label | 5bbbf63e-84d5-57d4-b81d-3b4a2d9c9628 |  | note | QUALITY DOCUMENTATION - Mark-up on drawings
checkpoint-group |  |  | section | 2.0 - MILLED SURFACE CONSTRUCTION (IN TIE IN AREAS)
checkpoint-status |  |  | checkpoint | 2.1 - Finished Level
label | 90e76620-edbd-592b-8ecd-11d2bfb2eaa9 |  | note | SPECIFICATION REFERENCE - TNZ F/1 11.2.2
label | 9b55ae87-5799-5fbc-8c24-d8034f772a9f |  | note | TEST REQUIRED - String line or equivalent
label | 48b9280a-cb62-5c4e-8f47-26702b99c2ad |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side, min 3 measurements across lane = 147 Measurements
label | 9d6b8145-6a10-5d23-8e6f-33fb64a45590 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 2d88100b-0113-5334-869b-79016cc38c00 |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | 4c719e5b-767b-5f76-96c2-505723b09ac9 |  | note | ACCEPTANCE CRITERIA - +0mm / -30mm
label | ef89b83d-2c9e-5b02-916b-4151a046a68e |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 2.2 - Finished Level (post milled)
label | 5ed9e17e-edb7-5215-ae47-b0feb1550169 |  | note | TEST REQUIRED - Visual inspection of milled surface
label | b6ab7e46-1785-53b8-b030-9d585f3b4cf0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS -
label | de58ae45-65fc-539b-ab97-39481f7537e1 |  | note | • Site walkover between WestLink Delivery Manager and Construction Project Manager to ensure milled surface acceptability and compliance.
label | f4fcb43b-fd90-5ceb-b32e-b8a4dbb52e92 |  | note | • Min 24hr notice to be given prior to
label | 8e675a82-0c60-53f2-b7ea-4c6a46c5e8ed |  | note | TASK ASSIGNED TO - Construction Project Manager
label | 58106729-6efd-5cfe-a2e5-d7ff2fb0cb56 |  | note | MEASURING DEVICES OR METHOD - Visual inspection
label | eb21b8c1-071b-536a-bbc6-5e259fc48bcb |  | note | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager
label | 39c6b04e-c6c5-5e03-8e68-0ee00836eb6d |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied
checkpoint-status |  |  | checkpoint | 2.3 - Compaction
label | a55598d1-6241-5928-bf70-38bf6a564cb2 |  | note | SPECIFICATION REFERENCE - TNZ F/1 10.5.1
label | 99317257-fdd3-5191-b732-5d0b8e4b215f |  | note | TEST REQUIRED - Proof Roll
label | e69ded2c-4441-5bea-a8a8-4e54b7ea2237 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 100% coverage
label | 4675be4d-453b-58a6-a4cd-afa1cbaf0527 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | c72573dc-b6ea-5fce-8d8d-b4e8c9e63d76 |  | note | MEASURING DEVICES OR METHOD - Smooth wheel roller with min loading 6259 kg/m width or large miller
label | 4278ee99-c7bd-5f93-b587-0762b495e6de |  | note | ACCEPTANCE CRITERIA - ≤ 5mm
label | 03180a24-e9d7-5668-9f32-eb743c8cfb8e |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-group |  |  | section | 3.0 - BASECOURSE LAYER MATERIAL TESTING - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | 3.1 - Crushing Strength
label | 285bb64b-558c-5ec3-ac82-267df6900929 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.1
label | b8c840ef-ff0d-528e-b8bc-766c753beac5 |  | note | TEST REQUIRED - Crushing Resistance Test
label | 9736b78c-90ed-5423-91a6-fe5812f5a005 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | f5c9db30-e0ba-5c4f-a467-fa8dfc653f76 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | fd4c791e-7a15-5f96-b320-836b20433e0d |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.10
label | ae26ad61-31aa-53a0-b426-df70d31e612f |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 130 KN load
label | 3f116a49-f8a8-50bc-b559-d1016c94ead5 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 3.2 - Weathering Quality
label | 11694627-d0c7-54d0-8b8d-1324649dfe73 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.2
label | f6203ada-f08d-52ec-8302-e4db70fc2517 |  | note | TEST REQUIRED - Weathering Quality Index Test
label | 07709774-b958-5873-9c4d-5dd3174a0ca3 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 9d7eed86-986d-5ba5-b8bc-6258df7bab8d |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 8eebb7f5-9423-550f-82bf-8d13961a0a65 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.11
label | 2aa5c050-d793-5917-a6a9-26ac50f38184 |  | note | ACCEPTANCE CRITERIA - AA, AB, AC, BA, BB or CA
label | 2cad21eb-5e8b-5d64-b0ca-2c43508e8049 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 3.3 - Soaked CBR
label | 0f5e0ffa-22f0-51ab-9694-e22d18286e82 |  | note | SPECIFICATION REFERENCE - TNZ M/4 3.3.3
label | 1206aa10-85be-52d5-8d4c-d927d6aaf898 |  | note | TEST REQUIRED - Remoulded soaked CBR
label | e7a80d33-934f-5ab8-b344-8ebd91f87d3d |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | 03cf5c38-8505-5c90-a7d7-9a7cc9f9dfe6 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 8e7d245b-0b01-5833-8430-14778ea76a31 |  | note | MEASURING DEVICES OR METHOD -
label | 40048089-ef53-528b-a18d-c5e4b6bd4852 |  | note | • Compaction to NZS 4402: 1986 Test 4.1.3 at OMC.
label | a256e34a-6a7d-57f0-86b3-87c4bd1d71dd |  | note | • CBR testing to NZS 4407 : 1981 Test 3.15
label | 2e53bd25-464c-5c31-89e5-da013acb61c2 |  | note | ACCEPTANCE CRITERIA - ≥ 80%
label | dbfea0e9-777e-57c7-bdaf-5ad1393f91c7 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 3.4 - Sand equivalent
label | 09b6050f-84a1-5830-a8a2-2d12244806bc |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.1.1
label | 6894234f-d1ce-578d-a4a8-fb3e70e83a4c |  | note | TEST REQUIRED - Sand equivalent
label | 37f6fd52-62bb-5fbb-9530-c4d68e6e7f11 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS -
label | 5895c467-be1d-5db1-84c7-09415619ce62 |  | note | • 0-400m3=2 tests;
label | a7aea9eb-730c-543f-ab21-bbda379d5fa3 |  | note | • 400-1500m3=3 tests;
label | 61768e92-23ff-533d-b47d-6a1a4b256102 |  | note | • 1500- 4000m3=4 tests;
label | 914b809f-dd26-530c-ac0a-b4bc5dc01f20 |  | note | • >4000m3=1 test/1000m3
label | a0a9240e-ed59-5f3a-9fbd-18ebfe763382 |  | note | • 3 Tests
label | 9e5d9947-2d81-5ab7-a9de-984bc359726a |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 038131a7-e255-51f7-9770-2ecfec53b029 |  | note | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | 4a0928df-e750-5d75-9f1d-7e69e68dec65 |  | note | ACCEPTANCE CRITERIA - ≥ 40
label | e8515476-ac58-5e44-bba3-85e54ed219e8 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 3.5 - Broken Faces Content
label | 8922590f-af7e-5d52-b6aa-0bbad5da3abb |  | note | SPECIFICATION REFERENCE - TNZ M/4 4.2.2
label | d4660db4-3937-5122-8674-dcfb7e286cda |  | note | TEST REQUIRED - Broken face content
label | d238ac7d-b3dc-5536-9ce6-5ae58d9c8ffa |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS -
label | 999ce258-4eb4-506d-bc4b-cd94853cdbbb |  | note | • 0-400m3=2 tests;
label | ea35efba-32ab-5911-84bf-868838dae02c |  | note | • 400-1500m3=3 tests;
label | 34dd1860-38bc-5309-a7cc-810b02a127a5 |  | note | • 1500- 4000m3=4 tests;
label | ced9a941-c03e-5592-a532-ec9b515b9889 |  | note | • >4000m3=1 test/1000m3
label | 768c47f8-3cb1-5832-86e6-64746172c0d0 |  | note | • 3 Tests. n.b. not required if sourced from 100% crushed rock quarry
label | 86baab58-8bca-5438-aa92-481aac12d000 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 8921c27d-c685-5901-a332-b6584e60dc9f |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.14
label | 980b9622-9477-583e-8035-9fafa5ec23a7 |  | note | ACCEPTANCE CRITERIA - ≥ 70%
label | 2e67b700-9e29-5e04-953b-eb845482ea6c |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 3.6 - Particle size distribution
label | fc3e2fba-6b9d-5d07-9cb1-91b9e3a748a4 |  | note | SPECIFICATION REFERENCE - Design
label | 62b72ae1-a47c-52f3-9740-54de3b432246 |  | note | TEST REQUIRED - Wet sieving test
label | e4b185bc-a790-5fff-b59d-e988bb40bb15 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS -
label | 249b268c-8ac1-575e-bb04-05dbde8d1af1 |  | note | • 0-400m3=2 tests;
label | 5f413ec3-903f-5cbb-8ab3-7dc9e66a3e4d |  | note | • 400-1500m3=3 tests;
label | 4a2afe1f-8618-5dc7-be62-1e2ed23fdfd1 |  | note | • 1500- 4000m3=4 tests;
label | bd79795b-d597-54f8-ac1d-b8cf5690d427 |  | note | • >4000m3=1 test/1000m3
label | ada1eb93-a55c-5bc4-9e53-22496337fa35 |  | note | • 3 Tests (1 test must be from same sample as MDD/OMC test)
label | c6fa6f89-68f9-5b9d-b954-e288ab46e5c1 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 0f2cb93b-f9b9-5549-b56b-51172ad13bfc |  | note | MEASURING DEVICES OR METHOD - NZS4407 4407 : 1991, Test 3.8.1
label | 52e7ea4a-eb04-5c06-b024-e9e3a50ff76c |  | note | ACCEPTANCE CRITERIA -
label | f07d979d-989f-542f-a904-41990a1a80b5 |  | note | • 100% passing 37.5mm
label | 0c2d30e4-1c8b-5ce6-b23f-3ae0cf1f7b11 |  | note | • 66 - 81% passing 19mm
label | 2ea82362-300e-5e00-b73b-8535cc32897c |  | note | • 43 - 57 passing 9.5mm
label | 283c374d-2446-512e-9858-9617880a2024 |  | note | • 28 - 43 passing 4.75mm
label | 7eba562e-25bc-58ae-9585-6eb4a4fbdb80 |  | note | • 19 - 33 passing 2.36mm
label | 189f5621-23bd-56d4-bb68-9b028eb97de8 |  | note | • 12 - 25 passing 1.18mm
label | 7c79a57f-e6af-560f-8b9f-8fb86437995b |  | note | • 7 - 19 passing 600µm
label | 0150ff7d-4162-556f-bb9d-e1b20e2d4384 |  | note | • 3 - 14 passing 300µm
label | d28aca1e-6554-5e89-9460-ed834c89ea5d |  | note | • 0 - 10 passing 150µm
label | d9ac5536-9eb2-5b78-8e52-9ef6d18947bb |  | note | • 0 - 7 passing 75µm
label | b3f80ed6-efa6-5ca0-bd0c-feb2f89eb4c8 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 3.7 - Solid Density
label | 43265674-d188-59c9-9fea-31f2dd70f693 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | b29128b3-ff09-5c42-b457-793df10de7e3 |  | note | TEST REQUIRED - Solid Density
label | 5853ebdc-4a1e-5149-8476-2e0d644eb97a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 2 tests
label | c198bd6b-3f87-518b-ba2b-e281b898af2a |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d2b62a75-c9bd-5646-b1bb-31d508a18ae6 |  | note | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.7
label | b6f3f5a1-95bc-5c13-af55-2a71b8fcc666 |  | note | ACCEPTANCE CRITERIA - report value only
label | f7ec1fc2-bfb2-56b0-ac7f-c305cb6e0921 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 3.8 - Determination of MDD & OWC
label | 0b3480c1-d8c5-5aca-b6bd-d4ff978a8a2a |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | 1d45ff59-059e-5ba8-9dfa-aad2969da2d7 |  | note | TEST REQUIRED - 5 point compaction curve
label | 177f89c2-93cd-5569-9984-70e2e435a302 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 2 tests
label | 0d1d030b-2dbf-510c-895a-3c8457b611d5 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e6b11428-a65c-5a90-8575-bc1ebd9f2df7 |  | note | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.3
label | 04c638ab-44e9-5cc6-b461-8ec0204dd288 |  | note | ACCEPTANCE CRITERIA - report value only
label | 2b9bfc89-1eca-561f-a372-d8a6b4be97c8 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-group |  |  | section | 4.0 - BASECOURSE LAYER CONSTRUCTION - TNZ M/4 AP40
checkpoint-status |  |  | checkpoint | 4.1 - Formation
label | f9bea1ec-4e2a-547d-93d6-cc951cfc88f2 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.7
label | 7ad1e2bb-604b-56fd-8663-c59cfbd24139 |  | note | TEST REQUIRED - 3m straight edge or approved equivalent
label | 09fcf65b-3799-51b7-82f8-ccc2487d249e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 28 Tests
label | 0992f521-a87b-5b23-93dd-5851cc6ac82e |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | ebe20a90-4c8f-5599-8621-6bd5065c8bac |  | note | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | 812ab184-c2af-5b23-9698-88b753eeef84 |  | note | ACCEPTANCE CRITERIA - +/- 10mm
label | 98ef4994-06e7-53fb-8eca-3e046cac300b |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 4.2 - Finished Level
label | 19e90a54-cbf0-551b-bcec-fa85b1b92063 |  | note | SPECIFICATION REFERENCE - TNZ B/2 5.1
label | b6cd469d-d14b-5b0c-8f5a-92becc4ec005 |  | note | TEST REQUIRED - String line or equivalent
label | 96a12cbf-062a-522b-9765-d3ac8c99f5e1 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 28 Tests
label | 1dd69213-2bf8-54cc-aba9-319a2c414f85 |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 813c537b-eb9b-5ddf-8bfd-74bae6c04f1d |  | note | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | 3369d211-f012-5fc3-b218-511081b66f2c |  | note | ACCEPTANCE CRITERIA - +15mm / -5mm
label | 50364777-98bf-515d-868c-15112bff9a0b |  | note | QUALITY DOCUMENTATION - Inspection checklist
checkpoint-status |  |  | checkpoint | 4.3 - Plateau Density Test
label | 1dfaf018-a8d8-595a-a425-02c8beb27ed2 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.5 (b)
label | a8146429-bcac-54b9-b8c7-e1efdcca2daf |  | note | TEST REQUIRED - Plateau Density Test
label | e8cd622e-48f3-556a-9ae3-335c5fc21ead |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test minimum
label | 3f124d47-b67c-587b-b375-b18124b32ee4 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | c515c810-0dbb-58aa-b437-bd688644f987 |  | note | MEASURING DEVICES OR METHOD - NDM
label | 0509b7ec-66ea-53a4-81f9-3339a3aa0396 |  | note | ACCEPTANCE CRITERIA - report value only
label | 1c121fcf-98df-5e58-8017-8301c5a8b92d |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 4.4 - Compaction
label | ad3db6d3-34e5-594b-86d6-0712d3c87f86 |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.6
label | 51b433e2-a3d0-5f7d-b3db-689638d73b04 |  | note | TEST REQUIRED - NDM
label | 30d474bd-d016-53aa-b07b-97a54d900db8 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 10 tests
label | ed0a9be0-a123-5bb9-be90-00d92fa6a629 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 7f5bd814-c76b-518e-afb7-657375b4d13f |  | note | MEASURING DEVICES OR METHOD - NDM
label | d1c42e22-892b-512d-bfb7-de1919a5fd64 |  | note | ACCEPTANCE CRITERIA - Mean ≥ 98% MDD, Min ≥ 95%, Total voids ≤ 20%
label | d7817aca-823c-55ed-8181-e372d2d37e6e |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 4.5 - Degree of Saturation
label | 5feed54f-e0bc-54bb-a76a-df6af67cbdce |  | note | SPECIFICATION REFERENCE - TNZ B/2 12
label | 41e322d9-4f01-5015-b418-5dcc941bf817 |  | note | TEST REQUIRED - NDM
label | 1ebaa8ee-35f3-58a2-9f58-b46fe999a7f4 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 10 tests
label | 9777ef79-00eb-538b-9adb-a20d97914fc9 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | cfd519ad-47f4-51cc-9c19-91bde1beea40 |  | note | MEASURING DEVICES OR METHOD - NDM
label | dfd3df3d-c6eb-583b-9ecf-d0e66ae0a56c |  | note | ACCEPTANCE CRITERIA - < 60% (or 80% on consultation with the pavement designer)
label | 059b5726-dfd9-564b-860a-baa53f2a9700 |  | note | QUALITY DOCUMENTATION - IANZ Report
checkpoint-status |  |  | checkpoint | 4.6 - Surface Finish
label | 011b96ab-90b2-5879-8958-1ab245ab79fa |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | f1db5663-678b-5d3f-8c87-7e468dc7aee9 |  | note | TEST REQUIRED - Visual Inspection
label | 112ddaef-969e-5ef7-b6d4-2f6d0caaa29e |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale. Min 24hr notice to be given prior to inspection.
label | 382115fa-bed6-5fbb-a77e-4fba6354ab7b |  | note | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | 9b81afad-88a4-514f-9b00-224833bc499e |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | 043a16f7-8c3e-56d3-8aea-7900411e9687 |  | note | ACCEPTANCE CRITERIA -
label | 0ecd9e28-90e2-52d2-83a1-fab85c600a48 |  | note | • The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | 0611cec1-f35c-5011-99ea-887d31e2a922 |  | note | ○ The large aggregate is
label | 95946748-0ac0-5412-bc24-fd898643817b |  | note | ○ exposed to the surface;
label | 3c7f2f60-5723-5482-aa0c-8856e8b26191 |  | note | ○ held in place with a matrix of smaller aggregates
label | 9350f658-c3fc-50b7-aa9b-a89fb4befe83 |  | note | ○ The smaller aggregate is held firmly in place by fine material;
label | 74219fec-605e-5426-a443-4ec78ab0658f |  | note | ○ The matrix does not displace under normal trafficking or sweeping.
label | a5d2b81a-0cd6-5247-b1e3-a585a5c50777 |  | note | • The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 108b2e9b-4bc7-56b5-bf47-cab94e2a9e3a |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-status |  |  | checkpoint | 4.7 - Ride Quality
label | 6398dcf6-5972-5498-85a6-825f2e4e7761 |  | note | SPECIFICATION REFERENCE - Internal measure
label | 60528650-68cf-5e16-9b68-858565b1c9c5 |  | note | TEST REQUIRED - Ride quality test to AG:AM/T002
label | fe9c1e4d-d80f-5815-9d7b-9c667ba99e66 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Within 12 months of first coat seal
label | c9bf62b1-f86c-5d5b-9ff9-60fabc6f2525 |  | note | TASK ASSIGNED TO - Either by pavement subcontractor or by Westlink Asset Management team from latest HSD survey
label | df69ff00-f25e-509c-a476-96052b940cb9 |  | note | MEASURING DEVICES OR METHOD - inertial laser profiler or response-type roughness meter
label | e4c43d87-7e15-52e7-9ea7-b1b9704d52de |  | note | ACCEPTANCE CRITERIA - no 100m moving average > 60 counts
label | ddde0c7c-cc4a-57bd-bf21-c2b7977e7c65 |  | note | QUALITY DOCUMENTATION - Certified test report
checkpoint-group |  |  | section | 5.0 - BITUMEN - TO GAIN APPROVAL
checkpoint-status |  |  | checkpoint | 5.1 - Penetration
label | 2b1ce6cd-a2aa-527e-bd5b-7749cbf813b7 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | ba9c42c2-f57e-53bf-8b8a-2bc2eaf242f5 |  | note | TEST REQUIRED - Penetration at 25°C, 100g, five seconds
label | b2a4a453-2463-5712-9856-293d866b3436 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | c6037f60-08b0-50d4-9d82-9b6b900eeea4 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 3f6f5336-3357-5cbc-8b84-5d211af6d713 |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | 5590bb9c-cdf5-5110-8f37-cdf21758e401 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 5.2 - Viscosity
label | 065ae696-fd40-5da5-8006-0d42ed01e80e |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 28bbdee6-b38d-53af-a2c0-0792469ee64c |  | note | TEST REQUIRED - Viscosity PaS at 60°C
label | c7b78966-805f-5d6d-a3c9-e4303067f6d5 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | a9abffcd-8f5c-5272-a591-91a561cc1998 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 8b08652e-417f-5652-9268-9de28a149d98 |  | note | MEASURING DEVICES OR METHOD - AS 2341.2 or ASM D2171
label | 2a1f4a7c-539f-530c-ae81-2188a29f357b |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 5.3 -
label | fc9b4843-0a7a-5589-ae01-fb2b9ecca2cb |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 0687a600-0319-535c-a0f1-fd48351256ba |  | note | TEST REQUIRED - Viscosity mm2/s at 135°C
label | 19ceaea4-aa03-5130-a6ba-d3dae88032f5 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | b329e10c-4a01-5ace-9755-f563c3ab0334 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 63691a48-ab0f-5767-8af7-85bb5d34b7be |  | note | MEASURING DEVICES OR METHOD - AS 2341.3 or ASM D2170
label | 38a52ac6-2b02-596e-bce2-03a32d5224b5 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 5.4 - Flash Point
label | bd0b597f-68da-5b32-bb6b-ffa509f7bba1 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 23626205-8adf-5798-a51e-0e8835d192be |  | note | TEST REQUIRED - Flash point (Cleveland open cup), °C
label | 15ec3f0c-0a4e-5b5e-98be-4aff6a76aff7 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 6ccf4af0-8156-59ff-b470-a3139dba6e3b |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 435df66f-cedb-55bb-bc7c-02d4ea063209 |  | note | MEASURING DEVICES OR METHOD - ASTM D92
label | d6bb3f31-2af0-5b38-9bd2-683a0e78ba67 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint-status |  |  | checkpoint | 5.5 - Solubility
label | 1570b19f-d6ec-5e39-b42b-84c68272b919 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 2574f192-875c-54b2-a151-0d948dd1a764 |  | note | TEST REQUIRED - Solubility in Trichloroethylene, % or Solubility in Toluene, %
label | c12635d3-299d-5c0f-b5bc-6888636a591c |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | b8d2e448-8c96-506a-8704-47ce46fc2f1c |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | d0a5d4cf-0c40-5350-95d1-6a2de7ad8209 |  | note | MEASURING DEVICES OR METHOD - ASTM D2042, AS 2341.8
label | 19cf77a9-9b07-50ac-beff-6ba03ee12391 |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | a6aad24d-d217-5c3d-b174-f2ec78ef5e13 |  | note | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 5.6 - Rolling Thin Film
label | 2496321c-8305-52da-8291-8b65d290ef12 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | e87ebd35-1c2a-5f05-baa2-ad87626e4cc8 |  | note | TEST REQUIRED - Rolling Thin Film Oven Test
label | ec47f020-9e9b-58d9-a171-32deea3cc1cd |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 0fe352db-e7b4-5d72-87a3-99fca8f75410 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 8f4144f2-c852-54d1-8a26-78c790e8452a |  | note | MEASURING DEVICES OR METHOD - ASTM D2872 or AS 2341.10
label | 368985a7-307c-57db-afce-15786b1f6e7f |  | note | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 5.7 - Penetration
label | a8398be0-da69-5974-96d4-ee14925d5b0d |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | d6a1cdf0-c1c5-5704-b518-d59164487626 |  | note | TEST REQUIRED - Penetration of residue, at 25°C, 100g, five seconds, % of original
label | 23cafae6-70a5-5c50-81b9-2bc417853c80 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 683685cc-dd79-5eb4-a69a-065d5ec86baa |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | fdacee67-fc6a-53ed-a09b-dd12dbe13146 |  | note | MEASURING DEVICES OR METHOD - ASTM D5
label | 6dc703c4-f467-5769-9f8f-be583b66764d |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | 6a6e0a40-3d3a-5371-9f1e-724de6cfbadd |  | note | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint-status |  |  | checkpoint | 5.8 - Ductility
label | b6cece44-eaa6-5af3-9641-a8d024619785 |  | note | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | 57a2a92d-b800-5f9c-aee8-c4b485becda7 |  | note | TEST REQUIRED - Ductility of residue, at 25°C, (metres)
label | 8a27068f-53eb-5d9e-b3df-00645aee1518 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | 4aee4b98-e3df-5274-9c41-0e3963214cb4 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 56db0c67-e3ca-5fb5-996d-d2ea333417f2 |  | note | MEASURING DEVICES OR METHOD - ASTM D113
label | edc5a9b3-28fe-5705-880e-698be854fb1c |  | note | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | 03ad5a65-5e55-533c-a995-3c815ffef24b |  | note | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint-group |  |  | section | 6.0 - SEALING CHIP MATERIAL TESTING
checkpoint-status |  |  | checkpoint | 6.1 - Crushing Strength
label | 4e64d6ca-20f2-503d-b8ea-16d73098418f |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.2
label | ad067325-0266-5406-b453-4f8fc6d18907 |  | note | TEST REQUIRED - Crushing Resistance Test
label | d6ef7489-f6b7-5451-9771-9d4f4858a1df |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality
label | 1aeace1c-c7d9-513b-ba35-39973a216856 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 6d83ef6a-59c3-57d2-b5fd-994c5b207842 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.10
label | 0640fde5-c261-558b-a068-4b57a9e0c354 |  | note | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 230 KN load
label | ec24ab67-4866-5781-8798-d462d784e2e9 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 6.2 - Weak Particles Test
label | 66b8a46d-dd5d-5c75-8709-069901be2045 |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.4
label | 5c9d2032-53d0-5500-8947-03dd792b8ff4 |  | note | TEST REQUIRED - Australian Weak Particles Test
label | c7e0b57b-dfa2-5fb7-b953-2cde4bf58ca8 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Only undertaken in cases of dispute
label | 97c4f6aa-313d-5851-a341-7ca1e3eee131 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | e3499521-faac-5939-9a30-703dfa269f06 |  | note | MEASURING DEVICES OR METHOD - AS 1141.32-1995
label | 61485efd-9c7d-582a-9bcd-2a72e2158264 |  | note | ACCEPTANCE CRITERIA - Maximum of 1%
label | d0f6a404-c74c-59dc-b647-d72206dace0a |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 6.3 - Polished Stone Value
label | 7c110f4d-280f-5c34-80e2-c71f432f5b5e |  | note | SPECIFICATION REFERENCE - TNZ M/6 3.5
label | 6d9ba1a1-825e-5590-80d9-b60cc9333dba |  | note | TEST REQUIRED - Polished Stone Value Test
label | c8aa480f-a359-5a1a-8134-bfb5c3a7dae5 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality
label | 1737cfc3-227c-5cbf-86b4-7b5888a847ac |  | note | TASK ASSIGNED TO - Accredited PSV Testing Agency
label | 1ea5295f-f925-541d-bfe6-2feac79a9888 |  | note | MEASURING DEVICES OR METHOD - BS 812: Part 114
label | d0a28efc-4226-569f-ac3b-b32bc081b633 |  | note | ACCEPTANCE CRITERIA - PSV Required = 43
label | eaf258b9-ac02-5413-93ae-d66062e3ee87 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 6.4 - Cleanliness
label | 2cbf5a8c-3391-549d-9ba8-02ff68b58318 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.1
label | 6e8471d2-c07d-5244-ba3d-b2e2b8a2f5c0 |  | note | TEST REQUIRED - Cleanliness Test
label | 3ea4d1cd-7c30-5d3c-8a11-7b085a7eec06 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 1ef6f157-8168-58b0-9dd5-d146e8922b5d |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | b56a5cf2-6c7d-5fd9-ab2c-f5712d876ea0 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | 255b8785-14a4-5bad-8012-d7eaef72d8eb |  | note | ACCEPTANCE CRITERIA -
label | d12f14bd-4d9a-5d87-92ba-9d297f0ea1fb |  | note | • Grade 2 - 89 min
label | d71f755d-9ce8-5932-9b77-c9c1510976f4 |  | note | • Grade 3 - 87 min
label | 5749f0d5-4caa-5e14-a684-f0d3afbb6884 |  | note | • Grade 4 - 85 min
label | d7392858-ce9b-5786-a852-e802dc41c134 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 6.5 - Size & Shape
label | 19d2e479-40cf-594c-8840-1a3ae03e6934 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | bd93daf5-101a-5da3-bd1e-1071e70cdb84 |  | note | TEST REQUIRED - Size & Shape
label | 45dac549-b9e2-5acf-aa71-db96f4996d82 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 2729dcda-0699-5a64-9c1a-c67ea81b1d12 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 7bdf09f3-7330-5760-892d-f3a4311633c9 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.13
label | 763dd3f1-859f-5e98-b545-c81e59469095 |  | note | ACCEPTANCE CRITERIA -
label | 945a24aa-2ecc-5b25-bb7f-8f868e8ca732 |  | note | • Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD
label | 11beef8d-0417-5487-87b5-378584079ae9 |  | note | • Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD
label | f630b253-4b78-5cc0-9257-432dc46b6c27 |  | note | • Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD
label | d35dd955-242a-579f-ad37-839050ee17cb |  | note | • 1.1% passing 4.75mm
label | 6187e2b5-3b9a-5b90-8442-ec99d6623155 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 6.6 - Broken Faces
label | e129aa4d-d0dc-5f97-a583-422aa46e43f8 |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | 63de384d-9d24-5bc2-ba40-b14623673754 |  | note | TEST REQUIRED - Broken Faces Test
label | 86c07d50-a08c-517a-9782-198aeea934e0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | be3855e5-6f27-5b2b-97e9-4a90b6440d79 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 9e2bfe15-88ca-5681-84fc-41091564c3c8 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.14
label | 06525da2-0396-50d3-b430-f59903d1fd9c |  | note | ACCEPTANCE CRITERIA - 98% with minimum two broken faces
label | 9a161dfa-29ab-526a-a994-52e7748b94b4 |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-status |  |  | checkpoint | 6.7 - Grading
label | b3197621-9319-5a22-8006-c77c88a27bad |  | note | SPECIFICATION REFERENCE - TNZ M/6 4.2.2
label | e578eb18-a450-5f1d-b7b5-b6046d50749c |  | note | TEST REQUIRED - Grading
label | 44ad0ea7-8683-5750-8200-2ad46f048735 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | 8050e982-e5e7-5895-8db1-ab2df63eec48 |  | note | TASK ASSIGNED TO - IANZ accredited laboratory
label | 7855f546-208d-5b97-9173-d20eeeab6967 |  | note | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.8
label | bc3697eb-3a30-5e06-89c6-85315e075b8f |  | note | ACCEPTANCE CRITERIA -
label | c977150c-da45-5265-802f-92e3a8450c1a |  | note | • Grade 5
label | 5453c5d5-797a-5324-a42e-04362e3617fd |  | note | ○ 100% passing 13.2mm
label | e8b4d5f1-e5db-5ce2-be2b-3e89d74a6cb9 |  | note | ○ 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300µm
label | 5ccd7fc5-3c1e-5a1e-8d85-0bad83072e77 |  | note | • Grade 6
label | 6d9f3649-c019-57c0-affc-918119c041e9 |  | note | ○ 100% passing 9.5mm
label | 3f60c695-47cf-5f36-afcd-4dff10de5841 |  | note | ○ 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300µm
label | c1b515f8-312e-5d54-9b50-6f2e62fdbf7d |  | note | QUALITY DOCUMENTATION - IANZ Test report
checkpoint-group |  |  | section | 7.0 - SEAL DESIGN
checkpoint-status |  |  | checkpoint | 7.1 - Seal design
label | f1e9dc05-c938-59b0-9cd7-2e5e04badfb0 |  | note | SPECIFICATION REFERENCE - TNZ P/3
label | dee9c87a-8699-5079-b3f3-19037bd2124c |  | note | TEST REQUIRED - Seal design
label | 343f267f-22a9-5442-b56b-a7f493e81403 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | 4749dd6d-1c27-5c7b-b013-5317f8f8ac9d |  | note | TASK ASSIGNED TO - Contractor's Quality Manager
label | 1fcf12ca-7f91-5e27-9c98-729dea7b0944 |  | note | MEASURING DEVICES OR METHOD - report only
label | 126351c1-bc2d-5be0-83b7-ccfc553b12da |  | note | ACCEPTANCE CRITERIA - report only
label | f6695570-e22b-5764-b7a0-f324b38dd883 |  | note | QUALITY DOCUMENTATION - Seal design
checkpoint-status |  |  | checkpoint | 7.2 - Seal design approval
label | 2c0893b3-b6ef-5a84-9902-07b68a93c80c |  | note | SPECIFICATION REFERENCE - Internal measure
label | 5ca7b17f-99af-5a45-955c-18bc9ba42831 |  | note | TEST REQUIRED - Internal verification
label | 75595f98-78d4-5f25-afd2-63d8870854f0 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | b42c89cc-7811-5a6e-b17b-a1c6cd5844d9 |  | note | TASK ASSIGNED TO - Downer Surfacing Expert
label | 201ae837-9fae-5c62-89d2-5689fc48e97e |  | note | MEASURING DEVICES OR METHOD - report only
label | d772f01a-f823-5353-b1fd-332162c4413c |  | note | ACCEPTANCE CRITERIA - report only
label | 522f00d3-95c2-5e99-ad9c-3c70151d08b8 |  | note | QUALITY DOCUMENTATION - Email from Downer surfacing expert confirming that the treatment selection and seal design has been reviewed to confirm it is fit for purpose
checkpoint-status |  |  | checkpoint | 7.3 - Surface Finish
label | ea94c16d-b1ab-5af3-978f-e15493c794fe |  | note | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | b9fc8ad2-3e17-5282-9330-032b3576d733 |  | note | TEST REQUIRED - Visual Inspection
label | 08e1661d-5ed7-5ad4-8481-370746f7882a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | 973343a4-6066-5cc2-8eab-c8136662c3f2 |  | note | TASK ASSIGNED TO - Sealing subcontractor quality representative
label | 850a0bf0-bc04-5b58-86c6-0891635dc31b |  | note | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | 528191df-9b58-5b62-bc4f-aaba379fdee2 |  | note | ACCEPTANCE CRITERIA -
label | 193db903-ef5d-5bb8-8eb8-f53cbb8de343 |  | note | • The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | 344b042d-9b2e-53ac-88ab-2cce797a40c7 |  | note | ○ The large aggregate is
label | e53e43ed-5b08-5c06-82d8-fa2fc2bc7bde |  | note | ○ exposed to the surface;
label | c0ae1c2f-8e5a-58fb-87b7-fdabd3a3df91 |  | note | ○ held in place with a matrix of smaller aggregates
label | 43d65601-0135-5335-bf16-a7fe6ff85586 |  | note | ○ The smaller aggregate is held firmly in place by fine material;
label | 26755e14-e90a-5c4d-b976-17cc3423a043 |  | note | ○ The matrix does not displace under normal trafficking or sweeping.
label | 8edcc0b5-d9f8-57f2-8e4b-3e3718148f40 |  | note | • The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | 6567371f-95e6-5b75-a333-42a64873618f |  | note | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint-group |  |  | section | 8.0 - SEALING RECORDS
checkpoint-status |  |  | checkpoint | 8.1 - Blend sheet
label | 0a5a4612-4eb9-5604-8fc9-801e373ef16b |  | note | SPECIFICATION REFERENCE - Client request
label | f98fe109-3b75-5b75-a92e-a34cd0e8127a |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | b17f8d3e-9c87-506f-b84d-a2b13b7cbe95 |  | note | TASK ASSIGNED TO - Bitumen blending facility
label | 4501ef25-200b-5370-83fd-20e5022d135a |  | note | ACCEPTANCE CRITERIA - Report value only
label | de9aaff2-4e27-5498-8eaf-b9c1700546de |  | note | QUALITY DOCUMENTATION - Blend sheet
checkpoint-status |  |  | checkpoint | 8.2 - Spray sheets
label | d36f2d40-913f-5508-98b7-b950a1928711 |  | note | SPECIFICATION REFERENCE - Client request
label | d2636d1d-03fc-590e-b582-ef64a5e1af32 |  | note | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | e420ace8-d7f4-53e3-87d7-e932ee839eb0 |  | note | TASK ASSIGNED TO - Sealing Manager
label | 5524e5c5-6935-51fa-96bf-8779f3e72bc3 |  | note | ACCEPTANCE CRITERIA - Report value only
label | a49c3155-a2a3-58d4-9adc-4746e4f7d789 |  | note | QUALITY DOCUMENTATION - Spray sheets