## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-009-STR-Bored Piling | itp |  |  |  |  | ITP-009-STR-Bored Piling Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-009-STR-Bored Piling
note | ITP Description: Bored Piling
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): 009-STR
note | Revision Number: 0
note | Revision Date: 11/10/2022
note | ITP created by:
note | ITP approved for use by:
note | 1.1 - Non Dependent
note | Reference Documents:
note | • VicRoads Section 606 July 2017
note | 1.2 - Non Dependent
note | Reference Documents:
note | • VicRoads Section 610 Feb 2020
note | 1.3 - Non Dependent
note | Reference Documents:
note | • VicRoads Section 611 November 2018
note | 1.4 - Non Dependent
note | Reference Documents:
note | • AS2159-2009
note | 1.5 - Non Dependent
note | Reference Documents:
note | • AS3810.1 2018
note | 1.6 - Non Dependent
note | Reference Documents:
note | • AS5100.3-2017
section | Preliminaries - Materials
checkpoint | 2.1 Concrete Mix
note | REFERENCE:
note | 610.07
note | Table 610.071
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Concrete Mix is Registered with VicRoads.
note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 ACRS Certification (for Reinforcement)
note | REFERENCE: 611.05 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Current ACRS certification for materials and for bar processing.
note | • Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once for each supplier, 14 days of award of contract
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
note | REFERENCE: 610.26 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Working Platform certification
note | REFERENCE: -
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.2 Piling Operations Work Procedure
note | REFERENCE: 606.03 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.3 Temporary Steel Casings
note | REFERENCE: 606.03 (b)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, once, prior to use
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.4 Casting Under Water Procedure
note | REFERENCE: 606.06 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | • Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, once, prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.5 Boring With Bentonite or Polymer Fluids
note | REFERENCE: 606.03 (c)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | • Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, once, prior to commencement of boring
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.6 Dynamic Pile Testing Procedure
note | REFERENCE: 606.07 (c)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, prior to testing
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.7 Pre-qualified Pile Testing Consultant
note | REFERENCE: 606.07
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
note | • Details of the consultant to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, two weeks prior to testing
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.8 Reinforcement Welding Specifications & Qualifications
note | REFERENCE:
note | 611.13 (a)
note | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
note | 611.14 (b)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
textbox | Enter: Teambinder Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, once, prior to welding
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-construction Activities
checkpoint | 4.1 IFC Drawings
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to starting Works and at regular intervals
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: All
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.2 Survey Set-out
note | REFERENCE:
note | IFC Drawings
note | 606.08 (a - c)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
note | • Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Surveyor
note | • SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.3 Protection of Adjacent Piles
note | REFERENCE: 606.04
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Pile construction shall not:
note | i. result in damage to adjacent newly cast piles due to ground vibration.
note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SPE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Construction Activities
checkpoint | 5.1 Boring Operations
note | REFERENCE:
note | IFC Drawings
note | 606.03 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
note | • Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
note | • Excavation clean and de-watered (where applicable) for inspection.
note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
note | • Excavated material to be disposed of as appropriate to maintain a clean site.
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Surveyor
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.2 Formwork Extension
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Surveyor
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.3 Inspection of Pile Excavation
note | REFERENCE: 606.05
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
note | • Attach: Geotechnical Field Sheet or Report
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Geotechnical Engineer
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.4 Reinforcement - Placement
note | REFERENCE:
note | IFC Drawings
note | 611.06
note | 611.09
note | 611.10
note | 611.11
note | 611.12
note | 606.06 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
note | • Projecting reinforcement is the correct length and location.
note | • Splice lengths achieve the minimum length and are in contact for this length.
note | • The reinforcement surface condition is free from dirt, debris and damage.
note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Foreman
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.5 Reinforcement - Electrical Continuity
note | REFERENCE:
note | IFC Drawings
note | 610.29 (d)
note | 610.43
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Pile reinforcement cage to be made electrically continuous by:
note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Earthing Engineer
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.6 Cast-in Items
note | REFERENCE:
note | IFC Drawings
note | 610.46 (a), Table 610.462
note | 610.47 (a), Table 610.472
note | AS3810.1 Table 3.3.6.2
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
note | ii. Running dimensions of a group of the above = ±6mm
note | iii. Ducts and conduit location = ±12mm
note | iv. Diameter of ducts and conduits = ±3mm
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Foreman
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.7 Pre-pour Inspection
note | REFERENCE:
note | IFC Drawings
note | 610.18 (a) (ii) & (iii)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
note | • All foreign material has been completely removed from the excavation.
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.8 Weather Conditions & Evaporation Limits
note | REFERENCE:
note | Hot and/or Cold Weather Concreting Procedure
note | 610.17
note | 610.17 (a) & (e)
note | Table 610.171
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
note | • Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Foreman
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.9 Concrete Testing - Sampling Frequency
note | REFERENCE:
note | Site Sampling & Testing Procedure
note | 610.16 (b), Table 610.161
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Concrete cast in one continuous operation to be tested at a frequency as shown below:
note | 0m3 to 10m3 = 1 sample
note | 10m3 to 25m3 = 2 samples
note | 25m3 to 50m3 = 3 samples
note | 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
note | • For each additional 50m3 and additional sample shall be taken.
note | • Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
note | • Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
note | • Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Concrete Tester
note | • Foreman
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
note | REFERENCE: 610.13 (b)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Spread range = 550mm to 750mm
note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
note | • Passability = ≤10mm (aggregate height differential)
note | • Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each sample of Self-compacting Concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Concrete Tester
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
note | REFERENCE: Site Sampling & Testing Procedure 610.16
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Correct quantity of cylinders manufactured per sample.
note | • Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each sample
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Concrete Tester
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
note | REFERENCE:
note | Piling Quality Procedure
note | 610.18 (a) & (b)
note | 610.18 (d) (i)
note | 606.06 (a & b)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
note | • All concrete batches are traceable.
note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
note | • The initial discharge is pumped to waste until a consistent workable mix is discharged.
note | • The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
note | • Record: Required information on the Concrete Pour Record.
note | • Attach: Concrete Pour Record
note | • Attach: Concrete Dockets
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each load
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: SP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Foreman
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: -
textbox | Date Completed:
checkpoint | 5.13 Surface Finishes
note | REFERENCE:
note | IFC Drawings
note | 610.31
note | 610.20
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Surface finish as per IFC drawings.
note | • Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
note | • Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Foreman
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Pile Trimming
note | REFERENCE:
note | IFC Drawings
note | AS2159 Clause 7.2.2 - 3
note | 606.06 (a & b)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage
note | • Any weak or damaged concrete shall be removed back to sound concrete.
note | – – – – – – – – – – – – – – – – –
note | METHOD:
note | • Measure
note | • Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.2 Compressive Strength Test Results
note | REFERENCE:
note | IFC Drawings
note | Table 610.05.051
note | 610.16 (g)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
note | • Attach: Compressive Strength Test Results
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each cylinder
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.3 Pile Integrity Testing
note | REFERENCE:
note | 606.07 (a, d & e)
note | AS2159 Clause 8.8
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
note | • Cross-sectional area = ≥95%
note | • If any test fails, all piles shall be tested.
note | • Attach: Pile Integrity Test Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Testing Consultant
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.4 Static Load Testing
note | REFERENCE:
note | IFC Drawings
note | 606.07 (b, d & e)
note | AS2159 Clause 8.4
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
note | i. Displacement vs Time Graph = linear or decreasing rate of creep
note | ii. Creep rate = <2mm / log cycle of time at the test load
note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
note | • Attach: Static Load Test Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, as shown on the IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Testing Consultant
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.5 Dynamic Pile Testing
note | REFERENCE:
note | 606.07 (c, d & e)
note | AS2159 Clause 8.7
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
note | • Measured Ultimate capacity = ≥ values on IFC drawings
note | • Attach: Dynamic Pile Test Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Testing Consultant
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.6 As-built Survey
note | REFERENCE:
note | IFC Drawings
note | 606.08 (a - c)
note | AS2159 Clause 7.2.2
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The following tolerances apply to piles:
note | i. Pile head plan location = ±75mm
note | ii. Variance from vertical or rake = 1:100
note | iii. Irregularities in straightness = 1:100
note | iv. RL = ±25mm
note | • Attach: Survey As-builts / Survey Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each pile
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | • Surveyor
note | • SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.7 Non-conformance Report (NCR) Closure
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, prior to closure of this lot / element / Work area
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Metropolitan Roads Program Alliance Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP