## Sheet1
Type | Name | Values | Prefix | Postfix
checklist-flat | TST PHRP Testing Stormwater Drainage & Downpipe (Water Test)
checkpoint | Stormwater drainage tested & Downpipe checked off as below
checkpoint-no-status | Test Area
Text | Document section of building stormwater drainage and/or downpipe being tested (eg. grid references or apartment numbers must be added)
Text | Provide overall length of pipe being tested (stormwater drainage and/or downpipe) |  |  | m
Text | Provide size (DN) of stormwater drainage pipe or downpipes being tested |  |  | mm
Checkpoint | Pipe grade is as per IFC shop drawing (show photo with level documenting grade has been achieved)
Checkpoint | Pipe openings and/or inspection opening have been plugged off
Checkpoint | A mark has been placed to show height water level is being tested to
Checkpoint | The stormwater drainage pipe has been filled with water as per section 9.4.1 of AS3500.3.2021
Checkpoint | The internal downpipe been filled with water as per section 9.3.1 of AS3500.3.2021
checkpoint-no-status | Test Phase
Text | Start of test: Note start time and include photo of water level at the start of test
Text | End of test: Note end time and include photo of water level at end of test
Checkpoint | The test has been deemed successful
checkpoint-no-status | Acknowledgement
Text | Name of Richstone Group representative conducting the test
Text | If the head contractor witnessed the test, include their name
bool | Tested sticker has been applied
checklist-flat | TST PHRP Testing Sanitary Drainage & Downpipe (Water Test)
checkpoint | Sewer drainage tested & checked off as below
checkpoint-no-status | Test Area
Text | Document section of building sewer drainage being tested (eg. grid references or apartment numbers must be added)
Text | Provide overall length of pipe being tested |  |  | m
Text | Provide size (DN) of sewer drainage pipe being tested |  |  | mm
Checkpoint | Pipe grade is as per section 6.6.1 of AS3500.2.2021 (show photo with level documenting grade has been achieved)
Checkpoint | Pipe openings and/or inspection opening have been plugged off
Checkpoint | A mark has been placed to show height water level is being tested to
Checkpoint | The sewer drainage pipe has been filled with water as per section 15.2 of AS3500.2.2021
checkpoint-no-status | Test Phase
Text | Start of test: Note start time and include photo of water level at the start of test
Text | End of test: Note end time and include photo of water level at end of test
Checkpoint | The test has been deemed successful
checkpoint-no-status | Acknowledgement
Text | Name of Richstone Group representative conducting the test
Text | If the head contractor witnessed the test, include their name
bool | Tested sticker has been applied