## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP005 - Stormwater Drainage | itp |  |  |  |  | FH-ZU2-QU-ITP005 - Stormwater Drainage - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | ○ using the correct and complete set of drawings
label | ○ all drawings are the latest revision.
label | Reference Documents - Drawings and Aconex Register
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Up to date drawing sets & ITP
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS & WP.
label | Reference Documents - CEMP, TMP, SWMS & WP
label | Inspection/Test Method - Verify
label | Record of conformity - Site and Office Inspection
label | HP*
label | Responsibility - Project/Site Engineer/Supervisor
date | Date Completed:
checkpoint | 1.3 - Excavation Permit
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Excavation Permit issued by APAM obtained prior to any excavation on site.
label | Reference Documents - Excavation Permit
label | Inspection/Test Method - Verify
label | Record of conformity - Proof of signed permit
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 2.0 - Stormwater Products and Materials
checkpoint | 2.1 - Drainage Pipes (RCPs)
label | Frequency - Prior to commencem ent of works
label | Acceptance Criteria - Drainage pipes supplied in accordance with AS4058. Material submission approval.
label | Reference Documents - CL16.6.1
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Pipe Support Cradles
label | Frequency - Prior to commencem ent of works
label | Acceptance Criteria - Pipe to sit on firm foundation with pipe support cradles. Material submission/ Shop drawing submission.
label | Reference Documents - Cl16.5.6.1
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.3 - Encasement Material
label | Frequency - Prior to commencem ent of works
label | Acceptance Criteria - Encasement Material to be 5Mpa lean mix concrete for all RCP’s. Material submission approval.
label | Reference Documents - Cl16.5.6.1 & 16.6.2.2 & Tender Clarificatio ns #36
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Backfill Material
label | Frequency - Prior to commencem ent of works
label | Acceptance Criteria - Backfill material to be 6% cement stabilised sand to pavement formation level. Material submission approval.
label | Reference Documents - Cl16.5.6 & 16.6.2.2
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex Ref
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Stormwater Delivery
checkpoint | 3.1 - RCP Delivery
label | Frequency - Each Delivery
label | Acceptance Criteria - Drainage pipes supplied and delivered as per approved Material submission. Manufacturer’s conformance report.
label | Reference Documents - CL16.6.1 & AS4058
label | Inspection/Test Method - Verify
label | Record of conformity - Order Acceptance Form
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 4.0 - Construction Activities
checkpoint | 4.1 - Survey Setout
label | Frequency - Prior to construction and each lot
label | Acceptance Criteria - Set out the stormwater drainage as shown on the Drawings to identify the locations, lengths and levels at outlets and inlets of pipes. This constitutes a Hold Point.
label | Reference Documents - Cl16.7.1
label | Inspection/Test Method - Survey
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Excavation
label | Frequency - Each Lot
label | Acceptance Criteria - All excavation to be performed to the minimum depths, widths and batter slopes as shown on the Drawings, regardless of the type of material.
label | ○ Trench excavation is to commence at the downstream end, where practical.
label | ○ The width of trench to be such that the horizontal clearance from the outside of the pipe to wall of the trench to be minimum 300mm when under the runway and taxiway graded strip. Trench width outside of the runway and taxiway graded strip to be the greater of 150mm and D/6.
label | ○ Subgrade Inspection to constitute a Hold Point.
label | Reference Documents - Cl16.8.1 & Cl16.6.2.2
label | Inspection/Test Method - Verify
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Project/Site Engineer Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Site Dewatering
label | Frequency - Each Lot
label | Acceptance Criteria - Excavations are to be kept free from water during construction and backfilling and provide pumps, well-points or other equipment as necessary.
label | ○ Any temporary works to be designed such that flooding upstream of the diversion does not occur. This constitutes a Hold Point.
label | Reference Documents - Cl16.8.4
label | Inspection/Test Method - Site Inspection
label | Record of conformity - Aconex Ref
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Confirm Ground Conditions
label | Frequency - Each Drainage Line
label | Acceptance Criteria - 1 x DCP test to be undertaken per drainage line to confirm ground conditions.
label | ○ Contractor to notify the Contract Administrator of any area of the foundation which contains material that is inadequate to support the proposed drainage structure.
label | ○ Inadequate material is deemed to have a bearing pressure less than 130kPa, equivalent to 4 DCP blows per 100mm, per note 4 on drawing ZULU-BECA-012-DWG-07102.
label | ○ Inadequate foundation material is to be replaced with a layer of coarse crushed aggregate compacted to 95% relative standard compaction to AS1289 Section 5.5.1 over a geotextile Bidim A29 or approved equivalent.
label | Reference Documents - Cl16.8.2 & Tender Clarificatio n 179
label | Inspection/Test Method - Site Inspection
label | Record of conformity - DCP, Test Results
label | TP
label | Responsibility - Project/Site Engineer/Beca
date | Date Completed:
checkpoint | 4.5 - Bedding
label | Frequency - Each Lot
label | Acceptance Criteria - Bedding material/ subgrade to be prepared for laying the pipes. Pipe support cradles to be placed on firm bedding. This constitutes a Witness Point.
label | Reference Documents - Cl.16.6.2.1
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
checkpoint | 4.6 - Laying of Pipes (Sample)
label | Frequency - First Lot
label | Acceptance Criteria - Initial sample 20m length of concrete pipeline to be laid and approved by the Contract Administrator for line and level before continuing construction of pipe network, Hold Point.
label | Reference Documents - Cl.16.9.1.6
label | Inspection/Test Method - Verify & Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Laying and Jointing of Pipes
label | Frequency - Each Lot
label | Acceptance Criteria - Concrete Pipes to be rigidly supported by approved steel pipe cradle during laying.
label | ○ Pipes to be placed with spigot end facing downstream.
label | ○ Pipes to be laid with the word ‘TOP’ and or lifting holes uppermost. Lifting holes to be plugged after installation.
label | ○ All Concrete Pipes to be checked and subject to the approval of the Contract Administrator prior to commencement of backfilling, Hold Point.
label | Reference Documents - Cl.16.9.1.6
label | Inspection/Test Method - Verify & Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.8 - Survey
label | Frequency - Each Lot
label | Acceptance Criteria - The alignment, level and grade to be checked on the obvert of every third concrete pipe unit.
label | Invert levels at the upstream and downstream ends to be submitted to the Contract Administrator for review.
label | Deviation from Invert Level
label | ○ Maximum deviation from design invert level to not exceed 20mm and not result in zero grade or reversal of grade in any length of concrete pipe.
label | ○ Where the design pipe grade is less than 1%, maximum deviation from pipe socket to pipe socket does not exceed 20 mm.
label | ○ Maximum deviation from design invert level between upstream and downstream structures to not exceed 20mm and not result in zero grade or reversal of grade in any length of concrete pipe.
label | Deviation from Alignment
label | ○ Maximum deviation of the concrete pipe from the alignment shown on the Drawings to not exceed 25mm.
label | Reference Documents - Cl.16.7 & 16.9.1.6
label | Inspection/Test Method - Survey
label | Record of conformity - Survey Report
label | SCP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.9 - Backfill Materials
label | Frequency - Each Lot
label | Acceptance Criteria - RCP’s under Runway and Taxiway Graded Strip
label | ○ 5MPa wet lean mix to 200mm above pipe obvert
label | ○ 6% Cement Stabilised Sand to pavement formation level
label | RCP’s outside Runway and Taxiway Graded Strip
label | ○ 5MPa wet lean mix 150mm above pipe overt completed in stages
label | ○ Site won material completed in 200mm loose layer thickness (maximum) to pavement formation level or 6% stabilised sand
label | Reference Documents - Cl.16.5.6 & IFC Drawings & Tender Clarificatio n #164
label | Inspection/Test Method - Verify and Site Inspection
label | Record of conformity - Delivery Docket and ITP Signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 5.0 - Testing and Inspection
checkpoint | 5.1 - Compaction Requirements (RCPs)
label | Frequency - 1 test per lot.
label | Acceptance Criteria - Concrete Backfill Under Runway and Taxiway Graded Strip
label | ○ 1 compressive strength test for each 50m3 of backfill
label | ○ Concrete Backfill Outside Runway and Taxiway Graded Strip
label | ○ 1 compressive strength test for each 100m3 of backfill
label | ○ Backfill Zone - Outside the Runway and Taxiway Graded Strip
label | ○ Minimum RD of 95% SMDD (1 lot consists of every 50m3 for concrete backfill and every 2nd layer of backfill zone material.)
label | Reference Documents - Cl.16.5.6.3 (c) & Cl.16.9.6
label | Inspection/Test Method - Site Inspection
label | Record of conformity - Test Records
label | TP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 5.2 - Inspection of drainage lines
label | Frequency - Prior to constructing pavement
label | Acceptance Criteria - CCTV inspection of RCPs required at the completion of the works. Submission of CCTV footage to the Contract Administrator for review is a Hold Point.
label | Reference Documents - Cl.16.10.1
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Ref
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: