## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP006 - Subsoil Drainage | itp |  |  |  |  | FH-ZU2-QU-ITP006 - Subsoil Drainage - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | ○ using the correct and complete set of drawings.
label | ○ all drawings are the latest revision.
label | Reference Documents - IFC Drawings
label | Inspection/Test Method - Document Review
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS & WP.
label | Reference Documents - CEMP, TMP, SWMS & WP
label | Inspection/Test Method - Verify
label | Record of conformity - Site and Office Inspection
label | HP*
label | Responsibility - Project/Site Engineer/Supervisor
date | Date Completed:
checkpoint | 1.3 - Excavation Permit
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Excavation Permit issued by APAM obtained prior to any excavation on site.
label | Reference Documents - Approved Permits
label | Inspection/Test Method - Verify
label | Record of conformity - Proof of permit & ITP signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 2.0 - Subsoil Materials
checkpoint | 2.1 - Subsoil Drainage Pipes
label | Frequency - Prior to commencing work
label | Acceptance Criteria - Pavement Subsoils:
label | ○ 100mm Dia slotted with filter fabric (sock) CL1000 SN20.
label | Subsoil Collector Pipes:
label | ○ AGL Carrier Pipe: 80mm Dia PN12 uPVC Non-Perforated Pipe.
label | ○ SSD Carrier Pipe: 150mm Dia PN12 uPVC Non-Perforated Pipe.
label | Reference Documents - Cl.16.5.3, Cl.16.5.4 & IFC Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Order Inspection Checklist
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.2 - Bedding and Backfill
label | Frequency - Prior to commencing work
label | Acceptance Criteria - Subsoil Drain Pipes Under Pavement
label | ○ 100% recycled crushed glass (sand) meeting VicRoads (Section 702) Grade A2 or A3 material or approved equivalent.
label | Subsoil Collector Pipes – Under Pavement
label | ○ Approved 15MPa lean mix.
label | Subsoil Collector Pipes In Grass
label | ○ 100% recycled crushed glass (sand) meeting VicRoads (Section 702) Grade A2 or A3 material or approved equivalent.
label | ○ Excavated Soil
label | Reference Documents - IFC Drawings & VicRoads Section 702
label | Inspection/Test Method - Verify
label | Record of conformity - Visual Inspection & Delivery Docket
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.3 - Geotextile Fabric
label | Frequency - Prior to commencing work
label | Acceptance Criteria - Non-woven type complying with the requirements of VicRoads for first stage filter.
label | Reference Documents - Cl.16.5.8 & VicRoads Section 702
label | Inspection/Test Method - Verify
label | Record of conformity - Visual Inspection & Delivery Docket
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 3.0 - Excavation and Installation
checkpoint | 3.1 - Trench Excavation
label | Frequency - Each Lot
label | Acceptance Criteria - Trenches shall be excavated to the minimum depths, widths and batter slopes as shown on the drawings.
label | Minimum Trench Widths: Subsoil Drain Pipes
label | ○ 300mm total width for the subsoil drain pipe (DN100).
label | Subsoil Collector Pipes
label | ○ Horizontal clearance from the outside of the pipe to the wall of the trench to be minimum of 150mm for all collector pipes (DN80 & DN150 both under pavement and in grassed areas).
label | – Excavated material disposed per approved CEMP.
label | – Completed excavation works shall constitute a Hold Point.
label | Reference Documents - Cl.16.8.1 & IFC Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Geotextile Placement
label | Frequency - Each Lot
label | Acceptance Criteria - Geotextiles in trench drains shall be placed to conform loosely to the shape of the trenches. The approved geotextile must fully envelope the drainage material in the trench with a minimum 150mm lap.
label | ○ Site trial to be undertaken to evaluate the proposed construction process and compaction method, Hold Point.
label | Reference Documents - Cl.16.9.4.2, Cl.16.9.4.5 & IFC Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Bedding
label | Frequency - Each Lot
label | Acceptance Criteria - Bedding for Subsoil Drain Pipes Under Pavement and Subsoil Collector Pipes in Grass
label | ○ Bedding of granular filter material:
label | ○ 100mm for subsoil drain pipes.
label | ○ 75mm for subsoil collector pipes
label | ○ Filter material shall be placed and compacted with minimum disturbance to pipes and in layers no greater than 200mm uncompacted.
label | Reference Documents - Cl.16.9.2 & IFC Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 3.4 - Laying and Jointing of Pipes
label | Frequency - Each Lot
label | Acceptance Criteria - Pipes laid at the depths and lines indicated on the drawings. Where grades are not specified, the bottom of the trenches shall be trimmed to provide no less than 0.5% longitudinal fall.
label | Reference Documents - Cl.16.9.2 & VicRoads Section 702.03, 702.09
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 3.5 - Backfill
label | Frequency - Each Lot
label | Acceptance Criteria - Backfill for Subsoil Drain Pipe (⌀100mm pipe)
label | ○ Granular filter material backfill is to be placed to the underside of the CTB layer.
label | Backfill for Subsoil Collector pipe ⌀150mm Under Pavement
label | ○ 15 MPa lean mix backfill is to be placed to a minimum of 150mm above the pipe crown to underside of pavement formation.
label | ○ Backfill to be completed in two stages to avoid pipe floatation.
label | Backfill for Subsoil Collector pipe ⌀150mm In Grassed Areas
label | ○ Granular filter material is to be placed to a minimum of 150mm above the pipe crown.
label | ○ Excavated soil recompacted in layers not exceeding 200mm loose thickness to underside of topsoil.
label | Backfill for Subsoil Collector pipe ⌀80mm
label | ○ 15MPa lean mix backfill to be placed to be placed to top of 150mm FCR subbase layer
label | ○ Backfill to be completed in two stages to avoid pipe floatation.
label | Reference Documents - Cl.16.9.2, IFC Drawings & Tender Clarification #38
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 3.6 - Subsoil Drain Outlet
label | Frequency - Each Lot
label | Acceptance Criteria - Subsoil outlet point to be located at a drainage pit, pipe end wall or outlet in a fill batter or drain. All subsoil drain outlets shall be fitted with Vermin Guards.
label | Reference Documents - IFC Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 3.7 - Flushout Risers
label | Frequency - As applicable
label | Acceptance Criteria - Cleanouts shall be located at the heads of all subsoil drains and as specified on the Drawings.
label | Reference Documents - Cl.16.9.2 & IFC Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 4.0 - Post Construction
checkpoint | 4.1 - Flushing Test
label | Frequency - Each Lot
label | Acceptance Criteria - Flushing test to be carried out for subsoil pipes to remove material that has entered the pipes during construction and to ensure that the drainage line is free from obstruction. This constitutes a Witness Point.
label | Reference Documents - Tender Clarificati on #33
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.2 - Records
label | Frequency - Each Lot
label | Acceptance Criteria - Levels and alignment recorded in as built documentation.
label | Reference Documents - As built Data
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Correspondence/Asbuilts
label | SCP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: