## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP007 - Precast Drainage Structures | itp |  |  |  |  | FH-ZU2-QU-ITP007 - Precast Drainage Structures - Rev 0
section | 1.0 - Preliminaries
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | ○ using the correct and complete set of drawings.
label | ○ all drawings are the latest revision.
label | Reference Documents - IFC Drawings
label | Inspection/Test Method - Document Review
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS & WP.
label | Reference Documents - CEMP, TMP, SWMS & WP
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Site and Office Inspection
label | HP*
label | Responsibility - Project/Site Engineer/Supervisor
date | Date Completed:
checkpoint | 1.3 - Excavation Permit
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Excavation Permit issued by APAM obtained prior to any excavation on site.
label | Reference Documents - Approved Permits
label | Inspection/Test Method - Verify
label | Record of conformity - Proof of permit & ITP signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 2.0 - Material Approvals
checkpoint | 2.1 - Precast Structures
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Details of the proposed precast drainage pits, headwalls, and culverts to be as specified on the IFC Drawings.
label | ○ Approval of the shop drawings constitutes a Hold Point.
label | ○ Outline of sampling and test program
label | Reference Documents - Cl16.6.1 & Manufacturer’s documents
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - Project/Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Access Cover and Grates
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All Pit covers to conform to AS 3996 and the applicable load class to be as noted on the Drawings. For all drainage pits, pit lids are to be Class D.
label | Reference Documents - Cl16.5.7.1 & IFC Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.3 - Box Culverts Bedding, Side, Overlay and Backfill Zone Materials.
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Materials are to be compliant with the requirements detailed in Cl.16.5.6. Material submission approval.
label | Reference Documents - Cl16.5.6 & 16.6.2.2
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Blinding for Drainage Pits and Headwalls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Approved bedding material as per IFC Drawings.
label | Reference Documents - IFC Drawings
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex Correspondence
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.5 - Geotextile Fabric
label | Frequency - Prior to commencing work
label | Acceptance Criteria - Non-woven type complying with the requirements of VicRoads for first stage filter.
label | Reference Documents - Cl.16.5.8 & VicRoads Section 702
label | Inspection/Test Method - Verify
label | Record of conformity - Visual Inspection & Delivery Docket
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 3.0 - Material Receival
checkpoint | 3.1 - Precast Structure Delivery
label | Frequency - Each Lot
label | Acceptance Criteria - Ensure each precast component is inspected upon arrival ensuring:
label | ○ Dimensions are as shown on manufacturer drawings.
label | ○ All blockouts in correct positions and to dimensions.
label | ○ No damage to any precast structure component to the satisfaction of FH Engineer
label | ○ No modifications to the pits are to be made without written approval from manufacturer.
label | ○ Manufacturer’s conformance report
label | Reference Documents - Cl16.6.1 & IFC Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Order Acceptance Form
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 4.0 - Drainage Pit, Headwall and Culvert Installation
checkpoint | 4.1 - Survey Setout
label | Frequency - Prior to construction and each lot
label | Acceptance Criteria - Set out the drainage structures as shown on the Drawings to identify the locations, lengths and levels:
label | ○ All pits, and inlet and outlet structures.
label | ○ Ends of wing walls and headwalls.
label | ○ At outlets and inlets of box culvert structures.
label | – Setout of each drainage system to constitute a Hold Point.
label | Reference Documents - Cl16.7.1
label | Inspection/Test Method - Survey
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Excavation
label | Frequency - Each Lot
label | Acceptance Criteria - Excavation to be performed to the minimum depths, widths and batter slopes as shown on the Drawings, regardless of the type of material.
label | Inspection of completed excavation works to constitute a Hold Point.
label | Pits:
label | ○ The shape of the excavation to be as required and the size sufficient to enable construction of the structure.
label | Box Culverts:
label | ○ The width of trench to be not less than the exterior width of the culvert plus 400mm, and not greater than that required for satisfactory backfilling.
label | Reference Documents - Cl16.8 & Cl 16.6.2.2
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Confirm Ground Conditions
label | Frequency - Each Structure
label | Acceptance Criteria - 1 x DCP test to be undertaken per drainage structure to confirm ground conditions.
label | ○ Contractor to notify the Contract Administrator of any area of the foundation with inadequate material to support the proposed drainage structure. Inadequate material is deemed to have a bearing pressure less than 130kPa, equivalent to 4 DCP blows per 100mm, as per note 4 on drawing ZULU-BECA-012- DWG-07102.
label | ○ Inadequate foundation material is to be replaced with a layer of coarse crushed aggregate compacted to 95% relative standard compaction to AS1289 Section 5.5.1 over a geotextile Bidim A29 or approved equivalent.
label | Reference Documents - Cl16.8.2 & Tender Clarification #38
label | Inspection/Test Method - Site Inspection
label | Record of conformity - DCP, Test Results
label | TP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.4 - Blinding for Drainage Pits and Headwalls
label | Frequency - Each Lot
label | Acceptance Criteria - Blinding to be installed as per the depths and widths shown on the Drawings.
label | ○ Pits: 50mm Crushed Rock bedding
label | ○ Headwalls: 100mm 15MPa Concrete blinding and 600x150mm apron cut off wall
label | Reference Documents - IFC Drawings & VicRoads SD
label | Inspection/Test Method - Verify and Visual Inspection
label | Record of conformity - Delivery Docket & This ITP Signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.5 - Bedding for Box Culverts
label | Frequency - Each Lot
label | Acceptance Criteria - Bedding material to comprise of approved select fill and to be placed for the full width of the trench.
label | ○ Upon completion, the bedding is to provide a uniform firm foundation with the top surface of the bedding shaped to the details shown on the drawings. This to constitute a Witness Point.
label | Reference Documents - CL16.5.6. 1
label | Inspection/Test Method - Verify and Visual Inspection
label | Record of conformity - Delivery Docket & This ITP Signed
label | WP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
checkpoint | 4.6 - Positioning of Precast Structures
label | Frequency - Each Lot
label | Acceptance Criteria - Precast structures installed as per survey set out points marked on blinding / bedding layer
label | Reference Documents - Cl.16.8.1 & IFC Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.7 - Backfill Materials for Box Culverts
label | Frequency - Each Lot
label | Acceptance Criteria - Side Zone, Overlay Zone and Backfill Zone Subject to Vehicle Loads
label | ○ Approved Select fill material.
label | ○ Completed in layers with maximum thickness of Cl200mm loose material.
label | Overlay and Backfill Zone – Not Subject to Vehicle Loads
label | ○ Ordinary fill material compliant with Cl.16.5.6.3 of Beca’s specification
label | Reference Documents - Cl.16.5.6 & IFC Drawings
label | Inspection/Test Method - Verify and Site Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.8 - Compaction Requirements (Box Culvert)
label | Frequency - 1 test per lot.
label | ○ "1 test per layer of bedding for bedding materials and every 2nd layer for side, overlay and backfill zone materials."
label | Acceptance Criteria - Bed Zone – Minimum 90% SMDD
label | ○ Side Zone Not Subject to Vehicle Loads – Minimum RD of 95% SMDD
label | ○ Side Zone Subject to Vehicle Loads – Minimum of 95% SMDD
label | ○ Overlay and Backfill Zone Not Subject to Vehicle Loads – Minimum 90% SMDD
label | ○ Overlay and Backfill Zone Subject to Vehicle Loads – Minimum 95% SMDD
label | Reference Documents - Cl.16.5.6. 1 (b) (iv)
label | Inspection/Test Method - Site Inspection
label | Record of conformity - Test Records
label | TP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: