## Sheet1
1 | Preliminaries | [7 empty] | 1 - Preliminaries | [8 empty] | 1 - Preliminaries
1.1 | Check for correct documentation | Prior to commencing activity | Ensure that all employees and subcontractors are: ○ using the correct and complete set of drawings. ○ all drawings are the latest revision. | IFC Drawings | Document Review | This ITP Signed | HP* | Project / Site Engineer | 1.1 - Check for correct documentation | Frequency - Prior to commencing activity | Acceptance Criteria - Ensure that all employees and subcontractors are: ○ using the correct and complete set of drawings. ○ all drawings are the latest revision. | Reference Documents - IFC Drawings | Inspection/Test Method - Document Review | Record of conformity - This ITP Signed | HP* | Responsibility - Project / Site Engineer | Date Completed: | 1.1 - Check for correct documentation
1.2 | Implementation of all measures and controls | Prior to commencing activity | All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS CHAR(AMP) WP. | CEMP, TMP, SWMS CHAR(AMP) WP | Visual Inspection | Site and Office Inspection | HP* | Project/ Site Engineer/ Supervisor | 1.2 - Implementation of all measures and controls | Frequency - Prior to commencing activity | Acceptance Criteria - All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS CHAR(AMP) WP. | Reference Documents - CEMP, TMP, SWMS CHAR(AMP) WP | Inspection/Test Method - Visual Inspection | Record of conformity - Site and Office Inspection | HP* | Responsibility - Project/ Site Engineer/ Supervisor | Date Completed: | Frequency - Prior to commencing activity
1.3 | Excavation Permit | Prior to commencing activity | Excavation Permit issued by APAM obtained prior to any excavation on site. | Approved Permits | Verify | Proof of permit CHAR(AMP) ITP signed | HP* | Project/ Site Engineer | 1.3 - Excavation Permit | Frequency - Prior to commencing activity | Acceptance Criteria - Excavation Permit issued by APAM obtained prior to any excavation on site. | Reference Documents - Approved Permits | Inspection/Test Method - Verify | Record of conformity - Proof of permit CHAR(AMP) ITP signed | HP* | Responsibility - Project/ Site Engineer | Date Completed: | Acceptance Criteria - Ensure that all employees and subcontractors are: ○ using the correct and complete set of drawings. ○ all drawings are the latest revision.
2 | Material Approvals | [7 empty] | 2 - Material Approvals | [8 empty] | Reference Documents - IFC Drawings
2.1 | Precast Structures | Prior to commencing activity | Details of the proposed precast drainage pits, headwalls, and culverts to be as specified on the IFC Drawings. Approval of the shop drawings constitutes a Hold Point. ○ Outline of sampling and test program | Cl16.6.1 CHAR(AMP) Manufactu rer’s document s | Document Review | Aconex Correspond ence | HP | Project/ Site Engineer | 2.1 - Precast Structures | Frequency - Prior to commencing activity | Acceptance Criteria - Details of the proposed precast drainage pits, headwalls, and culverts to be as specified on the IFC Drawings. Approval of the shop drawings constitutes a Hold Point. ○ Outline of sampling and test program | Reference Documents - Cl16.6.1 CHAR(AMP) Manufactu rer’s document s | Inspection/Test Method - Document Review | Record of conformity - Aconex Correspond ence | HP | Responsibility - Project/ Site Engineer | Date Completed: | Inspection/Test Method - Document Review
2.2 | Access Cover and Grates | Prior to commencing activity | All Pit covers to conform to AS 3996 and the applicable load class to be as noted on the Drawings. For all drainage pits, pit lids are to be Class D. | Cl16.5.7.1 CHAR(AMP) IFC Drawings | Verify | This ITP Signed | HP* | Project/ Site Engineer | 2.2 - Access Cover and Grates | Frequency - Prior to commencing activity | Acceptance Criteria - All Pit covers to conform to AS 3996 and the applicable load class to be as noted on the Drawings. For all drainage pits, pit lids are to be Class D. | Reference Documents - Cl16.5.7.1 CHAR(AMP) IFC Drawings | Inspection/Test Method - Verify | Record of conformity - This ITP Signed | HP* | Responsibility - Project/ Site Engineer | Date Completed: | Record of conformity - This ITP Signed
2.3 | Box Culverts Bedding, Side, Overlay and Backfill Zone Materials. | Prior to commencing activity | Materials are to be compliant with the requirements detailed in Cl.16.5.6. Material submission approval. | Cl16.5.6 CHAR(AMP) 16.6.2.2 | Document Review | Aconex Correspond ence | HP | Project/ Site Engineer Beca | 2.3 - Box Culverts Bedding, Side, Overlay and Backfill Zone Materials. | Frequency - Prior to commencing activity | Acceptance Criteria - Materials are to be compliant with the requirements detailed in Cl.16.5.6. Material submission approval. | Reference Documents - Cl16.5.6 CHAR(AMP) 16.6.2.2 | Inspection/Test Method - Document Review | Record of conformity - Aconex Correspond ence | HP | Responsibility - Project/ Site Engineer Beca | Date Completed: | HP*
2.4 | Blinding for Drainage Pits and Headwalls | Prior to commencing activity | Approved bedding material as per IFC Drawings. | IFC Drawings | Document Review | Aconex Correspond ence | HP* | Project/ Site Engineer | 2.4 - Blinding for Drainage Pits and Headwalls | Frequency - Prior to commencing activity | Acceptance Criteria - Approved bedding material as per IFC Drawings. | Reference Documents - IFC Drawings | Inspection/Test Method - Document Review | Record of conformity - Aconex Correspond ence | HP* | Responsibility - Project/ Site Engineer | Date Completed: | Responsibility - Project / Site Engineer
2.5 | Geotextile Fabric | Prior to commencing work | Non-woven type complying with the requirements of VicRoads for first stage filter. | Cl.16.5.8 CHAR(AMP) VicRoads Section 702 | Verify | Visual Inspection CHAR(AMP) Delivery Docket | IP | Project/ Site Engineer | 2.5 - Geotextile Fabric | Frequency - Prior to commencing work | Acceptance Criteria - Non-woven type complying with the requirements of VicRoads for first stage filter. | Reference Documents - Cl.16.5.8 CHAR(AMP) VicRoads Section 702 | Inspection/Test Method - Verify | Record of conformity - Visual Inspection CHAR(AMP) Delivery Docket | IP | Responsibility - Project/ Site Engineer | Date Completed: | Date Completed:
3 | Material Receival | [7 empty] | 3 - Material Receival | [8 empty] | 1.2 - Implementation of all measures and controls
3.1 | Precast Structure Delivery | Each Lot | Ensure each precast component is inspected upon arrival ensuring: ○ Dimensions are as shown on manufacturer drawings. ○ All blockouts in correct positions and to dimensions. ○ No damage to any precast structure component to the satisfaction of FH Engineer ○ No modifications to the pits are to be made without written approval from manufacturer. ○ Manufacturer’s conformance report | Cl16.6.1 CHAR(AMP) IFC Drawings | Visual Inspection | Order Acceptance Form | HP* | Project/ Site Engineer | 3.1 - Precast Structure Delivery | Frequency - Each Lot | Acceptance Criteria - Ensure each precast component is inspected upon arrival ensuring: ○ Dimensions are as shown on manufacturer drawings. ○ All blockouts in correct positions and to dimensions. ○ No damage to any precast structure component to the satisfaction of FH Engineer ○ No modifications to the pits are to be made without written approval from manufacturer. ○ Manufacturer’s conformance report | Reference Documents - Cl16.6.1 CHAR(AMP) IFC Drawings | Inspection/Test Method - Visual Inspection | Record of conformity - Order Acceptance Form | HP* | Responsibility - Project/ Site Engineer | Date Completed: | Frequency - Prior to commencing activity
4 | Drainage Pit, Headwall and Culvert Installation | [7 empty] | 4 - Drainage Pit, Headwall and Culvert Installation | [8 empty] | Acceptance Criteria - All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS CHAR(AMP) WP.
4.1 | Survey Setout | Prior to construction and each lot | Set out the drainage structures as shown on the Drawings to identify the locations, lengths and levels: ○ All pits, and inlet and outlet structures. ○ Ends of wing walls and headwalls. ○ At outlets and inlets of box culvert structures. Setout of each drainage system to constitute a Hold Point. | Cl16.7.1 | Survey | This ITP Signed | HP | Project/ Site Engineer Beca | 4.1 - Survey Setout | Frequency - Prior to construction and each lot | Acceptance Criteria - Set out the drainage structures as shown on the Drawings to identify the locations, lengths and levels: ○ All pits, and inlet and outlet structures. ○ Ends of wing walls and headwalls. ○ At outlets and inlets of box culvert structures. Setout of each drainage system to constitute a Hold Point. | Reference Documents - Cl16.7.1 | Inspection/Test Method - Survey | Record of conformity - This ITP Signed | HP | Responsibility - Project/ Site Engineer Beca | Date Completed: | Reference Documents - CEMP, TMP, SWMS CHAR(AMP) WP
4.2 | Excavation | Each Lot | Excavation to be performed to the minimum depths, widths and batter slopes as shown on the Drawings, regardless of the type of material. Inspection of completed excavation works to constitute a Hold Point. Pits: The shape of the excavation to be as required and the size sufficient to enable construction of the structure. Box Culverts: The width of trench to be not less than the exterior width of the culvert plus 400mm, and not greater than that required for satisfactory backfilling. | Cl16.8 CHAR(AMP) Cl 16.6.2.2 | Verify | This ITP Signed | HP | Project/ Site Engineer Beca | 4.2 - Excavation | Frequency - Each Lot | Acceptance Criteria - Excavation to be performed to the minimum depths, widths and batter slopes as shown on the Drawings, regardless of the type of material. Inspection of completed excavation works to constitute a Hold Point. Pits: The shape of the excavation to be as required and the size sufficient to enable construction of the structure. Box Culverts: The width of trench to be not less than the exterior width of the culvert plus 400mm, and not greater than that required for satisfactory backfilling. | Reference Documents - Cl16.8 CHAR(AMP) Cl 16.6.2.2 | Inspection/Test Method - Verify | Record of conformity - This ITP Signed | HP | Responsibility - Project/ Site Engineer Beca | Date Completed: | Inspection/Test Method - Visual Inspection
4.3 | Confirm Ground Conditions | Each Structure | 1 x DCP test to be undertaken per drainage structure to confirm ground conditions. Contractor to notify the Contract Administrator of any area of the foundation with inadequate material to support the proposed drainage structure. Inadequate material is deemed to have a bearing pressure less than 130kPa, equivalent to 4 DCP blows per 100mm, as per note 4 on drawing ZULU-BECA-012- DWG-07102. Inadequate foundation material is to be replaced with a layer of coarse crushed aggregate compacted to 95% relative standard compaction to AS1289 Section 5.5.1 over a geotextile Bidim A29 or approved equivalent. | Cl16.8.2 CHAR(AMP) Tender Clarification #38 | Site Inspection | DCP, Test Results | TP | Project/ Site Engineer | 4.3 - Confirm Ground Conditions | Frequency - Each Structure | Acceptance Criteria - 1 x DCP test to be undertaken per drainage structure to confirm ground conditions. Contractor to notify the Contract Administrator of any area of the foundation with inadequate material to support the proposed drainage structure. Inadequate material is deemed to have a bearing pressure less than 130kPa, equivalent to 4 DCP blows per 100mm, as per note 4 on drawing ZULU-BECA-012- DWG-07102. Inadequate foundation material is to be replaced with a layer of coarse crushed aggregate compacted to 95% relative standard compaction to AS1289 Section 5.5.1 over a geotextile Bidim A29 or approved equivalent. | Reference Documents - Cl16.8.2 CHAR(AMP) Tender Clarification #38 | Inspection/Test Method - Site Inspection | Record of conformity - DCP, Test Results | TP | Responsibility - Project/ Site Engineer | Date Completed: | Record of conformity - Site and Office Inspection
4.4 | Blinding for Drainage Pits and Headwalls | Each Lot | Blinding to be installed as per the depths and widths shown on the Drawings. Pits: 50mm Crushed Rock bedding Headwalls: 100mm 15MPa Concrete blinding and 600x150mm apron cut off wall | IFC Drawings CHAR(AMP) VicRoads SD | Verify and Visual Inspection | Delivery Docket CHAR(AMP) This ITP Signed | HP* | Project/ Site Engineer | 4.4 - Blinding for Drainage Pits and Headwalls | Frequency - Each Lot | Acceptance Criteria - Blinding to be installed as per the depths and widths shown on the Drawings. Pits: 50mm Crushed Rock bedding Headwalls: 100mm 15MPa Concrete blinding and 600x150mm apron cut off wall | Reference Documents - IFC Drawings CHAR(AMP) VicRoads SD | Inspection/Test Method - Verify and Visual Inspection | Record of conformity - Delivery Docket CHAR(AMP) This ITP Signed | HP* | Responsibility - Project/ Site Engineer | Date Completed: | HP*
4.5 | Bedding for Box Culverts | Each Lot | Bedding material to comprise of approved select fill and to be placed for the full width of the trench. Upon completion, the bedding is to provide a uniform firm foundation with the top surface of the bedding shaped to the details shown on the drawings. This to constitute a Witness Point. | CL16.5.6. 1 | Verify and Visual Inspection | Delivery Docket CHAR(AMP) This ITP Signed | WP | Project/ Site Engineer Beca | 4.5 - Bedding for Box Culverts | Frequency - Each Lot | Acceptance Criteria - Bedding material to comprise of approved select fill and to be placed for the full width of the trench. Upon completion, the bedding is to provide a uniform firm foundation with the top surface of the bedding shaped to the details shown on the drawings. This to constitute a Witness Point. | Reference Documents - CL16.5.6. 1 | Inspection/Test Method - Verify and Visual Inspection | Record of conformity - Delivery Docket CHAR(AMP) This ITP Signed | WP | Responsibility - Project/ Site Engineer Beca | Date Completed: | Responsibility - Project/ Site Engineer/ Supervisor
4.6 | Positioning of Precast Structures | Each Lot | Precast structures installed as per survey set out points marked on blinding / bedding layer | Cl.16.8.1 CHAR(AMP) IFC Drawings | Verify | This ITP Signed | IP | Project/ Site Engineer | 4.6 - Positioning of Precast Structures | Frequency - Each Lot | Acceptance Criteria - Precast structures installed as per survey set out points marked on blinding / bedding layer | Reference Documents - Cl.16.8.1 CHAR(AMP) IFC Drawings | Inspection/Test Method - Verify | Record of conformity - This ITP Signed | IP | Responsibility - Project/ Site Engineer | Date Completed: | Date Completed:
4.7 | Backfill Materials for Box Culverts | Each Lot | Side Zone, Overlay Zone and Backfill Zone Subject to Vehicle Loads ○ Approved Select fill material. ○ Completed in layers with maximum thickness of Cl200mm loose material. Overlay and Backfill Zone – Not Subject to Vehicle Loads ○ Ordinary fill material compliant with Cl.16.5.6.3 of Beca’s specification | Cl.16.5.6 CHAR(AMP) IFC Drawings | Verify and Site Inspection | This ITP Signed | IP | Project/ Site Engineer | 4.7 - Backfill Materials for Box Culverts | Frequency - Each Lot | Acceptance Criteria - Side Zone, Overlay Zone and Backfill Zone Subject to Vehicle Loads ○ Approved Select fill material. ○ Completed in layers with maximum thickness of Cl200mm loose material. Overlay and Backfill Zone – Not Subject to Vehicle Loads ○ Ordinary fill material compliant with Cl.16.5.6.3 of Beca’s specification | Reference Documents - Cl.16.5.6 CHAR(AMP) IFC Drawings | Inspection/Test Method - Verify and Site Inspection | Record of conformity - This ITP Signed | IP | Responsibility - Project/ Site Engineer | Date Completed: | 1.3 - Excavation Permit
4.8 | Compaction Requirements (Box Culvert) | 1 test per lot. “1 test per layer of bedding for bedding materials and every 2nd layer for side, overlay and backfill zone materials.” | Bed Zone – Minimum 90% SMDD Side Zone Not Subject to Vehicle Loads – Minimum RD of 95% SMDD Side Zone Subject to Vehicle Loads – Minimum of 95% SMDD Overlay and Backfill Zone Not Subject to Vehicle Loads – Minimum 90% SMDD Overlay and Backfill Zone Subject to Vehicle Loads – Minimum 95% SMDD | Cl.16.5.6. 1 (b) (iv) | Site Inspection | Test Records | TP | Project/ Site Engineer | 4.8 - Compaction Requirements (Box Culvert) | Frequency - 1 test per lot. “1 test per layer of bedding for bedding materials and every 2nd layer for side, overlay and backfill zone materials.” | Acceptance Criteria - Bed Zone – Minimum 90% SMDD Side Zone Not Subject to Vehicle Loads – Minimum RD of 95% SMDD Side Zone Subject to Vehicle Loads – Minimum of 95% SMDD Overlay and Backfill Zone Not Subject to Vehicle Loads – Minimum 90% SMDD Overlay and Backfill Zone Subject to Vehicle Loads – Minimum 95% SMDD | Reference Documents - Cl.16.5.6. 1 (b) (iv) | Inspection/Test Method - Site Inspection | Record of conformity - Test Records | TP | Responsibility - Project/ Site Engineer | Date Completed: | Frequency - Prior to commencing activity
Acceptance Criteria - Excavation Permit issued by APAM obtained prior to any excavation on site.
Reference Documents - Approved Permits
Inspection/Test Method - Verify
Record of conformity - Proof of permit CHAR(AMP) ITP signed
HP*
Responsibility - Project/ Site Engineer
Date Completed:
2 - Material Approvals
2.1 - Precast Structures
Frequency - Prior to commencing activity
Acceptance Criteria - Details of the proposed precast drainage pits, headwalls, and culverts to be as specified on the IFC Drawings. Approval of the shop drawings constitutes a Hold Point. ○ Outline of sampling and test program
Reference Documents - Cl16.6.1 CHAR(AMP) Manufactu rer’s document s
Inspection/Test Method - Document Review
Record of conformity - Aconex Correspond ence
HP
Responsibility - Project/ Site Engineer
Date Completed:
2.2 - Access Cover and Grates
Frequency - Prior to commencing activity
Acceptance Criteria - All Pit covers to conform to AS 3996 and the applicable load class to be as noted on the Drawings. For all drainage pits, pit lids are to be Class D.
Reference Documents - Cl16.5.7.1 CHAR(AMP) IFC Drawings
Inspection/Test Method - Verify
Record of conformity - This ITP Signed
HP*
Responsibility - Project/ Site Engineer
Date Completed:
2.3 - Box Culverts Bedding, Side, Overlay and Backfill Zone Materials.
Frequency - Prior to commencing activity
Acceptance Criteria - Materials are to be compliant with the requirements detailed in Cl.16.5.6. Material submission approval.
Reference Documents - Cl16.5.6 CHAR(AMP) 16.6.2.2
Inspection/Test Method - Document Review
Record of conformity - Aconex Correspond ence
HP
Responsibility - Project/ Site Engineer Beca
Date Completed:
2.4 - Blinding for Drainage Pits and Headwalls
Frequency - Prior to commencing activity
Acceptance Criteria - Approved bedding material as per IFC Drawings.
Reference Documents - IFC Drawings
Inspection/Test Method - Document Review
Record of conformity - Aconex Correspond ence
HP*
Responsibility - Project/ Site Engineer
Date Completed:
2.5 - Geotextile Fabric
Frequency - Prior to commencing work
Acceptance Criteria - Non-woven type complying with the requirements of VicRoads for first stage filter.
Reference Documents - Cl.16.5.8 CHAR(AMP) VicRoads Section 702
Inspection/Test Method - Verify
Record of conformity - Visual Inspection CHAR(AMP) Delivery Docket
IP
Responsibility - Project/ Site Engineer
Date Completed:
3 - Material Receival
3.1 - Precast Structure Delivery
Frequency - Each Lot
Acceptance Criteria - Ensure each precast component is inspected upon arrival ensuring: ○ Dimensions are as shown on manufacturer drawings. ○ All blockouts in correct positions and to dimensions. ○ No damage to any precast structure component to the satisfaction of FH Engineer ○ No modifications to the pits are to be made without written approval from manufacturer. ○ Manufacturer’s conformance report
Reference Documents - Cl16.6.1 CHAR(AMP) IFC Drawings
Inspection/Test Method - Visual Inspection
Record of conformity - Order Acceptance Form
HP*
Responsibility - Project/ Site Engineer
Date Completed:
4 - Drainage Pit, Headwall and Culvert Installation
4.1 - Survey Setout
Frequency - Prior to construction and each lot
Acceptance Criteria - Set out the drainage structures as shown on the Drawings to identify the locations, lengths and levels: ○ All pits, and inlet and outlet structures. ○ Ends of wing walls and headwalls. ○ At outlets and inlets of box culvert structures. Setout of each drainage system to constitute a Hold Point.
Reference Documents - Cl16.7.1
Inspection/Test Method - Survey
Record of conformity - This ITP Signed
HP
Responsibility - Project/ Site Engineer Beca
Date Completed:
4.2 - Excavation
Frequency - Each Lot
Acceptance Criteria - Excavation to be performed to the minimum depths, widths and batter slopes as shown on the Drawings, regardless of the type of material. Inspection of completed excavation works to constitute a Hold Point. Pits: The shape of the excavation to be as required and the size sufficient to enable construction of the structure. Box Culverts: The width of trench to be not less than the exterior width of the culvert plus 400mm, and not greater than that required for satisfactory backfilling.
Reference Documents - Cl16.8 CHAR(AMP) Cl 16.6.2.2
Inspection/Test Method - Verify
Record of conformity - This ITP Signed
HP
Responsibility - Project/ Site Engineer Beca
Date Completed:
4.3 - Confirm Ground Conditions
Frequency - Each Structure
Acceptance Criteria - 1 x DCP test to be undertaken per drainage structure to confirm ground conditions. Contractor to notify the Contract Administrator of any area of the foundation with inadequate material to support the proposed drainage structure. Inadequate material is deemed to have a bearing pressure less than 130kPa, equivalent to 4 DCP blows per 100mm, as per note 4 on drawing ZULU-BECA-012- DWG-07102. Inadequate foundation material is to be replaced with a layer of coarse crushed aggregate compacted to 95% relative standard compaction to AS1289 Section 5.5.1 over a geotextile Bidim A29 or approved equivalent.
Reference Documents - Cl16.8.2 CHAR(AMP) Tender Clarification #38
Inspection/Test Method - Site Inspection
Record of conformity - DCP, Test Results
TP
Responsibility - Project/ Site Engineer
Date Completed:
4.4 - Blinding for Drainage Pits and Headwalls
Frequency - Each Lot
Acceptance Criteria - Blinding to be installed as per the depths and widths shown on the Drawings. Pits: 50mm Crushed Rock bedding Headwalls: 100mm 15MPa Concrete blinding and 600x150mm apron cut off wall
Reference Documents - IFC Drawings CHAR(AMP) VicRoads SD
Inspection/Test Method - Verify and Visual Inspection
Record of conformity - Delivery Docket CHAR(AMP) This ITP Signed
HP*
Responsibility - Project/ Site Engineer
Date Completed:
4.5 - Bedding for Box Culverts
Frequency - Each Lot
Acceptance Criteria - Bedding material to comprise of approved select fill and to be placed for the full width of the trench. Upon completion, the bedding is to provide a uniform firm foundation with the top surface of the bedding shaped to the details shown on the drawings. This to constitute a Witness Point.
Reference Documents - CL16.5.6. 1
Inspection/Test Method - Verify and Visual Inspection
Record of conformity - Delivery Docket CHAR(AMP) This ITP Signed
WP
Responsibility - Project/ Site Engineer Beca
Date Completed:
4.6 - Positioning of Precast Structures
Frequency - Each Lot
Acceptance Criteria - Precast structures installed as per survey set out points marked on blinding / bedding layer
Reference Documents - Cl.16.8.1 CHAR(AMP) IFC Drawings
Inspection/Test Method - Verify
Record of conformity - This ITP Signed
IP
Responsibility - Project/ Site Engineer
Date Completed:
4.7 - Backfill Materials for Box Culverts
Frequency - Each Lot
Acceptance Criteria - Side Zone, Overlay Zone and Backfill Zone Subject to Vehicle Loads ○ Approved Select fill material. ○ Completed in layers with maximum thickness of Cl200mm loose material. Overlay and Backfill Zone – Not Subject to Vehicle Loads ○ Ordinary fill material compliant with Cl.16.5.6.3 of Beca’s specification
Reference Documents - Cl.16.5.6 CHAR(AMP) IFC Drawings
Inspection/Test Method - Verify and Site Inspection
Record of conformity - This ITP Signed
IP
Responsibility - Project/ Site Engineer
Date Completed:
4.8 - Compaction Requirements (Box Culvert)
Frequency - 1 test per lot. “1 test per layer of bedding for bedding materials and every 2nd layer for side, overlay and backfill zone materials.”
Acceptance Criteria - Bed Zone – Minimum 90% SMDD Side Zone Not Subject to Vehicle Loads – Minimum RD of 95% SMDD Side Zone Subject to Vehicle Loads – Minimum of 95% SMDD Overlay and Backfill Zone Not Subject to Vehicle Loads – Minimum 90% SMDD Overlay and Backfill Zone Subject to Vehicle Loads – Minimum 95% SMDD
Reference Documents - Cl.16.5.6. 1 (b) (iv)
Inspection/Test Method - Site Inspection
Record of conformity - Test Records
TP
Responsibility - Project/ Site Engineer
Date Completed: