## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP019 - Topsoil & Grassing | itp |  |  |  |  | ITP019 - Topsoil & Grassing
section | 1.0 Preliminary activities
checkpoint | 1.1 - Check for correct documentation
note | Frequency: Prior to commencing any activity
note | Acceptance Criteria:
note | • Current revision drawing is being used including the subcontractors copy.
note | • Current Revision to be obtained via Aconex
note | Reference Documents: Drawings and Aconex
note | Inspection/ Test Method: Visual inspection
note | Record of conformity: This Signed ITP
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
note | Frequency: Prior to commencing any activity
note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
note | Reference Documents: PSP, EMP, TMP, SWMS, WP
note | Inspection/ Test Method: Inspect
note | Record of conformity: This Signed ITP
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | 1.3 - Material Approval
note | Frequency: Prior to hydro seeding
note | Acceptance Criteria:
note | • Hydro mulch application to be Flexterra HP-FGH, Vital-Bon, or Mydro Mulch 1000 to be used only for soil stabilisation for when working around live runways/taxiways unless agreed otherwise by Melbourne Airport.
note | • Hydroseedlings to use 50% couch and 50% perennial at 80kg per hectare.
note | • Approval from Contract Administrator required for:
note | ○ Fertilizer
note | ○ Grass seed mix
note | ○ Hydromulching mixture
note | ○ Propriety stabilisation material
note | Reference Documents:
note | • Appendix J
note | • 7203 (ii)
note | • 7214
note | • 7215
note | • WP 7215-1
note | • WP 7215-2
note | • WP 7215-3
note | Inspection/ Test Method: Verify
note | Record of conformity: ACONEX, This signed ITP
note | WP
note | Responsibility: Site Engineer/ Contract Administrator
textbox | Date Completed:
section | 2.0 Herbicide
checkpoint | 2.1 - Herbicide
note | Frequency: Prior to topsoil placement
note | Acceptance Criteria: Selective herbicides will be used for broad-leaved weeks in grass areas. Glyphosate are to be applied in grass areas with the use of “Spot-spraying” to treat selected weeks such as Surrated tussock.
note | Reference Documents: Appendix J SP7203 (i)
note | Inspection/ Test Method: Visual Inspection
note | Record of conformity: This signed ITP
note | HP*
note | Responsibility: Environmental Coordinator
textbox | Date Completed:
section | 3.0 Placement of top soil
checkpoint | 3.1 - Topsoil placement
note | Frequency: Each Lot
note | Acceptance Criteria:
note | • APAM engineering standard (MAS-CVL-001-V1 Grassing Airside 24/12/2021) calls for a uniform thickness of not less than 100mm of topsoil prior to seeding and subject to the Contractor making necessary allowance for compaction of the topsoil prior to Hydro mulching.
note | • The finished compacted thickness of the topsoil layer in erosion areas must not be less than 100 mm in accordance to APAM engineering standard (MAS-CVL-001-V1 Grassing Airside 24/12/2021).
note | • Topsoil will be placed and spread to fill voids in the surface. During compaction, the surface of the topsoil must be smooth and free from lumps of the soil.
note | • Topsoil must be free of aggregates exceeding 20mm in diameter.
note | Reference Documents:
note | • Cl 5.2 Drawing no. 12554937-C464
note | • Appendix J 7209 (a) HP 7209-1
note | • Appendix J 7209 (b)
note | • Appendix J 7209 (d)
note | Inspection/ Test Method: Verify
note | Record of conformity: Survey data
note | HP
note | Responsibility: Site Engineer Foreman
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Fertiliser Application Rate
note | Frequency: Each Lot
note | Acceptance Criteria:
note | • Fertiliser (refer Section 7203(c)) must be applied to the surface of the topsoil at a uniform rate of 40 g/m2. A wetting agent must also be incorporated.
note | • Fertiliser must be thoroughly mixed into the topsoil layer using a rake or other approved method.
note | Reference Documents: Appendix J 7209 (c)
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed
note | HP*
note | Responsibility: Site Engineer Foreman
textbox | Date Completed:
section | 4.0 Hydromulching
checkpoint | 4.1 - Watering before Application
note | Frequency: Each Lot
note | Acceptance Criteria: Water the topsoil to ensure it is moistened to its full depth before applying the hydromulching mixture to the prepared surface.
note | Reference Documents: Appendix J 7210 (a)
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | 4.2 - Hydromulching
note | Frequency: Each Lot
note | Acceptance Criteria:
note | • Apply the slurry using high pressure pumping equipment operated by trained personnel. Spray the mixed slurry under pressure, maintaining a thoroughly mixed supply, operating on a front so that the mixture is evenly distributed over the area.
note | • Complete each front before commencing the next.
note | Reference Documents: Appendix J 7210 (b)
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
section | 5.0 Propriety Stabilisation
checkpoint | 5.1 - Propriety Stabilisation
note | Frequency: Prior to opening area to airport traffic
note | Acceptance Criteria:
note | • Areas not turfed and with exposed topsoil, must be treated as follows:
note | – bitumen emulsion at a net bitumen application rate of 0.15 ℓ/m2 or as indicated on the Drawings, or
note | – surface stabilisation material as specified in 7203(h) at the application rate specified on the Drawings or recommended by the manufacturer.
note | Reference Documents: Appendix J 7209 (e)
note | Inspection/ Test Method: Verify
note | Record of conformity: This signed ITP
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
section | 6.0 Grass Establishment
checkpoint | 6.1 - Watering Schedule
note | Frequency: Prior to commencement of watering
note | Acceptance Criteria: Watering of the seeded areas shall be planned by the Contractor in advance to avoid interference with aircraft operations and the times and dates of watering shall be submitted for approval by the Contract Administrator not less than 7 days prior to the day of proposed watering.
note | Reference Documents: Appendix J 7210 (c) (iii) WP 7210-1
note | Inspection/ Test Method: Verify
note | Record of conformity: Aconex Approval
note | WP
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | 6.2 - Watering
note | Frequency: Each Lot
note | Acceptance Criteria:
note | • Before Germination:
note | ○ Water the seeded area with a fine spray until the topsoil is moistened to its full depth. Continue watering until germination to keep the surface damp and the topsoil moist but not waterlogged.
note | • After Germination:
note | ○ Water the seeded area to maintain a healthy condition, progressively hardened off to the natural climatic conditions.
note | Reference Documents: Appendix J 7210 (c) (i) & (ii)
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
section | 7.0 Post Construction
checkpoint | 7.1 - Reinstatement of Disturbed Surfaces
note | Frequency: As Required
note | Acceptance Criteria: Contractor will install and maintain necessary soil erosion restorations as to reinstate disturbed surfaces.
note | Reference Documents: Appendix J 1404 (f)
note | Inspection/ Test Method: Inspection Point
note | Record of conformity: This signed ITP
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
textbox | Date: