## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-079-UT-LOT-XXX - Desc | itp |  |  |  | yes | ITP 0079 - Watermain Construction | 1ba60867-9f57-4091-b816-8b5de0e3acd9
section | Lot Information
checkpoint | 1.0 Lot Information
textbox | Lot Created On
textbox | Lot Opened On
textbox | Work Commenced On
dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
textbox | From and To Chainage
dropdown | Construction Element | UTIL
dropdown | Activity | WATE - Water
dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
textbox | Engineer Responsible
textbox | comments
section | 1 - Preliminary Works
checkpoint | 1 Issued for construction drawings
note | Frequency: Prior to commencement
note | - - - - - - - - -
note | Acceptance Criteria: Ensure the most current revision of drawings is used to conduct the works.
note | - - - - - - - - -
note | Reference Documents: IFC drawings
note | - - - - - - - - -
note | Inspection / Test Method: Review
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Daily Prestart Form
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Project Manager/Engineer
checkpoint | 2 Permits with relevant authorities
note | Frequency: Prior to commencement
note | - - - - - - - - -
note | Acceptance Criteria: Permits to be obtained by relevant authorities
note | - - - - - - - - -
note | Reference Documents: DBYD
note | - - - - - - - - -
note | Inspection / Test Method: Review DBYD
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist Excavation Permit
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Project Manager/Engineer & Superintendent
section | 2 - SURVEY, SETOUT & LOCATION OF EXISTING SERVICES
checkpoint | 3 Survey set-out
note | Frequency: Prior to commencement
note | - - - - - - - - -
note | Acceptance Criteria: Building line pegs to be installed prior to any excavation
note | - - - - - - - - -
note | Reference Documents: IFC drawings
note | - - - - - - - - -
note | Inspection / Test Method: Visual check
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | SCP
note | - - - - - - - - -
note | Responsibility: Surveyor
checkpoint | 4 Service location
note | Frequency: Prior to Excavations onsite
note | - - - - - - - - -
note | Acceptance Criteria: All existing services to be located and protections in place
note | - - - - - - - - -
note | Reference Documents: DBYD
note | - - - - - - - - -
note | Inspection / Test Method: Review drawings and DBYD
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist Excavation Permit
note | - - - - - - - - -
note | WP
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer/Superintendent
checkpoint | 4.1 Installation of property service conduits
note | Frequency: Prior to commencement
note | - - - - - - - - -
note | Acceptance Criteria: All service ducts required by road contractor to be installed prior to works to be inspected and ensure they meet MRWA standards
note | - - - - - - - - -
note | Reference Documents: MRWA-W-110
note | - - - - - - - - -
note | Inspection / Test Method: Visual check
note | - - - - - - - - -
note | Record of Conformity: Site Daily Diary Entry
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
section | 3 - MATERIAL CONFORMANCE
checkpoint | 5 Correct pipe and fittings onsite
note | Frequency: When delivered
note | - - - - - - - - -
note | Acceptance Criteria: Inspect materials in delivery against order. Pipe size matches plans
note | - - - - - - - - -
note | Reference Documents: Delivery docket/ IFC drawings
note | - - - - - - - - -
note | Inspection / Test Method: Visual check
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
checkpoint | 6 Correct embedment / backfill materials onsite
note | Frequency: When delivered
note | - - - - - - - - -
note | Acceptance Criteria: Inspect bedding material to ensure suitability
note | - - - - - - - - -
note | Reference Documents: MRWA-W-201 to 203
note | - - - - - - - - -
note | Inspection / Test Method: Visual check
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
section | 4 - ENVIRONMENTAL & SAFETY
checkpoint | 7 Environmental controls
note | Frequency: Daily
note | - - - - - - - - -
note | Acceptance Criteria: Ensure environmental controls in place and being maintained as per the site EMP (if the civil contractor is responsible for managing the site then as long as we do not distrust their controls this item can be ticked as N/A)
note | - - - - - - - - -
note | Reference Documents: EMP
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Daily Prestart Form
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
checkpoint | 8 Safety controls
note | Frequency: Daily
note | - - - - - - - - -
note | Acceptance Criteria: Ensure safety controls are in place as per the relevant safety instructions and SWMS
note | - - - - - - - - -
note | Reference Documents: SMP
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Daily Prestart Form
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
section | 5 - TRENCHING & EXCAVATION
checkpoint | 9 Trenching
note | Frequency: Prior to entry into open trench
note | - - - - - - - - -
note | Acceptance Criteria: Ensure trench width and depth are within tolerance
note | - - - - - - - - -
note | Reference Documents: IFC drawings / MRWA-W-202
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | SCP
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
checkpoint | 10 Trenching
note | Frequency: Prior to entry into open trench
note | - - - - - - - - -
note | Acceptance Criteria: Ensure trench foundation & wall firm, stiff & suitable
note | - - - - - - - - -
note | Reference Documents: MRWA-W-202
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
checkpoint | 11 Placement of embedment material
note | Frequency: Prior to backfilling of specified area of trench
note | - - - - - - - - -
note | Acceptance Criteria: Ensure pipe bedding depth is acceptable
note | - - - - - - - - -
note | Reference Documents: MRWA-W-202
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
section | 6 - PIPE INSTALLATION
checkpoint | 12 Pipe laying
note | Frequency: Prior to backfilling of specified area of trench
note | - - - - - - - - -
note | Acceptance Criteria: Ensure pipe joint deflection is acceptable and witness marks are applied and visible
note | - - - - - - - - -
note | Reference Documents: MRWA-W-103
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
checkpoint | 13 Property services
note | Frequency: Prior to backfilling of specified area of trench
note | - - - - - - - - -
note | Acceptance Criteria: Ensure tapping collars are installed as per measurements on plans
note | - - - - - - - - -
note | Reference Documents: IFC drawings
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | SCP
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
checkpoint | 14 Dual water property services
note | Frequency: Prior to backfilling of specified area of trench
note | - - - - - - - - -
note | Acceptance Criteria: Ensure tapping collars are installed as per dual water specifications (to the left of the DW)
note | - - - - - - - - -
note | Reference Documents: IFC drawings / MRWA-W110 & 111
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | WP
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer/Superintendent
checkpoint | 15 Valve installation
note | Frequency: Prior to backfilling of specified area of trench
note | - - - - - - - - -
note | Acceptance Criteria: Ensure valves are installed correctly.
note | - - - - - - - - -
note | Reference Documents: IFC drawings / WSA page 233 15.4
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | SCP
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
checkpoint | 16 Hydrant installation
note | Frequency: Prior to backfilling of specified area of trench
note | - - - - - - - - -
note | Acceptance Criteria: Ensure hydrants are installed correctly.
note | - - - - - - - - -
note | Reference Documents: IFC drawings / WSA page 233 15.4
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | SCP
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
checkpoint | 17 Washout installation
note | Frequency: Prior to backfilling of specified area of trench
note | - - - - - - - - -
note | Acceptance Criteria: Ensure washouts are installed correctly.
note | - - - - - - - - -
note | Reference Documents: IFC drawings / WSA page 233 15.4
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | SCP
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer
section | 7 - CONCRETE ANCHOR BLOCKS
checkpoint | 18 Acceptance of concrete delivery
note | Frequency: When concrete is required
note | - - - - - - - - -
note | Acceptance Criteria: Concrete delivered to site to be acceptable. WIN 25 WSA approved mix (20Mpa, 20mm rock , 80 slump)
note | - - - - - - - - -
note | Reference Documents: Concrete delivery docket
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Watermain Anchor Block Checklist – Procedural Verification Checklist ITC-803
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager
checkpoint | 19 Installation of anchor blocks and thrust restraints
note | Frequency: When concrete is required
note | - - - - - - - - -
note | Acceptance Criteria: Installed anchor blocks / thrust restraints are acceptable
note | - - - - - - - - -
note | Reference Documents: MRWA-W-204,205A & 205B
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Watermain Anchor Block Checklist – Procedural Verification Checklist ITC-803
note | - - - - - - - - -
note | WP
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer/Superintendent
checkpoint | 19.1 Correct steel reinforcement used in restraint
note | Frequency: Prior to anchor blocks being poured
note | - - - - - - - - -
note | Acceptance Criteria: Reinforcement is as per MRWA 205-A, 205-B and according to thrust area as noted in face sheet of project plan
note | - - - - - - - - -
note | Reference Documents: MRWA W 205-A and 205-B
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Watermain Anchor Block Checklist – Procedural Verification Checklist ITC-803
note | - - - - - - - - -
note | WP
note | - - - - - - - - -
note | Responsibility: Site Manager/Engineer/Superintendent
section | 8 - BACKFILL OF TRENCHES
checkpoint | 20 Placement of embedment overlay
note | Frequency: Completion of pipelaying
note | - - - - - - - - -
note | Acceptance Criteria: Ensure overlay depth & installation is acceptable
note | - - - - - - - - -
note | Reference Documents: MRWA-W-202
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager
checkpoint | 21 Installation of detectable marker tape
note | Frequency: Completion of pipelaying
note | - - - - - - - - -
note | Acceptance Criteria: Detectable marker tape to be installed in first layer of backfill
note | - - - - - - - - -
note | Reference Documents: MRWA-W-202
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager
checkpoint | 22 Placement of compactable material in trafficable areas
note | Frequency: Completion of pipelaying
note | - - - - - - - - -
note | Acceptance Criteria: Backfill material to be acceptable & compaction of trench line completed
note | - - - - - - - - -
note | Reference Documents: MRWA-W-202,202
note | - - - - - - - - -
note | Inspection / Test Method: Visual / NATA if required
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager
checkpoint | 23 Monitoring of WC1 works
note | Frequency: Once per week
note | - - - - - - - - -
note | Acceptance Criteria: Crews compliance with all Fulton Hogan Procedures and SWMS
note | - - - - - - - - -
note | Reference Documents: Pipelines SMP, SWMS, Trenching Procedure
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Weekly Site Safety Inspection Checklist
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Project Manager/Engineer
checkpoint | 24 Monitoring of WC2 works
note | Frequency: Twice per week
note | - - - - - - - - -
note | Acceptance Criteria: Crews compliance with all Fulton Hogan Procedures and SWMS
note | - - - - - - - - -
note | Reference Documents: Pipelines SMP, SWMS, Trenching Procedure
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Weekly Site Safety Inspection Checklist
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Project Manager/Engineer
section | 9 - QUALITY
checkpoint | 25 Swabbing and flushing, Pressure test and Chlorination works
note | Frequency: Completion of pipelaying
note | - - - - - - - - -
note | Acceptance Criteria: Pressure testing held for 5hr duration
note | - - - - - - - - -
note | Reference Documents: WSA 03-2011 - 18.3, 19.2
note | - - - - - - - - -
note | Inspection / Test Method: Visual
note | - - - - - - - - -
note | Record of Conformity: Compliance checklist - Pipeline construction
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager
checkpoint | 26 Water quality testing.
note | Frequency: Completion of pipelaying
note | - - - - - - - - -
note | Acceptance Criteria: Conduct a bacteriological test on all new mains following satisfactory completion of swabbing/flushing and pressure testing of the water main
note | - - - - - - - - -
note | Reference Documents: WSA 03-2011 19.7
note | - - - - - - - - -
note | Inspection / Test Method: Written
note | - - - - - - - - -
note | Record of Conformity: The test results fall within the water quality parameter
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Manager
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
textbox | Work Completed On
section | Lot Verification
checkpoint | Lot Verification.
dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
textbox | Other:
dropdown | Lot Status | OUTSTANDING, CLOSED
textbox | Lot Closed On
textbox | comments