## PROJECT STRUCTURE
Folder Structure |  |  | Checklists
PROJECT: AON LEVEL 7
PROJECT: AON LEVEL 7 | INTERIOR FIT OUT
CONTAINMENT
CATNERY WIRE
CONTAINMENT - CATNERY WIRE INSTALL
CABLE TRAY INSTALL
CABLE TRAY INSTALL
OPEN AREA
OPEN AREA
LIGHTING 1ST FIX OPEN AREA
LIGHTING 2ND FIX OPEN AREA
POWER 1ST FIX OPEN AREA
POWER 2ND FIX OPEN AREA
LOBBY AREA
LOBBY AREA
LIGHTING 1ST FIX LOBBY
LIGHTING 2ND FIX LOBBY
BATHROOM
BATHROOM
LIGHTING 1ST FIX BATHROOM
LIGHTING 2ND FIX BATHROOM
POWER 1ST FIX BATHROOM
POWER 2ND FIX BATHROOM
DISTRIBUTION
SWITCHBOARD
DISTRIBUTION BOARD - AON LEVEL 7 SWITCHBOARD
DISTRIBUTION BOARD - COMMISSIONING - AON LEVEL 7 SWITCHBOARD

## CHECKPOINTS
TYPE | NAME
CHECKLIST | CONTAINMENT - CATENERY WIRE INSTALL
CHECKPOINT | WOOD EYE/CONCRETE ANCHORS INSTALLED AND CORRECTLY FIXED ONTO CONCRETE SLABS
CHECKPOINT | SUFFICIENT CATENERY WIRE SUPPORTS INSTALLED AT APPROX 1.2M INTERVALS
CHECKPOINT | CATENRY WIRES INSTALLED AT HIGH LEVEL AND MEETS CLEARENCE FROM OTHER SERVICES
CHECKPOINT | TURNBUCKLES IS TIGHTENED AND CATENERY WIRE IS WELL SECURED
CHECKPOINT | EXISTING CATNERY WIRES ARE SUPPORTED AND FIXED CORRECTLY WHERE REQUIRED
CHECKLIST | CABLE TRAY INSTALL
CHECKPOINT | CABLE TRAY INSTALL LOCATION CONFIRMED WITH LANTA SITE FORMAN
CHECKPOINT | SAMMY FIXING INSTALLED AT CORRECT LOCATION AND SECURE
CHECKPOINT | CABLE TRAY TRAPEZE BRACKETS INSTALLED AND PLUMBED
CHECKPOINT | CABLE TRAY INSTALLED AND SPACING BETWEEN TREPEZE IS SUFFICEINT FOR SUPPORT
CHECKPOINT | CABLE TRAY IS FIXED AND BOLTED ONTO UNISTRUT BRACKETS.
CHECKPOINT | CABLE TRAY INSTALLED WITH SPEC CLEARENCES TO OTHER SERVICES
CHECKPOINT | CABLE TRAY BONDED WITH CORRECT SIZE EARTH CABLE.
CHECKPOINT | SEISIMIC BRACING INSTALLED AND MEETS REQUIREMENT
CHECKLIST | LIGHTING 1ST FIX OPEN FLOOR AREA
CHECKPOINT | LIGHTING AREAS WIRED AS PER ELECTRICAL LIGHTING DRAWING
CHECKPOINT | EACH LIGHTING CIRCUIT WIRED BACK TO NEW TENANCY DB CONTACTOR
CHECKPOINT | EACH LIGHTING CIRCUIT LABELLED AND CONFIRMED AREA IT IS SWITCHING
CHECKPOINT | EMERGENCY LIGHTING CIRCUIT WIRED BACK TO ITS CORRESPONDING CIRCUIT
CHECKPOINT | EMERGENCY LIGHTING CABLE IS LABELLED AND CONFIMRED
CHECKPOINT | ALL CABLES ARE CABLE TIED ONTO ITS CATENERY WIRES NEATLY.
CHECKPOINT | CONTROL SWITCH WIRES INSTALLED BETWEEN TENANCY DB CONTACTOR AND LSP
CHECKPOINT | LSP FLUSH BOX INSTALLED IN AGREED LOCATION AND AT AGREED HEIGHT
CHECKLIST | LIGHTING 2ND FIX OPEN FLOOR AREA
CHECKPOINT | SURFACE SOCKETS AND LEADS INSTALLED ON ALL LED PAN LIGHTS
CHECKPOINT | SURFACE SOCKETS INSTALLED FOR ALL EMERGENCY SPITFIRES
CHECKPOINT | NEW PAN FITTINGS INSTALLED AS PER LIGHTING LAYOUT
CHECKPOINT | EXISTING PAN FITTINGS INSTALLED AS PER LIGHTING LAYOUT
CHECKPOINT | EXISTING EM AND EXIT FITTINGS INSTALLED AS PER LIGHTING LAYOUT
CHECKPOINT | ALL EM AND EXIT FITTINGS LABELLED AND PLOTTED ON AS BUILT
CHECKPOINT | ALL EM AND EXIT FITTINGS COMMISSIONED BY IN HOUSE ELECTRICIAN
CHECKPOINT | LSP SWITCH INSTALLED AND SWITCHING CORRECTLY TO ZONES
CHECKLIST | POWER 1ST FIX OPEN AREA
CHECKPOINT | CORRET CABLE CIRCUITS LABELLED AND CONFIRMED FOR EACH POWER CIRCUITS
CHECKPOINT | POWER CABLES INSTALLED AS PER ELECTRICAL LAYOUT
CHECKPOINT | CORRECT SIZE CABLE INSTALLED TO POWER LOCATIONS
CHECKPOINT | POWER CABLES CABLE TIED NEATLY ON CATENARY WIRE
CHECKPOINT | POWER CABLES LABELLED AND CONFIMRED WITH CORRECT CIRCUIT.
CHECKPOINT | POWER CABLES DROPPED IN CORRECT LOCATION.
CHECKPOINT | FLUSH BOXES MOUNTED AND LOCATION CONFIMRED.
CHECKLIST | POWER 2ND FIX OPEN AREA
CHECKPOINT | POWER POINTS FITTED OFF AS PER ELECTRICAL LAYOUT
CHECKPOINT | POWER POINTS LABELLED AND LIVEN TO CORRECT DB
CHECKPOINT | POWER POINTS TESTED AND COMMISSIONED.
CHECKPOINT | ALL TEST RESULTS DOCUMENTED ON COMMISSIONING SHEET
CHECKLIST | POWER 1ST FIX BATHROOM
CHECKPOINT | POWER CABLE CIRCUITS RAN TO DB - HOUSE COMPARTMENT IN DB RISER CUPBOARD
CHECKPOINT | CORRET CABLE CIRCUITS LABELLED AND CONFIRMED FOR EACH POWER CIRCUITS
CHECKPOINT | POWER CABLES INSTALLED AS PER ELECTRICAL LAYOUT
CHECKPOINT | CORRECT SIZE CABLE INSTALLED TO POWER LOCATIONS
CHECKPOINT | POWER CABLES CABLE TIED NEATLY ON CATENARY WIRE
CHECKPOINT | POWER CABLES LABELLED AND CONFIMRED WITH CORRECT CIRCUIT.
CHECKPOINT | POWER CABLES DROPPED IN CORRECT LOCATION.
CHECKPOINT | FLUSH BOXES MOUNTED AND LOCATION CONFIMRED.
CHECKPOINT | FLUSH BOX MOUNTED ABOVE SINK AT 1500MM AFFL FOR RCD OUTLET IN MALE/FEMALE BATHROOM
CHECKPOINT | FLUSH BOX MOUNTED AT 500MM AFFL FOR OTHER OUTLETS IN MALE/FEMALE BATHROOM
CHECKLIST | POWER 2ND FIX BATHROOM
CHECKPOINT | POWER POINTS FITTED OFF AS PER ELECTRICAL LAYOUT
CHECKPOINT | POWER POINTS LABELLED AND CONFIRMED TO CORRECT DB
CHECKPOINT | RCD OUTLET FITTED OFF ABOVE SINKS IN MALE/FEMALE BATHROOM AND LIVEN
CHECKPOINT | LOW LEVEL OUTLET FITTED OFF AND LIVEN
CHECKPOINT | POWER POINTS TESTED AND COMMISSIONED.
CHECKPOINT | ALL TEST RESULTS DOCUMENTED ON COMMISSIONING SHEET
CHECKLIST | LIGHTING 1ST FIX BATHROOM
CHECKPOINT | BATHROOM LIGHTING AREAS WIRED AS PER UPDATED ELECTRICAL LIGHTING DRAWING
CHECKPOINT | EXISTING LIGHTING CIRCUIT RELOCATED TO SUIT NEW LAYOUT
CHECKPOINT | EMERGENCY LIGHTING CIRCUIT RELOCATED TO SUIT NEW LAYOUT.
CHECKPOINT | EMERGENCY LIGHTING IS LABELLED AND CONFIMRED
CHECKPOINT | ALL CABLES ARE CABLE TIED ONTO ITS CATENERY WIRES NEATLY.
CHECKPOINT | ELV CABLE DROPPED INTO LOCATION FOR MIRROR LED STRIP IN MALE BATHROOM
CHECKPOINT | ELV CABLE DROPPED INTO LOCATION FOR MIRROR LED STRIP IN FEMALE BATHROOM
CHECKPOINT | AUTO/OFF/MAN FLUSH BOX MOUNTED IN MALE BATHROOM
CHECKPOINT | AUTO/OFF/MAN FLUSH BOX MOUNTED IN FEMALE BATHROOM
CHECKPOINT | AUTO/OFF/MAN FLUSH BOX MOUNTED IN DISABLE BATHROOM
CHECKLIST | LIGHTING 2ND FIX BATHROOM
CHECKPOINT | SURFACE SOCKETS AND TYPE D LIGHT INSTALLED AND WORKING
SENSORS INSTALLED, TESTED AND WORKING
CHECKPOINT | SURFACE SOCKETS AND EM LIGHT INSTALLED AND WORKING
CHECKPOINT | A2 FITTING INSTALLED AS PER ARCHITECTURAL SETOUT AND WORKING
CHECKPOINT | AUTO/OFF/MAN SWITCH INSTALLED AND WORKING IN MALE AND FEMALE TOILETS
CHECKPOINT | AUTO/OFF/MAN SWITCH INSTALLED AND WORKING IN DISABLE TOILET
CHECKPOINT | M1 LED STRIPS INSTALLED AND WORKING IN MALE AND FEMALE TOILETS.
CHECKPOINT | M1 LED DRIVER INSTALLED IN ACCESSIABLE LOCATION
CHECKLIST | LIGHTING 1ST FIX LOBBY
CHECKPOINT | LIGHTING AREAS WIRED AS PER ELECTRICAL LIGHTING DRAWING
CHECKPOINT | EXISTING LIGHTING CIRCUIT RELOCATED TO SUIT NEW LAYOUT
CHECKPOINT | EMERGENCY LIGHTING CIRCUIT RELOCATED TO SUIT NEW LAYOUT.
CHECKPOINT | EMERGENCY LIGHTING IS LABELLED AND CONFIMRED
CHECKPOINT | ALL CABLES ARE CABLE TIED ONTO ITS CATENERY WIRES NEATLY.
CHECKLIST | LIGHTING 2ND FIX LOBBY
CHECKPOINT | SURFACE SOCKETS INSTALLED FOR TYPE D LIGHTS
CHECKPOINT | SURFACE SOCKETS INSTALLED FOR EMERGENCY SPITFIRES
CHECKPOINT | EM AND EXIT FITTINGS INSTALLED AS PER LIGHTING LAYOUT
CHECKPOINT | EM AND EXIT FITTINGS LABELLED AND PLOTTED ON AS BUILT
CHECKPOINT | EM AND EXIT FITTINGS COMMISSIONED BY IN HOUSE ELECTRICIAN
CHECKPOINT | A3 FITTING INSTALLED AND WORKING
CHECKLIST | DISTRIBUTION BOARD - AON LEVEL 7 SWITCHBOARD
CHECKPOINT | NEW UPGRADED SWITCBOARD INSTALLED IN LOCATED AND SECURED
CHECKPOINT | DB-HOUSE NEW SUB MAINS TAILS CONNECTED INTO MCCB AND MAIN SWITCH
CHECKPOINT | TENANCY A SUB MAINS CONNECTED INTO MAIN SWITCH AND MCCB
CHECKPOINT | TENANCY B SUB MAINS CONNECTED INTO MAIN SWITCH AND MCCB
CHECKPOINT | DB-HOUSE SUB MAINS CONNECTED INTO TAP OFF BOX
CHECKPOINT | RISER TAP OFF BOX SUB MAINS CONNECTED TO TENANCY CHASIE MAIN SWITCH
CHECKPOINT | STRUCTURAL BONDING CABLE TERMINATED AT SWITCHBOARD.
CHECKPOINT | DB SCHEDULE COMPLETED
CHECKPOINT | DISTRIBUTION BOARD TEST SHEET COMPLETED
CHECKPOINT | DB SCHEDULE INSTALLED
CHECKPOINT | CLEAN OF ALL DEBRI AND MARKS
CHECKLIST | DISTRIBUTION BOARD - COMMISSIONING - AON LEVEL 7 SWITCHBOARD
CHECKPOINT | SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DB SCHEDULE COMPLETED, INSTALLED INTO DB AND ADDED TO DROPBOX
CHECKPOINT | DISTRIBUTION BOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DISTRIBUTION BOARD CHECK SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | EARTH BOND TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | TIMECLOCK TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | BOARD FREE FROM DEBRI, NO MARKS, ALL ACCESSORIES INSTALLED
CHECKPOINT | LABELLING COMPLETED ON ALL FIELD OUTLETS, SWITCHES AND ISOLATORS ETC
CHECKPOINT | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX