## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 60c2b040-aa6e-4961-9f36-569d1c8d77aa |  | checklist | Fire Hydrant QA |  |  |  |  | Yes | Fire Hydrant QA | 2fb995c0-88d8-46e2-adf9-0ce58625416f
checkpoint-group | 83d6b6d9-37e2-4043-a928-f45b1682a833 |  | section | Fire Hydrant - First Fix
checkpoint-status | 68e68a15-7034-4ddb-bf3f-449d998bbde2 |  | checkpoint | Substrate acceptable
checkpoint-status | 349e7b80-fa59-4a7d-a880-e201a76505af |  | checkpoint | Area accessible
checkpoint-status | e04c3425-1045-419e-9389-de7e8fda2e3c |  | checkpoint | First Fix completed and area cleared of waste (photos attached)
holdpoint | 3dcac318-350a-4696-a7d4-b7d1ea7b5641 |  | signoff | Main contractor sign off
checklist-sectioned | 9a924003-7efb-4c48-8d76-3a47094d87d3 |  | checklist | S - S - Fire Sprinkler |  |  |  |  | Yes | S - S - Fire Sprinkler | 35285400-55da-4994-a980-93e43eec3077
checkpoint-group | e36fc247-c838-488b-a3ae-c700c2348d8d |  | section | First Fix
checkpoint-status | b3381ccb-3aab-451c-a7a5-a5ce7e7fc43f |  | checkpoint | Substrate acceptable
checkpoint-status | 65a4826e-ad03-4429-be4a-94818772ed36 |  | checkpoint | Area accessible
checkpoint-status | 5e274cd7-033a-4653-8f8f-e93382f3ce1e |  | checkpoint | First fix completed and area cleared of waste
checkpoint-status | e9804e7c-20cd-4d02-a0b3-eba3aa2b7dc9 |  | checkpoint | Main contractor sign off
checkpoint-group | 973c0feb-f8aa-4448-ba10-adac0252338d |  | section | Second Fix
checkpoint-status | 31362e8a-673d-439a-acf3-11fe33cb11e3 |  | checkpoint | Second fix completed in all aspects and area cleared of waste
holdpoint | 6a2bcbec-3018-4731-a64c-e1dd034e729a |  | signoff | Main contractor sign off
checkpoint-group | 9b4673bf-dd84-4961-bada-def560f4c370 |  | section | Pressure Test
checkpoint-status | cab40441-3761-44f4-bfbc-594d4dc92ca1 |  | checkpoint | Pressure Test Info
checkpoint-status | 792229eb-2e3a-43a0-b384-557637242f3c |  | checkpoint | System pressure test details
checkpoint-status | 8896f420-e9a3-40da-bbdd-9addb59b8f6c |  | checkpoint | Installation conforms to accepted plans
checkpoint-status | 6ace52eb-e8ed-452f-83c8-90544954f290 |  | checkpoint | Equipment used is approved
checkpoint-status | eb4737d1-80ba-4e95-b320-b4e32e2fae30 |  | checkpoint | Test Results
checkpoint-status | 719d641b-3fe8-4e74-b004-87d1360cc1dc |  | checkpoint | Retest required
checkpoint-status | 25a2cca1-79da-41d5-bd89-ca5aaec49dec |  | checkpoint | Installer review completed
checkpoint-status | 965d9e93-2f57-4b6e-8269-2eb9a49d3081 |  | checkpoint | Main contractor review completed
holdpoint | 21ed8a60-23ca-48b8-806d-a5fa8d05b69c |  | signoff | Main contractor sign off
checklist-flat | 48618fc3-99d5-4ea9-bacf-1b08b107f5af |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 36ed9d4e-fabc-4ade-9d1e-aeea09b33cff
checkpoint-status | 7ffdf405-be9c-4ca9-86ba-d71ea9315da2 |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | d3b1853d-276b-54cb-8218-03df4ead3f59 |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 420e367e-70f7-5291-8a88-5f5ac0b1ef61 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | 9cb46c75-0014-4e08-8dce-41c3dc4d92d8 |  | signoff | Request Signoff
checklist-sectioned | dd931ca8-c8ad-4215-bd52-478c3b33b90b |  | checklist | S - S - Fire Alarm |  |  |  |  | Yes | S - S - Fire Alarm | 540b8334-2aa7-4bd0-952d-e2a6aea120dd
checkpoint-group | 7e8b9a87-9fed-4ca6-b6dc-98688062c5d8 |  | section | First Fix
checkpoint-status | cf80ed2c-303a-4273-989a-6f94797040d7 |  | checkpoint | Substrate acceptable
checkpoint-status | 2a255589-5df9-4847-84ed-a75731d1429e |  | checkpoint | Area accessible
checkpoint-status | ecde9c3d-87b7-4ebf-8a5a-ac2e63fb971a |  | checkpoint | Flush boxes fitted
checkpoint-status | 91cc82b4-6b6d-45a2-97b0-997e4e83b883 |  | checkpoint | Ready to line walls
checkpoint-status | d84b2dc4-1fa9-43ec-84f1-17a1b370ca10 |  | checkpoint | Ready to line ceiling
checkpoint-status | f0f16ab2-8d1b-4caf-a328-d355e247e18b |  | checkpoint | First fix completed and area cleared of waste
checkpoint-status | 82f9ff46-5d05-4ee2-87f4-2df2a0aeb9cd |  | checkpoint | Main contractor sign off
checkpoint-group | 4c3c179b-8eb0-4355-bfae-01b78592880f |  | section | Second Fix
checkpoint-status | cccf8300-1b20-4b1c-a842-3170cdaf4732 |  | checkpoint | Ceiling fitted off
checkpoint-status | f9357865-59bc-4486-830d-03507808d90b |  | checkpoint | Walls fitted off
checkpoint-status | e69c3014-2c42-45f8-bc5a-a356acc5c01f |  | checkpoint | Second fix completed in all aspects and area cleared of waste
checklist-flat | 011c65b5-0fd9-49f7-ba74-2dda0516b80f |  | checklist | B03&B04 - BCO10298055-2, BCO10298055-3, BCO10298055-4 |  |  |  |  | Yes | Completion Documentation | 587f9d12-fb28-4997-aab4-315b9ed6ea78
checkpoint-status | 3a996ff4-73d6-4d0a-b586-b896a45babc0 |  | checkpoint | Sprinkler and fire alarm system PS3 - Type 4 & Type 7
checkpoint-status | a40397ed-6d90-4e26-b436-ee4897c87404 |  | checkpoint | Monitoring of fire system - Confirmation letter
checkpoint-status | 62fae368-2726-45a7-9697-ded8c4e97ec2 |  | checkpoint | Fire alarm and sprinkler system - Cert of Completion (COC) Letter from AON for inspection
checkpoint-status | 32227875-a08c-466f-8a32-abd5d2417803 |  | checkpoint | Pressure Test results (per zone)
checkpoint-status | 9906d5d7-4f25-4c54-af1e-2524e1697fbe |  | checkpoint | As Built Plans for ALL installed systems (Fire Alarms & Sprinklers)
checkpoint-status | 0c01343c-2159-473c-96de-40690dd7db6a |  | checkpoint | Hydrant Flow Testing Results (for risers)
checkpoint-status | 3e7aefb1-4841-43a0-bdf0-ed1410e797f6 |  | checkpoint | Hydrant Riser Installation and schematic as built plans - PS3
checkpoint-status | 9cc442dd-53c1-40db-98c5-1e1d5d9eb881 |  | checkpoint | Letter from Fire engineer for safe occupancy
checkpoint-status | 988c5adf-51a3-4df1-afd2-11c2c7425437 |  | checkpoint | Fire Hold open - PS3 & As Built Plans
checkpoint-status | da6063bb-0e55-4118-9188-51a5b501542c |  | checkpoint | Fire Alarm Monitoring System monitoring letter from ADT Ltd
checkpoint-status | a5cf5c6f-2db9-4bc0-850d-131bcd6578ba |  | checkpoint | NZ Fire Service - Site visit required to familiarise themselves with the site layout in case of emergency
checklist-sectioned | a809e724-577f-49d0-9bda-9ca48b2d2f98 |  | checklist | Fire Alarm QA |  |  |  |  | Yes | Fire Alarm QA | c1f09f69-812d-4061-99f4-a794881ed6f0
checkpoint-group | 1c805be8-e16f-4803-84c1-dc45ec16a925 |  | section | Fire Alarm - First Fix
checkpoint-status | dfc953bd-9a5a-4243-a6dc-5008395018c8 |  | checkpoint | Substrate acceptable
checkpoint-status | 7ca3c2d3-4837-4c40-8120-1d1d7eeca987 |  | checkpoint | Area accessible
checkpoint-status | cfed5e03-d101-47fa-a917-e2fc89d6143c |  | checkpoint | Flush boxes fitted
checkpoint-status | d744981d-e067-4705-bc51-fb073de8945c |  | checkpoint | Ready to line walls
checkpoint-status | 2be62f00-1bc7-4bdd-ad9b-363201f6f995 |  | checkpoint | Ready to line ceiling
checkpoint-status | 53cfc1bb-f84e-4670-8a6b-81f8d8eac9f1 |  | checkpoint | First fix completed and area cleared of waste (photos attached)
holdpoint | ffdf0056-4cad-490a-bba2-3569ce517cf5 |  | signoff | Main contractor sign off
checkpoint-group | d0419d73-36fd-444c-b9dd-890320c8da79 |  | section | Fire Alarm - Second Fix
checkpoint-status | 6d5e70dc-0ee5-4254-902b-fb9cc4634dfe |  | checkpoint | Ceiling fitted off
checkpoint-status | c5941c25-987c-4ae0-8e16-fb165ba09210 |  | checkpoint | Walls fitted off
checkpoint-status | e7706016-22d6-4c60-9d84-c5ec780c990d |  | checkpoint | Second fix completed in all aspects and area cleared of waste (photos attached)
holdpoint | 4ba6cfa7-f189-4335-9146-383094513b09 |  | signoff | Main contractor sign off
checklist-flat | 2042ffd6-ccfb-4d64-a8d7-93368c0ee0de |  | checklist | Pre-Commencement Checks (B03 & B04) |  |  |  |  | Yes | Pre-Commencement Checklist | d7b3bdea-4a9e-4280-9461-ed29a7116d7d
checkpoint-status | c36b8f4d-a21b-410c-9763-ca5ffb400252 |  | checkpoint | Quality Management Plan Completed, Agreed and Attached
checkpoint-status | 110a3db7-c456-4888-bbf3-c5a7ebeb9415 |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status | ed4a2f8e-3711-475f-bae0-541c24169f74 |  | checkpoint | Relevant Breakdown & Checklist Setup on Conqa & Reviewed by Main Contractor
checkpoint-status | 2613dc1b-12c3-4d5c-9c55-4dbd970b9848 |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status | 043e90ad-37fc-4a44-97e5-e07f63bc9f07 |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status | 9c9b7aa3-d2ae-44f7-8cc4-d810ee25195e |  | checkpoint | Matrix/Insight Setup (if required)
checklist-sectioned | e3f9623a-410d-441a-a6bc-c9d0a69281a3 |  | checklist | Fire Sprinkler QA |  |  |  |  | Yes | Fire Sprinkler QA | f8c66e04-6990-4dd8-bead-8d8973c24f8c
checkpoint-group | b261ae28-4f08-409b-ac5d-7d81b7feb30f |  | section | Fire Sprinkler - First Fix
checkpoint-status | dc032c48-c7a3-4706-a12e-c83733f3dbae |  | checkpoint | Substrate acceptable
checkpoint-status | 722a6470-fdcc-4b93-9ecd-c138e6d3a198 |  | checkpoint | Area accessible
checkpoint-status | 73196fdb-5863-4645-8045-fc38291a4174 |  | checkpoint | First fix completed and area cleared of waste (photos attached)
holdpoint | 0c10e677-cede-49aa-a25e-51635c5ffd4e |  | signoff | Main contractor sign off
checkpoint-group | 695632f0-38ad-4a5f-bedd-e5e1c6cf03a3 |  | section | Fire Sprinkler - Second Fix
checkpoint-status | 035bab11-b20d-41b9-9763-831c3ef932ff |  | checkpoint | Second fix completed in all aspects and area cleared of waste (photos attached)
holdpoint | f38d873e-d215-40ae-ae99-59640779b354 |  | signoff | Main contractor sign off
checkpoint-group | 31e044a3-73e3-4442-abf9-55cfbc1fa543 |  | section | Pressure Test
checkpoint-status | 28f930c0-7b63-4776-8dbd-2fc70e4b5b24 |  | checkpoint | Pressure Test Info
checkpoint-status | d34f415d-2539-4e71-a474-9d79fb193749 |  | checkpoint | System pressure test details
checkpoint-status | 91573a46-5d2c-45bf-80b1-a31e8514b36e |  | checkpoint | Installation conforms to accepted plans
checkpoint-status | e2514af9-4dc9-4a4c-81e0-2049da14fd95 |  | checkpoint | Equipment used is approved
checkpoint-status | ccd38ef1-84b3-43e2-bf51-e3857865ec39 |  | checkpoint | Test Results
checkpoint-status | dd7a46df-a24a-4823-8f4a-759a182c2e50 |  | checkpoint | Retest required
checkpoint-status | bba664b4-722a-40d3-b943-2a97716e63dc |  | checkpoint | Installer review completed
checkpoint-status | 45a8bca6-2d4b-4f49-98b9-f23568572a09 |  | checkpoint | Main contractor review completed
holdpoint | 7b93aa21-c4f6-436b-9102-bef4a840a39b |  | signoff | Main contractor sign off