## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Rough In (Cavity Pockets Only) |  |  |  |  | Yes | Rough In (Cavity Pockets Only) | 0efa85f0-7c31-4639-a869-8203a63c3f9b
checkpoint-status |  |  | checkpoint | Cavity pockets installed
checkpoint-status |  |  | checklist | TV bracket noggins installed (attach photo) |  |  |  |  | Yes | TV bracket noggins installed (attach photo) | 0f1508e4-b942-48b5-bf57-8d44c514dfb1
checklist-flat |  |  | checklist | Rough In (Cavity Pockets, PMJ, Bathroom & Window Noggins) |  |  |  |  | Yes | Rough In (Cavity Pockets, PMJ, Bathroom & Window Noggins) | 1f0e88e6-04f9-41d2-a348-95daeadff256
checkpoint-status |  |  | checkpoint | Cavity pockets installed
checkpoint-status |  |  | checkpoint | Add pressed metal jamb
checkpoint-status |  |  | checkpoint | Add bathroom noggins
checkpoint-status |  |  | checkpoint | Add window noggins
checklist-flat |  |  | checklist | Apartment Rough In Checklist |  |  |  |  | Yes | Rough In Checklist | 2716c462-a73a-468c-8eb8-c5d265722710
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible (attach photo)
checkpoint-status |  |  | checkpoint | Previous substrate acceptable - Walls framed and timber studs installed
checkpoint-status |  |  | checkpoint | Cavity pockets installed
holdpoint |  |  | signoff | Raise remedial / Sign Off
checklist-flat |  |  | checklist | Townhouse Rough In |  |  |  |  | Yes | Townhouse Rough In | 40e3cdd4-10a6-4aab-a26a-b40f394df5db
checkpoint-status |  |  | checkpoint | Garage Reveal
checkpoint-status |  |  | checkpoint | Cavity Slide Pockets
checkpoint-status |  |  | checkpoint | Sanitary Blocking
checkpoint-status |  |  | checkpoint | Ceiling Blocking
checkpoint-status |  |  | checkpoint | Laundry Blocking
checkpoint-status |  |  | checkpoint | External Blocking
checklist-flat |  |  | checklist | Rough In (Cavity Pockets & PMJ) |  |  |  |  | Yes | Rough In (Cavity Pockets & PMJ) | 57af96a3-cfa5-4290-b1a7-a732816f8133
checkpoint-status |  |  | checkpoint | Cavity pockets installed
checkpoint-status |  |  | checkpoint | Add pressed metal jamb
checklist-flat |  |  | checklist | Fit Off |  |  |  |  | Yes | Fit Off | 702d2920-77c1-45fc-a4cf-c13b83d44e50
checkpoint-status |  |  | checkpoint | Installation of door hardware and door closes sufficiently
checkpoint-status |  |  | checkpoint | Bathroom and toilet vanity installed
checkpoint-status |  |  | checkpoint | Handrails, toilet rolls and towel rails installed
checkpoint-status |  |  | checkpoint | Entry door hardware installed and closes sufficiently
checkpoint-status |  |  | checkpoint | Fire tags installed on the door and door jamb
checkpoint-status |  |  | checkpoint | Shower trays installed
checkpoint-status |  |  | checkpoint | Area left clean and tidy (attach photo)
checkpoint-status |  |  | checkpoint | All work 100% completed to required specifications
checklist-flat |  |  | checklist | Installation |  |  |  |  | Yes | Installation | 79d26307-96fd-48ed-8d6f-2c909bae3677
checkpoint-status |  |  | checkpoint | Internal doors hung
checkpoint-status |  |  | checkpoint | Skirting installed
checkpoint-status |  |  | checkpoint | Cavity doors installed
checkpoint-status |  |  | checkpoint | Window architraves installed
checkpoint-status |  |  | checkpoint | Wardrobe jamb installed
checkpoint-status |  |  | checkpoint | Entry door hung
checkpoint-status |  |  | checkpoint | All install work 100% completed to required specifications
checkpoint-status |  |  | checkpoint | Area left clean and tidy (attach photo)
checklist-flat |  |  | checklist | Rough In (PMJ Only) |  |  |  |  | Yes | Rough In (PMJ Only) | 7c7f48ed-dadb-43a9-861e-2521e5d8919d
checkpoint-status |  |  | checkpoint | Add pressed metal jamb
checkpoint-status |  |  | checklist | Sanitary noggins installed (attach photo) |  |  |  |  | Yes | Sanitary noggins installed (attach photo) | 905a5807-86e1-40e2-8992-b47185b81845
checklist-flat |  |  | checklist | Townhouse Fix |  |  |  |  | Yes | Townhouse Fix | c2d99765-b0fa-46f3-83d9-b05f2b9a1552
checkpoint-status |  |  | checkpoint | Internal Doors Hung
checkpoint-status |  |  | checkpoint | Cavity Slide Doors Installed
checkpoint-status |  |  | checkpoint | Window Architraves Installed
checkpoint-status |  |  | checkpoint | Skirting Installed
checkpoint-status |  |  | checkpoint | Wardrobe Jamb Installed
checkpoint-status |  |  | checkpoint | All Install Work 100% Completed to Required Specifications
checkpoint-status |  |  | checkpoint | Area Left Clean & Tidy (Attach Photo)
checklist-flat |  |  | checklist | Townhouse Fit Off |  |  |  |  | Yes | Townhouse Fit Off | cd5f211e-0024-4fb6-bdcb-1657f7d1cb8b
checkpoint-status |  |  | checkpoint | Installation of Door Hardware/Stops & Door Closes Sufficiently
checkpoint-status |  |  | checkpoint | Sanitary Vanity Installed
checkpoint-status |  |  | checkpoint | Sanitary Handrails, Toilet Roll Holder, Heated Towel Rail, Robe Hook
checkpoint-status |  |  | checkpoint | Sanitary Shower Shelves Installed
checkpoint-status |  |  | checkpoint | Area Left Clean & Tidy (Attach Photo)
checklist-flat |  |  | checklist | Handover |  |  |  |  | Yes | Handover | ffab8f87-f711-4276-81c2-ccb731385597
checkpoint-status |  |  | checkpoint | All aspects of works completed and inspected by Ryman Foreman
checkpoint-status |  |  | checkpoint | Any rectification works have been carried out if required
checkpoint-status |  |  | checkpoint | Site left clean and tidy - All excess spoil and materials removed
checkpoint-status |  |  | checkpoint | General photos/comments/observations of Site Prior to Handover
holdpoint |  |  | signoff | ENSURE ALL CHECKPOINTS ARE SATISFACTORILY COMPLETED