## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-070-CIV-CAMMS-Tactile Installation | itp |  |  |  |  | ITP-070-CIV-CAMMS-Tactile Installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-070-CIV-CAMMS-Tactile Installation
label | ITP Description: CAMMS-Tactile Installation
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 070-CIV
label | Revision Number: 0
label | Revision Date: 28/02/2023
label | ITP created by: Chloe Mitchell
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: AS1428.4.1
label | 1.2 Non Dependent
label | Reference: VicRoads Section 160.A9
label | 1.3 Non Dependent
label | Reference: IFC Drawings
section | Preliminaries - Materials
checkpoint | 2.1 Material Conformance
label | REFERENCE: AS1428.4.1 Section 2.2 & 2.3.1
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Tactile Indicators must conform with the requirements of AS1428.1.1 Section 2.2 & 2.3.1
label | Attach: TeamBinder Material Approval Ref No
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to works start
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Documentations
checkpoint | 3.1 Documentation Conformance
label | REFERENCE: DoT Handover Process
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Tactile to be yellow in colour, VicRoads approved as per design note RDN 06-05 and DDA Compliant
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual & Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to works start
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set-out
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The required positions of the tactiles are clearly set out by a surveyor as per IFC Drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Installation
label | REFERENCE: AS1428.4.1 Section 2.3.3
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Notify Nominated Authority prior to installation.
label | Warning indicators shall be installed as follows:
label | (a) For the full width of the path of travel
label | (b) Perpendicular to the direction of travel when approaching the hazard.
label | (c) Set back 300 +/-10 mm from the edge of the hazard except at railway platforms and wharves.
label | (d) Where integrated warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below, over a minimum depth of 600 mm to 800 mm from the direction of approach.
label | (e) Where discrete warning TGSIs are used over a depth of 300 mm to 400 mm, the arrangement shall be as shown in Figure 2.1 below with a minimum of 6 discrete truncated cones in the direction of travel.
label | (f) Where discrete warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below with a minimum of 12 discrete truncated cones in the direction of travel.
label | Where required on a path of travel, warning indicators shall be located at both the top and bottom of stairways, ramps, escalators and moving walks
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual/Site Inspection & Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.2 Laboratory and On-site measurement of luminance contrast
label | REFERENCE: AS1428.4.1 Appendix E
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Submit Test report to AS1428.4.1 E5.4: The following shall be reported:
label | (a) Full description of the surfaces tested with product details where known.
label | (b) The instrument being a luminance meter with a 1° measurement area corrected to approximate the CIE 1931 Standard Observer.
label | (c) The location of the sample, if on-site.
label | (d) The location of the sample of the measurements on the TGSI.
label | (e) A description of the light source(s) illuminating the sample, including type, [e.g. fluorescent tube, incandescent, high pressure sodium discharge, metal halide, and colour (in general terms)].
label | (f) The mean luminous reflectance of the adjacent surrounds to the tactile indicator under the conditions set out in Paragraph E5.3
label | (g) The mean luminous reflectance of the tactile indicator under the conditions set out in Paragraph E5.3
label | (h) The luminance contrast with the surrounds on both sides of the tactile indicator.
label | (i) A reference to this test method, i.e., AS/NZS 1428.4, Paragraph E5, Appendix E.
label | Attach: Laboratory Test report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual/Site Inspection & Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.3 Distance between tactiles and sleeve
label | REFERENCE: DoT Handover Process
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Distance between tactile and sleeve to be a minimum of 300mm as per note 1 of the Handover Process
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 As-built Survey
label | REFERENCE: IFC Drawings VR 160.A9
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: As-constructed’ information shall be progressively documented during the work under the Contract and shall be provided to the Superintendent in a neat and clean format Attach: Survey As-built / Survey Report
label | Attach: Survey Conformance Data/Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP