## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP05 - Steel Reinforcement - Stairs |  |  |  |  | Yes | ITP05 - Steel Reinforcement - Stairs | 35a51015-5291-4c72-ab8a-3be4fd026cda
checkpoint-status |  |  | checkpoint | Check Correct Bar Size
checkpoint-status |  |  | checkpoint | Check Correct Spacing
checkpoint-status |  |  | checkpoint | Check Correct Cover
checkpoint-status |  |  | checkpoint | All pull out/screw bars installed to correct depth
checkpoint-status |  |  | checkpoint | Inspection by Builder/Engineer
checkpoint-status |  |  | checkpoint | Items Closed Out Prior to Pour
checkpoint-status |  |  | checkpoint | Ready for Concrete Placement
label | 23d46850-152b-5b96-9168-a6e78b99f8e2 |  | note | Titan SF pre-pour check sheet has been signed
checklist-flat |  |  | checklist | ITP01 - Steel Reinforcement - Slabs |  |  |  |  | Yes | ITP01 - Steel Reinforcement - Slabs | 437e73ea-7370-4ecc-919f-002aefb1d4db
checkpoint-status |  |  | checkpoint | Latest Drawing Check
checkpoint-status |  |  | checkpoint | Check Correct Lap
checkpoint-status |  |  | checkpoint | Check Correct Bar Size
checkpoint-status |  |  | checkpoint | Check Correct Spacing
checkpoint-status |  |  | checkpoint | Check Correct Lig Sizes
checkpoint-status |  |  | checkpoint | Check Correct Cover
checkpoint-status |  |  | checkpoint | Inspection by Builder/Engineer
checkpoint-status |  |  | checkpoint | Items Closed Out Prior to Pour
checkpoint-status |  |  | checkpoint | Ready for Concrete Placement
label | b8a325e7-8cbd-5945-8be8-23982c5838f6 |  | note | Titan SF pre-pour check sheet has been signed
checklist-flat |  |  | checklist | PT Tendon Extension Report Upload |  |  |  |  | Yes | PT Tendon Extension Report Upload | 449ff6ed-93d1-4441-885d-18501cdb92ac
checkpoint-status |  |  | checkpoint | Tendon Extension Report uploaded below
checklist-flat |  |  | checklist | Grouting ITP |  |  |  |  | Yes | Grouting ITP | 5ae7cde8-ad4e-42e1-9b58-c885ebb07369
checkpoint-status |  |  | checkpoint | Is the work area clear of debris and hoses installed ready for grouting?
checkpoint-status |  |  | checkpoint | Has the correct product been used to undertake grouting works?
checkpoint-status |  |  | checkpoint | Has the grout been mixed as per correct manufacturers specifications?
checkpoint-status |  |  | checkpoint | Have the duct and horizontal joint been filled?
checkpoint-status |  |  | checkpoint | If there is a leak, have the grout tubes been topped up?
checklist-flat |  |  | checklist | PT Post-Pour ITP |  |  |  |  | Yes | PT Post-Pour ITP | 9a8aa99b-75ff-4067-9b4a-132144c6ea47
checkpoint-status |  |  | checkpoint | Drawings and Revisions - uploaded below as necessary
checkpoint-status |  |  | checkpoint | Are the anchor blocks and wedges installed?
checkpoint-status |  |  | checkpoint | Has an initial stress (39kN) been carried out as per design requirements?
checkpoint-status |  |  | checkpoint | Has AusPT received confirmation via Aconex/sighted of the concrete test report prior to commencement of full stress?
checkpoint-status |  |  | checkpoint | Has the concrete test results reached minimum required strength (25mPa) as per Engineer’s requirements? Make a hold point.
checkpoint-status |  |  | checkpoint | Has a full stress (156kN) been carried out as per the design requirements?
checkpoint-status |  |  | checkpoint | Have the extensions been recorded and submitted?
checkpoint-status |  |  | checkpoint | Have the extensions been approved and received?
checkpoint-status |  |  | checkpoint | Have the tendons been cut & sealed?
checkpoint-status |  |  | checkpoint | Confirmation of Structural engineers’ acceptance of stressing record via to grouting
holdpoint |  |  | signoff | HOLDPOINT - Click here to request Engineer signoff
checkpoint-status |  |  | checkpoint | Have the tendons been grouted?
checkpoint-status |  |  | checkpoint | Batch ID and expiration date for grout enterred below
text | ec0945a6-f289-5a03-a9bd-cd45e83a3123 |  | textbox | Batch ID
text | 51971303-4f54-50ce-9528-f8270fcd5846 |  | textbox | Expiration Date
checklist-flat |  |  | checklist | PT Pre-Pour ITP |  |  |  |  | Yes | PT Pre-Pour ITP | 9d2b9ac6-9f19-4459-b97e-d812e43e504a
checkpoint-status |  |  | checkpoint | Drawings and Revisions - uploaded below as necessary
checkpoint-status |  |  | checkpoint | Are the Anchorages securely fixed and anti-burst installed?
checkpoint-status |  |  | checkpoint | Is the duct placed in the correct position and alignment, with joints sealed?
checkpoint-status |  |  | checkpoint | Has the tendon been installed with the correct position and alignment, with joints sealed?
checkpoint-status |  |  | checkpoint | Strand Information entered below
select | df683e79-aa89-5a82-ba93-1149a691cbe6 |  | dropdown | Strand 1 type | 12.7mm,15.2mm,N/A
text | 2f4c989f-4db8-535f-b902-1655c0ff6a6b |  | textbox | Coil Number
select | 2cd74588-ebcf-5a04-a309-144bff965e0a |  | dropdown | Strand 2 type | 12.7mm,15.2mm,N/A
text | 3600a24c-d211-5814-b1e3-08d5b3b1a6f9 |  | textbox | Coil Number
select | 70016ceb-9956-5093-ab7b-56f3e3682774 |  | dropdown | Strand 3 type | 12.7mm,15.2mm,N/A
text | 1b2425b5-86fb-5be1-a94b-94e700169c6b |  | textbox | Coil Number
select | cd5b942f-8681-504b-bc6f-f67d9f1cfb0d |  | dropdown | Strand 4 type | 12.7mm,15.2mm,N/A
text | c1f459c5-db4e-5036-877d-053a1e994818 |  | textbox | Coil Number
checkpoint-status |  |  | checkpoint | Are the Circle Dead Ends used, including anti-burst installed (onion or swage)?
checkpoint-status |  |  | checkpoint | Are tendons profiled correctly and supporting chairs secured?
checkpoint-status |  |  | checkpoint | All pans to have minimum 50mm clearance off of deck
checkpoint-status |  |  | checkpoint | Are grout hoses installed with anchorages sealed?
checkpoint-status |  |  | checkpoint | Has the post-tensioning system been inspected and signed off by an Engineer?
checklist-flat |  |  | checklist | ITP03 - Steel Reinforcement - Columns |  |  |  |  | Yes | ITP03 - Steel Reinforcement - Columns | c695f2ab-2971-4534-b858-2de17342c1f8
checkpoint-status |  |  | checkpoint | Correct Grid Reference on Column tag
checkpoint-status |  |  | checkpoint | Column orientation correct for hydraulic services install
checkpoint-status |  |  | checkpoint | Column Plumb
checkpoint-status |  |  | checkpoint | Reinforcement Installation Complete
label | 83300ba3-e42a-5656-83f6-31948224a373 |  | note | Note any bars that have been cut.
checkpoint-status |  |  | checkpoint | Inspection by Builder/ Engineer
checkpoint-status |  |  | checkpoint | Items closed out Prior to Pour
checkpoint-status |  |  | checkpoint | Ready for Sleeve
checkpoint-status |  |  | checkpoint | Plumbed at deck level and chairs installed
checklist-flat |  |  | checklist | ITP02 - Steel Reinforcement - Core |  |  |  |  | Yes | ITP02 - Steel Reinforcement - Core | ed85ea09-96fa-493d-9847-28df0d5452e1
checkpoint-status |  |  | checkpoint | Latest Drawing Check
checkpoint-status |  |  | checkpoint | Check Correct Bar Size
checkpoint-status |  |  | checkpoint | Check Correct Spacing
checkpoint-status |  |  | checkpoint | Check Correct Cover
checkpoint-status |  |  | checkpoint | Inspection by Builder/Engineer
checkpoint-status |  |  | checkpoint | Items Closed Out Prior to Pour
checkpoint-status |  |  | checkpoint | Ready for Concrete Placement
label | 8f245cba-831c-5c34-bc3d-38bb6218fcc4 |  | note | Titan SF pre-pour check sheet has been signed