## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Hayward Road Bridge No. 131 | itp |  |  |  |  | ITP - Hayward Road Bridge No. 131
section | Preliminary
checkpoint | Pre-Works Documentation
label | SPECIFICATION REFERENCE - Particular Specification, section 2.1, page 75
label | TEST REQUIRED - Insurance, Programme of Works, Traffic Management Plans, Site Safety Plan, Quality Plan, Environemental Management Plan, Temporary Works Designs, Notification Letter, Existing Conditions Report
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Prior to works commencing
label | ACCEPTANCE CRITERIA - Approved by Engineer
label | UCCL - S
label | WSP - H
holdpoint | HOLD POINT
section | Steel Components
checkpoint | Structural Steel and Bolts
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Material properties, Manufacturer's mill certificates
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On supply of materials
label | ACCEPTANCE CRITERIA - Bolts meet AS/NZS 2465. Steelwork meets AS/NZS 5131.
label | UCCL - S
checkpoint | Structural Steel Coating
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Ultrasonic coating thickness, Manufacturer's statement
label | INSPECTION BY - UCCL/Subcontractor
label | TASK TIMING OR TASK FREQUENCY - On completion of steel coating
label | ACCEPTANCE CRITERIA - Approved by Engineer. Bolts meet AS/NZS 1214. Steelwork meets AS/NZS 4680 and AS/NZS 2312.2.
label | UCCL - W
label | WSP - H
holdpoint | HOLD POINT
checkpoint | Structural Steel Welds
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Visual Inspection, Welding certificates
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - At completion of steel fabrication
label | ACCEPTANCE CRITERIA - Approved by Engineer
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
checkpoint | Timber Deck and Handrail Components
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Timber properties
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - On supply of materials
label | ACCEPTANCE CRITERIA - Meets Particular Specification and NZTPA specifications
label | UCCL - W
label | WSP - W
checkpoint | Granular Aggregates
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Grading, Soaked CBR, Crushing Resistance, Clay Index
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - One test per 750m³ stockpiled. Compliance certificate not more than 3 months old.
label | ACCEPTANCE CRITERIA - Approved by Engineer. Compliance certificates not more than 3 months old.
label | UCCL - S
label | WSP - A
checkpoint | Granular Fill Compaction
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 98
label | TEST REQUIRED - Clegg Impact Value
label | INSPECTION BY - UCCL/Engineer
label | TASK TIMING OR TASK FREQUENCY - Three tests per compacted layer (150mm) at each abutment.
label | ACCEPTANCE CRITERIA - As per WDC EES
label | UCCL - W
label | WSP - W
checkpoint | Pavement Compaction
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 98
label | TEST REQUIRED - Clegg Impact Value
label | INSPECTION BY - UCCL/Engineer
label | TASK TIMING OR TASK FREQUENCY - Six tests per compacted layer (150mm) at each abutment.
label | ACCEPTANCE CRITERIA - As per WDC EES
label | UCCL - W
label | WSP - W
checkpoint | Sealing Chip
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 98
label | TEST REQUIRED - Size, Shape, Grading, Cleanness, Crushing Resistance, Weathering Resistance
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Compliance certificate not more than 3 months old.
label | ACCEPTANCE CRITERIA - Approved by Engineer. Compliance certificates not more than 3 months old.
label | UCCL - W
label | WSP - W
checklist | Thompson Road Bridge No. 129 | itp |  |  |  |  | ITP - Thompson Road Bridge No. 129
section | Preliminary
checkpoint | Pre-Works Documentation
label | SPECIFICATION REFERENCE - Particular Specification, section 2.1, page 75
label | TEST REQUIRED - Insurance, Programme of Works, Traffic Management Plans, Site Safety Plan, Quality Plan, Environemental Management Plan, Temporary Works Designs, Notification Letter, Existing Conditions Report
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Prior to works commencing
label | ACCEPTANCE CRITERIA - Approved by Engineer
label | UCCL - S
label | WSP - H
holdpoint | HOLD POINT
section | Steel Components
checkpoint | Structural Steel and Bolts
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Material properties, Manufacturer's mill certificates
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On supply of materials
label | ACCEPTANCE CRITERIA - Bolts meet AS/NZS 2465. Steelwork meets AS/NZS 5131.
label | UCCL - S
checkpoint | Structural Steel Coating
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Ultrasonic coating thickness, Manufacturer's statement
label | INSPECTION BY - UCCL/Subcontractor
label | TASK TIMING OR TASK FREQUENCY - On completion of steel coating
label | ACCEPTANCE CRITERIA - Approved by Engineer. Bolts meet AS/NZS 1214. Steelwork meets AS/NZS 4680 and AS/NZS 2312.2.
label | UCCL - W
label | WSP - H
holdpoint | HOLD POINT
checkpoint | Structural Steel Welds
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Visual Inspection, Welding certificates
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - At completion of steel fabrication
label | ACCEPTANCE CRITERIA - Approved by Engineer
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
checkpoint | Timber Deck and Handrail Components
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Timber properties
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - On supply of materials
label | ACCEPTANCE CRITERIA - Meets Particular Specification and NZTPA specifications
label | UCCL - W
label | WSP - W
checkpoint | Granular Aggregates
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Grading, Soaked CBR, Crushing Resistance, Clay Index
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - One test per 750m³ stockpiled. Compliance certificate not more than 3 months old.
label | ACCEPTANCE CRITERIA - Approved by Engineer. Compliance certificates not more than 3 months old.
label | UCCL - S
label | WSP - A
checkpoint | Granular Fill Compaction
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 98
label | TEST REQUIRED - Clegg Impact Value
label | INSPECTION BY - UCCL/Engineer
label | TASK TIMING OR TASK FREQUENCY - Three tests per compacted layer (150mm) at each abutment.
label | ACCEPTANCE CRITERIA - As per WDC EES
label | UCCL - W
label | WSP - W
checkpoint | Pavement Compaction
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 98
label | TEST REQUIRED - Clegg Impact Value
label | INSPECTION BY - UCCL/Engineer
label | TASK TIMING OR TASK FREQUENCY - Six tests per compacted layer (150mm) at each abutment.
label | ACCEPTANCE CRITERIA - As per WDC EES
label | UCCL - W
label | WSP - W
checkpoint | Sealing Chip
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 98
label | TEST REQUIRED - Size, Shape, Grading, Cleanness, Crushing Resistance, Weathering Resistance
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Compliance certificate not more than 3 months old.
label | ACCEPTANCE CRITERIA - Approved by Engineer. Compliance certificates not more than 3 months old.
label | UCCL - W
label | WSP - W
checklist | McAlister Road Bridge No. A117A | itp |  |  |  |  | ITP - McAlister Road Bridge No. A117A
section | Preliminary
checkpoint | Pre-Works Documentation
label | SPECIFICATION REFERENCE - Particular Specification, section 2.1, page 75
label | TEST REQUIRED - Insurance, Programme of Works, Traffic Management Plans, Site Safety Plan, Quality Plan, Environemental Management Plan, Temporary Works Designs, Notification Letter, Existing Conditions Report
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Prior to works commencing
label | ACCEPTANCE CRITERIA - Approved by Engineer
label | UCCL - S
label | WSP - H
holdpoint | HOLD POINT
section | Steel Components
checkpoint | Structural Steel and Bolts
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Material properties, Manufacturer's mill certificates
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On supply of materials
label | ACCEPTANCE CRITERIA - Bolts meet AS/NZS 2465. Steelwork meets AS/NZS 5131.
label | UCCL - S
checkpoint | Structural Steel Coating
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Ultrasonic coating thickness, Manufacturer's statement
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - On completion of steel coating
label | ACCEPTANCE CRITERIA - Approved by Engineer. Bolts meet AS/NZS 1214. Steelwork meets AS/NZS 4680 and AS/NZS 2312.2.
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
checkpoint | Structural Steel Welds
label | SPECIFICATION REFERENCE - Particular Specification, section 1.1.17, page 97
label | TEST REQUIRED - Visual Inspection, Welding certificates
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Throughout steel fabrication
label | ACCEPTANCE CRITERIA - Approved by Engineer
label | UCCL - H
label | WSP - H
holdpoint | HOLD POINT
checkpoint | Superstrucutral Removal
label | SPECIFICATION REFERENCE - Particular Specification, section 13.3.1, page 88
label | TEST REQUIRED - Visual Inspection
label | INSPECTION BY - Engineer
label | TASK TIMING OR TASK FREQUENCY - Engineer's observation of superstructural removal
label | ACCEPTANCE CRITERIA - Approved by Engineer
label | UCCL - W
label | WSP - W
checkpoint | Capping Beam and Columns
label | SPECIFICATION REFERENCE - Particular Specification, section2.1.1.3, page99
label | TEST REQUIRED - Supplier Docket
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to delivery to site
label | ACCEPTANCE CRITERIA - Timber is Greenheart hardwood, 250mm x 250mm
label | UCCL - H
label | WSP - V
holdpoint | HOLD POINT