## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Preparation - Moisture Fix
section | Details
checkpoint | Check area clear of all other trades and their materials
checkpoint | Have moisture readings been taken or is it required
checkpoint | Is the pH level acceptable?
checkpoint | Check the concrete substrate dryness (RH)
checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
checkpoint | Grind Floor
checkpoint | Does floor have U3 finish (3mm variance over 3m)
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply Moisture Fix
checkpoint | Disc purged material
checkpoint | Apply Floor Levelling Compound
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Floor Preparation
section | Details
checkpoint | Check area clear of all other trades and their materials
checkpoint | Confirm if grinding, floor levelling or ramping has been allowed for - ask Project Supervisor
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Tile Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required and been allowed for - Ask Project Supervisor
checkpoint | Measure area
section | Installation
checkpoint | Confirm carpet tile pattern direction/layout
checkpoint | Confirm correct carpet tile is used for areas as per plan - include stock room , entry
checkpoint | Glue out floors
checkpoint | Install carpet tiles
checkpoint | Install trims as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL