## SWB1
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Ryan King |  | Action | Sydney Street Drainage Renewal
Manager |  | Alex Mattingly |  |  | W | Witness | StormWater Stage 1 - Sydney Street, Invercargill
Divisional/Regional/General Manager |  | Ed Palmer |  |  | H | Hold Point
Engineer |  | Rob Hayes |  |  | M | Monitor | Job Number: |  | 4530 | Version: | OO1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | ITP sign off |  | Sign off | H | Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed. | Prior to commencement | Review | Sign This ITP | Divisional Manager
2 | Materials to comply with contract specification | SR10.103 SR10.105 | Aggregate Certification | W | Laboratory test certificates: MDD and Grading Results | Prior to commencement | Lab report | Sign This ITP | Contract Manager
3 | Materials testing to be provided to Engineer for acceptance | SR10.103 SR10.105 | Aggregate Acceptance | W | Laboratory test certificates: MDD and Grading Results | Prior to commencement | Lab report | Sign This ITP | Contract Manager
4 | Ensure Approved Plans are on site. Safety/ Environmental/ Quality/ Asbestos/ TTMP/ Permits/ Consents/ Site Plans |  | Review | W | All plans/ permits produced under pre construction avaiable on site al all times | Prior to commencement | Review | Sign This ITP | Contract Manager
5 | Notice to Engineer Reveiewed by Divisional Manager |  | Review | W | All NTE's to be reviewed | Prior to submission to Engineer | Review | Sign This ITP | Contract Manager
6 | Variations Reveiewed by Divisional Manager |  | Review | W | All Variations to be reviewed | Prior to submission to Engineer | Review | Sign This ITP | Contract Manager
7 | Site Precondition Inspection |  | Review | W | Video record site walk over | Prior to work starting on site | Video | Sign This ITP | Contract Manager
8 | Pownet and Chorus loactes completed |  | Inspection | H | PowerNet and Chorus has been located, refernce back to plans to ensure everthing has been located | Prior to commencement | Inspection | Sign This ITP | Supervisor / Forman
9 | Correct materials delivered to site in acceptable condition |  | Material inspection | W | Complete inspection of materials as they arrive to site (particularly the concrete pipe) Engineers Rep to inspect materials | Upon pipe delvery | Inspection | Sign This ITP | Supervisor / Forman
10 | New StormWater Main Alignment | Construciton drawings | Inspection / Test Point | H | Alignment to be setout and confirmed on site by Engineers Rep | Prior to commencement | Inspection | Sign This ITP | Engineers Rep
11 | Inspect subgrade | AS/NZS 2566.2:2002 | Inspection/Scala | M | Inspect subgrade as exposed and scala if required, contact manager for further instruction if deemed unsuitable | During Construction | Inspection / Scala | Sign This ITP | Foreman
12 | Pipe Laying | AS/NZS 2566.2:2003 and Contract Doc | Pipe Laying | M | Pipe to be laid as per spec, contract and plans. | During Construction | Spot checks | Sign This ITP | Foreman/Supervisor
13 | Saddles onto main for laterals and sumps | Construciton drawings | Sign off | W | Instal as per construction plans | During Installation | Photos | Sign This ITP | Foreman
14 | Compaction of bedding | Contract Doc | Bedding | M | Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least). | During Construction | Monitor | Sign This ITP | Foreman
15 | 2550dia. Manhole Installation 1A-01 (if required) | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist
16 | 1500dia. Manhole Installation 1A-02 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist
17 | 1050dia. Manhole Installation 1A-03 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist
18 | 1050dia. Manhole Installation 1A-04 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist
19 | Road Sump Installation | Contract Doc | Inspection | W | Complete Sump Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Sump checklist for each sump
20 | Concrete Placement |  | Inspection | W | Engineers Rep to have viewed / inspected concrete formwork | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Photos & Concrete Dockets
21 | Encountered Services | Contract Doc Appendix X | Record | W | Record service on ICC encountered serives record sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor
22 | Drainage Connection | Contract Doc Appendix XI | Record | W | Record detail on ICC drainage connection sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor | Complete ICC drainage sheet for each laterial
23 | Plateau Testing |  | Test | H | Plateau test to be undertaken at start of backfill to calibrate compaction methodology | Test to be carried out at the start of backfilling | Test | Sign This ITP | Contract Manager | NDM test record
24 | Compaction of AP65 - Clegg tests | Contract Doc Appendix XIII | Rocord | W | AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet | During Construction | Clegg Test | Sign This ITP | Foreman/Supervisor | Complete ICC Clegg record sheet
25 | Compaction of AP65 - Test results to Engineer | Contract Doc | Test Point | W | AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
26 | Compaction of AP40 - Test results to Engineer | Contract Doc | Test Point | W | The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
27 | Flush and CCTV line |  | Inspection | H | Flush and CCTV line and pass footage back to engineer for review | Prior to asphalt | Inspection | Sign This ITP | Contract Manager
28 | Asphalt prep |  | Sign off | H | Engineer to approve area is ready for asphalt (including overcuts) . Prep is 50mm and has fall and compaction results have been recived | Prior to asphalt | Inspection | Sign This ITP | Engineer

## FWB1
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Ryan King |  | Action | Sydney Street Drainage Renewal
Manager |  | Alex Mattingly |  |  | W | Witness | FoulSewer Stage 1 - Sydney Street, Invercargill
Divisional/Regional/General Manager |  | Ed Palmer |  |  | H | Hold Point
Engineer |  | Rob Hayes |  |  | M | Monitor | Job Number: |  | 4530 | Version: | OO1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | ITP sign off |  | Sign off | H | Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed. | Prior to commencement | Review | Sign This ITP | Divisional Manager
2 | Materials to comply with contract specification | SR10.103 SR10.105 | Aggregate Certification | W | Laboratory test certificates: MDD and Grading Results | Prior to commencement | Lab report | Sign This ITP | Contract Manager
3 | Materials testing to be provided to Engineer for acceptance | SR10.103 SR10.105 | Aggregate Acceptance | W | Laboratory test certificates: MDD and Grading Results | Prior to commencement | Lab report | Sign This ITP | Contract Manager
4 | Ensure Approved Plans are on site. Safety/ Environmental/ Quality/ Asbestos/ TTMP/ Permits/ Consents/ Site Plans |  | Review | W | All plans/ permits produced under pre construction avaiable on site al all times | Prior to commencement | Review | Sign This ITP | Contract Manager
5 | Notice to Engineer Reveiewed by Divisional Manager |  | Review | W | All NTE's to be reviewed | Prior to submission to Engineer | Review | Sign This ITP | Contract Manager
6 | Variations Reveiewed by Divisional Manager |  | Review | W | All Variations to be reviewed | Prior to submission to Engineer | Review | Sign This ITP | Contract Manager
7 | Site Precondition Inspection |  | Review | W | Video record site walk over | Prior to work starting on site | Video | Sign This ITP | Contract Manager
8 | Pownet and Chorus loactes completed |  | Inspection | H | PowerNet and Chorus has been located, refernce back to plans to ensure everthing has been located | Prior to commencement | Inspection | Sign This ITP | Supervisor / Forman
9 | Correct materials delivered to site in acceptable condition |  | Material inspection | W | Complete inspection of materials as they arrive to site (particularly the concrete pipe) | Upon pipe delvery | Inspection | Sign This ITP | Supervisor / Forman
10 | New FoulSewer Main Alignment | Construciton drawings | Inspection / Test Point | H | Alignment to be setout and confirmed on site by Engineers Rep | Prior to commencement | Inspection | Sign This ITP | Engineers Rep
11 | Inspect subgrade | AS/NZS 2566.2:2002 | Inspection/Scala | M | Inspect subgrade as exposed and scala if required, contact manager for further instruction if deemed unsuitable | During Construction | Inspection / Scala | Sign This ITP | Foreman
12 | Pipe Laying | AS/NZS 2566.2:2003 and Contract Doc | Pipe Laying | M | Pipe to be laid as per spec, contract and plans. | During Construction | Spot checks | Sign This ITP | Foreman/Supervisor
13 | Saddles onto main for laterals and sumps | Construciton drawings | Sign off | W | Instal as per construction plans | During Installation | Photos | Sign This ITP | Foreman
14 | Compaction of bedding | Contract Doc | Bedding | M | Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least). | During Construction | Monitor | Sign This ITP | Foreman
15 | 1050dia. Manhole Installation F24669 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist
16 | 1050dia. Manhole Installation F21508 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist
17 | 1050dia. Manhole Installation F21500 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist
18 | Concrete Placement |  | Inspection | W | Engineers Rep to have viewed / inspected concrete formwork | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Photos & Concrete Dockets
19 | Encountered Services | Contract Doc Appendix X | Record | W | Record service on ICC encountered serives record sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor
20 | Drainage Connection | Contract Doc Appendix XI | Record | W | Record detail on ICC drainage connection sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor | Complete ICC drainage sheet for each laterial
21 | Plateau Testing |  | Test | H | Plateau test to be undertaken at start of backfill to calibrate compaction methodology | Test to be carried out at the start of backfilling | Test | Sign This ITP | Contract Manager | NDM Test record
22 | Compaction of AP65 - Clegg tests | Contract Doc Appendix XIII | Rocord | W | AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet | During Construction | Clegg Test | Sign This ITP | Foreman/Supervisor | Complete ICC Clegg record sheet
23 | Compaction of AP65 - Test results to Engineer | Contract Doc | Test Point | W | AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM Test record
24 | Compaction of AP40 - Test results to Engineer | Contract Doc | Test Point | W | The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM Test record
25 | Flush and CCTV line |  | Inspection | H | Flush and CCTV line and pass footage back to engineer for review | Prior to asphalt | Inspection | Sign This ITP | Contract Manager
26 | Asphalt prep |  | Sign off | H | Engineer to approve area is ready for asphalt (including overcuts). Prep is 50mm and has fall and compaction results have been recived | Prior to asphalt | Inspection | Sign This ITP | Engineer