## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Construction - StormWater Stage 1 - Sydney Street, Invercargill | itp
section | Details
checkpoint | 1 - ITP sign off
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed.
label | Frequency - Prior to commencement
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Divisional Manager
holdpoint | HOLD POINT
checkpoint | 2 - Materials to comply with contract specification
label | Specification / Standard - SR10.103 SR10.105
label | Inspection / Test Point - Aggregate Certification
label | ACTION - W
label | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
label | Frequency - Prior to commencement
label | Inspection / Test Method - Lab report
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 3 - Materials testing to be provided to Engineer for acceptance
label | Specification / Standard - SR10.103 SR10.105
label | Inspection / Test Point - Aggregate Acceptance
label | ACTION - W
label | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
label | Frequency - Prior to commencement
label | Inspection / Test Method - Lab report
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 4 - Ensure Approved Plans are on site. Safety/ Environmental/ Quality/ Asbestos/ TTMP/ Permits/ Consents/ Site Plans
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All plans/ permits produced under pre construction avaiable on site al all times
label | Frequency - Prior to commencement
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 5 - Notice to Engineer Reveiewed by Divisional Manager
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All NTE's to be reviewed
label | Frequency - Prior to submission to Engineer
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 6 - Variations Reveiewed by Divisional Manager
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All Variations to be reviewed
label | Frequency - Prior to submission to Engineer
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 7 - Site Precondition Inspection
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - Video record site walk over
label | Frequency - Prior to work starting on site
label | Inspection / Test Method - Video
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 8 - Pownet and Chorus loactes completed
label | Inspection / Test Point - Inspection
label | ACTION - H
label | Conformance Criteria (Whats Required) - PowerNet and Chorus has been located, refernce back to plans to ensure everthing has been located
label | Frequency - Prior to commencement
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor / Forman
holdpoint | HOLD POINT
checkpoint | 9 - Correct materials delivered to site in acceptable condition
label | Inspection / Test Point - Material inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete inspection of materials as they arrive to site (particularly the concrete pipe) Engineers Rep to inspect materials
label | Frequency - Upon pipe delvery
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor / Forman
checkpoint | 10 - New StormWater Main Alignment
label | Specification / Standard - Construciton drawings
label | Inspection / Test Point - Inspection / Test Point
label | ACTION - H
label | Conformance Criteria (Whats Required) - Alignment to be setout and confirmed on site by Engineers Rep
label | Frequency - Prior to commencement
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Engineers Rep
holdpoint | HOLD POINT
checkpoint | 11 - Inspect subgrade
label | Specification / Standard - AS/NZS 2566.2:2002
label | Inspection / Test Point - Inspection/Scala
label | ACTION - M
label | Conformance Criteria (Whats Required) - Inspect subgrade as exposed and scala if required, contact manager for further instruction if deemed unsuitable
label | Frequency - During Construction
label | Inspection / Test Method - Inspection / Scala
label | Verification Records - Sign This ITP
label | Signatory - Foreman
checkpoint | 12 - Pipe Laying
label | Specification / Standard - AS/NZS 2566.2:2003 and Contract Doc
label | Inspection / Test Point - Pipe Laying
label | ACTION - M
label | Conformance Criteria (Whats Required) - Pipe to be laid as per spec, contract and plans.
label | Frequency - During Construction
label | Inspection / Test Method - Spot checks
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
checkpoint | 13 - Saddles onto main for laterals and sumps
label | Specification / Standard - Construciton drawings
label | Inspection / Test Point - Sign off
label | ACTION - W
label | Conformance Criteria (Whats Required) - Instal as per construction plans
label | Frequency - During Installation
label | Inspection / Test Method - Photos
label | Verification Records - Sign This ITP
label | Signatory - Foreman
checkpoint | 14 - Compaction of bedding
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Bedding
label | ACTION - M
label | Conformance Criteria (Whats Required) - Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least).
label | Frequency - During Construction
label | Inspection / Test Method - Monitor
label | Verification Records - Sign This ITP
label | Signatory - Foreman
checkpoint | 15 - 2550dia. Manhole Installation 1A-01 (if required)
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
label | Frequency - During Construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete SR Manhole checklist
checkpoint | 16 - 1500dia. Manhole Installation 1A-02
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
label | Frequency - During Construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete SR Manhole checklist
checkpoint | 17 - 1050dia. Manhole Installation 1A-03
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
label | Frequency - During Construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete SR Manhole checklist
checkpoint | 18 - 1050dia. Manhole Installation 1A-04
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
label | Frequency - During Construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete SR Manhole checklist
checkpoint | 19 - Road Sump Installation
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete Sump Install Checklist
label | Frequency - During Construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete SR Sump checklist for each sump
checkpoint | 20 - Concrete Placement
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Engineers Rep to have viewed / inspected concrete formwork
label | Frequency - During Construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Photos & Concrete Dockets
checkpoint | 21 - Encountered Services
label | Specification / Standard - Contract Doc Appendix X
label | Inspection / Test Point - Record
label | ACTION - W
label | Conformance Criteria (Whats Required) - Record service on ICC encountered serives record sheet
label | Frequency - During Construction
label | Inspection / Test Method - Record
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
checkpoint | 22 - Drainage Connection
label | Specification / Standard - Contract Doc Appendix XI
label | Inspection / Test Point - Record
label | ACTION - W
label | Conformance Criteria (Whats Required) - Record detail on ICC drainage connection sheet
label | Frequency - During Construction
label | Inspection / Test Method - Record
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete ICC drainage sheet for each laterial
checkpoint | 23 - Plateau Testing
label | Inspection / Test Point - Test
label | ACTION - H
label | Conformance Criteria (Whats Required) - Plateau test to be undertaken at start of backfill to calibrate compaction methodology
label | Frequency - Test to be carried out at the start of backfilling
label | Inspection / Test Method - Test
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
label | Comments - NDM test record
holdpoint | HOLD POINT
checkpoint | 24 - Compaction of AP65 - Clegg tests
label | Specification / Standard - Contract Doc Appendix XIII
label | Inspection / Test Point - Rocord
label | ACTION - W
label | Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet
label | Frequency - During Construction
label | Inspection / Test Method - Clegg Test
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete ICC Clegg record sheet
checkpoint | 25 - Compaction of AP65 - Test results to Engineer
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Test Point
label | ACTION - W
label | Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals
label | Frequency - During Construction
label | Inspection / Test Method - NDM Test
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
label | Comments - NDM test record
checkpoint | 26 - Compaction of AP40 - Test results to Engineer
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Test Point
label | ACTION - W
label | Conformance Criteria (Whats Required) - The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals
label | Frequency - During Construction
label | Inspection / Test Method - NDM Test
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
label | Comments - NDM test record
checkpoint | 27 - Flush and CCTV line
label | Inspection / Test Point - Inspection
label | ACTION - H
label | Conformance Criteria (Whats Required) - Flush and CCTV line and pass footage back to engineer for review
label | Frequency - Prior to asphalt
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
holdpoint | HOLD POINT
checkpoint | 28 - Asphalt prep
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Engineer to approve area is ready for asphalt (including overcuts) . Prep is 50mm and has fall and compaction results have been recived
label | Frequency - Prior to asphalt
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Engineer
holdpoint | HOLD POINT
checklist | ITP - Construction - FoulSewer Stage 1 - Sydney Street, Invercargill | itp
section | Details
checkpoint | 1 - ITP sign off
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed.
label | Frequency - Prior to commencement
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Divisional Manager
holdpoint | HOLD POINT
checkpoint | 2 - Materials to comply with contract specification
label | Specification / Standard - SR10.103 SR10.105
label | Inspection / Test Point - Aggregate Certification
label | ACTION - W
label | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
label | Frequency - Prior to commencement
label | Inspection / Test Method - Lab report
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 3 - Materials testing to be provided to Engineer for acceptance
label | Specification / Standard - SR10.103 SR10.105
label | Inspection / Test Point - Aggregate Acceptance
label | ACTION - W
label | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
label | Frequency - Prior to commencement
label | Inspection / Test Method - Lab report
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 4 - Ensure Approved Plans are on site. Safety/ Environmental/ Quality/ Asbestos/ TTMP/ Permits/ Consents/ Site Plans
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All plans/ permits produced under pre construction avaiable on site al all times
label | Frequency - Prior to commencement
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 5 - Notice to Engineer Reveiewed by Divisional Manager
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All NTE's to be reviewed
label | Frequency - Prior to submission to Engineer
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 6 - Variations Reveiewed by Divisional Manager
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All Variations to be reviewed
label | Frequency - Prior to submission to Engineer
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 7 - Site Precondition Inspection
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - Video record site walk over
label | Frequency - Prior to work starting on site
label | Inspection / Test Method - Video
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
checkpoint | 8 - Pownet and Chorus loactes completed
label | Inspection / Test Point - Inspection
label | ACTION - H
label | Conformance Criteria (Whats Required) - PowerNet and Chorus has been located, refernce back to plans to ensure everthing has been located
label | Frequency - Prior to commencement
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor / Forman
holdpoint | HOLD POINT
checkpoint | 9 - Correct materials delivered to site in acceptable condition
label | Inspection / Test Point - Material inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete inspection of materials as they arrive to site (particularly the concrete pipe)
label | Frequency - Upon pipe delvery
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor / Forman
checkpoint | 10 - New FoulSewer Main Alignment
label | Specification / Standard - Construciton drawings
label | Inspection / Test Point - Inspection / Test Point
label | ACTION - H
label | Conformance Criteria (Whats Required) - Alignment to be setout and confirmed on site by Engineers Rep
label | Frequency - Prior to commencement
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Engineers Rep
holdpoint | HOLD POINT
checkpoint | 11 - Inspect subgrade
label | Specification / Standard - AS/NZS 2566.2:2002
label | Inspection / Test Point - Inspection/Scala
label | ACTION - M
label | Conformance Criteria (Whats Required) - Inspect subgrade as exposed and scala if required, contact manager for further instruction if deemed unsuitable
label | Frequency - During Construction
label | Inspection / Test Method - Inspection / Scala
label | Verification Records - Sign This ITP
label | Signatory - Foreman
checkpoint | 12 - Pipe Laying
label | Specification / Standard - AS/NZS 2566.2:2003 and Contract Doc
label | Inspection / Test Point - Pipe Laying
label | ACTION - M
label | Conformance Criteria (Whats Required) - Pipe to be laid as per spec, contract and plans.
label | Frequency - During Construction
label | Inspection / Test Method - Spot checks
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
checkpoint | 13 - Saddles onto main for laterals and sumps
label | Specification / Standard - Construciton drawings
label | Inspection / Test Point - Sign off
label | ACTION - W
label | Conformance Criteria (Whats Required) - Instal as per construction plans
label | Frequency - During Installation
label | Inspection / Test Method - Photos
label | Verification Records - Sign This ITP
label | Signatory - Foreman
checkpoint | 14 - Compaction of bedding
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Bedding
label | ACTION - M
label | Conformance Criteria (Whats Required) - Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least).
label | Frequency - During Construction
label | Inspection / Test Method - Monitor
label | Verification Records - Sign This ITP
label | Signatory - Foreman
checkpoint | 15 - 1050dia. Manhole Installation F24669
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
label | Frequency - During Construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete SR Manhole checklist
checkpoint | 16 - 1050dia. Manhole Installation F21508
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
label | Frequency - During Construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete SR Manhole checklist
checkpoint | 17 - 1050dia. Manhole Installation F21500
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
label | Frequency - During Construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete SR Manhole checklist
checkpoint | 18 - Concrete Placement
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Engineers Rep to have viewed / inspected concrete formwork
label | Frequency - During Construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Photos & Concrete Dockets
checkpoint | 19 - Encountered Services
label | Specification / Standard - Contract Doc Appendix X
label | Inspection / Test Point - Record
label | ACTION - W
label | Conformance Criteria (Whats Required) - Record service on ICC encountered serives record sheet
label | Frequency - During Construction
label | Inspection / Test Method - Record
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
checkpoint | 20 - Drainage Connection
label | Specification / Standard - Contract Doc Appendix XI
label | Inspection / Test Point - Record
label | ACTION - W
label | Conformance Criteria (Whats Required) - Record detail on ICC drainage connection sheet
label | Frequency - During Construction
label | Inspection / Test Method - Record
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete ICC drainage sheet for each laterial
checkpoint | 21 - Plateau Testing
label | Inspection / Test Point - Test
label | ACTION - H
label | Conformance Criteria (Whats Required) - Plateau test to be undertaken at start of backfill to calibrate compaction methodology
label | Frequency - Test to be carried out at the start of backfilling
label | Inspection / Test Method - Test
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
label | Comments - NDM Test record
holdpoint | HOLD POINT
checkpoint | 22 - Compaction of AP65 - Clegg tests
label | Specification / Standard - Contract Doc Appendix XIII
label | Inspection / Test Point - Rocord
label | ACTION - W
label | Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet
label | Frequency - During Construction
label | Inspection / Test Method - Clegg Test
label | Verification Records - Sign This ITP
label | Signatory - Foreman/Supervisor
label | Comments - Complete ICC Clegg record sheet
checkpoint | 23 - Compaction of AP65 - Test results to Engineer
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Test Point
label | ACTION - W
label | Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals
label | Frequency - During Construction
label | Inspection / Test Method - NDM Test
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
label | Comments - NDM Test record
checkpoint | 24 - Compaction of AP40 - Test results to Engineer
label | Specification / Standard - Contract Doc
label | Inspection / Test Point - Test Point
label | ACTION - W
label | Conformance Criteria (Whats Required) - The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals
label | Frequency - During Construction
label | Inspection / Test Method - NDM Test
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
label | Comments - NDM Test record
checkpoint | 25 - Flush and CCTV line
label | Inspection / Test Point - Inspection
label | ACTION - H
label | Conformance Criteria (Whats Required) - Flush and CCTV line and pass footage back to engineer for review
label | Frequency - Prior to asphalt
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Contract Manager
holdpoint | HOLD POINT
checkpoint | 26 - Asphalt prep
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Engineer to approve area is ready for asphalt (including overcuts). Prep is 50mm and has fall and compaction results have been recived
label | Frequency - Prior to asphalt
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Engineer
holdpoint | HOLD POINT