## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Prestart Inspections
section | Details
checkpoint | Site has been cleaned in advance of our arrival on site
checkpoint | Walls are plumb and level
label | IMPORTANT
checkpoint | Tiling works running to programme - prior trades completed
checkpoint | Has prior trades QA been signed off by main contractor
checkpoint | Gib compound and sanding cleaned up from rooms
checkpoint | Task Analysis signed onto by tilers and provided to main contractor
checkpoint | Inductions completed
checkpoint | Site Inspection checklist has been completed
checkpoint | All tools tagged and tested - (photo's required)
checkpoint | Tiler has current sitesafe - Input number and expiry
checkpoint | Tiler has correct PPE
checkpoint | Correct drawings supplied as per onsite
checklist | QA - Floor Prep Bathrooms
section | Floor/wall Preparation
checkpoint | Is the area clean, and cleared, ready for necessary preparation
checkpoint | Are flanges installed at correct depth in accordance with specified wastes
checkpoint | Has screeding been completed to shower at correct height and falls - A48 material
checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
checkpoint | Install shower upstand with Hebel
checklist | QA - Waterproofing
section | Waterproofing
checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
checkpoint | Waterproofing coat # 1 applied to floors and walls Ardex WPM750 (take photos)
checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat ArdexWPM750 (take photos)
checkpoint | Flood tests, if required, undertaken and photos provided.
checklist | QA - Waterproofing - Spa Room
section | Waterproofing Spa room
checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
checkpoint | Apply liquid ARDEX waterproofing to ice bath, plinths & heated seat
checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat ArdexWPM750 (take photos)
checkpoint | Flood tests, if required, undertaken and photos provided.
checklist | QA - Tiling Installation
section | Tiling bathroom floor and walls
checkpoint | Tiles set out according to latest drawing - always check revisions on site
checkpoint | Specified product used with notched trowel or required product
checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Install 600x600 tile space Corten tiles to bathroom floors
checkpoint | Wall tiles set out to match floor grout lines or as per drawings install tiles to walls
checkpoint | INTAL tiles to hebel upstand
checkpoint | Install 1200x600 tile space corten tiles to shower walls only
checkpoint | Grout nominated is the correct colour and applied evenly and correctly
checkpoint | Grout is consistent throughout and no missing grout.
checkpoint | Tiling completed, checked and Supervisor sign off
checkpoint | Silicone is completed to all tile junctions where required
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
checklist | QA - Crazy Pavers External
section | Crazy Pavers External
checkpoint | surface grind of substrate prior to installation
checkpoint | prime substrate prior to installation
checkpoint | ensure set out correct as per sheet (1) 04
checkpoint | Install of crazy pavers to external area (Designstore P Trav Czy Trevertine Crazy pavers)
checkpoint | Grout nominated is the correct colour and applied evenly and correctly
checkpoint | Grout is consistent throughout and no missing grout.
checkpoint | Apply 2 coats of Fila sealer to completed crazy paving
checkpoint | Pavers completed, checked and supervisor signed off
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
checklist | QA - Tiling Installation Spa Room
section | Tiling to spa area
checkpoint | Tiles set out according to latest drawing - always check revisions on site
checkpoint | Specified product used with notched trowel or required product
checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | All Joints to be mitred
checkpoint | Install of crazy pavers to Spa floor area. (Designstore P Trav Czy Trevertine Crazy Pavers)
checkpoint | Install of 1200x600 tiles space corten tiles to vertical Vanity faces
checkpoint | Install of 1200x600 tiles space corten tiles to Heated seat vertical faces and top
checkpoint | Install of 1200x600 tiles to tap plinth vertical faces and top
checkpoint | Install of 1200x600 tiles space corten tiles to Bath vertical faces (external & Internal)
checkpoint | Install of 1200x600 tiles space corten tiles bath floor
checkpoint | Install 1200x600 tiles space corten tiles to bath tops
checkpoint | Tiling completed, checked and Supervisor sign off
checkpoint | Silicone is completed to all tile junctions where required
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
checklist | QA - Other Information
section | Other Information
checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
checkpoint | change of details and or instructions
checkpoint | Site specific details to be added
checkpoint | Material Details - Notes to be added of materials used on site
checklist | Final Sign Off for Invoicing
section | Details
checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.