## Sheet1
1.1 | Approved JMF for Asphalt Base or Wearing Course | As Per DN1210-WSP-GCO-0160 | H | Before Works commence | Confirm requirements are followed | JMF Validated in accordance with NZTA M/10:2020 | Mix Design Report | Paving Contractor | JMF expiry date and validation details in here | A | I | R | 1.1 - Approved JMF for Asphalt Base or Wearing Course | Detail of Activity / Test - As Per DN1210-WSP-GCO-0160 | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - Confirm requirements are followed | Acceptance Criteria - JMF Validated in accordance with NZTA M/10:2020 | Record documents (QCP - Quality Control Portal) - Mix Design Report | Responsibility - Paving Contractor | Project Specific Notes / Instructions - JMF expiry date and validation details in here | Designer - A | Eng. Rep / NZTA - I | Contractor - R | 1.1 - Approved JMF for Asphalt Base or Wearing Course
1.2 | Site Conditions | Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place | H | Before Works commence | Confirm requirements are followed | Weather conditions and Site is suitable for paving | Site Diary | Paving Contractor |  |  | I | R | 1.2 - Site Conditions | Detail of Activity / Test - Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - Confirm requirements are followed | Acceptance Criteria - Weather conditions and Site is suitable for paving | Record documents (QCP - Quality Control Portal) - Site Diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Detail of Activity / Test - As Per DN1210-WSP-GCO-0160
1.3 | Traffic Loops | Communication with affected parties | H | Minimum of 7 days Before Works commence | Visual | Notify RC at least 7 days before surfacing is programmed | Communication | Paving Contractor | only required where existing traffic loops are present |  | A | R | 1.3 - Traffic Loops | Detail of Activity / Test - Communication with affected parties | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Minimum of 7 days Before Works commence | Inspection / Test method - Visual | Acceptance Criteria - Notify RC at least 7 days before surfacing is programmed | Record documents (QCP - Quality Control Portal) - Communication | Responsibility - Paving Contractor | Project Specific Notes / Instructions - only required where existing traffic loops are present | Designer - | Eng. Rep / NZTA - A | Contractor - R | Action (Hold, Monitor, Witness) - H
1.4 | Paving Plan | Paving Plan to be completed | H | Before Works commence | NZTA M10: 2020 Clause 9.5.1 | Paving Plan to be completed for each shift with dimensions, location and type of (hot/cold) joints, areas and tonneages | String Sheet | Paving Contractor |  |  | I | R | 1.4 - Paving Plan | Detail of Activity / Test - Paving Plan to be completed | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence | Inspection / Test method - NZTA M10: 2020 Clause 9.5.1 | Acceptance Criteria - Paving Plan to be completed for each shift with dimensions, location and type of (hot/cold) joints, areas and tonneages | Record documents (QCP - Quality Control Portal) - String Sheet | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
2.1 | Temperatures | Mixing of aggregates and bitumen | M | Constant monitoring of temperature by calibrated euipment | Plant temperature probes | PNZTA M10: 2020 states max. 170 deg.C | Plant site diary | Asphalt Manufacturer |  | I | I | R | 2.1 - Temperatures | Detail of Activity / Test - Mixing of aggregates and bitumen | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Constant monitoring of temperature by calibrated euipment | Inspection / Test method - Plant temperature probes | Acceptance Criteria - PNZTA M10: 2020 states max. 170 deg.C | Record documents (QCP - Quality Control Portal) - Plant site diary | Responsibility - Asphalt Manufacturer | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Inspection / Test method - Confirm requirements are followed
2.2 | Production Asphalt | Particle Size Distribution | M | 1 per 200t at asphalt plant | NZS 4407 Test 3.8.1 | NZTA M10: 2020 Refer to Table 5.3 | IANZ accredited test cert | Asphalt Manufacturer |  | I | I | R | 2.2 - Production Asphalt | Detail of Activity / Test - Particle Size Distribution | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant | Inspection / Test method - NZS 4407 Test 3.8.1 | Acceptance Criteria - NZTA M10: 2020 Refer to Table 5.3 | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert | Responsibility - Asphalt Manufacturer | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Acceptance Criteria - JMF Validated in accordance with NZTA M/10:2020
2.3 | Production Asphalt | Binder Content | M | 1 per 200t at asphalt plant |  | NZTA M10: 2020 Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3 | IANZ accredited test cert | Asphalt Manufacturer |  | I | I | R | 2.3 - Production Asphalt | Detail of Activity / Test - Binder Content | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant | Inspection / Test method - | Acceptance Criteria - NZTA M10: 2020 Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3 | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert | Responsibility - Asphalt Manufacturer | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Record documents (QCP - Quality Control Portal) - Mix Design Report
2.4 | Production Asphalt | Max. Specific Gravity (MSG) of mix | M | 1 per 600t at asphalt plant |  | Report | IANZ accredited test cert | Asphalt Manufacturer |  | I | I | R | 2.4 - Production Asphalt | Detail of Activity / Test - Max. Specific Gravity (MSG) of mix | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant | Inspection / Test method - | Acceptance Criteria - Report | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert | Responsibility - Asphalt Manufacturer | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Responsibility - Paving Contractor
2.5 | Production Asphalt | Air Voids at lab design compaction | M | 1 per 600t at asphalt plant |  | NZTA M10: 2020: Individual Test Results: +2.0, -1.0 Mean of Three Test Results: +1.2, -0.6 | IANZ accredited test cert | Asphalt Manufacturer |  | I | I | R | 2.5 - Production Asphalt | Detail of Activity / Test - Air Voids at lab design compaction | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant | Inspection / Test method - | Acceptance Criteria - NZTA M10: 2020: Individual Test Results: +2.0, -1.0 Mean of Three Test Results: +1.2, -0.6 | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert | Responsibility - Asphalt Manufacturer | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Project Specific Notes / Instructions - JMF expiry date and validation details in here
3.1 | Membrane Seal | Application of Membrane Seal | M | Per Lot | Sealing Records | Application rate, chip type and binder as per membrane seal design | Sealing Records | Paving Contractor |  | I | I | R | 3.1 - Membrane Seal | Detail of Activity / Test - Application of Membrane Seal | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot | Inspection / Test method - Sealing Records | Acceptance Criteria - Application rate, chip type and binder as per membrane seal design | Record documents (QCP - Quality Control Portal) - Sealing Records | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Designer - A
3.2 | Temperature | Asphalt Delivery temperature | M | Every Load on delivery to the Paver Hopper | Temperature Probe | Target ≥ 150 deg.C. in the Paver Min. ≥ 130 deg.C in the Paver CHAR(LESS)130°C to be Rejected | Site Diary | Paving Contractor |  | I | I | R | 3.2 - Temperature | Detail of Activity / Test - Asphalt Delivery temperature | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper | Inspection / Test method - Temperature Probe | Acceptance Criteria - Target ≥ 150 deg.C. in the Paver Min. ≥ 130 deg.C in the Paver CHAR(LESS)130°C to be Rejected | Record documents (QCP - Quality Control Portal) - Site Diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Eng. Rep / NZTA - I
3.3 | Temperature | Compaction Temperature | M | During compaction | Temperature Probe/Infrared gauge | ≥ 125°C at commencement of compaction. CHAR(LESS) 80°C - Stop Rolling | Site diary | Paving Contractor |  | I | I | R | 3.3 - Temperature | Detail of Activity / Test - Compaction Temperature | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - During compaction | Inspection / Test method - Temperature Probe/Infrared gauge | Acceptance Criteria - ≥ 125°C at commencement of compaction. CHAR(LESS) 80°C - Stop Rolling | Record documents (QCP - Quality Control Portal) - Site diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Contractor - R
3.4 | Mat | Load Locate | M | Each load | M/10 | Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | Paving Run Sheet | Paving Contractor |  | I | I | R | 3.4 - Mat | Detail of Activity / Test - Load Locate | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Each load | Inspection / Test method - M/10 | Acceptance Criteria - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | Record documents (QCP - Quality Control Portal) - Paving Run Sheet | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | 1.2 - Site Conditions
3.5 | Mat | Thickness Monitoring | M | Continuously | Dipping | Target Loose Thickness -0mm / +10mm |  | Paving Contractor |  | I | I | R | 3.5 - Mat | Detail of Activity / Test - Thickness Monitoring | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Continuously | Inspection / Test method - Dipping | Acceptance Criteria - Target Loose Thickness -0mm / +10mm | Record documents (QCP - Quality Control Portal) - | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Detail of Activity / Test - Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place
3.6 | Mat | Compaction - NDM | M | Plateau to be completed on 1st run, thereafter monitor compaction/roller passes to achieve target density. | Insitu density and air voids | NZTA M/10: 2020 - section 9.9 |  | Paving Contractor | Use a calibrated NDM with established core correlation. Locate and mark cores, record NDM Bulk density by core location (including any offset used). | I | I | R | 3.6 - Mat | Detail of Activity / Test - Compaction - NDM | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Plateau to be completed on 1st run, thereafter monitor compaction/roller passes to achieve target density. | Inspection / Test method - Insitu density and air voids | Acceptance Criteria - NZTA M/10: 2020 - section 9.9 | Record documents (QCP - Quality Control Portal) - | Responsibility - Paving Contractor | Project Specific Notes / Instructions - Use a calibrated NDM with established core correlation. Locate and mark cores, record NDM Bulk density by core location (including any offset used). | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Action (Hold, Monitor, Witness) - H
3.7 | Mat | Compaction | H | Minimum of 1 mats and 1 joint | Insitu density and air voids | NZTA M/10: 2020 - section 9.9 | IANZ accredited test cert. | Paving Contractor | A pavement lot shall be an essentially homogeneous section of work completed within a shift of production. The lot shall be divided into an appropriate number of approximately equal sub-lots and a core shall be taken randomly within each sub-lot. The Engineer or their delegate shall use a random method for locating each core position, such as ASTM D5361 or a similar process. | A | I | R | 3.7 - Mat | Detail of Activity / Test - Compaction | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Minimum of 1 mats and 1 joint | Inspection / Test method - Insitu density and air voids | Acceptance Criteria - NZTA M/10: 2020 - section 9.9 | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert. | Responsibility - Paving Contractor | Project Specific Notes / Instructions - A pavement lot shall be an essentially homogeneous section of work completed within a shift of production. The lot shall be divided into an appropriate number of approximately equal sub-lots and a core shall be taken randomly within each sub-lot. The Engineer or their delegate shall use a random method for locating each core position, such as ASTM D5361 or a similar process. | Designer - A | Eng. Rep / NZTA - I | Contractor - R | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
3.8 | Mat | Thickness | H | Each load | M/10 | Calculated average Deth from run sheet | Paving Run Sheet | Paving Contractor |  | A | I | R | 3.8 - Mat | Detail of Activity / Test - Thickness | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - Each load | Inspection / Test method - M/10 | Acceptance Criteria - Calculated average Deth from run sheet | Record documents (QCP - Quality Control Portal) - Paving Run Sheet | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - A | Eng. Rep / NZTA - I | Contractor - R | Inspection / Test method - Confirm requirements are followed
3.9 | Mat | Shape | M | Continuously | 3m Straight edge | Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA M/10: 2020 - section 9.8. Not more than 5mm under a 3m Straight Edge. | Straight Edge Record | Paving Contractor |  | I | I | R | 3.9 - Mat | Detail of Activity / Test - Shape | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Continuously | Inspection / Test method - 3m Straight edge | Acceptance Criteria - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA M/10: 2020 - section 9.8. Not more than 5mm under a 3m Straight Edge. | Record documents (QCP - Quality Control Portal) - Straight Edge Record | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Acceptance Criteria - Weather conditions and Site is suitable for paving
3.1 | Paving Quality | Level | M | Per Site | As Built Survey | -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. NZTA M/10: 2020 - section 10.2 | Survey As builts | Paving Contractor |  | I | I | R | 3.1 - Paving Quality | Detail of Activity / Test - Level | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Per Site | Inspection / Test method - As Built Survey | Acceptance Criteria - -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. NZTA M/10: 2020 - section 10.2 | Record documents (QCP - Quality Control Portal) - Survey As builts | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Record documents (QCP - Quality Control Portal) - Site Diary
3.11 | Paving Quality | Alignment | M | Per Site | As Built Survey | Kerb to kerb | Survey As builts | Paving Contractor |  | I | I | R | 3.11 - Paving Quality | Detail of Activity / Test - Alignment | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production) - Per Site | Inspection / Test method - As Built Survey | Acceptance Criteria - Kerb to kerb | Record documents (QCP - Quality Control Portal) - Survey As builts | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - I | Contractor - R | Responsibility - Paving Contractor
3.12 | Post Paving Completion Checks | Site clear and cleanup | W | Each Site/Shift | Visual | Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete | Site Diary | Paving Contractor |  |  | I | R | 3.12 - Post Paving Completion Checks | Detail of Activity / Test - Site clear and cleanup | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift | Inspection / Test method - Visual | Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete | Record documents (QCP - Quality Control Portal) - Site Diary | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - | Eng. Rep / NZTA - I | Contractor - R | Project Specific Notes / Instructions -
4.1 | Assessment of all test results for conformity | Review against ITP Requirements | H | For each site on the project | Review | Reporting of any non-conforming results to Engineer via NCR | NCR | Paving Contractor |  | I | A | R | 4.1 - Assessment of all test results for conformity | Detail of Activity / Test - Review against ITP Requirements | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project | Inspection / Test method - Review | Acceptance Criteria - Reporting of any non-conforming results to Engineer via NCR | Record documents (QCP - Quality Control Portal) - NCR | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - A | Contractor - R | Designer -
4.2 | RAMM pavement and surface records | RAMM surfacing pavement data spreadsheet updated | W | For each site on the project | Prepare Data | Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. | RAMM Spreadsheet | Paving Contractor |  | I | A | R | 4.2 - RAMM pavement and surface records | Detail of Activity / Test - RAMM surfacing pavement data spreadsheet updated | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project | Inspection / Test method - Prepare Data | Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. | Record documents (QCP - Quality Control Portal) - RAMM Spreadsheet | Responsibility - Paving Contractor | Project Specific Notes / Instructions - | Designer - I | Eng. Rep / NZTA - A | Contractor - R | Eng. Rep / NZTA - I
Contractor - R
1.3 - Traffic Loops
Detail of Activity / Test - Communication with affected parties
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - Minimum of 7 days Before Works commence
Inspection / Test method - Visual
Acceptance Criteria - Notify RC at least 7 days before surfacing is programmed
Record documents (QCP - Quality Control Portal) - Communication
Responsibility - Paving Contractor
Project Specific Notes / Instructions - only required where existing traffic loops are present
Designer -
Eng. Rep / NZTA - A
Contractor - R
1.4 - Paving Plan
Detail of Activity / Test - Paving Plan to be completed
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
Inspection / Test method - NZTA M10: 2020 Clause 9.5.1
Acceptance Criteria - Paving Plan to be completed for each shift with dimensions, location and type of (hot/cold) joints, areas and tonneages
Record documents (QCP - Quality Control Portal) - String Sheet
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - R
2.1 - Temperatures
Detail of Activity / Test - Mixing of aggregates and bitumen
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Constant monitoring of temperature by calibrated euipment
Inspection / Test method - Plant temperature probes
Acceptance Criteria - PNZTA M10: 2020 states max. 170 deg.C
Record documents (QCP - Quality Control Portal) - Plant site diary
Responsibility - Asphalt Manufacturer
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
2.2 - Production Asphalt
Detail of Activity / Test - Particle Size Distribution
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
Inspection / Test method - NZS 4407 Test 3.8.1
Acceptance Criteria - NZTA M10: 2020 Refer to Table 5.3
Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
Responsibility - Asphalt Manufacturer
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
2.3 - Production Asphalt
Detail of Activity / Test - Binder Content
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
Inspection / Test method -
Acceptance Criteria - NZTA M10: 2020 Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3
Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
Responsibility - Asphalt Manufacturer
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
2.4 - Production Asphalt
Detail of Activity / Test - Max. Specific Gravity (MSG) of mix
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant
Inspection / Test method -
Acceptance Criteria - Report
Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
Responsibility - Asphalt Manufacturer
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
2.5 - Production Asphalt
Detail of Activity / Test - Air Voids at lab design compaction
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant
Inspection / Test method -
Acceptance Criteria - NZTA M10: 2020: Individual Test Results: +2.0, -1.0 Mean of Three Test Results: +1.2, -0.6
Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
Responsibility - Asphalt Manufacturer
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.1 - Membrane Seal
Detail of Activity / Test - Application of Membrane Seal
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
Inspection / Test method - Sealing Records
Acceptance Criteria - Application rate, chip type and binder as per membrane seal design
Record documents (QCP - Quality Control Portal) - Sealing Records
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.2 - Temperature
Detail of Activity / Test - Asphalt Delivery temperature
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper
Inspection / Test method - Temperature Probe
Acceptance Criteria - Target ≥ 150 deg.C. in the Paver Min. ≥ 130 deg.C in the Paver CHAR(LESS)130°C to be Rejected
Record documents (QCP - Quality Control Portal) - Site Diary
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.3 - Temperature
Detail of Activity / Test - Compaction Temperature
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - During compaction
Inspection / Test method - Temperature Probe/Infrared gauge
Acceptance Criteria - ≥ 125°C at commencement of compaction. CHAR(LESS) 80°C - Stop Rolling
Record documents (QCP - Quality Control Portal) - Site diary
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.4 - Mat
Detail of Activity / Test - Load Locate
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Each load
Inspection / Test method - M/10
Acceptance Criteria - Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
Record documents (QCP - Quality Control Portal) - Paving Run Sheet
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.5 - Mat
Detail of Activity / Test - Thickness Monitoring
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Continuously
Inspection / Test method - Dipping
Acceptance Criteria - Target Loose Thickness -0mm / +10mm
Record documents (QCP - Quality Control Portal) -
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.6 - Mat
Detail of Activity / Test - Compaction - NDM
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Plateau to be completed on 1st run, thereafter monitor compaction/roller passes to achieve target density.
Inspection / Test method - Insitu density and air voids
Acceptance Criteria - NZTA M/10: 2020 - section 9.9
Record documents (QCP - Quality Control Portal) -
Responsibility - Paving Contractor
Project Specific Notes / Instructions - Use a calibrated NDM with established core correlation. Locate and mark cores, record NDM Bulk density by core location (including any offset used).
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.7 - Mat
Detail of Activity / Test - Compaction
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - Minimum of 1 mats and 1 joint
Inspection / Test method - Insitu density and air voids
Acceptance Criteria - NZTA M/10: 2020 - section 9.9
Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
Responsibility - Paving Contractor
Project Specific Notes / Instructions - A pavement lot shall be an essentially homogeneous section of work completed within a shift of production. The lot shall be divided into an appropriate number of approximately equal sub-lots and a core shall be taken randomly within each sub-lot. The Engineer or their delegate shall use a random method for locating each core position, such as ASTM D5361 or a similar process.
Designer - A
Eng. Rep / NZTA - I
Contractor - R
3.8 - Mat
Detail of Activity / Test - Thickness
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - Each load
Inspection / Test method - M/10
Acceptance Criteria - Calculated average Deth from run sheet
Record documents (QCP - Quality Control Portal) - Paving Run Sheet
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - A
Eng. Rep / NZTA - I
Contractor - R
3.9 - Mat
Detail of Activity / Test - Shape
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Continuously
Inspection / Test method - 3m Straight edge
Acceptance Criteria - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA M/10: 2020 - section 9.8. Not more than 5mm under a 3m Straight Edge.
Record documents (QCP - Quality Control Portal) - Straight Edge Record
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.1 - Paving Quality
Detail of Activity / Test - Level
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Per Site
Inspection / Test method - As Built Survey
Acceptance Criteria - -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. NZTA M/10: 2020 - section 10.2
Record documents (QCP - Quality Control Portal) - Survey As builts
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.11 - Paving Quality
Detail of Activity / Test - Alignment
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production) - Per Site
Inspection / Test method - As Built Survey
Acceptance Criteria - Kerb to kerb
Record documents (QCP - Quality Control Portal) - Survey As builts
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - I
Contractor - R
3.12 - Post Paving Completion Checks
Detail of Activity / Test - Site clear and cleanup
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
Inspection / Test method - Visual
Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete
Record documents (QCP - Quality Control Portal) - Site Diary
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer -
Eng. Rep / NZTA - I
Contractor - R
4.1 - Assessment of all test results for conformity
Detail of Activity / Test - Review against ITP Requirements
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
Inspection / Test method - Review
Acceptance Criteria - Reporting of any non-conforming results to Engineer via NCR
Record documents (QCP - Quality Control Portal) - NCR
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - A
Contractor - R
4.2 - RAMM pavement and surface records
Detail of Activity / Test - RAMM surfacing pavement data spreadsheet updated
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
Inspection / Test method - Prepare Data
Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer.
Record documents (QCP - Quality Control Portal) - RAMM Spreadsheet
Responsibility - Paving Contractor
Project Specific Notes / Instructions -
Designer - I
Eng. Rep / NZTA - A
Contractor - R