## Sheet1
1 | ITP sign off |  | Sign off | H | Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed. | Prior to commencement | Review | Sign This ITP | Divisional Manager |  | 1 - ITP sign off | Specification / Standard - | Inspection / Test Point - Sign off | ACTION - H | Conformance Criteria (Whats Required) - Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed. | Frequency - Prior to commencement | Inspection / Test Method - Review | Verification Records - Sign This ITP | Signatory - Divisional Manager | Comments - | 1 - ITP sign off
2 | Materials to comply with contract specification | SR10.103 SR10.105 | Aggregate Certification | W | Laboratory test certificates: MDD and Grading Results | Prior to commencement | Lab report | Sign This ITP | Contract Manager |  | 2 - Materials to comply with contract specification | Specification / Standard - SR10.103 SR10.105 | Inspection / Test Point - Aggregate Certification | ACTION - W | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results | Frequency - Prior to commencement | Inspection / Test Method - Lab report | Verification Records - Sign This ITP | Signatory - Contract Manager | Comments - | Specification / Standard -
3 | Materials testing to be provided to Engineer for acceptance | SR10.103 SR10.105 | Aggregate Acceptance | W | Laboratory test certificates: MDD and Grading Results | Prior to commencement | Lab report | Sign This ITP | Contract Manager |  | 3 - Materials testing to be provided to Engineer for acceptance | Specification / Standard - SR10.103 SR10.105 | Inspection / Test Point - Aggregate Acceptance | ACTION - W | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results | Frequency - Prior to commencement | Inspection / Test Method - Lab report | Verification Records - Sign This ITP | Signatory - Contract Manager | Comments - | Inspection / Test Point - Sign off
4 | Ensure Approved Plans are on site. Safety/ Environmental/ Quality/ Asbestos/ TTMP/ Permits/ Consents/ Site Plans |  | Review | W | All plans/ permits produced under pre construction avaiable on site al all times | Prior to commencement | Review | Sign This ITP | Contract Manager |  | 4 - Ensure Approved Plans are on site. Safety/ Environmental/ Quality/ Asbestos/ TTMP/ Permits/ Consents/ Site Plans | Specification / Standard - | Inspection / Test Point - Review | ACTION - W | Conformance Criteria (Whats Required) - All plans/ permits produced under pre construction avaiable on site al all times | Frequency - Prior to commencement | Inspection / Test Method - Review | Verification Records - Sign This ITP | Signatory - Contract Manager | Comments - | ACTION - H
5 | Notice to Engineer Reveiewed by Divisional Manager |  | Review | W | All NTE's to be reviewed | Prior to submission to Engineer | Review | Sign This ITP | Contract Manager |  | 5 - Notice to Engineer Reveiewed by Divisional Manager | Specification / Standard - | Inspection / Test Point - Review | ACTION - W | Conformance Criteria (Whats Required) - All NTE's to be reviewed | Frequency - Prior to submission to Engineer | Inspection / Test Method - Review | Verification Records - Sign This ITP | Signatory - Contract Manager | Comments - | Conformance Criteria (Whats Required) - Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed.
6 | Variations Reveiewed by Divisional Manager |  | Review | W | All Variations to be reviewed | Prior to submission to Engineer | Review | Sign This ITP | Contract Manager |  | 6 - Variations Reveiewed by Divisional Manager | Specification / Standard - | Inspection / Test Point - Review | ACTION - W | Conformance Criteria (Whats Required) - All Variations to be reviewed | Frequency - Prior to submission to Engineer | Inspection / Test Method - Review | Verification Records - Sign This ITP | Signatory - Contract Manager | Comments - | Frequency - Prior to commencement
7 | Site Precondition Inspection |  | Review | W | Video record site walk over | Prior to work starting on site | Video | Sign This ITP | Contract Manager |  | 7 - Site Precondition Inspection | Specification / Standard - | Inspection / Test Point - Review | ACTION - W | Conformance Criteria (Whats Required) - Video record site walk over | Frequency - Prior to work starting on site | Inspection / Test Method - Video | Verification Records - Sign This ITP | Signatory - Contract Manager | Comments - | Inspection / Test Method - Review
8 | Pownet and Chorus loactes completed |  | Inspection | H | PowerNet and Chorus has been located, refernce back to plans to ensure everthing has been located | Prior to commencement | Inspection | Sign This ITP | Supervisor / Forman |  | 8 - Pownet and Chorus loactes completed | Specification / Standard - | Inspection / Test Point - Inspection | ACTION - H | Conformance Criteria (Whats Required) - PowerNet and Chorus has been located, refernce back to plans to ensure everthing has been located | Frequency - Prior to commencement | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor / Forman | Comments - | Verification Records - Sign This ITP
9 | Correct materials delivered to site in acceptable condition |  | Material inspection | W | Complete inspection of materials as they arrive to site (particularly the concrete pipe) | Upon pipe delvery | Inspection | Sign This ITP | Supervisor / Forman |  | 9 - Correct materials delivered to site in acceptable condition | Specification / Standard - | Inspection / Test Point - Material inspection | ACTION - W | Conformance Criteria (Whats Required) - Complete inspection of materials as they arrive to site (particularly the concrete pipe) | Frequency - Upon pipe delvery | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor / Forman | Comments - | Signatory - Divisional Manager
10 | New FoulSewer Main Alignment | Construciton drawings | Inspection / Test Point | H | Alignment to be setout and confirmed on site by Engineers Rep | Prior to commencement | Inspection | Sign This ITP | Engineers Rep |  | 10 - New FoulSewer Main Alignment | Specification / Standard - Construciton drawings | Inspection / Test Point - Inspection / Test Point | ACTION - H | Conformance Criteria (Whats Required) - Alignment to be setout and confirmed on site by Engineers Rep | Frequency - Prior to commencement | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Engineers Rep | Comments - | Comments -
11 | Inspect subgrade | AS/NZS 2566.2:2002 | Inspection/Scala | M | Inspect subgrade as exposed and scala if required, contact manager for further instruction if deemed unsuitable | During Construction | Inspection / Scala | Sign This ITP | Foreman |  | 11 - Inspect subgrade | Specification / Standard - AS/NZS 2566.2:2002 | Inspection / Test Point - Inspection/Scala | ACTION - M | Conformance Criteria (Whats Required) - Inspect subgrade as exposed and scala if required, contact manager for further instruction if deemed unsuitable | Frequency - During Construction | Inspection / Test Method - Inspection / Scala | Verification Records - Sign This ITP | Signatory - Foreman | Comments - | 2 - Materials to comply with contract specification
12 | Pipe Laying | AS/NZS 2566.2:2003 and Contract Doc | Pipe Laying | M | Pipe to be laid as per spec, contract and plans. | During Construction | Spot checks | Sign This ITP | Foreman/Supervisor |  | 12 - Pipe Laying | Specification / Standard - AS/NZS 2566.2:2003 and Contract Doc | Inspection / Test Point - Pipe Laying | ACTION - M | Conformance Criteria (Whats Required) - Pipe to be laid as per spec, contract and plans. | Frequency - During Construction | Inspection / Test Method - Spot checks | Verification Records - Sign This ITP | Signatory - Foreman/Supervisor | Comments - | Specification / Standard - SR10.103 SR10.105
13 | Saddles onto main for laterals and sumps | Construciton drawings | Sign off | W | Instal as per construction plans | During Installation | Photos | Sign This ITP | Foreman |  | 13 - Saddles onto main for laterals and sumps | Specification / Standard - Construciton drawings | Inspection / Test Point - Sign off | ACTION - W | Conformance Criteria (Whats Required) - Instal as per construction plans | Frequency - During Installation | Inspection / Test Method - Photos | Verification Records - Sign This ITP | Signatory - Foreman | Comments - | Inspection / Test Point - Aggregate Certification
14 | Compaction of bedding | Contract Doc | Bedding | M | Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least). | During Construction | Monitor | Sign This ITP | Foreman |  | 14 - Compaction of bedding | Specification / Standard - Contract Doc | Inspection / Test Point - Bedding | ACTION - M | Conformance Criteria (Whats Required) - Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least). | Frequency - During Construction | Inspection / Test Method - Monitor | Verification Records - Sign This ITP | Signatory - Foreman | Comments - | ACTION - W
15 | 1050dia. Manhole Installation F24669 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist | 15 - 1050dia. Manhole Installation F24669 | Specification / Standard - Contract Doc | Inspection / Test Point - Inspection | ACTION - W | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist | Frequency - During Construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Foreman/Supervisor | Comments - Complete SR Manhole checklist | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
16 | 1050dia. Manhole Installation F21508 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist | 16 - 1050dia. Manhole Installation F21508 | Specification / Standard - Contract Doc | Inspection / Test Point - Inspection | ACTION - W | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist | Frequency - During Construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Foreman/Supervisor | Comments - Complete SR Manhole checklist | Frequency - Prior to commencement
17 | 1050dia. Manhole Installation F21500 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist | 17 - 1050dia. Manhole Installation F21500 | Specification / Standard - Contract Doc | Inspection / Test Point - Inspection | ACTION - W | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist | Frequency - During Construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Foreman/Supervisor | Comments - Complete SR Manhole checklist | Inspection / Test Method - Lab report
18 | Concrete Placement |  | Inspection | W | Engineers Rep to have viewed / inspected concrete formwork | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Photos CHAR(AMP) Concrete Dockets | 18 - Concrete Placement | Specification / Standard - | Inspection / Test Point - Inspection | ACTION - W | Conformance Criteria (Whats Required) - Engineers Rep to have viewed / inspected concrete formwork | Frequency - During Construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Foreman/Supervisor | Comments - Photos CHAR(AMP) Concrete Dockets | Verification Records - Sign This ITP
19 | Encountered Services | Contract Doc Appendix X | Record | W | Record service on ICC encountered serives record sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor |  | 19 - Encountered Services | Specification / Standard - Contract Doc Appendix X | Inspection / Test Point - Record | ACTION - W | Conformance Criteria (Whats Required) - Record service on ICC encountered serives record sheet | Frequency - During Construction | Inspection / Test Method - Record | Verification Records - Sign This ITP | Signatory - Foreman/Supervisor | Comments - | Signatory - Contract Manager
20 | Drainage Connection | Contract Doc Appendix XI | Record | W | Record detail on ICC drainage connection sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor | Complete ICC drainage sheet for each laterial | 20 - Drainage Connection | Specification / Standard - Contract Doc Appendix XI | Inspection / Test Point - Record | ACTION - W | Conformance Criteria (Whats Required) - Record detail on ICC drainage connection sheet | Frequency - During Construction | Inspection / Test Method - Record | Verification Records - Sign This ITP | Signatory - Foreman/Supervisor | Comments - Complete ICC drainage sheet for each laterial | Comments -
21 | Plateau Testing |  | Test | H | Plateau test to be undertaken at start of backfill to calibrate compaction methodology | Test to be carried out at the start of backfilling | Test | Sign This ITP | Contract Manager | NDM Test record | 21 - Plateau Testing | Specification / Standard - | Inspection / Test Point - Test | ACTION - H | Conformance Criteria (Whats Required) - Plateau test to be undertaken at start of backfill to calibrate compaction methodology | Frequency - Test to be carried out at the start of backfilling | Inspection / Test Method - Test | Verification Records - Sign This ITP | Signatory - Contract Manager | Comments - NDM Test record | 3 - Materials testing to be provided to Engineer for acceptance
22 | Compaction of AP65 - Clegg tests | Contract Doc Appendix XIII | Rocord | W | AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet | During Construction | Clegg Test | Sign This ITP | Foreman/Supervisor | Complete ICC Clegg record sheet | 22 - Compaction of AP65 - Clegg tests | Specification / Standard - Contract Doc Appendix XIII | Inspection / Test Point - Rocord | ACTION - W | Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet | Frequency - During Construction | Inspection / Test Method - Clegg Test | Verification Records - Sign This ITP | Signatory - Foreman/Supervisor | Comments - Complete ICC Clegg record sheet | Specification / Standard - SR10.103 SR10.105
23 | Compaction of AP65 - Test results to Engineer | Contract Doc | Test Point | W | AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM Test record | 23 - Compaction of AP65 - Test results to Engineer | Specification / Standard - Contract Doc | Inspection / Test Point - Test Point | ACTION - W | Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals | Frequency - During Construction | Inspection / Test Method - NDM Test | Verification Records - Sign This ITP | Signatory - Contract Manager | Comments - NDM Test record | Inspection / Test Point - Aggregate Acceptance
24 | Compaction of AP40 - Test results to Engineer | Contract Doc | Test Point | W | The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM Test record | 24 - Compaction of AP40 - Test results to Engineer | Specification / Standard - Contract Doc | Inspection / Test Point - Test Point | ACTION - W | Conformance Criteria (Whats Required) - The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals | Frequency - During Construction | Inspection / Test Method - NDM Test | Verification Records - Sign This ITP | Signatory - Contract Manager | Comments - NDM Test record | ACTION - W
25 | Flush and CCTV line |  | Inspection | H | Flush and CCTV line and pass footage back to engineer for review | Prior to asphalt | Inspection | Sign This ITP | Contract Manager |  | 25 - Flush and CCTV line | Specification / Standard - | Inspection / Test Point - Inspection | ACTION - H | Conformance Criteria (Whats Required) - Flush and CCTV line and pass footage back to engineer for review | Frequency - Prior to asphalt | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Contract Manager | Comments - | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
26 | Asphalt prep |  | Sign off | H | Engineer to approve area is ready for asphalt (including overcuts). Prep is 50mm and has fall and compaction results have been recived | Prior to asphalt | Inspection | Sign This ITP | Engineer |  | 26 - Asphalt prep | Specification / Standard - | Inspection / Test Point - Sign off | ACTION - H | Conformance Criteria (Whats Required) - Engineer to approve area is ready for asphalt (including overcuts). Prep is 50mm and has fall and compaction results have been recived | Frequency - Prior to asphalt | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Engineer | Comments - | Frequency - Prior to commencement
Inspection / Test Method - Lab report
Verification Records - Sign This ITP
Signatory - Contract Manager
Comments -
4 - Ensure Approved Plans are on site. Safety/ Environmental/ Quality/ Asbestos/ TTMP/ Permits/ Consents/ Site Plans
Specification / Standard -
Inspection / Test Point - Review
ACTION - W
Conformance Criteria (Whats Required) - All plans/ permits produced under pre construction avaiable on site al all times
Frequency - Prior to commencement
Inspection / Test Method - Review
Verification Records - Sign This ITP
Signatory - Contract Manager
Comments -
5 - Notice to Engineer Reveiewed by Divisional Manager
Specification / Standard -
Inspection / Test Point - Review
ACTION - W
Conformance Criteria (Whats Required) - All NTE's to be reviewed
Frequency - Prior to submission to Engineer
Inspection / Test Method - Review
Verification Records - Sign This ITP
Signatory - Contract Manager
Comments -
6 - Variations Reveiewed by Divisional Manager
Specification / Standard -
Inspection / Test Point - Review
ACTION - W
Conformance Criteria (Whats Required) - All Variations to be reviewed
Frequency - Prior to submission to Engineer
Inspection / Test Method - Review
Verification Records - Sign This ITP
Signatory - Contract Manager
Comments -
7 - Site Precondition Inspection
Specification / Standard -
Inspection / Test Point - Review
ACTION - W
Conformance Criteria (Whats Required) - Video record site walk over
Frequency - Prior to work starting on site
Inspection / Test Method - Video
Verification Records - Sign This ITP
Signatory - Contract Manager
Comments -
8 - Pownet and Chorus loactes completed
Specification / Standard -
Inspection / Test Point - Inspection
ACTION - H
Conformance Criteria (Whats Required) - PowerNet and Chorus has been located, refernce back to plans to ensure everthing has been located
Frequency - Prior to commencement
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor / Forman
Comments -
9 - Correct materials delivered to site in acceptable condition
Specification / Standard -
Inspection / Test Point - Material inspection
ACTION - W
Conformance Criteria (Whats Required) - Complete inspection of materials as they arrive to site (particularly the concrete pipe)
Frequency - Upon pipe delvery
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor / Forman
Comments -
10 - New FoulSewer Main Alignment
Specification / Standard - Construciton drawings
Inspection / Test Point - Inspection / Test Point
ACTION - H
Conformance Criteria (Whats Required) - Alignment to be setout and confirmed on site by Engineers Rep
Frequency - Prior to commencement
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Engineers Rep
Comments -
11 - Inspect subgrade
Specification / Standard - AS/NZS 2566.2:2002
Inspection / Test Point - Inspection/Scala
ACTION - M
Conformance Criteria (Whats Required) - Inspect subgrade as exposed and scala if required, contact manager for further instruction if deemed unsuitable
Frequency - During Construction
Inspection / Test Method - Inspection / Scala
Verification Records - Sign This ITP
Signatory - Foreman
Comments -
12 - Pipe Laying
Specification / Standard - AS/NZS 2566.2:2003 and Contract Doc
Inspection / Test Point - Pipe Laying
ACTION - M
Conformance Criteria (Whats Required) - Pipe to be laid as per spec, contract and plans.
Frequency - During Construction
Inspection / Test Method - Spot checks
Verification Records - Sign This ITP
Signatory - Foreman/Supervisor
Comments -
13 - Saddles onto main for laterals and sumps
Specification / Standard - Construciton drawings
Inspection / Test Point - Sign off
ACTION - W
Conformance Criteria (Whats Required) - Instal as per construction plans
Frequency - During Installation
Inspection / Test Method - Photos
Verification Records - Sign This ITP
Signatory - Foreman
Comments -
14 - Compaction of bedding
Specification / Standard - Contract Doc
Inspection / Test Point - Bedding
ACTION - M
Conformance Criteria (Whats Required) - Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least).
Frequency - During Construction
Inspection / Test Method - Monitor
Verification Records - Sign This ITP
Signatory - Foreman
Comments -
15 - 1050dia. Manhole Installation F24669
Specification / Standard - Contract Doc
Inspection / Test Point - Inspection
ACTION - W
Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
Frequency - During Construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Foreman/Supervisor
Comments - Complete SR Manhole checklist
16 - 1050dia. Manhole Installation F21508
Specification / Standard - Contract Doc
Inspection / Test Point - Inspection
ACTION - W
Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
Frequency - During Construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Foreman/Supervisor
Comments - Complete SR Manhole checklist
17 - 1050dia. Manhole Installation F21500
Specification / Standard - Contract Doc
Inspection / Test Point - Inspection
ACTION - W
Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
Frequency - During Construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Foreman/Supervisor
Comments - Complete SR Manhole checklist
18 - Concrete Placement
Specification / Standard -
Inspection / Test Point - Inspection
ACTION - W
Conformance Criteria (Whats Required) - Engineers Rep to have viewed / inspected concrete formwork
Frequency - During Construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Foreman/Supervisor
Comments - Photos CHAR(AMP) Concrete Dockets
19 - Encountered Services
Specification / Standard - Contract Doc Appendix X
Inspection / Test Point - Record
ACTION - W
Conformance Criteria (Whats Required) - Record service on ICC encountered serives record sheet
Frequency - During Construction
Inspection / Test Method - Record
Verification Records - Sign This ITP
Signatory - Foreman/Supervisor
Comments -
20 - Drainage Connection
Specification / Standard - Contract Doc Appendix XI
Inspection / Test Point - Record
ACTION - W
Conformance Criteria (Whats Required) - Record detail on ICC drainage connection sheet
Frequency - During Construction
Inspection / Test Method - Record
Verification Records - Sign This ITP
Signatory - Foreman/Supervisor
Comments - Complete ICC drainage sheet for each laterial
21 - Plateau Testing
Specification / Standard -
Inspection / Test Point - Test
ACTION - H
Conformance Criteria (Whats Required) - Plateau test to be undertaken at start of backfill to calibrate compaction methodology
Frequency - Test to be carried out at the start of backfilling
Inspection / Test Method - Test
Verification Records - Sign This ITP
Signatory - Contract Manager
Comments - NDM Test record
22 - Compaction of AP65 - Clegg tests
Specification / Standard - Contract Doc Appendix XIII
Inspection / Test Point - Rocord
ACTION - W
Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet
Frequency - During Construction
Inspection / Test Method - Clegg Test
Verification Records - Sign This ITP
Signatory - Foreman/Supervisor
Comments - Complete ICC Clegg record sheet
23 - Compaction of AP65 - Test results to Engineer
Specification / Standard - Contract Doc
Inspection / Test Point - Test Point
ACTION - W
Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals
Frequency - During Construction
Inspection / Test Method - NDM Test
Verification Records - Sign This ITP
Signatory - Contract Manager
Comments - NDM Test record
24 - Compaction of AP40 - Test results to Engineer
Specification / Standard - Contract Doc
Inspection / Test Point - Test Point
ACTION - W
Conformance Criteria (Whats Required) - The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals
Frequency - During Construction
Inspection / Test Method - NDM Test
Verification Records - Sign This ITP
Signatory - Contract Manager
Comments - NDM Test record
25 - Flush and CCTV line
Specification / Standard -
Inspection / Test Point - Inspection
ACTION - H
Conformance Criteria (Whats Required) - Flush and CCTV line and pass footage back to engineer for review
Frequency - Prior to asphalt
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Contract Manager
Comments -
26 - Asphalt prep
Specification / Standard -
Inspection / Test Point - Sign off
ACTION - H
Conformance Criteria (Whats Required) - Engineer to approve area is ready for asphalt (including overcuts). Prep is 50mm and has fall and compaction results have been recived
Frequency - Prior to asphalt
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Engineer
Comments -