## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP005 – Crack Sealing | itp |  |  |  | Yes | ITP005 – Crack Sealing | 02f724e8-81d1-400a-9c5a-5b37b2d41992
checkpoint-group |  |  | section | 1. Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | c1b714cc-30c9-57b1-8f61-7d114c9c1375 |  | note | Frequency - Prior to commencing any activity
label | 74d58787-a9e2-5522-be89-e046c2f230c6 |  | note | Acceptance Criteria - Current revision drawing is being used including the Subcontractor’s copy. Current revision to be obtained via Aconex.
label | 28b32f16-d8b9-5fa5-bb24-d45aaff12ae1 |  | note | Reference Documents - Drawings and drawing registers on Aconex
label | ae6d2613-cc48-5af6-93b9-38a4ebbdd4a4 |  | note | Inspection/ Test Method - Visual inspection
label | c0e20226-82fe-54d6-9b86-1cb4863f51aa |  | note | Record of conformity - This ITP signed
label | 648edee9-3948-53d9-a79a-a9d11aa94e4d |  | note | HP*
label | 64bd9716-0bbd-56c8-8d1c-fadddff151dd |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 2180f7a5-ac85-5995-8b99-f29f352af3bf |  | note | Frequency - Prior to commencing any activity
label | 3a409288-b362-567b-98a7-f1fb98ce398d |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 589ba2df-5cc4-5202-a86d-110d38d52596 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | 55f2c3d9-d52f-5b8b-bf00-90a68f012159 |  | note | Inspection/ Test Method - Visual Inspection
label | 26453423-eeb4-5d54-addd-f5083e25f85d |  | note | Record of conformity - This ITP signed
label | e20abcfb-19d7-537d-b910-8947e88541d6 |  | note | HP*
label | e7843c67-9004-5837-9ada-94c5e0a2dace |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.3 - Definition of the work area
label | 4d8f2ab6-134a-5971-93ee-3419706dbf54 |  | note | Frequency - Prior to commencing any activity
label | a32c17de-b2f9-59d9-b057-b5160aef8394 |  | note | Acceptance Criteria - Work area has been cleared and surveyed (marked on site). Limits of work clearly defined.
label | 5e00e07b-4549-5a5a-95bb-0344731cfbfc |  | note | Reference Documents - Drawings
label | ea4d45a4-cd43-5607-8e8f-210c38fd54ff |  | note | Inspection/ Test Method - Visual Inspection
label | 64657b94-d980-5b18-beea-b5f7f063cb47 |  | note | Record of conformity - This ITP signed
label | 9080aeac-3b07-582d-b6b2-457a984b29d3 |  | note | HP*
label | 74fe8532-e298-5004-949d-982423b23c3f |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.4 - Material Sources – Conformance Test Certificates/Reports
label | 5dfee6cb-fc85-53d2-9a28-009ffbd5f4ed |  | note | Frequency - At least 2 weeks prior to application on site
label | f59a435b-3659-552c-85c6-d818b650022f |  | note | Acceptance Criteria - Details of proposed Rubberised Bituminous Bandage (RBB) sealant product including manufacturer’s data sheet and recommendations for application to be submitted for approval.
label | 31a60a95-6150-5447-b668-3a6075d9a22c |  | note | Reference Documents - Cl 15.3
label | 706b204f-acc7-5e7f-b66a-d98134f1a9fe |  | note | Inspection/ Test Method - Verify
label | 7044ea12-fbd7-577d-b66a-ee577ad66d7c |  | note | Record of conformity - Aconex Correspondence
label | 41276baa-a5f8-5a61-802d-05128005f411 |  | note | HP
label | 02156797-33c2-592b-93a8-e60ec339f2f1 |  | note | Responsibility - Project Engineer Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Materials
checkpoint-status |  |  | checkpoint | 2.1 - Rubberised Bituminous Sealant
label | 6a562928-52e9-5a18-89b8-99072dc0a720 |  | note | Frequency - Prior to commencing any activity
label | 9f467099-a948-5492-a45d-846a978f19f4 |  | note | Acceptance Criteria - RBB must be a proprietary polymer modified bitumen (PMB) crack and joint bandage product and be suitable for climate conditions of the site. RBB to have following properties:
label | 96912b78-6f30-52c3-818e-a1f48ddb004d |  | note | – Minimum softening point to be 95°C
label | 556b34ba-0fef-50a0-8d69-70339c0193ba |  | note | – Penetration at 25°C between 20 and 50
label | 42ce6582-75de-5d63-9032-2561b474aec5 |  | note | – Flow at 60°C at 5 hours to be maximum 5mm
label | d8b3f085-7e75-543e-b806-726aceeba6e6 |  | note | – Viscosity at 180°C to be maximum 3Pa.s
label | 1d097911-1bdd-5de5-a66d-e5e4b44e5049 |  | note | Reference Documents - Cl 15.3
label | 434da82a-4e5f-54d7-8794-eede00cdc684 |  | note | Inspection/ Test Method - Verify
label | f4150c42-7717-5ae1-b33a-2769a7603ead |  | note | Record of conformity - Manufacturer Datasheet
label | efb92ccd-2e2d-5681-ac12-7e23f471fb3a |  | note | HP
label | 493c0870-9875-5e54-8bec-4d572286aa84 |  | note | Responsibility - Project Engineer Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preparation
checkpoint-status |  |  | checkpoint | 3.1 - Preparation of cracks
label | 4d7db7bf-56b9-52a7-be01-d3c1a13708c8 |  | note | Frequency - Prior to commencing works
label | f1ecee61-1e3b-5397-92ec-17c8895b52c0 |  | note | Acceptance Criteria - Cracks, joints and all other locations to be sealed must be sufficiently cleaned and dried out prior to sealing. All wide (greater than 8mm) and/or deep cracks in all types of pavement must be choked with dry sand to not less than 10mm below the surface of the pavement.
label | 0fd270e9-aa9f-588e-84c1-88205b4acf5b |  | note | Reference Documents - Cl 15.4.1
label | c092819e-0fe1-58c2-b5d3-a2042b33ba1f |  | note | Inspection/ Test Method - Visual Inspection
label | c0d89cf5-5ff7-57a1-b993-26306ebc6e48 |  | note | Record of conformity - This ITP signed
label | 899927e0-dc7a-5ca3-8c8f-a44b0a6a7834 |  | note | IP
label | ed2df05b-43bc-5ca5-9b52-9a55d54f0713 |  | note | Responsibility - Site Engineer
checkpoint-group |  |  | section | 4. Sealing
checkpoint-status |  |  | checkpoint | 4.1 - Trial Application
label | 301188eb-0676-5387-b430-7eccf1261abf |  | note | Frequency - Prior to continuing with crack sealing works
label | 98abeeb8-7864-5e34-b91b-4304a647e47f |  | note | Acceptance Criteria - A 50m length of RBB to be applied at location agreed with Principal’s Design Consultant for inspection and approval.
label | 9b80a145-0051-55aa-99dd-e61635b53c21 |  | note | Reference Documents - Cl 15.4.2.2
label | 69b82379-2d99-50c6-9cc2-27b9d9393501 |  | note | Inspection/ Test Method - Verify
label | bdaa20d5-d3b2-54fe-8a13-fa728b1ff947 |  | note | Record of conformity - Aconex Correspondence
label | 9b9071d4-1fd7-5f24-9784-894de3320acf |  | note | HP
label | 9b96dba6-eb64-56a3-92a9-5295bc2fd56e |  | note | Responsibility - Project Engineer Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Applying Sealant
label | ce9a08bb-77ec-5c1d-8424-741093d32e1f |  | note | Frequency - During crack sealing works
label | caca9c70-6488-5bcc-90dd-ffb51022f9dc |  | note | Acceptance Criteria - Sealant bandage must be within 50 to 75mm wide with the thickness not exceeding 1.5mm unless otherwise noted on drawings.
label | bb086261-eb67-5372-87e8-f050685ae561 |  | note | Reference Documents - Cl 15.4.2.3, Cl 15.4.2.4, Cl 15.4.2.5
label | 74ea88bb-618a-5eb9-bcfa-cefdbbb369fc |  | note | Inspection/ Test Method - Visual Inspection
label | d14b53bb-3d35-5e87-99a2-a68a13b9a703 |  | note | Record of conformity - This ITP signed
label | f1517b97-3cbe-5984-a999-edeb8bcb7095 |  | note | IP
label | 0a99c414-4ca1-5074-8b59-037dbd604310 |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4.3 - Protection of Applied Sealant
label | 7b1baff0-0758-5eae-ac46-4cef85355d7a |  | note | Frequency - During crack sealing works
label | 22b85004-2326-5553-8131-53ebe8ba0e4a |  | note | Acceptance Criteria - Installed sealant must be protected from damage by traffic (and possible pick up on construction vehicles and aircraft tyres) until it has cooled to ambient temperature.
label | b42c2ca8-df82-536b-b5e2-51abd3154cb0 |  | note | Reference Documents - Cl 15.4.2.1
label | 00fd2131-04f7-5be9-b6e8-f7252268dd7a |  | note | Inspection/ Test Method - Visual Inspection
label | 5744c988-37ba-5df1-ac0a-1157641aa61c |  | note | Record of conformity - This ITP signed
label | e3c364d6-0923-551f-be92-b2ef72eab97a |  | note | IP
label | 03f8330e-741e-532a-b257-53f4fbd22410 |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4.4 - Cleaning up
label | e81582c4-188a-53eb-ae09-ce511d6fd77e |  | note | Frequency - After sealing works
label | a24955d2-390d-53da-af2d-34327fd6ed0a |  | note | Acceptance Criteria - Any sealant split on surface of pavements must be cleaned off immediately.
label | 81335c1a-68e5-52eb-b5ce-16decaf15321 |  | note | Reference Documents - Cl 15.5
label | 1a533feb-4c79-541b-a405-2516322dcc66 |  | note | Inspection/ Test Method - Visual Inspection
label | e789c341-3c57-54ce-9d80-acf9539a65bf |  | note | Record of conformity - This ITP signed
label | 1a72882a-61b6-57db-8e4e-426d43bd7851 |  | note | IP
label | 8a98d2ca-dc3b-5253-8d54-6ffdc3d2b962 |  | note | Responsibility - Site Engineer
checkpoint-group |  |  | section | 5. Post Construction
checkpoint-status |  |  | checkpoint | 5.1 - Conformance
label | 729c3a34-2f47-5171-8f4f-07caf1b4cb5e |  | note | Frequency - At completion of each work
label | 56bd640e-13be-53af-b1ad-521316a39094 |  | note | Acceptance Criteria - Each lot package must include the following:
label | 88dcc619-0a93-5e98-b5cc-d511dcf93263 |  | note | – Equipment used
label | 2a83c384-40d5-5673-9460-447abff8c2fb |  | note | – Product used including the batch number
label | 6a5f98f9-c489-5898-b734-159c81720d40 |  | note | – Date and start and finish times
label | 1e86e002-2512-5869-a1e5-061da73f50de |  | note | – Weather conditions including range of air temperature
label | 6cf31426-59d3-52e8-8f50-71c3e554f9c3 |  | note | – Hourly sealant temperature
label | 2896c8cc-474f-597b-a9a7-80920f676e73 |  | note | Reference Documents - Cl 15.6
label | fb73ed61-0b45-503f-9234-48a6dbfd7016 |  | note | Inspection/ Test Method - Verify
label | 703c649f-0d62-5b01-83c7-8eca5665150b |  | note | Record of conformity - This ITP signed
label | c6d76573-eeba-5c8e-b17c-42427a582a66 |  | note | IP
label | e76f4978-6b96-5e68-8854-7d0796807770 |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 9e22482a-9a0c-5e6a-ad6d-031526a9cbe5 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 104d419b-c0dd-5dfd-94a5-b87a54cd84fc |  | textbox | Name:
text | 1d376049-cc5e-5ebc-bc5c-db787cf50310 |  | textbox | Position:
date | 4bca19e1-7550-5755-9967-1057aa027002 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP021-2 – Reinstallation of Secondary Cable | itp |  |  |  | Yes | ITP021-2 – Reinstallation of Secondary Cable | 1cfb7361-a366-4c0e-9e8b-c7d8bdaa7ec3
checkpoint-group |  |  | section | 1. Installation of New Secondary Cable in Existing Shallow Base Canister
checkpoint-status |  |  | checkpoint | 1.1 - Mark and cut
label | c9ce93bd-32e5-5f01-bd8d-97141d69681b |  | note | Frequency - Each Lot
label | 172c1f4c-5c6c-5e78-a572-0a40c418ff28 |  | note | Acceptance Criteria - Slots marked out and cut from to light base.
label | c2d8f07a-4621-5e36-8465-818866d08379 |  | note | Reference Documents - Drawing sets:
label | b3d52a34-773a-5777-8f00-4ea58f706f49 |  | note | • 60692389- SHT-01_1-10
label | 3bf9a24d-56f8-5aef-a9dd-4f0709295422 |  | note | • 60692389- SHT-01_2-10
label | e31705a1-94bc-5c4e-87c8-01075816544a |  | note | Inspection/ Test Method - Verify
label | 9dd02238-7d01-5371-9ea4-33ab5ae7b545 |  | note | Record of conformity - This ITP Signed / Avionics CL002
label | 48028c4b-8ff2-5355-a286-c9cc1ebb5e35 |  | note | HP*
label | a6c2e4e2-f9b9-58db-9a98-ee27c226b5e3 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.2 - Cabling
label | ddc9bfb0-b3fa-58e8-8b18-2800ae758d7b |  | note | Frequency - Each Lot
label | 8724c8a9-2991-5ae2-b484-f2812687ba2d |  | note | Acceptance Criteria - Cables ran and connected from existing base via joints/slots/conduits to SIT pit.
label | a5e3595d-9a84-5ab3-920a-26c555bb9161 |  | note | Reference Documents - Drawing sets:
label | bcb241a5-faac-5338-8767-4950358bcc71 |  | note | • 60692389- SHT-01_1-10
label | f384c5d9-67c4-51fe-94b3-5446f230bcb6 |  | note | • 60692389- SHT-01_2-10
label | 967e7192-55e6-5fab-8164-9110ef701258 |  | note | Inspection/ Test Method - Verify
label | f06df35c-37d0-560b-ab68-955c58b7211d |  | note | Record of conformity - This ITP Signed / Avionics CP002
label | 9364342e-9b6d-51f3-9c2f-f1223a6e7f9a |  | note | IP
label | 79ec13e7-c19b-586c-8dc2-9695826a7d9d |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.3 - Sealing
label | bcb93093-ad5b-582e-b027-5f2f590e16fe |  | note | Frequency - Each Lot
label | a252292e-9f29-5b34-9bd4-082c38f7f5e8 |  | note | Acceptance Criteria - Once cables installed, backing rod placed and expansion joints sealed with approved product.
label | c0095fc4-f3c5-5c43-8b17-04433a49a4d3 |  | note | Reference Documents - Drawing sets:
label | 2cba519e-86ee-52f4-96a8-862b6b8e0a5b |  | note | • 60692389- SHT-01_1-10
label | 49901a61-1077-59c0-ab01-0b729cdd0852 |  | note | • 60692389- SHT-01_2-10
label | 1db8b096-aafa-5753-9f7b-f35bf747285a |  | note | Inspection/ Test Method - Verify
label | fbdad067-8d36-50b5-bf33-8beb15f69e41 |  | note | Record of conformity - This ITP Signed / CL002
label | eea10b64-57e7-5e9f-9ab9-93471b2aa673 |  | note | IP
label | a905c71e-ab24-5cfb-80d4-d12aa2980bbc |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.6 - Finishing, Testing, Demobilisation
label | d1aacb6a-e58f-55a9-bfa5-4321b9490333 |  | note | Frequency - Each Lot
label | bb2692db-c28c-55a9-8754-2200d04c27b9 |  | note | Acceptance Criteria - Gasket positioned on light top, light plugged and positioned to current orientation. Light tested and area cleaned before demobilisation.
label | 5647c4e6-6c78-5ea0-90a4-862c81e30fe0 |  | note | Reference Documents - Drawing sets:
label | 1fe85205-ed49-5399-b116-86deaad472ec |  | note | • 60692389- SHT-01_1-10
label | 476a4b48-9184-56b3-9ca0-f98edc7bbd28 |  | note | • 60692389- SHT-01_2-10
label | d883cbbd-0e28-5490-bff4-809c61f8ed01 |  | note | Inspection/ Test Method - Verify
label | a659c63b-8bc2-5ecd-bb1f-9d080b858ee5 |  | note | Record of conformity - This ITP Signed / Avionics CL002
label | b2e4ab8a-ed78-5969-b2f3-508556c15900 |  | note | IP
label | 1108fd0c-e44b-5144-9d3c-96bc4288f1fc |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | Final Inspection
label | d8ae4fd7-cd40-5a1d-b213-6a1ab7133ed3 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 3a4254a6-7855-55a8-812f-9a57d4afee56 |  | textbox | Name:
text | e39b3e56-dfff-5cc3-98bf-cfc0ad96c0c1 |  | textbox | Position:
date | 9a513d9d-f6d0-580b-9237-250b4864b054 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP004D – Asphalt Production (Type H Shoulder Mix) | itp |  |  |  | Yes | ITP004D – Asphalt Production (Type H Shoulder Mix) | 219a1f35-284b-4497-831f-8f035d0f0f01
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - Submission of Production Plan
label | b023efc6-ab7a-55d8-806c-f09793968324 |  | note | Frequency - Prior to commencing works
label | b753e57d-b3ec-57f8-9f6a-a2e600b9ab7f |  | note | Acceptance Criteria - The production plan must demonstrate that the production capacity and the hot storage capacity of the mixing plant is sufficient to supply asphalt to complete the work undertaken within any work period on time.
label | d5c3b643-5b7b-53fb-ae33-9c116b337933 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.1
label | dd3f59a8-21b8-5ea9-9b6d-37dc81a59e97 |  | note | Inspection / Test Method - Verify
label | 0c417096-5ef1-5315-8f66-dc2e07a8e8ed |  | note | Record of conformity - Aconex Corresponde nce
label | 8d68eea1-5884-59bf-8374-20db1995b14b |  | note | HP
label | 61fd5ff2-ca80-58ce-bb1e-38387ff0e0ef |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Checking of Weighting Devices and Certificates
label | f8486746-199c-561d-9a89-68efca0a599a |  | note | Frequency - Prior to commencing works
label | e90131bb-ec42-53d7-9572-b6779aa7deb6 |  | note | Acceptance Criteria - The Contractor must supply details of current certification of weighing equipment including belt weighers and weighbridges to the Contract Administrator.
label | 263b8335-2a4a-5439-8870-9dfb5560f9b7 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.6
label | 503cde49-d4f7-5d0d-be96-04c98a91691a |  | note | Inspection / Test Method - Verify
label | 264b52d4-bc02-54ab-88ac-88511bf824c0 |  | note | Record of conformity - Aconex Corresponde nce
label | 9308e8ba-719f-52ee-92f6-89e68d677b6a |  | note | WP
label | e3a654f8-244b-53b2-b467-ca11749dd4ab |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 1.3 - Calibration of the mixing plant
label | b85f63d3-2a03-586e-89af-475d7483bda3 |  | note | Frequency - Prior to commencing works
label | 54920da3-4ccc-5b4c-ab09-4c61fdf40b55 |  | note | Acceptance Criteria - Calibrating all necessary devices and parameters at the mixing plant to achieve the “Job Mix”. Established plants must provide historical records of the asphalt production over the previous one (1) month to verify consistency.
label | ebcbaf37-13b9-5f95-a3d8-a78a5401d9f6 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.11
label | aeac7e51-5fc8-52d9-85d0-c9549099a49e |  | note | Inspection / Test Method - Verify
label | c402ed54-57a6-549f-b890-9375bfe3382d |  | note | Record of conformity - Historical records of asphalt production, This ITP signed
label | a1b59a03-13ab-59dd-9bb1-d8d5f43e9fbd |  | note | WP
label | 14cae121-21b4-5bb9-90ab-11b33c118564 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 1.4 - Submission and review of mix design
label | e5bf5448-f770-5a58-b27d-d069750ff8ee |  | note | Frequency - Prior to commencing works
label | 8e3f39f8-ad0a-5b77-80d9-926d23295db3 |  | note | Acceptance Criteria - Submission and review of a mix design report detailing the mix which meets the requirements of the specification.
label | 13ae2080-06e8-599e-a63e-18f5bb22dfc4 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.11.4
label | bbfab554-07e1-577b-b2db-a9dc40a96893 |  | note | Inspection / Test Method - Verify
label | a136de46-658c-5909-9020-91ff2ac07c18 |  | note | Record of conformity - Aconex Corresponde nce
label | 669f8575-6b25-5f51-a4fb-f5be125c5d44 |  | note | HP
label | c1224e2e-cff1-5633-9592-ae00ad4ed633 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Asphalt Production – Type H Shoulder Mix
checkpoint-status |  |  | checkpoint | 2.1 - Temperature
label | d588cfa9-60ea-53bd-b54a-48b821889ae4 |  | note | Frequency - Every loaded truck or at intervals of 15 minutes if more than one truck is dispatched in 15 minutes.
label | 4242bd14-691d-5d59-9d11-4a084c5c26e1 |  | note | Acceptance Criteria - ≤175oC
label | 588bc1e7-8a70-5d79-a8bb-9f65acdf1505 |  | note | Reference Documents - Section 407.11(a), 407.15
label | cf15fd0c-3665-5844-9570-2d84927f481e |  | note | Inspection / Test Method - Thermometer
label | 0010b976-15ca-5d4b-aa3d-13906a7a42a8 |  | note | Record of conformity - Load inspection sheet / docket
label | 23c0856d-c613-5635-bd3f-dbb045fa2051 |  | note | TP
label | 661e4939-b228-50c2-9f50-4ac65d464981 |  | note | Responsibility - Plant Operator / Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.2 - Temperature
label | 0faf15e0-f141-56c6-a5e4-5c4c82939d6f |  | note | Frequency - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | a626db77-fec6-55ad-a0e9-2b329cb642f3 |  | note | Acceptance Criteria - ≤175oC
label | 537dff2f-e853-52d4-9c66-bf6e3ec72f14 |  | note | Reference Documents - Internal
label | 3b9b58b9-7d35-51b8-bb55-bae9f605433e |  | note | Inspection / Test Method - Thermometer
label | 042eb804-d0c9-5615-a5e8-0d387e5cde6b |  | note | Record of conformity - Load inspection sheet / test report
label | a0abe44f-0315-57e9-9c88-932d056851f8 |  | note | TP
label | 9d3d9da5-bc60-51e4-88ab-be1a589fc5d4 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.3 - Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating
label | d6cbe038-bf0e-55f9-b577-49bf5bc59552 |  | note | Frequency - Every loaded truck
label | 415f1f69-a15e-5955-9e6f-af58bb31a477 |  | note | Acceptance Criteria - >95% coarse aggregate coated with binder, no obvious separated binder or uncoated particles
label | 6b7a800d-a03b-5e33-ab5c-d80a7cffc55b |  | note | Reference Documents - Section 407.11 (b)
label | b65707a6-0276-5f56-b098-030a8903e318 |  | note | Inspection / Test Method - Visual Check
label | b5d0c057-b7ce-5dcf-ae99-0ca83788b6b7 |  | note | Record of conformity - Load inspection sheet
label | 83399d07-575e-586b-a7a0-3cd1c21fa947 |  | note | TP
label | 8d58d558-f907-546d-b461-d769edc710e5 |  | note | Responsibility - Plant Operator
checkpoint-status |  |  | checkpoint | 2.4 - Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating
label | e40535d9-d4f5-5a5a-8692-f769243fc33f |  | note | Frequency - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | e3d4adb9-3dad-5966-a1b0-749a43264bfe |  | note | Acceptance Criteria - >95% coarse aggregate coated with binder, no obvious separated binder or uncoated particles
label | 9a7717c5-27dd-5fb6-a5d2-6cabfaf56101 |  | note | Reference Documents - Internal
label | d032295a-0d82-59c4-a35b-61167e7aee8d |  | note | Inspection / Test Method - Visual Check
label | a2c0a448-9736-564c-a7e4-0bddb64ea78c |  | note | Record of conformity - Load inspection sheet
label | 44b46158-3918-5eab-9da8-9b5f856bd0f7 |  | note | TP
label | ff439c17-44fd-5cc2-b538-9224c729e6cb |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.5 - Maximum density
label | 1d8243d9-46d1-58f9-97ea-06405a3aa519 |  | note | Frequency - On every production day
label | 9ae2f7d0-5395-5f24-8295-c944d7f3cf48 |  | note | Acceptance Criteria - ± 35 kg/m3 of its 6-point rolling average
label | c630c268-2c91-59dc-a0e1-997527f88e58 |  | note | Reference Documents - Section 407.11(e), 407.15
label | cba3afeb-ea11-5540-9ed1-9d92c460a3ef |  | note | Inspection / Test Method - AS2891.7.1
label | 76bb3446-5ebe-546f-bbc9-dae73f512966 |  | note | Record of conformity - NATA - accredited test certificate
label | d4da95a6-c029-5993-80ac-2ca26f4c2285 |  | note | TP
label | 999322b2-0592-54ef-81ac-ac3ab9f50d63 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.6 - Binder content
label | ea2df928-8089-5093-8ec2-40c19605ee5d |  | note | Frequency - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | 86030758-0fa7-5c82-a3c9-8e6c55745abd |  | note | Acceptance Criteria - ±0.3% of mix design specification
label | d563e251-2b3d-5ad3-a114-985de0dad91f |  | note | Reference Documents - Section 407.10, 407.15
label | 37057013-b3b4-5b3d-9e94-e7b4e4ff140c |  | note | Inspection / Test Method - AS2891.3.3 or AGPT/T234
label | 91544a98-1667-51e5-8f68-ad8ba45e3c23 |  | note | Record of conformity - NATA - accredited test certificate
label | d06498fd-0225-53a6-8845-b75a127788d8 |  | note | TP
label | 4404441d-a696-5b5e-a43a-255e540845a6 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.7 - Full sieve analysis
label | c7a77c8c-4d72-54c0-931e-8156de50aa87 |  | note | Frequency - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | f7c1050f-d53a-56e4-bebb-34167fa58a2a |  | note | Acceptance Criteria - See Table 1 Table 1 of this document.
label | 4cf5dc2b-fa2f-5bb3-96cc-52b5271ddb27 |  | note | – – – – – – – – – – – –
label | c3be207f-1b4d-56c3-af0e-e3e97fffe783 |  | note | Table 1: Production tolerances for mix grading (Table 407.101 in DoT Section 407)
label | 1af990cb-e8a9-5664-9dbd-9e49ace051b0 |  | note | 1. If post compaction grading is checked by binder extraction and sieve analysis after placement, the positive tolerances shall be increased by one percentage point.
label | d5cde75b-b850-5450-b3ce-88a6024ea493 |  | note | – – – – – – – – – – – –
label | 0f0d9b66-c230-5f86-b362-c38b56e6292d |  | note | Sieve size AS (mm) ¦¦ Tolerance on percentage passing (by mass)
label | c65e967e-decd-564d-8915-c949db771890 |  | note | Sieve size AS (mm) ¦¦ Size 7 ¦¦ Size 10 ¦¦ Size 14 ¦¦ Size 20
label | 3352eb44-a4af-5885-b9da-c81cce867e09 |  | note | – – – – – – – – – – – –
label | a22fde1e-b8e2-588c-87e2-0869e3710a83 |  | note | 37.5 ¦¦ Nil ¦¦ Nil ¦¦ Nil ¦¦ Nil
label | ec61fe1e-8837-5c9f-96fd-e9470f05a332 |  | note | 26.5 ¦¦ Nil ¦¦ Nil ¦¦ Nil ¦¦ Nil
label | 941f637d-f21e-57fb-98da-087ceac769fb |  | note | 19.0 ¦¦ Nil ¦¦ Nil ¦¦ Nil ¦¦ ± 6
label | dfa9a2a6-9593-5de1-b455-4c144a27f10c |  | note | 13.2 ¦¦ Nil ¦¦ Nil ¦¦ ± 6 ¦¦ ± 6
label | b41f9956-68bc-581f-a04e-45035cb43c93 |  | note | 9.5 ¦¦ Nil ¦¦ ± 6 ¦¦ ± 6 ¦¦ ± 6
label | 71f4b4f3-f815-51db-bc34-cf2eccbce813 |  | note | 6.70 - 4.75 ¦¦ ± 6 ¦¦ ± 6 ¦¦ ± 6 ¦¦ ± 6
label | 022665f8-4284-5af8-8150-08a2a6763714 |  | note | 2.36 – 0.600 ¦¦ ± 5 ¦¦ ± 5 ¦¦ ± 5 ¦¦ ± 5
label | b4eeb0e5-e028-512b-958c-a566a6171f40 |  | note | 0.300 – 0.150 ¦¦ ± 3 ¦¦ ± 3 ¦¦ ± 3 ¦¦ ± 3
label | b278d924-ab24-5ba7-8e3b-f1909a7ba208 |  | note | 0.075 ¦¦ ± 1.0 ¦¦ ± 1.0 ¦¦ ± 1.0 ¦¦ ± 1.0
label | c7817df2-5018-5ae5-8abc-9ccdc033a8b1 |  | note | – – – – – – – – – – – –
label | 30f83b20-4a75-5a89-9abf-357217789e44 |  | note | Reference Documents - Section 407.10, 407.15
label | 0ad5aff4-71ba-5a38-b59b-90df584a07ef |  | note | Inspection / Test Method - AS2891.3.3 or AGPT/T234
label | 2604035e-837c-5121-9e8a-ac14952aafed |  | note | Record of conformity - NATA - accredited test certificate
label | d324a91d-b442-5a8a-ab80-5d46db69738e |  | note | TP
label | 2242739b-9bf8-5f96-ae59-41601ca97e41 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.8 - Moisture content
label | 04d7ada3-a7eb-5e39-9f2f-2a2703e3a6f9 |  | note | Frequency - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | 93467b7b-35da-5c59-8005-a0d496cfd112 |  | note | Acceptance Criteria - ≤0.5% moisture
label | 14763c0f-bd32-5362-89d6-816c27f1b7ed |  | note | Reference Documents - Section 407.11 (b)
label | 9012f20b-5e1c-51f8-ad5c-640f129eef0d |  | note | Inspection / Test Method - RC 211.01
label | b53a9f45-68f2-5d57-9145-8a41252bb268 |  | note | Record of conformity - NATA - accredited test certificate
label | 14616931-7d8f-5b2d-94e4-6126081328ea |  | note | TP
label | ef5ecdea-cc50-548b-9c2e-2fd0332c36e7 |  | note | Responsibility - Laboratory Technician
checkpoint-group |  |  | section | 3. RAP Testing - RAP Level 1 and 2 (as per Table 407.121 Section 407)
checkpoint-no-status |  |  | checkpoint | Notes
label | 791e8e5d-07cb-5226-8868-1598c61e21fd |  | note | (1) An approved RAP management plan addressing RAP stockpile management, RAP sampling and testing, RAP process control, RAP traceability, RAP binder blend viscosity (RAP Level 2) and asphalt plant capability shall be submitted to DoT at least 14 days prior to the asphalt works. No asphalt containing RAP shall be supplied until DoT approves the management plant.
checkpoint-status |  |  | checkpoint | 3.1 - Moisture content of RAP
label | 382bb2c7-af98-5f86-8d98-ac596c50b54b |  | note | Frequency - One test per 500 tonnes of RAP
label | 9edf7775-44da-5369-bab1-da83a6951cd1 |  | note | Acceptance Criteria - Not exceeding the maximum moisture content acceptable for the asphalt plant nominated in the RAP Management Plan – Fulton Hogan Infrastructure Services. Any materials with moisture content greater than the nominated moisture content should be allowed to drain before being utilised.
label | 783bae64-949b-54e2-8643-d219917b9ecd |  | note | Reference Documents - Section 407.13(c) FH RAP Managemen t Plan Section 3.2
label | d539007c-1b57-56ab-92f1-1af35e2329d1 |  | note | Inspection / Test Method - AS2891.10
label | 152231e8-476a-5d31-85e2-d70f41bff25f |  | note | Record of conformity - NATA - accredited test certificate
label | be70d133-e36a-5926-b199-5da87755fd66 |  | note | TP
label | 6a82d5b5-3cd2-58b7-8628-bd1ce2c168d0 |  | note | Responsibility - Laboratory Technician / RAP Yard Supervisor
checkpoint-status |  |  | checkpoint | 3.2 - Binder content of RAP
label | d168f53b-6e3a-54ea-a4b4-c636b7f69bf1 |  | note | Frequency - One test per 500 tonnes of RAP
label | 02d2e5fb-1a72-5a89-a3f0-ec6fe9290f9d |  | note | Acceptance Criteria - ± 0.5 of target binder content, 1 out of 10 consecutive results is allowed outside tolerance
label | 9669c665-5b28-5cfc-b0c2-5b6a23f32f4b |  | note | Reference Documents - Section 407.13(c), 407.11
label | 975af466-75bb-5c40-a055-7b8ca22ab632 |  | note | Inspection / Test Method - AS2891.3.3
label | 953689f8-1e81-5a76-9659-330214f5f5b9 |  | note | Record of conformity - NATA - accredited test certificate
label | d7effce7-9336-52f1-816e-bf6d25fc10bd |  | note | TP
label | 8649f968-4e5a-52bf-b6c3-9ebaab315df0 |  | note | Responsibility - Laboratory Technician / RAP Yard Supervisor
checkpoint-status |  |  | checkpoint | 3.3 - Sieve analysis of RAP
label | fc099baa-50a7-50ed-8c3c-3e05ecfb2339 |  | note | Frequency - One test per 500 tonnes of RAP
label | 82fb341b-0319-5051-bce2-e3debe89abf5 |  | note | Acceptance Criteria - See Table 2 Table 2 of this document.
label | 7b5d6fc5-7884-5c9d-8b4d-fca67dde8783 |  | note | – – – – – – – – – – – –
label | b376f72c-cde8-5c3c-9916-78b0b202eb0d |  | note | Table 2: RAP grading tolerances (Table 407.131 in DoT Section 407)
label | 30d99b19-0501-58fe-964e-76b19522506a |  | note | – – – – – – – – – – – –
label | 4bb3d824-f943-53fd-96ea-78147a97d581 |  | note | Description ¦¦ Tolerance (from target grading) ¦¦ Allowable number of results outside of tolerance
label | 774612eb-4561-5f03-a1e9-d805e6522894 |  | note | – – – – – – – – – – – –
label | ab0d5dae-c116-5831-9b4e-c047bc34737d |  | note | Passing 26.5 mm sieve and larger ¦¦ ± 10 ¦¦ 1 out of 5 consecutive results
label | a3aa8770-fcf8-50cc-9961-7789d855d791 |  | note | Passing 4.75 mm to 19.0 mm sieve ¦¦ ± 8 ¦¦ 1 out of 5 consecutive results
label | e0ce29d3-e736-554b-852b-30a1fe155574 |  | note | Passing 1.18 mm and 2.36 mm ¦¦ ± 6 ¦¦ 1 out of 5 consecutive results
label | 6eebb0e6-4fba-5d4c-b1e7-3b46967e5d36 |  | note | Passing 0.300 mm and 0.600 mm ¦¦ ± 5 ¦¦ 1 out of 5 consecutive results
label | a36b6170-411b-5b28-9a35-92c4c139b277 |  | note | Passing 0.150 mm ¦¦ ± 3 ¦¦ 1 out of 5 consecutive results
label | eeab3ac3-5039-5dde-9d03-2add183885c0 |  | note | Passing 0.075 mm ¦¦ ± 2 ¦¦ 1 out of 10 consecutive results
label | cc4d0226-4ddc-5aba-b88f-8fafccab01db |  | note | – – – – – – – – – – – –
label | 8070a810-74fc-5a86-8e9b-30d54a5fb84a |  | note | Reference Documents - Section 407.13(c)
label | b88c0830-69bc-5a90-8980-eda8802a2935 |  | note | Inspection / Test Method - AS2891.3.3
label | 7c14569c-214b-55c3-a27b-0a695ab481fc |  | note | Record of conformity - NATA - accredited test certificate
label | d2c3c9e6-a1a8-514a-b61a-8af1b4b9db54 |  | note | TP
label | c9129709-3d5e-553b-b8ad-d7744f4470b9 |  | note | Responsibility - Laboratory Technician / RAP Yard Supervisor
checkpoint-group |  |  | section | 4. RAP Testing - RAP Level 2 (as per Table 407.121 Section 407)
checkpoint-no-status |  |  | checkpoint | Notes
label | cf4906c7-93ca-5487-9227-1ec3814a2aeb |  | note | (1) An approved RAP management plan addressing RAP stockpile management, RAP sampling and testing, RAP process control, RAP traceability, RAP binder blend viscosity (RAP Level 2) and asphalt plant capability shall be submitted to DoT at least 14 days prior to the asphalt works. No asphalt containing RAP shall be supplied until DoT approves the management plant.
checkpoint-status |  |  | checkpoint | 4.1 - Binder viscosity
label | 79b9953d-324c-503f-a693-299d85267c8c |  | note | Frequency - One test per 1000 tonnes lot of RAP used for Level 2 mixes as per Table 407.121
label | 1624da97-d2bd-5086-8bfc-eb180d696aa2 |  | note | Acceptance Criteria - Viscosity of the blend of virgin and RAP binder shall fall within the range in the table below:
label | 50f2d064-3eb5-57b0-aa7a-611f6e1ef7d9 |  | note | – – – – – – – – – – – –
label | 77e22264-3bd7-53e5-8228-f71bb16bf97f |  | note | Specified Binder Class ¦¦ Binder Blend Viscosity Range (Pa.s @ 60°C)
label | 4d2681f5-4897-5092-89e9-b2a10d145714 |  | note | – – – – – – – – – – – –
label | 13feb3b1-5a02-559c-b50d-f89dc5a24fc5 |  | note | C170 ¦¦ 170 – 240
label | 150d34c4-3376-5a91-9748-42606d257f02 |  | note | C320 ¦¦ 320 – 500
label | a6164d84-4ec5-568e-af37-e46b9efc510b |  | note | C600 ¦¦ 600 – 880
label | 38cf26f0-a98a-50a2-b091-1e51423b3f95 |  | note | – – – – – – – – – – – –
label | fa1e25dd-8a88-5c0d-83b3-2972e85dbd9e |  | note | Reference Documents - Section 407.13(e)
label | 35a940ea-8141-52a7-9bec-14595080e917 |  | note | Inspection / Test Method - AGPT/T192 or AS 2341.2, AGPT/T193
label | 2030b848-062f-53c6-973b-d4c3479d7d94 |  | note | Record of conformity - NATA - accredited test certificate
label | 19dbb1e0-01d8-519f-b399-5eb165f00942 |  | note | TP
label | ab081e3c-4f2a-5d93-965f-e2b8c45b5f72 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | Final Inspection
label | 83445666-1328-523d-ac38-2f7fcbe4018b |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
text | 382b918f-2b3f-5072-ba1f-e189078bc615 |  | textbox | Name:
text | 134ec37d-11d6-5516-9924-5d9f3ebd3fea |  | textbox | Position:
date | 2d18722d-4131-509f-956a-bfb9f51f7d7d |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP007 – Pavement Grooving | itp |  |  |  | Yes | ITP007 – Pavement Grooving | 27af6bda-8a43-41a3-a91a-988a48be8c81
checkpoint-group |  |  | section | 1. Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 061d356e-d48e-5509-9ae9-8343261da314 |  | note | Frequency - Prior to commencing any activity
label | e4587003-4067-505f-8b72-244a468e9e7f |  | note | Acceptance Criteria - Current revision drawing is being used including the Subcontractor’s copy. Current revision to be obtained via Aconex.
label | 33d9bb98-4d7f-59b3-b9e4-dd1d004bd98d |  | note | Reference Documents - Drawings and drawing registers on Aconex
label | 4cd0c26c-2777-58ae-abfc-d317bbd522d6 |  | note | Inspection/ Test Method - Visual inspection
label | ad4ebf38-4d1c-5b68-82b9-b71eca4f2e6b |  | note | Record of conformity - This ITP signed
label | 9c808b07-f0f1-53ec-8f2b-7c9eb9e3afd0 |  | note | HP*
label | 98a1c5f9-359b-51cf-b35b-0caced36333e |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 7a3fdbc9-7450-58a8-aab4-726865ccac05 |  | note | Frequency - Prior to commencing any activity
label | cc2759d6-3879-51ca-b73f-08fe1393dde0 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 4a916968-012a-555e-a2f0-33f2964212fe |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | 1251f65e-550b-5104-b1c5-c3edb0c94e4d |  | note | Inspection/ Test Method - Visual Inspection
label | e04ce296-04e9-5d02-beda-4733f53237c7 |  | note | Record of conformity - This ITP signed
label | 1ab3420b-2803-59d4-8724-bc6729f55cff |  | note | HP*
label | c5e32673-df44-5732-b4ea-2cbbe9f855c9 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.3 - Definition of the work area
label | 7f459ef0-db4b-50de-807b-e1d517474760 |  | note | Frequency - Prior to commencing any activity
label | 66c2ec27-919f-5ae8-b3f7-206ef67feb38 |  | note | Acceptance Criteria - Work area has been cleared and surveyed (marked on site). Limits of work clearly defined.
label | 63abd070-6a85-5282-a3a3-8e235918ef7a |  | note | Reference Documents - Drawings
label | 1280d287-a4e8-53af-a99a-4e5576e41ade |  | note | Inspection/ Test Method - Visual Inspection
label | 67998dbd-38c6-580e-be5b-472f7db2edb3 |  | note | Record of conformity - This ITP signed
label | 17c73df7-e5c3-5cd5-b31d-0391f5d5a75d |  | note | HP*
label | f1f47b1b-83c1-51d6-b435-f44acd5a6b2b |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.4 - Grooving Machine
label | d283acd7-1886-5a3e-9f7d-c1e2bc1536cf |  | note | Frequency - Prior to commencing any activity
label | f3dd5667-8888-528e-8de9-c5f86ae3689a |  | note | Acceptance Criteria - Details of proposed grooving machines to be submitted to Contract Administrator for approval.
label | 314c3f49-ca4c-5c57-b9f0-e0059b70825b |  | note | Reference Documents - Cl 20.3
label | 632c1b0b-9f51-5b10-a084-e452a0622dbd |  | note | Inspection/ Test Method - Verify
label | 4af626d8-ea69-5f76-8bcc-ead14e1e7b82 |  | note | Record of conformity - Aconex Correspondence
label | 9a348b8f-fd87-55b4-830d-51ab211fd024 |  | note | HP
label | b23dc034-3b1c-5d97-ba1d-e53ae2224a11 |  | note | Responsibility - Project Engineer Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Grooving
checkpoint-status |  |  | checkpoint | 2.1 - Pavement Conditions
label | ca34960d-ec88-5e30-ab10-e2239bdefe71 |  | note | Frequency - During grooving works
label | ccd397fa-d52f-5d23-94b7-4de3e232b301 |  | note | Acceptance Criteria - Pavement to be thoroughly inspected and in an acceptable and suitable condition for grooving prior to works commencing.
label | 7ffcfdc2-19a0-5f8b-82ad-87875f190a27 |  | note | Reference Documents - Cl 20.2
label | 5a58e74c-c0e3-5db0-8772-3443c2f42d0d |  | note | Inspection/ Test Method - Visual Inspection
label | a674fbad-2810-5187-b0fd-8a5865683311 |  | note | Record of conformity - This ITP signed
label | 9663ab67-995b-575c-a621-d75098a27781 |  | note | IP
label | 9f61fbd4-ca14-5f40-a354-fd25875c81e0 |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Grooving Pattern – Trapezoidal
label | 5008e6de-6be9-527c-b831-18cc020fde11 |  | note | Frequency - During grooving works
label | b087dfec-ba76-5db1-82ac-f6aae0f21604 |  | note | Acceptance Criteria - Trapezoidal grooves must be:
label | 546b67d9-405e-5ccb-a959-e7cbd0d8e643 |  | note | – Nominally 6mm deep by 6mm wide at the bottom and 12mm wide at the top and spaced evenly at 57mm centre to centre
label | eacc12a9-f735-5096-9154-893c9496e20f |  | note | – Transverse and continuous
label | ae8bf54e-aed0-5c40-bca7-ae63ec0934b9 |  | note | – At true 90 degree angle to runway and taxiway centrelines unless indicated otherwise
label | be3dc281-31bc-5553-add7-18f3f1873337 |  | note | ○ Around in-pavement light fittings, grooving must cease maximum 450mm from centreline of light in all directions.
label | 9bc04d8e-9808-5358-8bdf-cdefc8767a70 |  | note | Reference Documents - Cl 20.4.1.1
label | bf3826ed-02d7-59ed-9e62-c06275bf8663 |  | note | Inspection/ Test Method - Inspection
label | e7773e63-62c0-5804-93ce-fbe79f28b1fc |  | note | Record of conformity - This ITP signed
label | dbb67b6d-ebb3-56ef-ac68-5cf411863f42 |  | note | IP
label | 2fd95ee9-2e8b-5afa-8757-b31ef3078bb3 |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 2.3 - Tolerances – Trapezoidal
label | 83e1b6af-c0e6-5749-aa90-520618d65be0 |  | note | Frequency - During grooving works
label | 4d37b3cd-aead-534c-98c1-f67320c7087a |  | note | Acceptance Criteria - Grooving works must be as per the following allowable tolerances:
label | ff1b6e2c-46d5-5d8a-a31b-ec42be289f3f |  | note | – Spacing to be evenly spaced, no less than 54mm and no more than 60mm centre to centre
label | ae4cc5e6-8dfc-58b1-a5e3-0a4f5774ed27 |  | note | – Width:
label | dbf3a57b-f303-5ab0-b294-1cb9b3f5b6ef |  | note | – At surface - must not be less than 11.5mm and not more than 15mm
label | 3b312814-7baa-5972-bc22-b33a8ee4b80e |  | note | – At bottom - must not be less than 4.5mm and not more than 8mm
label | 79d1ff2a-872e-53cb-87f0-bf0529b4c0bf |  | note | – Depth must not be less than 4.5mm and no more than 8mm
label | a616ea81-3928-5235-a68d-7da54e25f5fa |  | note | Reference Documents - Cl 20.4.1.3
label | 5dea21fb-547d-5e62-87d3-feaf959a6000 |  | note | Inspection/ Test Method - Inspection
label | 4e4ea286-dcc0-5a13-b659-bb54a8761ac9 |  | note | Record of conformity - This ITP signed
label | 4e346915-988c-5db2-a91a-cb77545db1a5 |  | note | IP
label | 1e726714-eb45-5a5d-aae4-dfc6722f019a |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 2.4 - Grooving New Pavement Surface
label | 058d3426-e1c7-5a62-a13f-dcb424b1f93d |  | note | Frequency - During grooving works
label | af421ace-b2cb-551f-849f-8cb0f3e62e2a |  | note | Acceptance Criteria - Contract Administrator to witness measurement of groove dimensions
label | ad1375b4-d8ff-52d9-918b-75d64e9e3091 |  | note | Reference Documents - Cl 20.4.1
label | 59be9314-8c73-5127-b74f-a1d9a8c66897 |  | note | Inspection/ Test Method - Inspection
label | 39cb52b8-b80c-5dfa-b955-ef53602063e0 |  | note | Record of conformity - This ITP signed
label | cb7106d7-695a-5482-8757-52d40708f15f |  | note | WP
label | 271493ec-30bf-5eaf-a39a-681773b1ac34 |  | note | Responsibility - Site Engineer Principal’s Representative
checkpoint-group |  |  | section | 3. Slurry Removal
checkpoint-status |  |  | checkpoint | 3.1 - Removal of Slurry
label | e70c8b32-c64f-53bc-b6d9-b26e6ff8c9f5 |  | note | Frequency - Progressively during works and after
label | 7b04c531-6e42-5124-bb43-7b3e68ca344c |  | note | Acceptance Criteria - Grooving machine must flush the grooves of all slurry during grooving process. Any residual slurry must be removed using high-pressure water in combination with hand or mechanical sweeping. Slurry must not be allowed to harden in the groove.
label | 99982dec-e05b-5962-8166-cd30febedd60 |  | note | Reference Documents - Cl 20.4.2
label | e8b737e2-119b-580f-8462-d326327a27d9 |  | note | Inspection/ Test Method - Visual Inspection
label | 7239f738-4275-546c-a860-a052979b8c54 |  | note | Record of conformity - This ITP signed
label | ac80449f-2470-520d-9fd3-439f1599c3de |  | note | IP
label | 24679c02-7bdb-5612-9c13-f7a967591b2b |  | note | Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3.2 - Notification of Completion of Cleaning
label | e308d980-cf1f-595b-ac37-0d1bfaa99955 |  | note | Frequency - At each of each work period
label | aefd8ba5-6182-5d65-becc-9ec328573e16 |  | note | Acceptance Criteria - Contract Administrator is notified of completion of cleaning of pavement surface
label | b002cb79-f570-507d-af07-5376f4245966 |  | note | Reference Documents - Cl 20.4.2
label | 2bb9cddf-23a2-5262-b192-7ad278661d9a |  | note | Inspection/ Test Method - Visual Inspection
label | ccba46a3-ff67-5bfa-8f83-414ea22d52ea |  | note | Record of conformity - This ITP signed
label | 70f810b8-b473-517b-8217-84d98857d99d |  | note | WP
label | f4b277c8-487d-5356-8a96-8e0e1e841eaa |  | note | Responsibility - Site Engineer Principal’s Representative
checkpoint-status |  |  | checkpoint | Final Inspection
label | c6ca9bad-6861-51ef-96d1-6f6523ffe1af |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | da94ecca-12af-5a5c-8a9a-75839e9c11eb |  | textbox | Name:
text | f51236e4-e046-592f-ae60-e5189f10a829 |  | textbox | Position:
date | 23a880ea-0e52-5a55-bbf5-6b6030df2ea0 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP004E - Asphalt Placement | itp |  |  |  | Yes | ITP004E - Asphalt Placement | 36b5d9e1-0db5-47be-824f-67ddb882aedf
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | fde7cd44-aff7-55e0-81db-c662ca0259ae |  | note | Frequency - Prior to commencing works
label | 55463d1d-6469-5f03-bc37-35d84f9f2418 |  | note | Acceptance Criteria - Current revision of drawings, technical specifications and any other construction documentation is being utilised by Fulton Hogan and subcontractors. Current revisions of these documents to be obtained via Aconex.
label | 2afe8b59-02a8-5291-b590-ecbec988c6e0 |  | note | Reference Documents - Current Revisions in Aconex
label | c28bfe08-176e-5ee9-99b0-b1d15b903daa |  | note | Inspection/ Test Method - Verify
label | 553c28bc-be80-5501-90e6-1c7cbb39038c |  | note | Record of conformity - This ITP signed
label | 47af0f3f-abde-59e2-af18-f57d21d2454e |  | note | HP*
label | c81ff543-fed5-57eb-b310-f24ce5e3734a |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | cda7091e-0d32-596d-8dc1-81a81a687807 |  | note | Frequency - Prior to commencing works
label | 1c05c7cd-4aeb-53c0-ae38-c45c638d143a |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
label | 322059a3-ca82-56c7-91d3-49d4b02046fb |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | 3f36436a-6bc9-51fd-85b9-ec35af5ceb7a |  | note | Inspection/ Test Method - Visual Inspection
label | 8ceddebf-73e6-5928-ba01-a608d0967c82 |  | note | Record of conformity - This ITP signed
label | b031864c-f4d2-5eeb-9f1f-d0c781bfdf7c |  | note | HP*
label | 76570f13-a949-5aba-8375-ccf7c0f5c0c5 |  | note | Responsibility - FH Project Engineer / Site Supervisor
checkpoint-status |  |  | checkpoint | 1.3 - Plant & Equipment Check
label | c7b48b21-6206-51ca-b4c7-658a1eeae924 |  | note | Frequency - Prior to commencing works
label | 44ba3b9f-1b69-5fce-b3d8-cf0b1773445b |  | note | Acceptance Criteria - Asphalt plant & equipment meeting the requirements of Project Specification. Pre-Start checks completed by operators of plant and equipment. All plant and equipment are acceptable for use. Any faults are reported. Standby equipment in place where required.
label | d172b012-5618-58e8-8c41-85ec1aa9e806 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13
label | 5a0e64be-b5c5-5a6e-aaf1-379b21a6cb09 |  | note | Inspection/ Test Method - Verify
label | 69e74811-381c-577c-8ff7-ce7e391162a8 |  | note | Record of conformity - This ITP signed
label | 7ce2f8f4-eda1-56a0-a7de-24df28f6e1c7 |  | note | HP*
label | 2a9ed288-71d0-5589-b658-f31c4041a109 |  | note | Responsibility - FH Project Engineer / Site Supervisor
checkpoint-status |  |  | checkpoint | 1.4 - Tack/Bond Coat Material Submission
label | 2b0ed318-1aa1-5684-8785-d2faae8e015f |  | note | Frequency - Prior to commencing works
label | 84f9adfc-aced-58ad-8c56-6b9901924c7b |  | note | Acceptance Criteria - Details of the proposed tack coat (CRS170/60) shall be submitted to the Contract Administrator for review. Details of the proposed bond coat shall be submitted to the Contract Administrator for review.
label | 1ff6ac0d-9910-5519-af71-eadaa1c07614 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 13.5.1, 13.5.2
label | ff07b300-bcbe-5c73-b278-f868a7b974a2 |  | note | Inspection/ Test Method - Verify
label | 479ca9ea-0707-5f19-b5b7-d0944f3466e4 |  | note | Record of conformity - Aconex Correspondence
label | e8559063-0386-51c5-b6f7-1c1846ccae0c |  | note | HP
label | 9f53036d-0ed0-5513-acb8-9f7418a08f33 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Tack Coat
checkpoint-status |  |  | checkpoint | 2.1 - Surface Preparation
label | bc7565bf-ee97-5dff-8946-616246ab645a |  | note | Frequency - Prior to applying tack coat
label | ddde55ea-dcf8-5c6c-9d0c-a61557e236c7 |  | note | Acceptance Criteria - Immediately before applying the tack coat, all loose and foreign materials shall be removed from the surfaces to approximately 150mm beyond the edge of the area to be coated. Tack and bond coats must not be applied on a wet surface, or when the surface temperature is below 5 degrees Celsius.
label | a815f16a-add4-536f-85dc-d06a5bb671b3 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 13.6.1, 13.6.3
label | 9fec8348-ae35-5ef7-83cc-0340dafa5e27 |  | note | Inspection/ Test Method - Visual Inspection
label | edb9779a-0665-55c3-97e3-0a90b947b83d |  | note | Record of conformity - This ITP signed
label | ede789ae-faaa-5307-bf8b-63a75aeee2d4 |  | note | HP
label | 457ea8f6-7882-5664-a873-88b326c54be3 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Application of Tack/Bond Coat
label | fb6b6afc-2cc2-5b46-8648-99dfa0ed13d4 |  | note | Frequency - During Works
label | 1d09eadf-d113-5df6-8359-a0f8c3ebfdd4 |  | note | Acceptance Criteria - Tack coat shall be applied such that a uniform cover at the specified application rate over the full surface is achieved. Vertical faces and edges shall receive two (2) full applications of tack coat. The residual bitumen application rate of the tack coat shall be a minimum of 0.15 litres/m² for both planed and un-planed surfaces. Tack coat must be substantially broken over (> 80%) of the surface of the paving run. The bitumen application rate of the bond coat must be a minimum of 0.25 litres/m² (unless specified otherwise by the Bond Coat manufacturer) for both planed and un-planed surfaces.
label | 245fde46-721b-5c8b-aad3-8d1b0947bcf7 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 13.6.2
label | 215c766d-e9a6-56bd-abca-492f507475a2 |  | note | Inspection/ Test Method - Verify
label | f9a182cb-daec-5fdc-ac83-3d5ce8c8b407 |  | note | Record of conformity - This ITP signed
label | eed2797f-f307-5898-ab4c-79efe10a90db |  | note | WP
label | 2a1fc62e-aa35-5584-afb4-fa35a0391631 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 2.3 - Submission of spray application rates
label | ada843ac-f72c-526f-a719-de0426356bee |  | note | Frequency - At the completion of each shift
label | 53dc08f3-1102-5c08-afc3-dabcb6720bce |  | note | Acceptance Criteria - The Contractor shall submit records of spray application rates daily. Note: Spray records will not be provided for applications on vertical faces and edges.
label | 7a57a133-0ecf-53ea-9822-38452852348f |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 13.7.3
label | acfcb992-f4f7-5534-96c4-a5d609a49665 |  | note | Inspection/ Test Method - Verify
label | 0bca03d0-cc95-5935-b043-2851b5dc6a51 |  | note | Record of conformity - Aconex Correspondence
label | 17043901-f692-5641-9617-48f266780553 |  | note | HP
label | 30e202a2-d3ba-55db-82ab-9f092086b7dc |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Hot Mix Asphalt Placement
checkpoint-status |  |  | checkpoint | 3.1 - Shift plan and paving plan
label | e3a6b104-b8ce-5b08-a6cb-b7fccb60facd |  | note | Frequency - Prior to each placement shift
label | 1aab0e00-90a5-5b40-a9be-069a85a95f52 |  | note | Acceptance Criteria - The shift plan and paving plan is to detail the works planned to be undertaken each shift as well as detail any contingencies. The shift plan is to be submitted at least 8 hours prior to commencement and a paving plan is to be submitted at least 2 hours prior to commencement.
label | c6332b30-50d2-57b2-9969-0ff228e71636 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.15.2, 14.15.3
label | 2dbea006-d4a6-5bfd-9134-46a35c830082 |  | note | Inspection/ Test Method - Verify
label | cb244cfc-fb09-5f8a-87b5-57f15d66a737 |  | note | Record of conformity - Shift and Paving Plans Aconex Correspondence
label | 5d6d6fe5-6287-582c-91f6-5b399f5b6508 |  | note | HP
label | b5e56811-cf8b-533f-a5cf-1c4c7212a738 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Ambient weather conditions for placing
label | 59865424-58e7-5681-8717-c531c30a4b3e |  | note | Frequency - Prior to placement
label | ab925e59-01ac-5b1c-9be9-fbc3f8166401 |  | note | Acceptance Criteria - Asphalt shall be placed on a surface which is dry and only when rain is not imminent. Asphalt paving lengths of not more than 50m must be undertaken when wind speeds are in excess of 25km/h. Approved joint heaters must be used.
label | 2953491b-3104-5881-bf4e-b15a12ca4ed1 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.15.4.1
label | 1483c9c5-e0c9-5d65-bae3-c9b15ca3bd02 |  | note | Inspection/ Test Method - Verify
label | c4639fa0-0851-5b68-b207-78450a9d076b |  | note | Record of conformity - This ITP signed
label | 16256db5-ca13-5bf7-8981-15ab8cde23fd |  | note | HP*
label | 460147f6-3c2b-5430-a21e-02eb436db344 |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 3.3 - Surface Preparation
label | b07a42b8-f69d-5123-aef2-72db48abeb8f |  | note | Frequency - Prior to placement
label | f1ff51c9-1e66-5966-8e78-e83677c92f88 |  | note | Acceptance Criteria - The surface on which the asphalt is to be placed has been jointly inspected by the Contract Administrator and the Contractor, and it is agreed to be suitable.
label | 3fde935b-239f-5628-a1da-a2b892a0f661 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.15.4.1
label | 4ee9f1c5-507e-55bb-8e2e-573fa3880199 |  | note | Inspection/ Test Method - Visual Inspection
label | 5190889a-61b9-5c7c-ad3f-22deffb7758e |  | note | Record of conformity - This ITP signed
label | 2fb50313-ac12-5467-90ea-25726387e623 |  | note | HP
label | 67260d0b-a37c-5f39-8af7-efefab033cb2 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Surface Finish of Wearing Course
label | 80cebe65-1a00-5d6c-9214-bfc2429c35b8 |  | note | Frequency - During paving and after final roll
label | 6846095c-9ed3-53e4-9833-c011d2edf269 |  | note | Acceptance Criteria - The finished surface of the asphalt has a tightly bonded and closed surface texture, free of excessive segregation and open textured or bony joints. The finished surface of asphalt surface courses shall not pond water and shall be free from roller marks including pneumatic tyred roller ruts.
label | 09fdfb66-d52e-513c-b14b-2164ac7a89a7 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.18.5.1
label | 66b194b1-ccb8-5cfa-a4e4-5c3771320875 |  | note | Inspection/ Test Method - Visual Inspection
label | 1de89f38-9021-558a-8870-f1a96979374d |  | note | Record of conformity - This ITP signed
label | e7461fd9-cdf6-59e6-b8e6-bacc8cfd57bc |  | note | HP*
label | a378849c-5955-534a-bd33-74f645118d46 |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 3.5 - Surface Smoothness Testing
label | c37a0beb-81d5-5e3b-81d0-70bd198c1110 |  | note | Frequency - After completion of pneumatic tyred rolling
label | df0f0dc9-e042-5c8e-a2cc-ad39b15d7cec |  | note | Acceptance Criteria - The finished surface of asphalt shall not deviate from the testing edge of an approved 3.5m straight edge by more than 3mm (longitudinally) and 5mm (transversely) on aircraft pavements, and 5mm (longitudinally) and 7mm (transversely) on shoulders.
label | 13093314-5ceb-5efe-9cd3-b51f4e9ceddc |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.18.5.2
label | 0055de65-053e-52a2-887d-ea8f81e4079e |  | note | Inspection/ Test Method - Visual Inspection
label | 1857f542-fe08-55d6-82d2-9a874a1b4c83 |  | note | Record of conformity - This ITP signed
label | 3cbea391-6ad7-5a82-aa12-24ca2b923c46 |  | note | HP
label | 087dcddd-a4df-5b99-b773-38f5413b6886 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Compaction Testing
checkpoint-status |  |  | checkpoint | 4.1 - Compaction Testing (SP1 Patching Mix)
label | 673b3281-487b-5494-9f1b-6f88e474f71e |  | note | Frequency - Compaction Test Frequency (SP1 Patching Mix) is as per AECOM – MAPMP 2.0 DP1 Spec. Table 14-23
label | 2e2779b3-9bab-55d8-90c6-687ad7ed091a |  | note | Acceptance Criteria - The in-situ air voids content to be determined using a calibrated nuclear density gauge (NDG) with approved correlation for test locations away from joints. For test locations on longitudinal joints, in-situ air voids content to be determined from core samples. For test locations away from joints: Individual Air Voids: Minimum 2% and Maximum 7% Characteristic Air Voids: Minimum 3% and Maximum 7% For test locations on longitudinal joints: Individual Air Voids: Minimum 2% and Maximum 8% Characteristic Air Voids: Minimum 3% and Maximum 8%
label | 890433fb-2c75-547a-adea-0291a7a5c9bb |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.18.2, Table 14-23, 14-24
label | d3f3b269-10bd-5057-9556-3c04a302cdc3 |  | note | Inspection/ Test Method - Verify
label | 4c878b3c-b34c-5a1f-ac1d-4c620b7245a6 |  | note | Record of conformity - NATA accredited test certificate
label | 483b43cf-3b73-5c01-9024-e65485b0bd76 |  | note | TP
label | 65680631-6362-59b0-82cd-7794b3fbf10b |  | note | Responsibility - FH Project Engineer / Laboratory Technician
checkpoint-status |  |  | checkpoint | 4.2 - Compaction Testing (Type H Shoulder Mix)
label | 49643256-0e83-5abf-8463-df16d6f561e6 |  | note | Frequency - Compaction Test Frequency (Type H Shoulder Mix) is as per AECOM – MAPMP 2.0 DP1 Spec. Table 14-22
label | ebb96663-8df2-5e2f-980d-23d1f86dbebe |  | note | Acceptance Criteria - The in-situ air voids content to be determined using a calibrated nuclear density gauge (NDG) with approved correlation for test locations away from joints. For test locations on longitudinal joints, in-situ air voids content to be determined from core samples. For test locations away from joints: Individual Air Voids: Minimum 3% and Maximum 8% Characteristic Air Voids: Minimum 3% and Maximum 8% For test locations on longitudinal joints: Individual Air Voids: Minimum 3% and Maximum 9% Characteristic Air Voids: Minimum 3% and Maximum 9%
label | 0963377e-14bf-57c1-8976-4f89d728366d |  | note | Reference Documents - DCWC Mgt-GCOR-001386 AECOM – MAPMP 2.0 DP1 Spec. Table 14-22
label | a9ec63cf-560e-5359-8fd1-f8b9e7b6c89c |  | note | Inspection/ Test Method - Verify
label | 80f5a875-3947-5a8b-abe0-cd1b684184f5 |  | note | Record of conformity - NATA accredited test certificate
label | 3fa15361-3413-5725-86e5-0000d69dcb3c |  | note | TP
label | 122c323e-4961-5f21-87b9-ea77583955f7 |  | note | Responsibility - FH Project Engineer / Laboratory Technician
checkpoint-group |  |  | section | 5. Completion
checkpoint-status |  |  | checkpoint | 5.1 - Finished Surface Levels
label | ede89861-84c4-5f9d-be37-c4c278e64175 |  | note | Frequency - Per Lot & Per Asphalt Layer
label | 24a5cc0d-c4d0-5b82-b335-cf466dd78079 |  | note | Acceptance Criteria - The finished surface level of the completed pavement shall not vary by more than 5mm below or 5mm above the finished surface level specified on the Drawings. The Contractor shall provide the Contract Administrator with a record of the finished surface levels together with a summary indicating the magnitude of the departures from the specified finished surface levels shown on the Drawings with the corresponding Lot submission.
label | 189ae4f4-80f4-58d3-918d-a313d0c199a7 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.18.4.2
label | 39de46d9-f94c-5287-b3b3-3afe126d9847 |  | note | Inspection/ Test Method - Verify
label | 2c70f02d-7e85-5224-bb2d-7eb2c81c4e1c |  | note | Record of conformity - This ITP signed Survey Reports
label | e4dc80fc-901f-527a-bb75-7d9d467b6110 |  | note | HP
label | be746b72-f7de-5b6d-b1ce-4b0b8c30164e |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Surveyed Average Layer Thicknesses
label | a9bf666e-965a-5ea4-a9e7-4c607fbb8c91 |  | note | Frequency - Per Lot & Per Asphalt Layer
label | 8f7a8c82-ba69-5709-b60e-5fd872700189 |  | note | Acceptance Criteria - The Contractor shall provide the Contract Administrator with a copy of the thickness determinations, including the magnitude of any departure from the specified thickness, with the corresponding Lot submission or if departures exist, as soon as practically possible.
label | 2e3f677c-0568-55ac-81b6-bb689a2ceef4 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.18.3.1, 14.18.3.2
label | ee646bdd-c372-5bbe-b467-11c05c3dbd0c |  | note | Inspection/ Test Method - Verify
label | c39db748-5368-5b5f-9f09-cbfee4bcc585 |  | note | Record of conformity - This ITP signed Survey Reports
label | e00ee907-63c4-57b3-b862-5e42458151aa |  | note | HP
label | 179b7516-7fcc-528b-8366-bb3a699c3224 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | c833300e-adb9-56e7-b57a-bf3d33b4343c |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
text | d0e88641-4191-52a0-a14e-3ac7a95ee91a |  | textbox | Print Name:
text | 213c4814-a56b-5c18-b2e8-54e10507da2e |  | textbox | Position:
date | 6c156a86-3720-5668-af4c-1bad93392fb5 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP001 – Demolition and Service Location | itp |  |  |  | Yes | ITP001 – Demolition and Service Location | 4126bb83-2a4c-4cdd-803a-64e600bee7ff
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - The current revision of drawings are being used including subcontractors copy.
label | e451fa2a-bf7a-5311-bae7-0b261bd9e103 |  | note | Frequency - Prior to commencing works
label | c52621fc-8a80-5d03-aadf-8140d8e698b8 |  | note | Acceptance Criteria - Current revision drawings are being used, including the subcontractors copy. Current revision to be obtained via Aconex
label | 6eef650b-6ce2-59d0-9e87-0080bd0ab51f |  | note | Reference Documents - Current Revision Drawings in Aconex
label | a56bcad9-9f6b-5681-ba9e-f09cddb2e98e |  | note | Inspection/ Test Method - Visual Inspection
label | 5a881b14-b6e5-546f-9179-d6387cdc5ec7 |  | note | Record of conformity - This ITP signed
label | ca83b3d3-a2de-5969-87e2-3f6d880fca04 |  | note | HP*
label | a944e7db-7d6a-5e41-9c12-818db97a77af |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Dilapidation Report
label | 5ce6a6f3-3a9a-5654-9e78-65439ce98201 |  | note | Frequency - Prior to commencing works
label | 963323c9-c3c3-529b-be80-bcbe4c7c598d |  | note | Acceptance Criteria - Prior to the Works, the Contractor must provide the Contract Administrator and Principal’s Design Consultant with a fully detailed dilapidation survey recording the current condition of aircraft pavements, aircraft pavement surface features, underground services, roads, drives, footpaths and adjoining premises.
label | e7c26a3c-89a4-5ea5-8e53-2972a6eeddd5 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl1.23.1
label | 1d92130c-9ceb-5e38-9696-692220aa23c7 |  | note | Inspection/ Test Method - Verify
label | 4913e422-961a-57d4-a0b0-87ad09e119d7 |  | note | Record of conformity - Aconex Correspondence
label | 64ee6ce5-c0c8-5541-8951-5eea4f12363b |  | note | HP
label | c53aaf24-6e9b-5941-8d00-bf5c37bc3145 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Service Location and Detection Methodology
label | e90a3039-1e71-54f4-97d9-821ca3ab356f |  | note | Frequency - Prior to commencing works
label | 9af3d57e-cbd7-515c-b7ee-0118b617559a |  | note | Acceptance Criteria - The Contractor must submit a methodology of service detection to the Contract Administrator for review.
label | eb4ab646-b3f5-53ac-89b2-ae66d8ebe08a |  | note | • Within 20m of intrusive works the Contractor must locate and mark the ground position of all underground services and structures.
label | 5514b730-423d-558d-8d36-818fd8c1c85a |  | note | • Services located within the works area must be exposed using hand tools or specialist sensitive excavation techniques (NDD).
label | 499aa3fa-69b6-5d26-b153-018be7217f77 |  | note | • This methodology is contained within the work procedure for demolition.
label | dd731314-fe0f-5983-9bf1-ed21e9489d2b |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl3.2.1 & AECOM – MAP MP 2.0 Spec. Cl3.2.2
label | be60e866-7601-55c3-8068-978389eca1c3 |  | note | • FH-DP1PM-WP001 Section 3.2
label | 4bb4c060-5878-5250-ab3c-444e2d7d1617 |  | note | Inspection/ Test Method - Verify
label | 23a35fc7-eb6b-5697-8739-3c093c7f97b2 |  | note | Record of conformity - This ITP signed
label | fcc1c18a-eec5-5ff4-a987-21937a8c83ae |  | note | WP
label | 39b5a662-39e0-501d-8a1f-9b37e582e602 |  | note | Responsibility - FH Project Engineer Contract Administrator
checkpoint-status |  |  | checkpoint | 1.4 - Demolition Work Plan
label | 4fd5e26f-d17e-512f-a72d-4c887e6f2db3 |  | note | Frequency - Prior to commencing works
label | 6c0978f7-03c7-524c-96ac-a24df2eeed17 |  | note | Acceptance Criteria - The Contractor must prepare a Demolition Work Plan and shall submit this plan to the Contract Administrator at least ten (10) business days prior to the works commencing for approval.
label | 3ad95fbd-4265-509f-9ffe-f701602bf94c |  | note | • The Contractor must maintain pavements surrounding the demolition site in a clean condition that is free from debris and saw and core cuttings, slurry etc
label | 567494d0-deb2-5ae4-94eb-e51344c05deb |  | note | • Precautions to protect the existing remaining pavement from damage must be undertaken where tracked equipment are required to traverse or operate on existing pavement.
label | dee362ba-0ed9-5c1d-8f43-d89323b881e1 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl4.5 & AECOM – MAP MP 2.0 Spec. Cl4.6.3
label | 3820e23a-f39e-533a-a083-44fd7ea0421f |  | note | Inspection/ Test Method - Verify
label | b92cd670-f161-51cd-8d90-496f342093d2 |  | note | Record of conformity - This ITP signed
label | dbd2e819-061c-5536-83bf-fb9282317efa |  | note | HP
label | 8d30254a-663a-5764-89ad-78053f197b07 |  | note | Responsibility - FH Project Engineer Contract Administrator
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Obtain approvals to start works
label | e354c684-42ab-5450-b061-334fbbabb57c |  | note | Frequency - Prior to commencing works
label | 85ce99f6-295c-5f3f-bdb1-a12636c6f41e |  | note | Acceptance Criteria - The Contractor needs to obtain all required works approval from the Principal as required. This must include excavations, hot works, electrical isolation permits and crane access. Evidence of permits being obtained by the Contractor must be submitted to the Contract Administrator prior to works commencing.
label | 466e523f-8c6c-5ce3-b36e-34558fd44f75 |  | note | • Fulton Hogan Excavation permit issued to plant operators.
label | e554df67-6da7-522e-a049-99fc26249bff |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl4.4
label | d56c0406-5f05-54b6-aa77-a6ea803f685e |  | note | Inspection/ Test Method - Verify
label | 7696d8e3-09a9-56b8-864b-2874d6c453d7 |  | note | Record of conformity - This ITP signed
label | d32d235f-459b-5f41-b6b4-12cffa6af0a7 |  | note | HP
label | a25071ba-1f84-5abf-a4ac-1847d9949ac1 |  | note | Responsibility - FH Project Engineer Contract Administrator
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Implementation of all measures and controls
label | 78525fc0-b343-5724-832b-ab985d5edcce |  | note | Frequency - Prior to commencing works
label | 43bf98c3-a6ad-5087-8ada-cadeba1448af |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 5a91760f-12e3-53b0-a795-ad547753ee70 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | 6e892edc-ac91-54c9-832b-a744d2412a2d |  | note | Inspection/ Test Method - Visual Inspection
label | f404247d-c887-5d11-8e7b-099885f4decb |  | note | Record of conformity - This ITP signed
label | e32b9ec4-0eb1-55a8-b690-3cf4da4c4da9 |  | note | HP*
label | a2da9781-bcef-5de3-b0c6-ac827ea40447 |  | note | Responsibility - FH Project Engineer / Site Supervisor
checkpoint-group |  |  | section | 2. Demolition Works
checkpoint-status |  |  | checkpoint | 2.1 - Services Detection
label | 1b660b5e-4e36-5b70-97df-5d1e3990b79b |  | note | Frequency - Each Lot
label | 2ae8213c-d4f0-5260-b5c2-d4bb9c0b4264 |  | note | Acceptance Criteria - Confirmation that Services Detection has been Completed for the Works area(s)
label | 90737bb8-a522-5edf-8c63-a781fe9a2d92 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl3.3.1
label | 1fb3479b-0015-5794-b62f-67909d873052 |  | note | Inspection/ Test Method - Visual Inspection
label | c1da686a-90e5-5561-a911-d802b00deabd |  | note | Record of conformity - This ITP signed
label | 54287634-139b-5bfb-a94f-e736befc7095 |  | note | HP
label | 4f40739f-11ce-546f-b341-1a8142905b4d |  | note | Responsibility - FH Project Engineer / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Discovery of Contaminated Materials
label | b275801d-e1e8-5d0b-b202-55ffa61ebd80 |  | note | Frequency - Each Lot
label | ceafb911-9098-5277-92d6-f3a343f6506f |  | note | Acceptance Criteria - If contaminated or hazardous materials are found, immediate notice is to be given to the Principal’s Representative. These include the following;
label | 62afce4a-859c-568a-b266-fdc782169eef |  | note | • Asbestos or material containing asbestos;
label | a3a7db0c-4c2a-5621-8240-245e23e24d96 |  | note | • Flammable or explosive liquids or gases;
label | 34f5220f-9e7f-560f-a047-0a8b8f800d7a |  | note | • Toxic, infective or contaminated materials;
label | 21961daa-d9b5-5358-be91-88c825caf57c |  | note | • Radiation or radioactive materials;
label | 33766565-94c0-5ce0-9225-0a3debe3514a |  | note | • Noxious or explosive chemicals; and
label | 615d5aed-9918-5754-a8fe-9d958c24f0f7 |  | note | • Tanks or other containers which have been used for storage of explosive, toxic, infective or contaminated substances.
label | 3869b836-7cd3-516f-a9e8-707536159340 |  | note | ○ A proposal for the procedure to remove contaminated or hazardous materials from the site to be agreed between FH, APAM and AECOM in accordance with all statutory and contractual requirements to approved locations.
label | 63b1c77e-4ceb-5364-9651-262595b24922 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl1.19
label | f9783270-b99a-5ce6-9a07-a076383e2a9e |  | note | • FH-DP1PM-WP001 Section 3.3.7.
label | 64d31025-da8d-537d-995e-1663bd59385c |  | note | Inspection/ Test Method - Verify
label | e6b8a0c5-9ced-5c5a-a8d5-77613e4fcd87 |  | note | Record of conformity - This ITP signed
label | 14f307bd-391f-59e3-af7e-138c7bfdf3c2 |  | note | HP*
label | 264a18d9-6447-54e7-98ea-97a188dbc396 |  | note | Responsibility - FH Project Engineer / Contract Administrator
checkpoint-status |  |  | checkpoint | 2.3 - Disposal of Demolished Materials
label | e4f64fb8-a33f-5fbb-afd3-3f3ba9d6f392 |  | note | Frequency - Each Lot
label | 63daef29-7b0e-55f1-90e0-946d0baf2b64 |  | note | Acceptance Criteria - The disposal of demolished materials is to be managed under the approved Construction Environmental Management Plan (CEMP).
label | 19d0096f-ebd2-51a0-9e23-4c2e6b401b32 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl4.6.5
label | f5052e03-03f8-518d-9561-e4747afc5922 |  | note | Inspection/ Test Method - Verify
label | fde1eaf0-4726-5622-af2a-3516769a9e10 |  | note | Record of conformity - This ITP signed
label | 7e66fe75-ff60-5ee2-bf2e-bab4304e3b17 |  | note | HP*
label | add96f63-5270-543a-bf82-38b717d8f343 |  | note | Responsibility - FH Project Engineer / Foreman
checkpoint-status |  |  | checkpoint | 2.4 - Completion
label | a8d501ff-5c3b-5239-8e70-ef7b279912e8 |  | note | Frequency - Each Lot
label | 46d81abd-0266-5a89-a775-dc7fe607a15b |  | note | Acceptance Criteria - The Contractor to make the area safe and clean post completion of works. Any temporary supports are to be removed at completion of demolition.
label | 209d3bdd-787f-5983-a9b0-169853ce0927 |  | note | Reference Documents - FH-DP1PM-WP001 Section 3.3.14
label | de87db96-f05c-568f-bd84-57adc63304ab |  | note | Inspection/ Test Method - Inspection
label | dc4f8a50-a0ae-5687-994f-a4da22b4b19f |  | note | Record of conformity - This ITP signed
label | ef0aec62-1520-54dd-a51d-3958d6f48f63 |  | note | HP*
label | c1a0ca52-3f5f-5ffe-a3b0-093bedb3ee31 |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 88f6e925-9f70-5997-abd1-0a63557faabc |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | d29489dc-31c6-5878-a2ea-15d6c6699b00 |  | textbox | Name:
text | 05b0406e-962e-58b1-a9e4-d01002915775 |  | textbox | Position:
date | e37fe8b5-98aa-5054-8c3d-bdb014c9b9fd |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP010 – Linemarking | itp |  |  |  | Yes | ITP010 – Linemarking | 45310de1-e457-4852-a4d7-bd2b64c9eefe
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | a3ca406c-4f5c-5268-8743-3bc35a9a6d1c |  | note | Frequency - Prior to commencing any activity
label | bf225765-26d6-5480-a359-79176160671c |  | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy.
label | 777a0766-a70e-5c18-85a3-9daf78715e88 |  | note | • Current revision to be obtained via Aconex
label | 52bc03e3-7210-5e76-b762-7eacc97b6581 |  | note | Reference Documents - Drawings and Aconex
label | 7cee347b-88bc-5718-936b-96940338b5dd |  | note | Inspection/ Test Method - Visual inspection
label | ec7f1ba0-756b-5b9b-9f32-cdc595fb9485 |  | note | Record of conformity - This Signed ITP
label | e8d34e63-5d01-5ab6-b294-3e3eae2c110d |  | note | HP*
label | d93ee044-5cc3-5796-bc19-b5f838a78569 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | d5416b29-c666-5388-a3f2-92504d0eaaea |  | note | Frequency - Prior to commencing any activity
label | a003dfc7-4ab5-5905-ac53-1aef2dfd77a0 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | cf0ba7f0-419c-5574-a4a7-a890d592f4a2 |  | note | Reference Documents - PSP, EMP, TMP, WP, SWMS
label | 0cddbb6d-01b4-5ac2-af2e-4968956523e1 |  | note | Inspection/ Test Method - Visual Inspection
label | 0fe05ce0-f95a-5a46-8010-a26ca0b798a5 |  | note | Record of conformity - Site and Office Inspection
label | 1fdbdd1f-6e12-5102-bb5c-91c15445efd1 |  | note | HP*
label | 05abe1e8-c875-58cf-bae5-4bc3897c53f4 |  | note | Responsibility - Project Engineer Site Supervisor
checkpoint-status |  |  | checkpoint | 1.3 - Plant and Equipment
label | aa0fa60b-cc77-589f-9c0b-178528e1c9af |  | note | Frequency - Prior to placing works
label | 1b3264dd-e362-5ed6-acc7-2808afe90ef1 |  | note | Acceptance Criteria - Plant and equipment used in the works are appropriate to achieve specification requirements
label | 4c2c8154-ba6f-550f-90d7-594a941e6d1c |  | note | Reference Documents - Cl 19.4
label | b0926957-f0b8-5e78-9adf-c6db8f64d9c3 |  | note | Inspection/ Test Method - Verify
label | 46df8582-d4e3-518a-97ef-0c80c5bbd3db |  | note | Record of conformity - This Signed ITP
label | e76bf4da-e056-540a-b10e-b3fd445207a4 |  | note | HP*
label | 16a7436e-bdc8-57dc-80e9-614274550f26 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.4 - Setting out
label | 8a200780-edcb-5fb1-9e43-b47ff782f9ef |  | note | Frequency - Prior to commencing works
label | ca3e3d34-3a87-50cf-9420-45e5670aa9fd |  | note | Acceptance Criteria - The contractor shall carry out the setting out of the pavement Markings as shown on the drawings.
label | 316b6d69-b128-5a83-9353-44946321931c |  | note | • Accuracy of survey set-out to be confirmed to be within +/- 25mm.
label | 52d2aa48-1385-553b-840a-7cec6a44eb30 |  | note | Reference Documents - Cl 19.6.4
label | 6e22c474-200a-5cae-8a77-a08e51416512 |  | note | Inspection/ Test Method - Verify
label | bafa8c06-b2a5-55fb-87fe-d08fc7859cde |  | note | Record of conformity - This Signed ITP
label | 2c91a4c2-b6ae-5b4f-8f3d-a522f6fb3045 |  | note | HP
label | 27b46e53-717a-5af8-b488-be3c29c38ee9 |  | note | Responsibility - Project Engineer Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Construction
checkpoint-status |  |  | checkpoint | 2.1 - Removal of Existing Line Marking
label | 1bcaf003-9424-5b2f-9c0a-87a802c679bc |  | note | Frequency - Each Lot
label | c7ff391e-38e2-56e1-852a-6cc35ea6bca9 |  | note | Acceptance Criteria - Existing and temporary paint markings shall be removed prior to application of permanent markings, where indicated on drawings or no longer needed, by the use of high-pressure water blasting
label | 0b191f1a-dabb-5b9f-ada9-aed664113478 |  | note | Reference Documents - Cl 19.6.1
label | f8181709-25cc-5342-9b98-d1d963132365 |  | note | Inspection/ Test Method - Verify
label | 0bad5a35-10dc-5c02-b777-8ef3f12530e1 |  | note | Record of conformity - This Signed ITP
label | 92169d71-28f0-5aab-94af-c5b7100d036c |  | note | HP
label | 3d4a4abb-0e8f-5bcb-872b-9dedfed1f9f7 |  | note | Responsibility - Project Engineer Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Surface preparation
label | c0eb4d8d-86a1-5e4c-8798-b7e07f1c2841 |  | note | Frequency - Each Lot
label | 65da0f9f-d45d-5be3-a844-d28257c1dceb |  | note | Acceptance Criteria - Immediately before application of paint, surfaces are to be dry and free from curing compound, dirt, grease, oil, laitance, or other foreign material that would reduce the bond between the paint and the pavement.
label | ba58dbaf-8c5a-5f17-94d7-a47574167470 |  | note | • The contractor shall verify in writing that the surface has been prepared in accordance to the manufacturers requirements. This shall be approved by the Principal’s Representative.
label | 1e266883-8762-57d5-ad98-c48158d52873 |  | note | Reference Documents - Cl 19.6.2.1 MAS-CVL-003 (Airside)
label | 47d37986-e189-5230-8ff2-3d92f3e08965 |  | note | Inspection/ Test Method - Visual Inspection
label | 5ab0a0a7-692c-5916-aa71-75e5111dbf95 |  | note | Record of conformity - This Signed ITP
label | f504fbd7-e1ce-5525-ada6-a27513f192ad |  | note | HP
label | ab54ccde-b41f-53e9-9407-782ab7cf70df |  | note | Responsibility - Project Engineer Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Weather Conditions
label | 2733dcb5-812d-508a-98ac-c3be12c8bd7c |  | note | Frequency - Each Lot
label | 8a7c834d-8307-58ed-93e6-d36bd4ffcb24 |  | note | Acceptance Criteria - Pavement marking must not proceed during wet weather or when the pavement surface is wet or when rain is likely or during high winds.
label | e4ab1f09-625e-5f4e-aa3f-9101f6c3a62a |  | note | Reference Documents - Cl 19.7
label | 5316c4ae-eace-53a8-b5f3-09871c9b2d19 |  | note | Inspection/ Test Method - Verify & Visual Inspection
label | 014129a0-4380-5829-bd43-43490ec5f151 |  | note | Record of conformity - This Signed ITP
label | 169382de-53da-5036-bfd2-97d182af9812 |  | note | IP
label | 582f5dff-b815-52f3-9fb7-268497a9a58f |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 2.4 - Application
label | 3052e5ca-1a6f-5e70-9b3b-e182fc87b6bb |  | note | Frequency - Each Lot
label | 5e842d34-f564-5b34-bf91-786d1c04fc48 |  | note | Acceptance Criteria - The paint must be applied in two even coats to provide the required minimum total dry film thickness as specified by the manufacturer.
label | 477fd1c0-2dcb-5800-bddf-6ee45b69319f |  | note | Reference Documents - Cl 19.6.5
label | f972196d-c753-5f46-abc3-713e4fe6622a |  | note | Inspection/ Test Method - Approval and Visual Inspection
label | e8b0cf58-91ac-55fe-a9eb-70dd30a55442 |  | note | Record of conformity - This Signed ITP
label | fd033474-d3ca-5464-bef0-d8e1035596e5 |  | note | HP*
label | 8c3c01f1-57ac-5c8f-abf6-2f3db136b7ba |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 2.5 - Application Rate and Conformity of Application
label | 962df6cc-d875-5d37-bf27-f8a290a655b5 |  | note | Frequency - Each Lot
label | 2b6d492f-8281-56d6-9840-4249a8a563e9 |  | note | Acceptance Criteria - Daily records of paint usage and area covered shall be maintained to ensure that the specified coverage is being obtained consistently.
label | fa21f4ff-aab2-5744-aa54-9bea6315d6a0 |  | note | Reference Documents - Cl 19.6.6
label | d26fbe6b-347c-58f1-b11e-a16e85666da9 |  | note | Inspection/ Test Method - Daily Records
label | 4e388ba7-c184-5f68-87af-effe51d076a4 |  | note | Record of conformity - This Signed ITP
label | 118b0448-a917-589d-8f01-deff143ceca2 |  | note | IP
label | df97d7b8-8784-51f3-be02-23283888810b |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | b482adfa-fd6c-5de0-9736-0f379c2cb132 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | b078aa60-aa0e-5df8-a20c-732fadd0fa32 |  | textbox | Name:
text | 34236484-05b7-5f7b-94d3-61751214b2b9 |  | textbox | Position:
date | f20d6f04-31f1-5b29-9184-b0862264092a |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | FH-DP1-PM-ITP008 - Minor Asphalt Works | itp |  |  |  | Yes | ITP008 – Subsoil Drainage | 6a3a8108-fdea-4b27-b7b6-8f56ff1e63d8
checkpoint-group |  |  | section | 1. Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 8f268b77-edc8-559c-853d-6b1fbacc8545 |  | note | Frequency - Prior to commenc ing any activity
label | 44850c9f-7f88-5222-896f-a3ac58e287ec |  | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
label | fb7bd970-1d09-5c80-b080-92a06e930a8c |  | note | Reference Documents - Drawings and drawing registers on Aconex
label | 9cdf7216-b75e-5449-b282-3f37f77f5faa |  | note | Inspection/ Test Method - Visual inspection
label | 34b38ecf-7efd-53a7-8891-9dacfad9ff19 |  | note | Record of conformity - This ITP signed
label | d08e489f-6373-5fe2-8b8a-ba7cc3340a58 |  | note | HP*
label | 67038ed8-460b-5cc6-97db-d3f8976f8bae |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | add06799-dc56-58ee-92d3-898ce4b37d01 |  | note | Frequency - Prior to commenc ing any activity
label | 79b883c3-21cf-549a-ad51-604ebbc3fdc9 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 9cf10057-e1ac-523f-8d4b-f772c238f695 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | 7523015a-29cc-541e-855e-53a7ea3922d8 |  | note | Inspection/ Test Method - Visual Inspection
label | feda99c4-8f88-5f0a-92e6-68d71ec96bd8 |  | note | Record of conformity - This ITP signed
label | 708363b5-9bd0-5a26-89f8-fb45f697b165 |  | note | HP*
label | b10ae669-02a8-51ad-871a-bfdd132d45ea |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.3 - Definition of the work area
label | 76fd599f-6143-58f3-b15d-077302dff450 |  | note | Frequency - Prior to commenc ing any activity
label | e9241b5a-bad1-5588-94c2-fb8b6ae96151 |  | note | Acceptance Criteria - Work area has been cleared and surveyed (marked on site). Limits of excavation clearly defined.
label | 7a91de06-e0f3-5ee0-b19d-ef7fb93798db |  | note | Reference Documents - Drawings
label | d2b079c3-74a3-52af-b89a-fac750f92994 |  | note | Inspection/ Test Method - Visual Inspection
label | abaa4c0d-bfc1-5a5e-bd46-f3f3ff3212ad |  | note | Record of conformity - This ITP signed
label | 6e037040-19b8-5d4a-a76f-426c312fcdbd |  | note | HP*
label | 12fb8905-d8ec-59bb-9c91-7dada119ac11 |  | note | Responsibility - Project Engineer
checkpoint-group |  |  | section | 2. Subsoil Material
checkpoint-status |  |  | checkpoint | 2.1 - Subsurface Drainage Pipes
label | 5b1925f7-85ad-56c6-b35d-3d2c73ebe5a3 |  | note | Frequency - Prior to Start
label | 7effdd2e-fb98-5819-9cd8-f90802a82890 |  | note | Acceptance Criteria - Subsoil Pipe material to be 150mm slotted agi class 1000 SN20, or approved alternative.
label | e515e9a4-cd2a-559d-9f85-9d094d83f037 |  | note | Reference Documents - Drawings
label | 09a2fbdb-cd77-54dd-8a25-b080147ed8ee |  | note | Inspection/ Test Method - Verify
label | cfa7f4a6-7190-5860-982b-fb28a2517e97 |  | note | Record of conformity - This ITP signed
label | 7f6b8c54-112b-587d-8148-b478d5af2921 |  | note | HP*
label | dec25b73-495c-5caa-a981-640f287b550b |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Bedding & Backfill Material
label | 62ed14ae-6013-589f-a5dc-b3e9a78cac3a |  | note | Frequency - Each Lot
label | 58b4dd78-db35-5bf6-b304-7190bdd4f441 |  | note | Acceptance Criteria - Backfill filter material - approved alternative, complying with VicRoads Section 702.
label | aa077d17-d9c5-5567-a42c-142505863e41 |  | note | Reference Documents - AECOM- MAPMP 2.0 Spec. Cl 8.4.2 Design Drawings
label | 25682e3a-a455-596d-b60b-dbf4b69f28c3 |  | note | Inspection/ Test Method - Verify
label | 7244b799-1c2e-59e6-96b5-8ee27eed68bf |  | note | Record of conformity - This ITP signed
label | 0b03a671-847d-55ad-8f00-768ef060c72e |  | note | HP*
label | c16df0f7-a77e-5bfa-a2c0-6e13618c115b |  | note | Responsibility - Project Engineer
checkpoint-group |  |  | section | 3. Excavation and Installation
checkpoint-status |  |  | checkpoint | 3.1 - Trench Excavation
label | 23194073-219c-564e-964f-6448fb697248 |  | note | Frequency - Each Lot
label | b3c07443-e9c5-501c-8031-b74ebf24a8b1 |  | note | Acceptance Criteria - Trenches excavated to dimensions and grades shown on design drawings. Excavation to allow for 100mm bedding material. The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in completed excavations. Excavated material disposed per approved CEMP.
label | d1944bcf-28e3-5dfb-94f0-b5753780ff7c |  | note | HP: Base of trench inspected prior to placing bedding material
label | 59a87ee4-ef43-5f53-95a4-16c9c7562ef5 |  | note | Reference Documents - Drawings & AECOM – "MAPMP 2.0
label | 8b422297-646c-5036-ba32-d6b7e2b76b23 |  | note | Spec. Cl 8.5.3, 8.5.4, 8.5.5 & 8.5.7"
label | 9aec0526-a4fb-5872-876e-ded8cd8280af |  | note | Vic Roads 702.08
label | 12dfeb7e-fe71-5700-b880-5ee83b91eb9c |  | note | Inspection/ Test Method - Verify
label | 4338d00e-102a-568a-ad17-414863d53984 |  | note | Record of conformity - This ITP Signed
label | 6e83994b-a128-59df-a423-14efdfcc3d72 |  | note | HP
label | 6595edd1-ce7b-5dbd-8bf6-1b417e8c4a58 |  | note | Responsibility - Project Engineer / Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Bedding, Laying Pipes & Backfill
label | d2ed11b4-d7be-58eb-b425-66cf6ff2d059 |  | note | Frequency - Each Lot
label | d9540ec8-8a4b-5c65-858c-751b44f8132c |  | note | Acceptance Criteria - In accordance to the dimensions outlined in the drawings. Tolerances: +/- 50mm from specified line +/- 25mm from specified level Minimum Grade 1 in 250, unless approved or designed otherwise. Bedding to be tamped and screeded or graded to level.
label | 1b565ae0-2542-5f73-bd78-5d470666811d |  | note | Reference Documents - Drawings & AECOM – MAPMP 2.0 Spec. Cl 8.5.4 & 8.5.5 Vic Roads 702.03, 702.09
label | 336325ab-803a-50a9-91c6-d7dbd5c5d19b |  | note | Inspection/ Test Method - Visual Inspection
label | 48ec3f4b-e2a4-5c47-99c3-a14b1c24203b |  | note | Record of conformity - This ITP Signed
label | 21b735ef-7f7d-5eee-8f78-dffa3516fdac |  | note | HP
label | 88bc3b59-c230-58f2-8714-3e0499e5da10 |  | note | Responsibility - Project Engineer / Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Laying and Jointing of Pipes
label | 6d4f86ce-de6a-5360-b858-2317f3eefa2f |  | note | Frequency - Each Lot
label | bb96d8f9-4bf8-5e84-b204-9ddb5e725324 |  | note | Acceptance Criteria - Pipes laid at the depths and lines indicated on drawings.
label | 7367ed3a-2fae-50e1-9007-627997583b55 |  | note | Reference Documents - Drawings
label | 1850a5a0-4369-5c8e-996c-0321dfefd88e |  | note | Inspection/ Test Method - Visual Inspection
label | a6b7bf54-587a-586d-9468-71847a7457af |  | note | Record of conformity - This ITP Signed
label | fb6f9ed6-62cd-5e9c-a094-81af3d87929c |  | note | HP*
label | 1e94b7c5-bfb8-52b9-9488-7c1726ed382e |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Subsoil Drain Outlet
label | db97bb79-82cc-58f9-b541-43f958caa2f0 |  | note | Frequency - Each lot
label | f8c8b260-7666-50e0-9422-ee411b23ddb5 |  | note | Acceptance Criteria - Outlets from subsoil drains shall be constructed to discharge into stormwater drainage system.
label | 2a3b7cd8-896c-522d-8005-29bf0cd36bae |  | note | Reference Documents - AECOM – MAPMP 2.0 Spec. Cl 8.5.6
label | 7cda3f4f-dac1-5fe7-a6ea-772590689dd1 |  | note | Inspection/ Test Method - Verify
label | dcfa8aa1-bf50-5039-b62c-8c81b2cd43ee |  | note | Record of conformity - This ITP Signed
label | 2b0397c8-2e90-51ed-b003-276d2600e77c |  | note | HP*
label | 8531e4db-5e90-5a82-90d4-566bdcf8ce1e |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 3.5 - Flush out risers
label | c085b5e2-cda3-53a6-8375-13ac5d21808b |  | note | Frequency - Each Lot
label | 7e17ee1f-082f-5df2-9223-c7e0142de366 |  | note | Acceptance Criteria - To be the same diameter as the subsoil pipe and be installed in locations indicated on the drawings.
label | 71a25b99-0e42-57f2-aace-0d0303ef0396 |  | note | Reference Documents - Drawings & Vic Roads 702.10
label | 47f6d33e-bf99-5243-abee-1dc950f03749 |  | note | Inspection/ Test Method - Visual Inspection
label | a4a60bd6-1095-5f6c-9e1c-f76389380ee6 |  | note | Record of conformity - This ITP Signed
label | 2826828f-7a03-576e-9c2f-84dfa7d62647 |  | note | HP*
label | 2ede5a57-3f10-5db4-a648-3a2e925e9ad5 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Flushing Test
label | 86194e5d-fa26-52dd-9432-9b70ea8e25e6 |  | note | Frequency - Each Lot
label | 8d1ee07c-02ea-53c6-a536-4e105934a014 |  | note | Acceptance Criteria - A flushing test shall be carried out on each subsurface drainage line after completion of subsurface drains, flushers and outlets. The test shall be witnessed by the Principal’s representative.
label | 479a4cf2-95ac-5cec-9e28-fbe14683478d |  | note | Reference Documents - Drawings & Vic Roads 702.09
label | 5682edbb-896b-511a-b604-c8bf17ff8dd3 |  | note | Inspection/ Test Method - Visual Inspection
label | 689412b3-5d1b-5839-9101-c1e4a640d89c |  | note | Record of conformity - This ITP Signed
label | 375a87ba-fe71-529e-8bea-796531e8a69c |  | note | WP
label | b4c6cfd4-f065-5216-9a78-114d2541da1a |  | note | Responsibility - Project Engineer / Principal’s Representative
checkpoint-group |  |  | section | 4. Post Construction
checkpoint-status |  |  | checkpoint | 4.1 - Records
label | 7f46220c-2c64-558d-94a7-b03efcae8388 |  | note | Frequency - Each Lot
label | 1d97d353-2260-567d-8336-7f28071d72cd |  | note | Acceptance Criteria - Levels and alignment recorded in as built documentation and provided to superintendent.
label | 064bb156-4185-582b-8f00-e6779bceee8d |  | note | Reference Documents - Vic Roads 702.03
label | b1f8dd07-f351-55cf-97a0-718b65b4c569 |  | note | Inspection/ Test Method - Inspection
label | 32cf3a7e-c3b4-5c55-8ff8-131dac998d06 |  | note | Record of conformity - Aconex Correspond ence
label | 849d96ba-3a9a-5caf-ae07-88b456ae7b60 |  | note | SCP
label | 6fa0c136-8058-58d5-8169-77b48c050265 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 48abf1b3-2720-5940-a07e-c4d48607bc98 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8a527336-437b-50d4-b052-40d71833d66b |  | textbox | Name:
text | 92fad45b-70e9-5976-bb60-6274d2634f41 |  | textbox | Position:
date | 05abea65-5051-55e5-bc9a-b875c8d49e5d |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP009 – Topsoil and Grassing | itp |  |  |  | Yes | ITP009 – Topsoil and Grassing | 70a5f66c-2095-4c40-9cfa-e3dc6049949d
checkpoint-group |  |  | section | 1. Preliminary activities
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | c43ed1c1-e19c-55c8-9623-ee090bcb0560 |  | note | Frequency - Prior to commencing any activity
label | e0ee3fb9-050f-5dc2-920e-ae8968ff5db6 |  | note | Acceptance Criteria - All employees and subcontractors are using the correct and complete set of drawings and all drawings are the latest revision.
label | a49917fe-723c-5749-a50c-75d175fc883e |  | note | Reference Documents - AECOM Drawings
label | 4a9cac7e-76d7-5951-83ca-94145720d541 |  | note | Inspection/ Test Method - Visual inspection
label | aa142f7d-c8fb-5e18-8dd0-83f1ee741fcc |  | note | Record of conformity - This Signed ITP
label | 9c69d1ef-3d42-59c1-b022-912bf62f17dd |  | note | HP*
label | 446973df-9728-5915-b22a-e276ad6be1fd |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 33603ab1-c736-5241-afb8-1c529711e0ec |  | note | Frequency - Prior to commencing any activity
label | 254b5aff-874b-596c-84dc-fda236a3f447 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS, WP and Weed Management Plan
label | b17eef8c-3c5d-5872-9cf8-4322aba2b021 |  | note | Reference Documents - PSP, WP, CEMP, TMP, SWMS, WMP
label | f565388b-ac16-52dd-be09-17587ce02e15 |  | note | Inspection/ Test Method - Inspect
label | 3db460a1-4984-51f1-80bc-30f34e3aedad |  | note | Record of conformity - This Signed ITP
label | b0d0b45c-35cf-503c-8fce-f17329a532db |  | note | HP*
label | 641d2393-72ba-573d-b82a-22a82eff86cd |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 1.3 - Material Approval
label | 2e3c1b08-6e26-520a-a714-968aeb480d9c |  | note | Frequency - Prior to placing
label | 6e251ffc-0935-511e-bcfd-21a1515740fc |  | note | Acceptance Criteria - Topsoil used for the works is won from the site.
label | 4ebb8062-d404-5d4b-ba73-6c0ec74c4269 |  | note | Reference Documents - Tender Clarifications #44
label | 564c62be-1228-51ba-879a-76abb6dd0043 |  | note | Inspection/ Test Method - Verify
label | 99095266-a988-5a20-bc95-a8b8e3ccb0ce |  | note | Record of conformity - This Signed ITP
label | ec015ef9-d311-5aca-b641-12229f8401cb |  | note | HP*
label | 258ad8b3-a89e-58fc-96f5-995501dcefe7 |  | note | Responsibility - FH Project Engineer
checkpoint-group |  |  | section | 2. Topsoil
checkpoint-status |  |  | checkpoint | 2.1 - Topsoil
label | ea0bb981-b5a2-55b0-ac98-23685b022fca |  | note | Frequency - Prior to topsoil placement
label | 72eb678a-1812-5c31-adb1-5b0e2a755bc8 |  | note | Acceptance Criteria - Topsoil shall be free from items including:
label | 2325100e-a8c5-559c-8686-43e60a5264d3 |  | note | ○ Clay lumps with a diameter greater than 50mm;
label | 6e42a1ab-42d6-5f63-91b5-f065c5df5ff8 |  | note | ○ Contaminants;
label | 7436fffd-8a4c-5c2c-8a8e-fdf1d5554699 |  | note | ○ Noxious pests and weeds;
label | 8776474c-8634-56b7-bb1f-a3ee74aff5c8 |  | note | ○ Refuse;
label | 81125475-ed1c-5892-832f-bbe7651433a9 |  | note | ○ Stones with a diameter greater than 50mm;
label | cb029b0f-fafe-581c-872d-9557e8c1419c |  | note | ○ Subsoil; and
label | 505a9e99-a7ca-543e-9249-8a7331149fab |  | note | ○ Tree and shrub roots.
label | 9f1950e5-d068-564f-b584-6a48ec105913 |  | note | Reference Documents - MAS-CVL-001 Grassing (Airside) Clause 9.4.1
label | e67b624b-74cf-56a1-885f-b02e6168fe17 |  | note | Inspection/ Test Method - Verify
label | ce487a2b-a789-540e-8d25-e298dbe0d412 |  | note | Record of conformity - This signed ITP
label | c7ca35a7-a04c-5072-8a76-ade7874fee1a |  | note | HP*
label | d81571e7-2485-5ea8-b014-20b27ccf2d7e |  | note | Responsibility - FH Project Engineer
checkpoint-group |  |  | section | 3. Placement of Topsoil
checkpoint-status |  |  | checkpoint | 3.1 - Topsoil placement
label | e045e531-78ca-5dbf-830e-7069522759f5 |  | note | Frequency - Each Lot
label | 8d32741d-8da0-5508-a527-653424d5a863 |  | note | Acceptance Criteria - Filling of grassed areas will comply with Airport specification:
label | 1d225707-33c1-5966-b6ad-39d1087f5849 |  | note | ○ 100mm thick topsoil
label | 2f545237-9bb6-50a8-99a8-7d1a2405c9c3 |  | note | ○ Smooth even profile
label | ddb7db07-e19c-52cf-b536-4a513bc84f5f |  | note | ○ Free of ridges or water pockets
label | 1009cf2a-af2a-567a-bdcf-a7b5162b5c2b |  | note | Reference Documents - MAS-CVL-001 Grassing (Airside) Clause 9.5.2 Tender Clarifications #47
label | 8d322783-de15-5a70-982b-359df5e5c7b4 |  | note | Inspection/ Test Method - Verify
label | d6487d3d-636d-5a75-9dcd-1a632b5eaa45 |  | note | Record of conformity - This Signed ITP
label | 65fa8213-2861-5467-81a1-41e2b2b55047 |  | note | HP*
label | 1c1d634a-21fe-5ab6-ae01-7676b0302f1d |  | note | Responsibility - FH Project Engineer
checkpoint-group |  |  | section | 4. Seeding
checkpoint-status |  |  | checkpoint | 4.1 - Hydro Seeding
label | fa54fb05-58f7-5f59-a33c-20836e718d51 |  | note | Frequency - Each Lot
label | 5d721882-72ee-55c9-a33e-be8d657fd248 |  | note | Acceptance Criteria - Application rates shall be in accordance with the Grassing Standard, but not less than six tonnes/ha Flexterra or alternative (Vital Bon / Hydro Mulch 1000) unless agreed otherwise.
label | 94b134a9-43f9-5f7f-8f75-ac7c412bf360 |  | note | Reference Documents - MAS-CVL-001 Grassing (Airside) Clause 9.4.3 Tender Clarifications #45/46
label | 770f7a51-b721-579c-80e9-5196b1161e76 |  | note | Inspection/ Test Method - Visual Inspection
label | 0b0c52e7-4c89-55e0-8599-09ebb773d51e |  | note | Record of conformity - This signed ITP
label | 72d34a59-136d-5693-b995-62ca16f65d68 |  | note | HP*
label | 13c022a7-c488-5f2e-b1af-8b7e84f09df4 |  | note | Responsibility - FH Project Engineer
checkpoint-group |  |  | section | 5. Post Construction
checkpoint-status |  |  | checkpoint | 5.1 - Watering
label | 5548c89b-3dbf-5b25-b274-65c5391fe311 |  | note | Frequency - Each Lot
label | aafff264-c131-531b-8941-7ea6134287f5 |  | note | Acceptance Criteria - Following grassing works, and where access can be obtained without impacting Airfield operations, the area is to be watered to promote healthy grass growth.
label | ae1e9426-da6b-58a8-a411-2e329154d02c |  | note | Reference Documents - MAS-CVL-001 Grassing (Airside)
label | 6f087404-ec6a-518d-84a7-a77d0bbd2fe0 |  | note | Inspection/ Test Method - Visual Inspection
label | 18eb9875-2cf7-5c2f-815e-9109997010a1 |  | note | Record of conformity - This signed ITP
label | 59cac05f-c017-58db-b6a3-fbce4114808b |  | note | HP*
label | 6b8484ea-b34b-58f1-be21-73fd63218ed4 |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 5.2 - Maintenance
label | 0bf18374-01c1-5117-ae00-1b92aa7fcb10 |  | note | Frequency - Each Lot
label | af238321-f32b-5c43-ad9e-105acec10c8f |  | note | Acceptance Criteria - Maintenance of grassed areas until 90% of grass has achieved average height of 100mm.
label | 505f16b4-9f13-59da-b758-07dea90b38c4 |  | note | Reference Documents - This ITP
label | 1187ebd3-937b-513e-b07f-f3bb359a09bf |  | note | Inspection/ Test Method - Verify
label | 99c50620-b59b-5ec1-bea9-7106aff57ce1 |  | note | Record of conformity - This ITP signed
label | 670d8a20-c21c-5f93-aa2e-7ed5de07c8da |  | note | HP*
label | 93012291-2f93-5aa8-9f81-dc0c2422abbd |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | b64a42e4-0465-55d0-b673-fb4e034caaf5 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | fa692a71-540e-5dd6-adb9-bb330d5b0857 |  | textbox | Name:
text | ec59f59b-2404-5eb9-b1ca-577fd29adde5 |  | textbox | Position:
date | 6be3d0eb-a1ab-535e-860f-d69a8bc735d5 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP004A – Asphaltic Planing | itp |  |  |  | Yes | ITP004A – Asphaltic Planing | 7313d27a-43b1-4698-bb1c-06d6478331e0
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | f70829bc-2a9d-55c1-baea-bb8ee0da8eba |  | note | Frequency - Prior to commencing works
label | 156ba819-ba26-577d-8c39-a11edf7b124b |  | note | Acceptance Criteria - Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | 3498eeb8-aa98-54bc-9a1d-59ac25d18f0c |  | note | ○ Current revisions of these documents to be obtained via Aconex.
label | 7c1105f1-da08-503e-bb95-33ae172919f4 |  | note | Reference Documents - Current Revisions in Aconex
label | 926621ac-5c4f-5a91-bb6b-354faffeba86 |  | note | Inspection/ Test Method - Verify
label | e4ff5dd0-cfc5-5bbd-8475-2489d38fee75 |  | note | Record of conformity - This ITP signed
label | 7450918f-4d66-563a-9354-0db8530e3698 |  | note | HP*
label | 4bc6f3ad-a8ec-5671-8a25-8c1f1cc36d86 |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 066b1ac7-b6f7-5532-a517-8caa9fe0e04e |  | note | Frequency - Prior to commencing works
label | 3c86c015-a43e-53ad-a814-62634b414ee8 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
label | 3a91304a-abb1-5b94-a2a5-a97a37c95ce2 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | 821d6f8b-28c9-5e5d-81ff-fab924a5af5b |  | note | Inspection/ Test Method - Visual Inspection
label | ea3adace-a05f-504a-a493-b4251d2fe8ac |  | note | Record of conformity - This ITP signed
label | 591efe62-480e-5a68-a9dc-7891688c772f |  | note | HP*
label | 8a9a0105-b39f-57ed-9b9a-989b46b2193c |  | note | Responsibility - FH Project Engineer / Site Supervisor
checkpoint-status |  |  | checkpoint | 1.3 - Plant & Equipment Check
label | 5a951372-4b00-5fe1-b0ad-0462823d3381 |  | note | Frequency - Prior to commencing works
label | b6427587-1adc-539f-972f-cad3ce94dd29 |  | note | Acceptance Criteria - Minimum of one working cold planning machine onsite meeting the requirements of Project Specification.
label | 06cd7ef6-0807-517e-80ae-78254a0f03df |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.3
label | ac34864e-9cf9-5559-a087-0e6cc9715ac2 |  | note | Inspection/ Test Method - Verify
label | 952fcb9b-d42b-5a47-ba9b-7a9a2ff62204 |  | note | Record of conformity - This ITP signed
label | 49d34cd0-d385-5dc9-b265-a0f8ba59da29 |  | note | HP*
label | 170723c2-a83a-51da-84eb-570e52d0c870 |  | note | Responsibility - FH Project Engineer / Site Supervisor
checkpoint-status |  |  | checkpoint | 1.4 - Weather Conditions
label | a8e7cdeb-b2f8-50b3-9228-03691f3e8571 |  | note | Frequency - Prior to commencing works
label | a2e50f1c-5eee-57a1-a0a4-4056f6c5eee5 |  | note | Acceptance Criteria - When significant rain or weather events are forecasted that will prevent satisfactory completion of the works, works will not be undertaken.
label | 2003a451-44ca-562c-aa6e-171702711a46 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. CL 11.5.2, 13.6.3 & 14.15.4.1
label | d3038d1c-c10e-584b-b934-9e9d107e3768 |  | note | Inspection/ Test Method - Verify
label | c3673b34-9765-5434-a60d-25eada96dbe5 |  | note | Record of conformity - This ITP signed
label | 9ec0c031-2015-58b1-8e51-24e6b7b6fdd0 |  | note | HP*
label | 0b49f4c5-16d7-5a3f-9877-c63bdc13ad9b |  | note | Responsibility - FH Project Engineer / Site Supervisor
checkpoint-group |  |  | section | 2. Asphaltic Planing
checkpoint-status |  |  | checkpoint | 2.1 - Set-out of area to be profiled
label | fcb99659-4e32-55df-ad29-6e162a65db0a |  | note | Frequency - Prior to commencing works
label | 73b8cca5-2a6d-592b-9337-2f9916fbcec2 |  | note | Acceptance Criteria - Planing areas and depths are as shown on the Drawings and to be confirmed on site by the Principal’s Design Consultant. Updated profiling areas and depths for SP1 patching works are as per DCWC Mgt-GCOR-001362 and DCWC Mgt- PMA-000144.
label | 2b05bbf5-ea9b-539b-bf9d-22eec3039186 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.2
label | 0b37fa02-a776-5c44-8e0a-127111c7e11c |  | note | Inspection/ Test Method - Visual Inspection
label | e416f4d3-0860-5450-b765-ba2febb8e9c0 |  | note | Record of conformity - This ITP signed
label | ade7e718-6aee-5a3f-8265-2e9b54008861 |  | note | WP
label | c3fe647b-b735-5dd5-97f2-91f823fe756e |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 2.2 - Profiled Surface
label | ae0a8d1a-9eee-52e6-8a65-ee1f5f559c1d |  | note | Frequency - During profiling
label | 461528a5-f5de-57fa-86cc-f477d64e4ba6 |  | note | Acceptance Criteria - The surface texture depth of the planed surface must be as agreed with the Principal’s Design Consultant, must be of the order of 3 mm to 6 mm and must be of a consistent appearance.
label | 3f39c807-9926-59e9-b4e8-6dbf341e2d75 |  | note | ○ No point on the planed surface must lie more than 6 mm below a 3 m straightedge placed on the planed surface in any direction.
label | aa569a44-c83a-51cf-8354-cda09db9cd57 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.4.1
label | 83dc189e-b4cd-5c0c-9b16-5465aa5aa20b |  | note | Inspection/ Test Method - Visual Inspection
label | 34f88a70-7879-5d64-9b2e-f7227ad6b1db |  | note | Record of conformity - This ITP signed
label | 73bbb120-b2c4-57fe-b140-e385a2774279 |  | note | HP*
label | 40a64737-5500-530a-ac33-0388de2b6d62 |  | note | Responsibility - FH Project Engineer / Site Supervisor
checkpoint-status |  |  | checkpoint | 2.3 - Profiled Edges
label | 265997f7-9a77-57f2-b49e-747e0c9e3d50 |  | note | Frequency - After completion of profiling
label | 31fea223-714d-52f8-b7d3-27e078f41ab4 |  | note | Acceptance Criteria - Where the cold planing equipment leaves edges along the perimeter of the excavation which are broken/chipped at the surface the Contractor must cut the edges.
label | e77f6097-d9f1-51ec-ae9f-7094956d4d00 |  | note | ○ The cut must be straight and parallel to the perimeter of the excavation and must remove all chipped and broken edges to provide a clean face between vertical and 45º using an approved method.
label | 21b9758f-a09b-5431-9ad5-5115c99a6f17 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.4.1
label | 6c38713e-b2c7-5bea-be02-e2f0a6f2a104 |  | note | Inspection/ Test Method - Visual Inspection
label | 49fc5d60-93f9-503e-9b48-22d2df2e7dfb |  | note | Record of conformity - This ITP signed
label | d4bab486-6180-5dc4-82c6-eef5bb8185de |  | note | HP*
label | 9a336601-214b-5c55-af83-b4c527695aff |  | note | Responsibility - FH Project Engineer / Site Supervisor
checkpoint-status |  |  | checkpoint | 2.4 - Cleaning of profiled surface and removal of profiled materials
label | e1cb8ca1-b09d-50fa-a7a0-d53b269d4456 |  | note | Frequency - During and after completion of profiling
label | 20d61935-3f89-56f9-bf43-3e9fceab4a08 |  | note | Acceptance Criteria - Once the profiling is complete, the sweeping and cleaning of the profiled surface will commence.
label | e94b66b0-6376-53d8-b4c2-3c9994ee8e80 |  | note | ○ All loose materials and dust to be removed and the profiled surface shall be clean prior to any subsequent works.
label | 85d8a64a-d037-5050-8bfb-f1375eeb175b |  | note | ○ Disposal of profilings is to be as per CEMP.
label | 122a6a6a-10a8-50f4-92f5-a8ef35735a24 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.4.2
label | ae1d2528-6a9f-5ced-9487-5e455f9dbeea |  | note | Inspection/ Test Method - Visual Inspection
label | d91aae8b-c48b-510c-8fd9-c8cd3f391219 |  | note | Record of conformity - This ITP signed
label | 138e9f7a-1ee7-5472-9e70-1fab83a41981 |  | note | WP
label | a0068b36-d1a8-52ef-8d8c-a5bbc96135aa |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 2.5 - Inspection of Profiled Surface
label | 347975b4-dd9b-546e-a112-e3d39e53b307 |  | note | Frequency - After completion of profiling
label | 328bc9f1-ccf2-5c6f-a664-4c70f5cc8194 |  | note | Acceptance Criteria - Once swept and cleaned, the profiled surface will be assessed by the Prinicpal’s Design Consultant for cleanliness as well as delamination, cracking and other issues likely to impact performance.
label | 73437aad-2fb2-5800-b910-d9959bed0879 |  | note | ○ An assessment will be made in conjunction with the Prinicpal’s Design Consultant whether any additional profiling is required and whether it can be undertaken in consideration of the circumstances of the shift.
label | 9ed4c903-ed09-5b25-863e-a6b831f83f99 |  | note | ○ Note that a minimum of 30mm of existing asphalt is to be retained to avoid disturbing the underlying existing granular pavement.
label | 1a495f19-212c-51b1-ad06-b44544b97b55 |  | note | ○ Photos and/or records will be taken to record any areas of concern and document what actions were undertaken.
label | 6218cee2-2c83-5e8d-ba52-304eca82613c |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.4.1, 12.4.2
label | 46ace8ba-d99b-5016-966c-695db079a70d |  | note | Inspection/ Test Method - Visual Inspection
label | ebf8dce5-b426-5c09-83d6-4385b57b63f5 |  | note | Record of conformity - This ITP signed, Photos/GIS Markup
label | c3e6a7aa-d5f5-58bd-9661-403ca59cef60 |  | note | HP
label | f41f86c4-0f7c-5539-bc56-546bfd985e48 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | bedf08ce-bbab-5040-b4a6-04defce959c0 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
text | 595e2e87-6902-5069-bd21-e272bc3ba392 |  | textbox | Name:
text | 5452b1bc-725c-5422-b281-8862cab42ab9 |  | textbox | Position:
date | 01eedcf5-f822-5cc1-ac20-a4a5a88f1781 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP021-4B – New Foundation Works – Installation | itp |  |  |  | Yes | ITP021-4B – New Foundation Works – Installation | 834406bf-1910-458d-9a5a-d996ac4e7161
checkpoint-group |  |  | section | 1. Re-installs
checkpoint-status |  |  | checkpoint | 1.1 - Preparation for the works to be undertaken
label | 9ec0508b-7a26-5460-91ec-90bc0a8979b7 |  | note | Frequency - Prior to Start
label | 494e8445-50f3-592a-96ad-eaa2cd19fc71 |  | note | Acceptance Criteria - Resurvey light position and aiming points.
label | 02ba1458-bcb8-556e-9351-bce7c17ac4d1 |  | note | Reference Documents - Drawing sets:
label | e661beaf-29b3-5e86-a0ee-e6a5704c8199 |  | note | • 60692389- SHT-01_1-10
label | 0b6460ec-f272-58ac-9c5d-49a3e48608a4 |  | note | • 60692389- SHT-01_2-10
label | 1d87aeed-50b3-5e95-9b14-9255d0754e93 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 8a956f82-d778-5c4b-9743-3d385f3ac5bd |  | note | Inspection/ Test Method - Verify
label | aef3b3d3-15ff-5cb3-9c44-ea363f6d0ec2 |  | note | Record of conformity - This ITP Signed / Avionics CL004B
label | 4e6135d0-b57d-5722-b8cf-3769b8368ac5 |  | note | HP*
label | bf37f103-654b-58fa-ab15-26126d40a566 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.2 - Core and inspect
label | d7b5541e-6fa4-53ec-968c-d472a101e918 |  | note | Frequency - Each Lot
label | a4827a9d-461b-5cd7-b062-1569b7b8249d |  | note | Acceptance Criteria - Core to depth of new foundation.
label | 681eaf66-7e60-5f1b-a572-5a2e473252bb |  | note | Reference Documents - Drawing sets:
label | 90569a6d-7348-5df2-b48d-59690309151b |  | note | • 60692389- SHT-01_1-10
label | 0562a0f6-13cd-5daa-a1fe-87c4d5835094 |  | note | • 60692389- SHT-01_2-10
label | eb5ea336-4650-552c-822d-3ff786f7fa7f |  | note | • Specification: 60692389-PS-01-AV-0001
label | 1107928e-b25e-53c5-9ccc-5136a26c41e8 |  | note | Inspection/ Test Method - Verify
label | 76c17acc-6184-5a50-bd6a-05218e80fdd1 |  | note | Record of conformity - This ITP Signed / Avionics CL004B
label | 64644ce1-006c-5597-b7e5-4e602f0c0e7f |  | note | IP
label | ba168a4d-1ab6-5f6b-9faf-21b0b263cfc6 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.3 - Installation of new can
label | 5427e444-7fa2-5599-a2e2-8e4528eee0a6 |  | note | Frequency - Each Lot
label | e503d7d8-0e62-55d4-81ff-d96474c0451b |  | note | Acceptance Criteria - New can mounted on positioning jig. Jig/can positioned, levelled, aligned. Spacers positioned and conduits checked for clearance. Epoxy poured.
label | c0bdbe2f-de2b-5dbe-b4f9-c9746f0fb35f |  | note | Reference Documents - Drawing sets:
label | a5c82c3f-c42c-5769-ade2-dc092b25c633 |  | note | • 60692389- SHT-01_1-10
label | 7435a913-8cf8-521e-a7c5-9dddfaccf5c9 |  | note | • 60692389- SHT-01_2-10
label | ab80029c-d466-5669-a91b-f542a7e17899 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 76c4303e-9938-5656-97b1-d6643f64be2b |  | note | Inspection/ Test Method - Verify
label | 750317bc-93db-5bd2-880e-1b1a4c9b1065 |  | note | Record of conformity - This ITP Signed / Avionics CL004B
label | b41385f3-60c5-5435-a205-854873640fa9 |  | note | IP
label | 503e5da8-0444-562a-bf2a-05b9eeb6418a |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.4 - Reinstallation of light
label | fa9967fa-3403-50f6-87be-41960adbcc91 |  | note | Frequency - Each Lot
label | 9ceddfba-ce89-5152-a773-c87703028e89 |  | note | Acceptance Criteria - Foundation hole cleaned and existing light to be positioned, identified.
label | a61437cd-90f4-5c91-81db-297327054be9 |  | note | • Light plugged back in and positioned. New bolts installed with required torque.
label | f01cc9c7-ff7b-520d-b6cf-08eb891a0c15 |  | note | Reference Documents - Drawing sets:
label | 91eeb0ec-88ba-5e29-b69b-9443f1a93958 |  | note | • 60692389- SHT-01_1-10
label | 978ae198-b43e-59ba-990e-7dde196d9584 |  | note | • 60692389- SHT-01_2-10
label | eec53f6f-8145-5d70-93b4-3bbf6c9a0f86 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 96abb3e5-b166-56b6-b23d-7c19f41203d1 |  | note | Inspection/ Test Method - Verify
label | 55495033-06e3-56e7-ba96-d36f1afa6cb4 |  | note | Record of conformity - This ITP Signed / Avionics CL004B
label | 7c1a0127-7c45-5a46-9b9d-d95e6f26dba8 |  | note | IP
label | fe02ab65-2b36-51af-8fca-1e3101ace399 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.5 - Finishing, demobilisation and testing
label | 72c64959-5b86-5789-bd38-143888e825ca |  | note | Frequency - Each Lot
label | f8287440-7aa6-5fbd-97ee-40fb2b9ab1e3 |  | note | Acceptance Criteria - Pavement area cleaned and equipment packed away. Work crews demobilised and FOD walk undertaken. Light tested once circuit re-energised.
label | 4cf420d7-e683-59f7-a6a9-ea1103470dea |  | note | Reference Documents - Drawing sets:
label | 90d79c87-ede9-595c-a337-4223b00c9ac9 |  | note | • 60692389- SHT-01_1-10
label | 140a84ae-5f3c-57f5-a8ee-90fbf7632c12 |  | note | • 60692389- SHT-01_2-10
label | e279e7ad-ed54-5cca-855a-11717fef5034 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 4a7dcc8f-c998-5dcc-8a62-69a18d884716 |  | note | Inspection/ Test Method - Verify
label | 97ba94fe-7272-5f59-bf40-f0b9903601d9 |  | note | Record of conformity - This ITP Signed / Avionics CL004B
label | f13a4eaa-7354-5741-ad71-2101025e7694 |  | note | IP
label | 9dc68024-1985-5de5-a4e4-1f22aabeab0b |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | Final Inspection
label | 3cfae073-e1f4-54cf-af43-5f67f1247029 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 0d7f55a4-5fc9-5b1a-a198-2fe56bbe5a80 |  | textbox | Name:
text | a7e72102-a916-5e60-9396-91218f635a29 |  | textbox | Position:
date | 664f4287-dffb-5ded-8b99-18dfaf836adf |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP002B - Crushed Rock Basecourse | itp |  |  |  | Yes | ITP002B - Crushed Rock Basecourse | 9a969d26-55ea-4497-b049-3a251fc088b0
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | 75763acd-c41a-54b1-b6d5-892feea78101 |  | note | Frequency - Prior to works
label | 585abae7-04b3-52f8-bae2-29c2ba277b2d |  | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Principal’s Representative
label | 21f9a8a8-13aa-5c73-b076-e34edaa67766 |  | note | Reference Documents - ACONEX
label | cad0e7cb-050b-52e4-a680-dbb753ae30ad |  | note | Inspection/ Test Method - Visual Inspection
label | f7fd0195-3722-591a-898e-c180b9ce23e6 |  | note | Record of conformity - Current drawings
label | 331feced-7d42-5128-82e4-a31ea83792f5 |  | note | HP*
label | d365fd3c-8f41-56a4-a003-5b17f0cec1a2 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Material Submission & Approval
label | defc7e58-ec5a-5d4a-a79c-bd187f78bba8 |  | note | Frequency - Prior to commencing works
label | d1133443-2663-5106-8fd3-84494068a9ee |  | note | Acceptance Criteria - At least seven (7) working days prior to the delivery of the Class 1 Crushed Rock the Contractor is to provide the following for review and approval;
label | 9ecad806-7e67-54c5-b500-5750ffb336b7 |  | note | • Grading Curve
label | ab36aa1b-846c-5de4-848c-0f3217a307d4 |  | note | • Atterbergs Limits
label | 0d317ced-974e-5024-8be5-5f329acfe1a9 |  | note | • CBR
label | ea17c212-3e9b-5a83-a135-f15d1df26a31 |  | note | • MDD
label | d484bd19-5e59-5240-85a2-628bb66ef407 |  | note | ○ Once approval has been received the Contractor is to obtain one reference sample weighing 50kg and which is to be kept on site.
label | bd226843-d188-5641-aeae-46eb1bcafc3e |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.4.1.2 & Cl.6.4.1.3
label | b7b61ad6-fd7f-5464-8847-dbcab51313da |  | note | Inspection/ Test Method - Verify
label | 3487fae2-a82c-5b14-b329-a6c4507799ac |  | note | Record of conformity - Aconex Reference
label | 75657c04-197a-566f-a162-7eeedc4d2f7b |  | note | HP
label | 67c5c409-091f-5bd6-a657-a152d0725530 |  | note | Responsibility - Project Engineer, AECOM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Production Testing
label | 4ee517fd-ae4a-5adf-8259-7c2f40848c6b |  | note | Frequency - Prior to commencing works
label | 6d56c227-7259-5eea-94b4-d23a3a68d292 |  | note | Acceptance Criteria - Supply information with respect to production testing, to requirements in VicRoads Section 812.
label | 97e2a503-8fff-532f-bf1c-b27948f40d3f |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.6.1 & VicRoads section 812
label | d7c1cd76-eb09-5b65-9f53-86da3897ed5f |  | note | Inspection/ Test Method - Verify
label | e1a0600e-e0f2-58a2-bf99-e879dfa2c0e1 |  | note | Record of conformity - Approved production testing results
label | 968b63b2-d78c-57c8-ba32-31b44ee147bc |  | note | TP
label | 0c94a056-94c1-5ddf-9515-7f82d4578c50 |  | note | Responsibility - Project Engineer, Principal’s Design Representative
checkpoint-status |  |  | checkpoint | 1.4 - Implementation of all measures and controls.
label | 67e71f01-0366-5cec-bf56-677e25492d7b |  | note | Frequency - Prior to commencing works
label | 6065ef5b-16e1-5854-98a5-65faeae3ddae |  | note | Acceptance Criteria - All necessary measures and controls are being implemented including: PSP, EMP, TMP, SWMS and WP.
label | 37c78d8d-6b77-5ddf-8bed-7d1beb4d1852 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | 73084a8d-edc2-51b2-aaf7-8055808b0f05 |  | note | Inspection/ Test Method - Visual inspection
label | 0226c1cd-c079-5a45-a7bd-3e84b81aee5b |  | note | Record of conformity - Site inspection
label | 372c84cb-82d8-559d-95df-888944f3e8e8 |  | note | HP*
label | 01ac9c94-3be8-5b0e-b4e4-bbf3c0b1a159 |  | note | Responsibility - Project Engineer
checkpoint-group |  |  | section | 2. Construction
checkpoint-status |  |  | checkpoint | 2.1 - Placing Crushed Rock
label | 0e84a207-335f-5843-addb-82e10c12f3b8 |  | note | Frequency - Each Lot
label | 69389381-2781-50eb-9d7d-145407be393c |  | note | Acceptance Criteria - The crushed rock base course is to be placed in 2 equal layers. The Contractor shall supply survey reports prior to the placement of prime coat or primerseal.
label | 9f736218-4a4b-510a-9529-72ba7531f29a |  | note | • The levels must be checked in a 5m square grid on the finished surface level and shall not deviate more than +0,10mm.
label | 5a9a0d27-423d-59f9-b0c7-c90f3a9a87b6 |  | note | • The levels shall be recorded in a .TXT format with the relevant points displayed in a PDF file.
label | 6a4fdc7a-0845-5c80-9c77-bfca0598098f |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.5.2.1 & Cl.6.5.2.5
label | 0268be74-b467-56f6-95b9-b214fafd6748 |  | note | Inspection/ Test Method - Visual Inspection
label | e3a3d8e5-5c32-5248-9367-e4abc291784c |  | note | Record of conformity - Survey Report and Visual Inspection
label | 1a22a5c1-4a90-5b89-a057-137851d6efad |  | note | HP*
label | e0e5957f-5b8d-50bd-856e-c9f37c547f3b |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Proof Rolling
label | 0a5f6c2e-55c0-5ec7-b45c-45fb2b45e2e7 |  | note | Frequency - Each Lot
label | 8c75e84a-f6a5-5222-9400-c7ff7b429cab |  | note | Acceptance Criteria - Proof rolling will occur upon the completion of compaction.
label | c49d7020-d561-556c-9324-13141b5655e6 |  | note | • The proof roll will be conducted in a systematic manner such that the entire area is covered uniformly.
label | fbe65308-1375-52c5-b8ec-ec70fc863e3b |  | note | • Only the top layer of the crushed rock basecourse is subject to proof rolling. Proof rolling to be undertaken with a multi wheel roller.
label | f066e6fd-b9ae-55c6-93ee-d559dee65dc3 |  | note | • The plant must travel at a speed no greater than 6km/hr.
label | 11ef8c6c-720f-5155-88b4-efeff58b9c4a |  | note | • Contractor shall notify the Principal’s Design Consultant so that they are present for the entire duration of proof rolling.
label | c8b698ca-a117-517d-9bfc-531b9f523198 |  | note | • Proof rolling shall be undertaken with the pneumatic tyred roller or watercart.
label | 021fd9e4-8fff-5164-84d0-104cf778a073 |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.5.1.2.1
label | a2ec46e0-af1c-5fa8-a2af-a0bcdff0ae4d |  | note | Inspection/ Test Method - Visual Inspection
label | 725447a7-e751-55c7-a553-6d088bfcbd21 |  | note | Record of conformity - This ITP Signed
label | 0e43e075-d5b0-536d-855e-50b332dbd56d |  | note | WP
label | 35b62db2-c758-56d6-aecc-efdd2e2595a1 |  | note | Responsibility - Project Engineer, Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 2.3 - Identification and treatment of unsuitable areas.
label | a07c03a3-8729-5538-83f8-49e7cdd4cad4 |  | note | Frequency - Each Lot
label | 3e38fe69-5279-5406-b0fc-47992ef4ccce |  | note | Acceptance Criteria - Should any area of crushed rock be disturbed or become unstable during proof rolling, the Principal’s Representative should be advised immediately and proof rolling of the area ceased.
label | b9609656-eb2e-55e0-a3a9-ea1753ebe38b |  | note | • Any areas of crushed rock layer that rut, yield or become unstable under the proof rolling must be investigated in the presence of the Principal’s Representative.
label | f24b425d-e6f4-57b3-ab26-a566ca670674 |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.5.1.2.1
label | 4a0e55d7-5a0c-5a14-9671-38e729a1efb9 |  | note | Inspection/ Test Method - Visual Inspection
label | 28dd6a1a-6fc9-58c1-b273-1b14d40bdc21 |  | note | Record of conformity - Visual Inspection
label | 9402bf04-91e0-5d30-8582-b928bb79a16c |  | note | HP*
label | 0147e11f-6eb4-52f8-a534-f2b77367a62f |  | note | Responsibility - Project Engineer, Principals Design Representative
checkpoint-status |  |  | checkpoint | 2.4 - Submission of Proof Roll Report
label | 49de4434-a802-54fe-8c37-84f31d0e6407 |  | note | Frequency - Each Lot
label | 3adddda7-a5e7-598c-8ae6-8ee3d6c47e70 |  | note | Acceptance Criteria - A Proof roll report must be submitted to the Contract Administrator and Principal’s Design Consultant for review.
label | a7fcfe94-0255-588e-bb5f-d54b4a99923b |  | note | • The hold point is released by the Contract Administrator or Principal’s Design Consultant after review and written approval of the proof rolling report.
label | b454af40-594e-5c08-937d-b057e1ff56cd |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.5.1.2.3
label | 8157e084-91ea-5a29-85dd-9a797eba8c85 |  | note | Inspection/ Test Method - Proof Roll Report
label | 75b87d67-f03e-5764-8521-148ae017364e |  | note | Record of conformity - Aconex
label | 264bb03c-0c3f-5d9d-ac9c-838e146653e4 |  | note | HP
label | 679fb2bb-a72f-5bdc-924a-d81138e84045 |  | note | Responsibility - Project Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Compaction Testing Report
label | 265b8e12-0925-5826-8b7a-e9c01259a2cb |  | note | Frequency - Each Lot
label | ce000869-dfa9-56b7-a63e-4409b459a7e7 |  | note | Acceptance Criteria - Submission of the compaction report shall be submitted to the Contract Administrator for review. The report is to include:
label | 8d751f55-ea23-5a16-94a9-527781e4e700 |  | note | • Details of the Lot being tested
label | 3a168984-199a-5f95-90bb-54f4b3148540 |  | note | • Test certificates (field density, MMDD)
label | 0f5a9c3b-646d-58f1-8ecd-ca472de0a141 |  | note | • Dry density ratio (characteristic and average)
label | 3355a456-0079-597d-a051-6a5fa307cfa2 |  | note | • Compliance or non-complaince of the lot
label | 77ae1673-6f8b-5336-83a5-844b3438b0b3 |  | note | • Rectification actions and outcome in case of non-conforming compaction
label | 869f064b-13aa-5f5c-a56c-5cb45b3f61da |  | note | ○ When minimum field density testing frequency is 6 per lot or greater:
label | 2d0037be-ab4d-5dcf-a576-e18cd91003bc |  | note | • Character dry density ratio ≥98% modified compaction
label | e6d3c2da-49e4-5fdc-a342-4d31cc78b19e |  | note | ○ When minimum field density testing frequency is less than 6 per lot:
label | 2590243c-5518-558b-bd17-5810150a0bec |  | note | • Average dry density ratio ≥98% modified compaction
label | 1f4d4d98-44c1-5994-922e-238a86a80a92 |  | note | Testing Frequency:
label | 61be3ed3-8c2a-5e4e-911a-a80422d312b3 |  | note | • Up to 800 m2 Min 4
label | f25171aa-fd83-51c3-8b05-5647f706f64c |  | note | • 801 m2 to 3,000 m2 Min 6
label | 71e498c7-4e20-5ba6-9199-f807d8d8a804 |  | note | • More than 3000 m2 Minimum of one (1) test per 500 m2 or part thereof
label | 9bafd915-5f28-5d06-9a32-9b84f607d0d4 |  | note | ○ Hold point released after review and written confirmation of the compaction report being received.
label | 2742baa5-b1d2-5b8d-a54d-5dd7e926b9fe |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.6.2.5
label | e64d1e39-22f5-50a7-8ced-9afd932fde46 |  | note | Inspection/ Test Method - Testing
label | b1cba137-7f3f-5e2e-89eb-689d331e52cc |  | note | Record of conformity - Compaction Testing Report & This signed ITP
label | e9b52d9c-b2e5-5c37-9c4e-e2adea1a244c |  | note | HP
label | 480e0998-8340-5b20-8534-1a62050f6e17 |  | note | Responsibility - Project Engineer, Contract Administrator
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Smoothness Testing
label | ec74f112-7090-57af-82e4-ac2cc2f1749b |  | note | Frequency - Each Lot
label | 97ad973d-f20b-5d00-b14d-c3ee1584f852 |  | note | Acceptance Criteria - Submission of the smoothness testing report is to be submitted to the contractor within seven (7) days of completion of the crushed rock lot.
label | 8a7f00b3-efa0-5a87-a35c-2c5e39693d47 |  | note | • Surface smoothness shall be undertaken using 3.5m straight edge that is either hand held or mobile.
label | 799668c5-f3e3-5100-b004-812439fe6cda |  | note | ○ The straight edge shall be operated along:
label | 4b7e0702-a709-5def-a911-7a9801236a84 |  | note | • A set of parallel lines not more than 10m apart covering the whole surface and on another set of parallel lines not more than 10m apart that are perpendicular to the first set. The surface of the crushed rock basecourse shall not deviate from the 3.5m long straight edge by more than 7mm, except in directions of where a grade change occurs.
label | 30eb9d3e-5eef-5ee7-a000-1358ed6cfe8c |  | note | Reference Documents - AECOM MAPMP2.0 DP1 Spec. Cl.6.5.2.2
label | 84dcd019-b194-5d0e-8b1d-607cecccf126 |  | note | Inspection/ Test Method - Visual Inspection
label | 2fc9bcfa-54a2-5393-afa6-d7a4bdf86f48 |  | note | Record of conformity - Straight Edge Report & This signed ITP
label | 0ac608f3-1c51-5ff4-9691-fb5ddbb8ca1e |  | note | HP
label | 76361d58-0af4-5c5e-ae04-b7fb805fd014 |  | note | Responsibility - Project Engineer, Contract Administrator
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 645fe97d-0889-54c1-a217-314437c9085b |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
text | beecdfb9-cbd1-5c64-9631-c1a2fb74f2fa |  | textbox | Name:
text | 52c10e39-e2b3-5db9-b6df-5702370743d2 |  | textbox | Position:
date | 55c7da03-58e6-5aca-856d-f1b48e5a7e6e |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP021-1 – Demolition and Isolation | itp |  |  |  | Yes | ITP021-1 – Demolition and Isolation | ad9ef77d-baf6-4d27-835c-3a013c84c866
checkpoint-group |  |  | section | 1. Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Preparation for the Works to be Undertaken
label | 387f5a41-384a-55fc-be1a-e3ce4b0e8026 |  | note | Frequency - Prior to Start
label | 8512ab75-c139-5341-bcf2-8e7ace95075d |  | note | Acceptance Criteria - Notify the Airport’s Engineering personnel at least two days prior to removing the works area from service and prior to returning the works area to service.
label | 80f8342a-7b3d-594a-9147-0de2f970883d |  | note | Reference Documents - Drawing sets:
label | 40e412b0-790d-5db4-becd-042640509244 |  | note | • 60692389- SHT-01_1-10
label | 7a3e38d2-c75a-5b29-af80-c413408a5171 |  | note | • 60692389- SHT-01_2-10
label | 2139891d-9120-5f9e-b6d1-00a07623efbb |  | note | Inspection/ Test Method - Verify
label | bbbf0585-5d6d-5c94-84ec-2577da0673a9 |  | note | Record of conformity - This ITP Signed / Aconex
label | 4a0f0c5f-64c4-5f19-bb57-5d2ee857c290 |  | note | HP*
label | 993ee621-5492-5dd8-9138-5e3d39ccf0cd |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - AGL Continuity of Service
label | ed4a47af-06fc-569f-8977-956e229e6e36 |  | note | Frequency - Prior to Start
label | 0046a875-b91f-5a28-b00e-1e0c9841187e |  | note | Acceptance Criteria - Ensure the continuity of service of the AGL facilities is maintained while undertaking the works.
label | 347ce85f-f10d-5435-9fbe-3480c96b6af6 |  | note | • No outages of any facilities shall be permitted unless prior approval has been received by the Contractor from the Contract Administrator.
label | 2d9ce5e0-2274-5683-bf7d-4e4e2501de21 |  | note | Reference Documents - Drawing sets:
label | cf56df2e-f037-5017-a3c9-012f401ef467 |  | note | • 60692389- SHT-01_1-10
label | 6f1b834a-afc3-51dd-ab9c-fc09258f906e |  | note | • 60692389- SHT-01_2-10
label | a73861ab-8563-5ed7-8a67-c887b174a620 |  | note | Inspection/ Test Method - Verify
label | 324c4b3d-5889-5f36-920f-71263cb4e889 |  | note | Record of conformity - This ITP Signed
label | a6d06324-f6bf-55fb-b3cb-3065d9dfb551 |  | note | HP*
label | 6b6ca3d7-2292-5d94-87f5-60b35474100e |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.3 - Check for correct documentation
label | 93ff5929-c854-56e1-b92d-99db66ac99b6 |  | note | Frequency - Prior to commencing any activity
label | 74d7bcf0-5bba-5acf-8a54-48e6ffeed14b |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | e970d41f-5510-5217-a4c8-12f5c9defb18 |  | note | Reference Documents - IFC Drawings
label | b875be50-7c25-52e2-8f8e-8154ff5b67e5 |  | note | Inspection/ Test Method - Verify
label | 1716ff81-14c3-5ff3-bb3b-69a494fdf722 |  | note | Record of conformity - This ITP Signed
label | 44cfebec-5d91-5b9d-9cd1-3140d13c2bdc |  | note | HP*
label | 95d882dc-a439-593c-88a7-823ac3d7fc1e |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.4 - Implementation of all measures and controls
label | 93320373-3053-58b4-b7b6-932f8e0e2173 |  | note | Frequency - Prior to commencing any activities
label | 931c29a9-fde6-59e0-97ef-62f243e900ae |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | 193aa33d-13a4-5d10-867a-34ae5e4b1774 |  | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | 82c03cec-33d1-5ae5-86a5-0a0518776d30 |  | note | Inspection/ Test Method - Verify
label | b1fa07dd-a009-5271-b51c-f9f3068831aa |  | note | Record of conformity - Site and Office Inspection
label | 8f84808d-c8b1-512b-9dfa-c6263facf7c5 |  | note | HP*
label | fc52f2e2-a658-58d3-8375-90c47fb2048e |  | note | Responsibility - Project Engineer / Site Supervisor
checkpoint-group |  |  | section | 2. Demolition and Isolation Works
checkpoint-status |  |  | checkpoint | 2.1 - Investigation, Location, Identification, Protection, Modification, Isolation, Extension or Relocation of Existing Features
label | b1eb78d0-dff1-57ad-9088-8d9906e26c5d |  | note | Frequency - Prior to commencing demolition works
label | 9a6bd9d3-6963-5b1f-a54a-0768985d39d7 |  | note | Acceptance Criteria - The Contractor must:
label | ebac65cb-3188-551e-b666-a2f4068851b4 |  | note | a. investigate and locate both above ground level features and below ground services that may be affected during the performance of the Work under the Contract;
label | 685737d1-e400-5ed4-94a5-72b050f3d30f |  | note | b. identify, protect, modify, extend or relocate existing features, services or facilities as necessary for the performance of the Work under the Contract to the satisfaction of the Principal and other relevant authorities;
label | a84bee71-4452-5ed4-b280-67a7d983f064 |  | note | Reference Documents - IFC Drawings
label | 5ba7f1ef-a92c-585a-82f8-702329625c18 |  | note | Inspection/ Test Method - Verify
label | 18053d84-9635-5308-95b3-f309aa98aeff |  | note | Record of conformity - This ITP signed / Avionics CL001-1, CL001-2, CL001-3
label | 05e58540-f88b-5b34-bfce-8982338c80ee |  | note | IP
label | 133e8b70-d4c7-55d9-b3f4-4e35d5b530af |  | note | Responsibility - Project Engineer/Avion ics
checkpoint-status |  |  | checkpoint | 2.2 - Demolition and/or removal of AGL
label | c35b39df-3789-5d50-85f9-5fbbc2db6628 |  | note | Frequency - Each Lot
label | 06d92eb4-1cb2-5c8d-bc52-00f82b2a5ff1 |  | note | Acceptance Criteria - Prior to any pavement overlay works, all light fittings and shallow bases impacted by the pavement reconstruction works shall be removed. The shallow bases shall be removed by neatly saw cutting a hole in the pavement slightly larger than the outside diameter of the light base.
label | 05e104f0-e338-5110-8dbc-d920f3c219d9 |  | note | Reference Documents - IFC Drawings
label | 774a92bc-1d9d-5999-aa23-7d746de8953c |  | note | Inspection/ Test Method - Verify
label | a8e450c5-74cc-5e36-9d0e-3d7f924e4302 |  | note | Record of conformity - This ITP signed / Avionics CL001-1, CL001-2, CL001-3
label | 5c92fb0e-c1ec-5845-92fa-5f0da2d3e4bc |  | note | IP
label | 5a9221fb-c981-59c4-93ac-ce61f3623ca3 |  | note | Responsibility - Project Engineer/Avion ics
checkpoint-status |  |  | checkpoint | Final Inspection
label | 99f7c5a1-9460-5a19-9ac9-61819a22e1c8 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 1debd9ab-681f-5d73-8ed2-43b7a25e4f40 |  | textbox | Name:
text | 2ead918a-3f3a-56b3-a048-df204623898b |  | textbox | Position:
date | fd8076fa-8729-55ce-8738-0b4c5df766f9 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP004B – Spray Sealing | itp |  |  |  | Yes | ITP004B – Spray Sealing | b43c2f26-2e8f-480d-8587-4b42df3b08b6
checkpoint-group |  |  | section | 1. Bitumen
checkpoint-status |  |  | checkpoint | (a) Bitumen
label | 456d3696-431e-53f9-a4ad-6b29c64215f0 |  | note | Freq. - Delivery Docket upon request
label | 656d08e9-7787-5a44-b062-6723bef40750 |  | note | Acceptance Criteria - Bitumen must be Class 170 complying with the requirements of AS 2008
label | 18170eb8-5985-50e4-a058-445f23e1fd01 |  | note | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.2
label | e3b8cde7-ce65-5f73-b36e-a0fa25fbe21d |  | note | Inspection/ Test Method - Verify
label | d7548321-a01e-50fd-afe2-c12bb9412368 |  | note | Conformance Record - This ITP signed
label | 34156d50-be91-535f-9225-fbdb215f35c0 |  | note | IP
label | 3b488043-cd26-51b1-bf0b-e5a5b1e7d66f |  | note | Responsibility - Lab Manager/SS Engineer
checkpoint-status |  |  | checkpoint | (b) Bitumen Emulsion
label | 8b1ad129-1075-51e1-a28b-4fd371c235c4 |  | note | Freq. - Delivery Docket upon request
label | 7e4e1cbf-6766-5043-886f-95188e0ec989 |  | note | Acceptance Criteria - Bitumen emulsion must comply with the requirements of AS 1160
label | de4a5f56-a572-50e9-9126-dc01fec1a66f |  | note | ○ Testing of the bitumen emulsion, as per ITP Bitumen Emulsions Manufacture Feb 2019 for Surfix 70 (for FibreDec), shall be done prior to releasing the product.
label | ca9a6410-93a1-55d6-9802-a20000d9f2ee |  | note | ○ Ensure minimal storage time (ideally use within 24 hours of production).
label | a4e3e698-e00a-55b5-8f0a-3a350a929777 |  | note | Reference Documents/Clause - VicRoads Technical Spec 408.08 (b) ITP FH National – Bitumen Emulsions CAG 010812 Section 2
label | cc06de47-c55d-5aca-8121-044446e4ba69 |  | note | Inspection/ Test Method - Verify
label | 673ae011-1ae2-51c1-b460-6eb762c91f4c |  | note | Conformance Record - This ITP signed
label | b488fd4e-c1fd-5d78-85ff-a0d2bb61614f |  | note | IP
label | e2c0c611-ebec-57b7-83d4-d617ae9bb713 |  | note | Responsibility - Lab Manager/SS Engineer
checkpoint-status |  |  | checkpoint | (c) Cutback Bitumen
label | b063d71a-5349-5743-b784-bbc4319c8cb5 |  | note | Freq. - Delivery Docket upon request
label | 3b11e9e4-4254-5571-b4a7-7d0d734f821d |  | note | Acceptance Criteria - Cutback bitumen must comply with the requirements of AS 2157 and must be Class AMC0 or AMC00
label | 7f824c94-052e-5049-afd1-d803a19256cd |  | note | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.1
label | 679bd88f-d0ef-5732-af8d-a63c7affa152 |  | note | Inspection/ Test Method - Verify
label | e5c114d4-34ea-52e1-b774-a4d2689ad976 |  | note | Conformance Record - This ITP signed
label | fd90c78e-234b-50df-a0b1-ee9559d258c0 |  | note | IP
label | 5679f22d-1049-5ec2-93dd-d31ae4b159e5 |  | note | Responsibility - Lab Manager/SS Engineer
checkpoint-status |  |  | checkpoint | (d) PMB and Proprietary Bitumen
label | 5830fae8-a338-5dfe-82ab-b74e63ad3423 |  | note | Freq. - Delivery Docket upon request
label | 964c792d-3757-5f75-81d1-d2a5a331b558 |  | note | Acceptance Criteria - Viscosity-grade binders must comply with the requirements of AS/NZS 2008. The class of PMB shall comply with the requirements of Austroads Technical Specification ATS- 3110.
label | d0f63f64-e59a-5770-9706-c4194ca0e2b3 |  | note | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.3
label | d9b921d5-9d8e-5268-943d-a898047500ec |  | note | Inspection/ Test Method - Verify
label | f28d772e-4462-5cb3-8c7a-605f6fde6101 |  | note | Conformance Record - This ITP signed
label | 4c411030-77d4-5ae4-94c2-7f319e58a606 |  | note | IP
label | c023d9af-4268-5333-8496-e150a85673fe |  | note | Responsibility - Lab Manager/SS Engineer
checkpoint-group |  |  | section | 2. Materials
checkpoint-status |  |  | checkpoint | (a) Cutter
label | ac38094e-83f8-5936-9039-c0a4e55a1806 |  | note | Freq. - Delivery Docket upon request
label | 483b9065-0b5c-564e-99dc-489847240259 |  | note | Acceptance Criteria - Any primer which is not prepared in a refinery must be prepared by mixing bitumen and cutter at the site of the Works. The cutter must be commercial quality power kerosene or aviation turbine fuel (Jet A-1).
label | 4b730d6e-2c29-5903-a5b0-881ae0e1c2ad |  | note | ○ No other type of cutter oil must be used under any circumstances. The cutter must be a clean, clear liquid containing no dissolved solids, foreign material or matter in suspension and must be liquid at 4°C.
label | a70548ad-2de6-525f-b218-6062182bbf99 |  | note | ○ The Contractor must declare the amount of cutter used in the primer or primerseal to the Contract Administrator.
label | 827974b7-8bb3-5cbc-89ee-209ced67f99e |  | note | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.4
label | 3fba1920-e92f-5aa3-80f4-51f37d4df37c |  | note | Inspection/ Test Method - Verify
label | 00f8893f-e705-5509-a808-d540173c0389 |  | note | Conformance Record - This ITP signed
label | 15c89c9d-65a0-5e19-943b-2b4229aa5a3c |  | note | IP
label | 75240aaa-f14f-5a21-a4d0-404790712253 |  | note | Responsibility - Lab Manager/SS Engineer
checkpoint-status |  |  | checkpoint | (b) Fibreglass
label | 1789c4e9-4e38-597d-8d12-7356be07e032 |  | note | Freq. - Prior to commencing works
label | 7118047d-2694-5cb3-a286-f38bcc019a5b |  | note | Acceptance Criteria - Ensure correct fibre is supplied.
label | 8162f9c8-5614-563b-9049-11afc5fd9fb3 |  | note | Reference Documents/Clause - CAG 010812 Section 2
label | 34066939-b526-5be3-baa9-d5da3a36a219 |  | note | Inspection/ Test Method - Verify
label | 7b96c7fc-c91d-5ba3-93d7-42f2cfcea996 |  | note | Conformance Record - Fibreglass datasheet
label | 626caf88-8b26-571e-b5f8-3aaadaad598d |  | note | IP
label | c0e26307-b443-59a4-a324-c47a55b148a3 |  | note | Responsibility - SS Engineer/ Supervisor
checkpoint-group |  |  | section | 3. Aggregate
checkpoint-status |  |  | checkpoint | (a) Aggregate Specification
label | abe48a5d-9578-5a65-a87b-2a3f372da7ef |  | note | Freq. - Delivery Docket upon request Maximum lot size 350t of same class and size
label | 296f898c-c40f-5279-a601-7be07a479753 |  | note | Acceptance Criteria - VicRoads Standard Specification Sections:
label | 497a9f41-5f90-5441-a3e3-685e9c8af263 |  | note | ○ 801 - Source Rock;
label | 694e5ac8-8552-5482-9ac0-29364eb6f4ab |  | note | ○ 831 – Aggregate; and
label | b92f2174-aab7-52a0-9a40-798282c64b38 |  | note | ○ 832 - Sands
label | 848d6da0-914b-53cd-9b3d-9771a71338b4 |  | note | Reference Documents/Clause - VicRoads Technical Spec 408.11 (a)
label | f8fd04fd-e174-5a62-8d59-615ccef1681d |  | note | Inspection/ Test Method - Verify
label | ce77967d-3a72-51a3-85c5-df95acaa609e |  | note | Conformance Record - This ITP signed
label | ce387f1c-30b6-56a7-ac0a-75d4ddeec586 |  | note | IP
label | 888ffb1b-1a09-5cab-b776-a39e916a57cb |  | note | Responsibility - Lab Manager/SS Engineer
checkpoint-status |  |  | checkpoint | (b) Aggregate Pre- coating Materials
label | 47829bda-f169-585a-a0b2-ee192bb1ca39 |  | note | Freq. - Delivery Docket upon request
label | 160110f6-18ae-56b0-9cf0-212918662e00 |  | note | Acceptance Criteria - Distillate based product, cutback bitumen, emulsion based product or proprietary product.
label | 736ad955-03f4-5c8a-a336-786fd3b5c20b |  | note | Reference Documents/Clause - VicRoads Technical Spec 408.09 (b) 408.11 (b)
label | 6c27b7eb-d9a2-5075-90e9-98e2fbaa03a9 |  | note | Inspection/ Test Method - Verify
label | 6f541f9e-955b-5467-abaf-8a2473c24d3b |  | note | Conformance Record - This ITP signed
label | 0809b269-3044-56ee-94d2-56bfd473badc |  | note | IP
label | 2a995342-212b-56be-82d6-c623f82384b6 |  | note | Responsibility - Spray Seal Supervisor
checkpoint-group |  |  | section | 4. Operation
checkpoint-status |  |  | checkpoint | (a) Material Test Reports
label | ac0da2eb-bf12-5338-97a8-43c2e39c8e78 |  | note | Freq. - Prior to commencing works
label | bad1d2a0-111a-5a3a-9739-d2630f9792e3 |  | note | Acceptance Criteria - Test reports for bitumen and proprietary emulsions must be submitted to the Contract Administrator.
label | 2fc0391f-87aa-5e54-bdb1-41c1b6a74df9 |  | note | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.4.7
label | 1fe8bf37-77ea-5f01-827d-0a8f9d245d21 |  | note | Inspection/ Test Method - Verify
label | 91efdf06-a537-546b-a9ca-9d2420e002e7 |  | note | Conformance Record - This ITP signed
label | 808466d5-9c5a-567e-be23-0eb20522e168 |  | note | HP
label | a959df11-0055-5f75-86d1-4de6def998dd |  | note | Responsibility - Spray Seal Engineer / Contract Administrator / Principle’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | (b) Works Method Statement
label | cd36b50e-cfce-5a91-bedc-ee864a513fc7 |  | note | Freq. - Prior to commencing works
label | 0a17709d-0fc0-51e9-8ca4-a710c4e98851 |  | note | Acceptance Criteria - The Contractor must submit a Works Method Statement (WMS) to the Contract Administrator.
label | cb22869c-0f06-517c-8dea-830d0cdb5095 |  | note | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.1
label | 6fce2ab5-d895-548d-96d4-0c90aecf1ea4 |  | note | Inspection/ Test Method - Verify
label | d5fcc78a-75b1-5527-8d76-9e07778c4ecf |  | note | Conformance Record - This ITP signed
label | 709d0a42-4932-57c5-9314-84dfba474701 |  | note | HP
label | ada019b5-b981-5343-822c-c63d79a469d9 |  | note | Responsibility - Spray Seal Engineer / Contract Administrator / Principle’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | (c) Calibration of Bitumen Sprayer
label | d14a0429-c42e-509a-aced-8f28b2a0a80e |  | note | Freq. - Prior to commencing works
label | db9e76df-18e7-5ff3-be8f-49d4fc8bd528 |  | note | Acceptance Criteria - Calibration Certificate to be provided.
label | 7a1d180e-d066-5fa7-a322-30511728dc83 |  | note | Reference Documents/Clause - VicRoads Technical Spec 408.07 AECOM – MAPMP 2.0 DP1 Spec. Cl 11.3.3
label | 2562800c-1efb-5dd7-9632-0451cf7b9d8d |  | note | Inspection/ Test Method - Verify
label | 065c1676-2fe0-5e24-a893-a8ab5dd7947a |  | note | Conformance Record - This ITP signed & Compliance Certificate
label | fdb1711a-89fa-5bf9-9399-04c9d9d64059 |  | note | HP*
label | d1334e81-7435-5a11-a8a6-62471716faff |  | note | Responsibility - Spray Seal Engineer/ Supervisor
checkpoint-status |  |  | checkpoint | (d) Commencement of works & Surface Preparation
label | 9785d933-c295-56ae-96df-efc51aaf37dd |  | note | Freq. - Prior to commencing works
label | baeb4e3d-1dbf-5368-aec8-3ee92aa6a98f |  | note | Acceptance Criteria - Works shall not commence until the Contractor & Superintendent of works agree that the prepared surface is ready & fit for sealing.
label | e91e82f8-312f-501c-b994-0884e5c17835 |  | note | ○ Surface is free of loose material and the surface is dry.
label | 63b11ca1-e3ef-5a73-90c2-3390fa33c4d6 |  | note | ○ Priming shall not be carried out within 24 hours of forecast rain.
label | ce336ca8-253c-5142-91af-38949c25271c |  | note | Reference Documents/Clause - VicRoads Technical Spec 408.04 (b) 408.09 (d) AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.2, 11.5.3
label | 4f69e8b5-8ceb-58f2-bbf0-98640d738142 |  | note | Inspection/ Test Method - Verify
label | 28c5f5ff-4f1f-5d5a-94a0-ab78c0b4f80e |  | note | Conformance Record - This ITP signed
label | 3de70017-19f6-56c1-82f9-94fb80a97ec8 |  | note | HP
label | ff3d7ea0-13ef-5e77-8c63-f2846a3e7ff0 |  | note | Responsibility - Spray Seal Engineer / Contract Administrator / Principle’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | (e) Minimum Temperature
label | 1990ca29-26ce-527b-bbc8-f79247d0d3ad |  | note | Freq. - Prior to commencing works
label | 6dfac89a-1bca-57a4-96d1-d685ea44e2af |  | note | Acceptance Criteria - The primer must be applied only when the surface temperature of the base course is at least 15°C and is expected to remain in excess of 15°C for the duration of the application of the primer.
label | b0b0a363-08ee-50df-9744-0df5c9887a8b |  | note | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.2
label | 0b82df91-4e7f-5afc-9f02-44b804462e5f |  | note | Inspection/ Test Method - Verify
label | 6b6ecd0e-1a05-5187-8b1e-40f830afaa07 |  | note | Conformance Record - This ITP signed
label | e58df18b-6105-56c7-abc5-9393859029f7 |  | note | IP
label | 555bc787-b571-5ef8-8ded-d1df073753d5 |  | note | Responsibility - Spray Seal Engineer/ Supervisor
checkpoint-status |  |  | checkpoint | (f) Primer Application Rate
label | 1f5a539e-1ef7-5edd-a3c2-a3fa82ff1ddd |  | note | Freq. - All works carried out
label | 064660bd-01c3-5150-a510-5b8d0a01b943 |  | note | Acceptance Criteria - The primer must be applied to the base course surface at an application rate of at least residual bitumen of 1.2 L/m2, measured at 15°C for priming crushed rock base.
label | df133f7c-8fd1-51fc-9d02-b675de0b9c2a |  | note | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.4.2
label | 86f42118-4036-51c1-8f1a-45bf2301e89c |  | note | Inspection/ Test Method - Verify
label | 2e9796fc-72cf-5d1b-8860-8133c5cb38be |  | note | Conformance Record - This ITP signed
label | 332a6a2a-3040-59ec-a229-3fd183baa497 |  | note | IP
label | ab6fa3ab-581d-5c30-af2d-29dd6a66f3cb |  | note | Responsibility - Spray Seal Supervisor
checkpoint-status |  |  | checkpoint | (g) Application of Primerseal Aggregate
label | c13d7f61-73f3-5a4a-b370-9f21c15c3751 |  | note | Freq. - All works carried out
label | 45564e9b-166b-5bf5-9984-ec7487bd6461 |  | note | Acceptance Criteria - The primerseal must penetrate the prepared surface uniformly. The residual bitumen on the surface must be sufficient to retain the sealing aggregate firmly, with no loose aggregate left on primerseal after rolling and sweeping.
label | 54164b58-44e0-5dd4-b76f-b3f7904a8f76 |  | note | ○ After rolling, the sealing aggregate must be embedded into the film of residual bitumen and the surface for no more than 50% of its Average Least Dimension.
label | 3985c019-7e0b-5630-ae7f-8ba446a3a489 |  | note | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.6
label | f436562e-4a39-5956-a04d-4c8cff7c41bb |  | note | Inspection/ Test Method - Visual Inspection
label | 87c93189-2c30-5959-96f1-5c9227c7f072 |  | note | Conformance Record - This ITP signed
label | 918e1308-1ac7-5473-9e96-300131bd03c6 |  | note | IP
label | f4821e82-8fc0-5bcc-b0bb-f87fdb3080be |  | note | Responsibility - Spray Seal Supervisor
checkpoint-status |  |  | checkpoint | (h) Removal of loose aggregate
label | 080ee4a4-5bee-5946-9f56-d411b2484bea |  | note | Freq. - All works carried out
label | 269727d0-ba74-5529-862d-84c3f60c5d52 |  | note | Acceptance Criteria - The primerseal must be swept and surface to be dry prior to the application of the next treatment. Sweeping must leave no loose aggregate on the surface.
label | 3ad7b752-b30a-53c8-894f-113d90cc2040 |  | note | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.6
label | 7036f414-f91a-5b57-a96a-7f25a581d945 |  | note | Inspection/ Test Method - Visual Inspection
label | 41ee2cb4-e0e9-5cbe-8bb9-3e3affd92d5f |  | note | Conformance Record - This ITP signed off
label | 6b3535de-cea4-55d4-84a6-7ea609b5df50 |  | note | IP
label | aeaa1833-4afe-52e2-9bc4-b2a1c185198b |  | note | Responsibility - Spray Seal Supervisor
checkpoint-group |  |  | section | 6. FibreDec Specific Items
checkpoint-status |  |  | checkpoint | (a) FibreDec Box Check
label | d4aa4823-dcf0-5c78-96df-a522164054ce |  | note | Freq. - Each Lot
label | ecd10ccf-bd3a-5dc0-bf7b-3847f5b38d71 |  | note | Acceptance Criteria - Applicator box is clean and rubber skirts are free from binder/glass build up
label | d43b6f24-810d-5dfd-b5be-ba75fc065f0b |  | note | Reference Documents/Clause - CAG 010812 Section 2
label | c7dad901-d17e-5cd4-b6da-3a327ccce5ad |  | note | Inspection/ Test Method - Visual Inspection
label | c2d1b9e7-b454-5007-97fa-3d2e4793acb9 |  | note | Conformance Record - This ITP signed
label | 73a10b9b-a866-5af7-9922-5e160d8f2c2d |  | note | IP
label | 2b950971-8a3d-5981-8fb6-f08e2ea83a61 |  | note | Responsibility - Spray Seal Engineer/ Supervisor
checkpoint-status |  |  | checkpoint | (b) Aggregate spreading
label | b5570691-014a-55a5-a43c-8f0a70a03cb7 |  | note | Freq. - Each Lot
label | 56bde68c-b3c5-5722-b7dd-965b7881dbcd |  | note | Acceptance Criteria - The correct aggregate spread rate shall be measured and assessed.
label | 2c366932-4636-5cbf-a4e2-654829008a95 |  | note | Reference Documents/Clause - AGTP Part 4K 6.7 408.1 408.13.e
label | 46e44254-ede8-55e5-b68d-c1eab83abc72 |  | note | Inspection/ Test Method - Verify
label | 88d5d5e8-7b62-58d0-b1ba-29e409e18d63 |  | note | Conformance Record - This ITP signed
label | 13f095df-1f1f-58ae-b202-d9b64b55acbb |  | note | IP
label | 3859085f-ec90-5b7f-bf6c-7b5671a56c86 |  | note | Responsibility - Spray Seal Engineer/ Supervisor
checkpoint-status |  |  | checkpoint | (c) Removal of loose aggregate
label | 92f3ee3e-03c0-51dc-8239-6f5b7333d666 |  | note | Freq. - Each Lot
label | 541f6f00-d485-5bc2-aa2c-4127bb8cc0de |  | note | Acceptance Criteria - All areas – within 8 hours of sealing unless otherwise agreed with the Superintendent.
label | ebaf5f08-4618-560e-a5bf-00eee03030a0 |  | note | NB:
label | 5622302c-efa0-5d89-91e5-9a941a71b084 |  | note | ○ For seal of nominal size ≥ 10mm, < 40 loose stones/m2 to remain after removal of loose aggregate.
label | 94caf094-4e49-59d9-b71d-1136de193dad |  | note | ○ For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain afterwards.
label | ac30b71e-0108-5333-9dab-6ab11cc90723 |  | note | Reference Documents/Clause - VicRoads Technical Spec 408.14
label | 808bf107-630c-565d-aaa1-582e4ed31e2b |  | note | Inspection/ Test Method - Visual Inspection
label | 38fd6cb4-548a-5120-b6da-1252cb2d396a |  | note | Conformance Record - This ITP signed
label | f0e9129a-87a0-5e35-b5c4-8f92c5fe7402 |  | note | IP
label | 772f6c1d-3b29-5bff-8d3d-519b401e0684 |  | note | Responsibility - Spray seal Supervisor
checkpoint-group |  |  | section | 7. Post-Operation
checkpoint-status |  |  | checkpoint | (a) Records
label | ca821256-9c68-5b5b-a3a5-e9ecfee57b6e |  | note | Freq. - Each Lot
label | 2cb4d16a-4b6d-5d73-87be-f741b86fcd54 |  | note | Acceptance Criteria - Job completion report (Spray Sheets) to be submitted within seven days of completion of sealing works.
label | 8c4a3093-d96f-5515-8744-20527a856a13 |  | note | Reference Documents/Clause - VicRoads Technical Spec 408.17
label | df49c0c2-ebbd-5ce8-9df3-75a7d5e44203 |  | note | Inspection/ Test Method - Verify
label | 19f64333-f1aa-52bb-9fce-e94821be5d11 |  | note | Conformance Record - Spray Sheet Record
label | 91b4cd79-fc6d-5068-a76d-d4354cf3234d |  | note | IP
label | c1c913ba-4a4b-56a4-a493-d0f286299680 |  | note | Responsibility - Spray Seal Engineer
checkpoint-status |  |  | checkpoint | (b) Primer Curing
label | c565c721-799c-5548-bab6-5e88a77c3895 |  | note | Freq. - Each Lot
label | 2ce0654b-796d-5a74-ab0d-e3bba6e8b788 |  | note | Acceptance Criteria - Following the application of the primer, the surface must be allowed to cure without being disturbed for a period of not less than 48 hours or longer as may be necessary to attain penetration into the surface and evaporation of the volatiles from the primer.
label | cc7c6fa4-a590-569b-b373-3538f7aa6f0d |  | note | Reference Documents/Clause - AECOM – MAPMP 2.0 DP1 Spec. Cl 11.5.4.4
label | 3ee23baa-7269-5401-a8af-d101295073c4 |  | note | Inspection/ Test Method - Verify
label | f2d0686b-a1b0-5224-9840-4a8de54340bf |  | note | Conformance Record - This ITP signed
label | 0aa66659-b1a0-57e0-96bd-dc22d36e7759 |  | note | IP
label | a3f93ad0-9865-5100-b087-12de32be8da5 |  | note | Responsibility - Spray Seal Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | aec108e6-ac82-5744-8738-2a5c562d9b79 |  | note | This is to verify that the final inspection has been carried out in accordance with the FH’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
text | 99ea441f-082f-5d47-8574-38b3b498ac86 |  | textbox | Name:
text | e8fb72ba-92cc-5c45-b7c2-11367c094e51 |  | textbox | Position:
date | 564228b6-3b5e-5b23-ab10-fab6eb5a5894 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP021-4A – New Foundation Works – Removal | itp |  |  |  | Yes | ITP021-4A – New Foundation Works – Removal | bac453aa-ef9f-402a-86bf-44cd5f8d0f69
checkpoint-group |  |  | section | 1. Removals
checkpoint-status |  |  | checkpoint | 1.1 - Preparation for the works to be undertaken
label | 9b1f094a-6484-5512-b42c-c2b7b50bff28 |  | note | Frequency - Prior to Start
label | 22057c2d-63a2-5b7b-a3bc-c2d28b8eb753 |  | note | Acceptance Criteria - Ensure survey set out is undergone, excavation permit obtained and (if required) services in work(s) area isolated. Dilapidation survey.
label | d847bf86-7517-51ca-8b02-ac3e6fa855c3 |  | note | Reference Documents - Drawing sets:
label | 2d349ecd-f7ca-55ff-8a75-dadf91ff1f89 |  | note | • 60692389- SHT-01_1- 10
label | 1dff0fea-91a3-5abc-8955-b31de1d8992e |  | note | • 60692389- SHT-01_2- 10
label | aebb0b5a-d5bb-5b3a-90aa-0109e2971db5 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 9a8f9a9e-8964-5559-8655-3823634e264a |  | note | Inspection/ Test Method - Verify
label | 99119b03-59ae-5eee-9d80-15c9e535b26b |  | note | Record of conformity - This ITP Signed / Avionics CL004A
label | dca9d378-3226-511c-9706-5cd069b46506 |  | note | HP*
label | f4235298-f73b-5c71-b5fa-dd2bc7060946 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.2 - Core and inspect
label | 6058dccd-794d-5c76-bd23-23ce7d8d31fb |  | note | Frequency - Each Lot
label | 93c69a91-5537-5109-819b-0bfe18dc6c45 |  | note | Acceptance Criteria - Light base cored into pavement and slot from base cut to pavement edge/expansion joint. Based removed and cleaned. Inspection to determine works method.
label | 5a57110a-c99f-54c3-bfbe-98c06e952686 |  | note | Reference Documents - Drawing sets:
label | 32383ddb-fdc8-5cd0-ba3a-d97cdb287dd2 |  | note | • 60692389- SHT-01_1-10
label | 48b7218c-8e0c-5e4f-a7c9-6888ffeffc6a |  | note | • 60692389- SHT-01_2-10
label | 4fe265a0-b7a1-5dc9-87bc-886e0382a6ba |  | note | • Specification: 60692389-PS-01-AV-0001
label | aaa1c9b3-5811-5984-94e2-ca90a7e86fbd |  | note | Inspection/ Test Method - Verify
label | 08511548-5618-5a12-82f9-6a87e5d8fbca |  | note | Record of conformity - This ITP Signed / Avionics CL004A
label | c8089bcd-055c-5082-af2c-9d78325cdc93 |  | note | IP
label | 9b378fad-2946-5a1e-a750-2b9da2716bf2 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.3 - ‘Method 2’ installation (SP1 only)
label | dfd55abe-ded0-538c-8fc7-e52f306682a0 |  | note | Frequency - Each Lot
label | 58ec732b-e859-5c48-bd51-bfdf982858f3 |  | note | Acceptance Criteria - Continue core to depth of basecourse.
label | d00afeda-c4fc-54dc-9773-207aeb40fc39 |  | note | • Reconnect conduits.
label | 22e95486-f6b0-5645-8233-426ecc157b9e |  | note | • Concrete poured to correct level and cover.
label | a35f7a55-0390-59dc-a4f4-4a853a68196e |  | note | • Spacers positioned and conduits/cabled cleaned.
label | 5bf81276-cbe2-5286-bd7a-813a9af3fb9f |  | note | • Mesh laid and rapid-set concrete poured.
label | da2abcd2-ad02-5ba8-a323-c7b189ffc6b4 |  | note | Reference Documents - Drawing sets:
label | 07d4b284-808a-5e1d-b2f7-65629672d57c |  | note | • 60692389- SHT-01_1- 10
label | ed8be1ff-9705-526d-a855-37fae3fdbca5 |  | note | • Specification: 60692389- PS-01-AV- 0001
label | 92794d88-2a8c-5e36-b3c5-1c02f08bbf0e |  | note | Inspection/ Test Method - Verify
label | ce10312d-2871-5b72-a152-bce9a29031e8 |  | note | Record of conformity - This ITP Signed / Avionics CL004A
label | 7d26e48b-a214-5a76-886a-7b3c89fffdf8 |  | note | IP
label | 20b03156-b758-58ff-97eb-8408232f686e |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.4 - Finishing and demobilisation
label | 2e772fbb-54d0-5021-a186-a5baf3e5522f |  | note | Frequency - Each Lot
label | d02200a4-5da6-5728-998d-5c548d305041 |  | note | Acceptance Criteria - Pavement area cleaned and equipment packed away. Work crews demobilised and FOD walk undertaken.
label | bce22c31-9749-580a-87f7-e0a236fdd304 |  | note | Reference Documents - Drawing sets:
label | ffd423f9-eb0c-55b6-906b-39b63a87c9ca |  | note | • 60692389- SHT-01_1-10
label | 2afb55e9-ea9e-50a5-b035-364383819dac |  | note | • 60692389- SHT-01_2-10
label | 33fbc54d-74db-5a07-92ba-c3b50c8a9776 |  | note | • Specification: 60692389-PS-01-AV-0001
label | 70a6c7dc-8feb-5452-9b32-f60ebcb0cdc1 |  | note | Inspection/ Test Method - Verify
label | c011ea6d-2553-580c-9312-1d9accc04191 |  | note | Record of conformity - This ITP Signed / Avionics CL004A
label | e06c53de-21f1-5001-9e01-9884734768e6 |  | note | IP
label | 36f74c54-d0ae-57f9-b9ba-df857abc1348 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | Final Inspection
label | fffaa5b7-89c2-5149-9ff9-be150cd20f32 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 465a37ac-532e-5248-8fe7-c067b296c1cc |  | textbox | Name:
text | 84b6d98e-d33c-5537-a093-355212f89ad5 |  | textbox | Position:
date | e8346b50-6a54-5b3d-bd77-bb329218c2bc |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP002A - Excavation, Subgrade Preparation and Capping Layer Preparation | itp |  |  |  | Yes | ITP002A - Excavation, Subgrade Preparation and Capping Layer Preparation | bbf9eec7-3fbb-4395-97ce-8afd5a8ccc8c
checkpoint-group |  |  | section | 1.0 Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | c9fa5dcb-72b7-5ef1-ac78-d8546faf396b |  | note | Frequency - Prior to commencing works
label | a9af4fc7-06bf-59a6-9023-304e81b457c2 |  | note | Acceptance Criteria - Current revision of drawings, technical specifications and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ad804acb-7dba-5347-ac10-41b78c5cc1ff |  | note | Current revisions of these documents to be obtained via Aconex.
label | c2c7da9d-870f-588e-a124-651ba31577a9 |  | note | Reference Documents - Current Revisions in Aconex
label | dc201d8c-3059-50cd-b31d-2320cb28e004 |  | note | Inspection / Test Method - Verify
label | 8c047d52-934e-506e-a866-e5edff9a4909 |  | note | Record of Conformity - This ITP signed
label | 537d9c92-e406-5372-998f-fa5dafa6e14c |  | note | HP*
label | a4a7156d-6d8b-56a7-aa8e-30c9300a1e7d |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 4e98d698-1d0a-56c7-98fd-d762bd223bcb |  | note | Frequency - Prior to commencing works
label | 6a1ea3d3-5907-5d66-ba93-f6c4c10f7c84 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | cbc5a0b2-c785-5910-b003-65f5b453705d |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | 0b0c3ae1-8dbc-502f-b050-ca2db46f5372 |  | note | Inspection / Test Method - Visual Inspection
label | 5684b35d-a730-5a15-8fa7-c0dba4306cab |  | note | Record of Conformity - This ITP signed
label | 8a236260-c927-59dd-a27e-1bf6b272bef1 |  | note | HP*
label | 25452023-122c-5479-ae6f-37cc7f32b919 |  | note | Responsibility - Project Engineer / Site Supervisor
checkpoint-status |  |  | checkpoint | 1.3 - Current excavation and isolation permit has been issued
label | e24c0fa4-ee84-56b6-8938-c4481bbeba14 |  | note | Frequency - Prior to commencing works
label | b67ce4a0-d736-5f24-a140-8d443b74e4bc |  | note | Acceptance Criteria - An Excavation Permit and an Isolation Permit issued by Melbourne Airport.
label | 9e382130-9f23-503b-a46e-3f14baf4b55a |  | note | Fulton Hogan Excavation Permit issued to plant operators.
label | d3e1992e-e0f8-55c2-bb2a-5290839ec269 |  | note | Reference Documents - Excavation Permit
label | 80747f84-2da5-574d-a339-7ad1bf9328b8 |  | note | Inspection / Test Method - Visual Inspection
label | 24898ae5-e966-5c7a-82e5-19dcf6e72b2e |  | note | Record of Conformity - Permits
label | e9c634f6-694d-5fe7-b274-63896f1c46e6 |  | note | HP*
label | 942a4cc4-bb30-59c6-ae90-580ef2c23f84 |  | note | Responsibility - Project Engineer / Foreman
checkpoint-status |  |  | checkpoint | 1.4 - Preliminary Testing During Enabling Works
label | 5689452a-75ee-5961-90d0-bdb81866c2f8 |  | note | Frequency - Prior to commencing works
label | 07f0e576-28d8-5dbe-be3a-56e36ed03cdf |  | note | Acceptance Criteria - Upon completion of DCP testing alongside the edge of the existing blast pavement of Taxiway K and C a DCP test report must be issued to the Contract Administrator and Principal’s Design Consultant for review.
label | 0be7e52d-7ee5-549a-a4f6-cd2bb7e54589 |  | note | Reference Documents - AECOM MAPMP 2.0 DP1 Spec. Cl 5.7
label | 74ea9056-0b0b-59fd-9bb4-ff43316c7eed |  | note | Inspection / Test Method - Verify
label | b983b6de-5272-52b9-808e-841b8c70ee3b |  | note | Record of Conformity - Aconex Reference / Test Report
label | 279ce3eb-3eb9-55d1-b9cb-a99b58e4d6b6 |  | note | HP
label | ab7ccfe1-c35e-5a53-955d-b3a29ed6c17b |  | note | Responsibility - Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Work Method Statement (WMS)
label | 66f5303c-4b9f-5c43-8bdb-2ba90687f181 |  | note | Frequency - Prior to commencing works
label | 53d1ba47-8ffa-51ba-8aad-d08acea958cb |  | note | Acceptance Criteria - The contractor is to submit a Work Method Statement (WMS) detailing the proposed methodology for subgrade preparation for expedient and standard works.
label | 4904b3b8-53b5-515f-ab78-2b6efd062865 |  | note | Reference Documents - AECOM MAPMP 2.0 DP1 Spec. Cl 5.10.1
label | 7f04f138-ffbf-50de-8953-b6104e30e52f |  | note | Inspection / Test Method - Verify
label | dad50300-4bc0-58f8-b4db-fed75e80dc03 |  | note | Record of Conformity - Aconex Reference / Work Method Statement
label | ab840139-c400-51a7-89a3-d46f8f8f48fc |  | note | HP
label | 0ac4a0bb-26fc-5ed6-837c-05945b26136d |  | note | Responsibility - Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Capping Material Approval
label | b34a94d1-255b-5fbd-9e20-87ec70663826 |  | note | Frequency - Prior to commencing works
label | e8e5cd36-d997-5d4d-a7f2-158855633266 |  | note | Acceptance Criteria - Prior to the commencement of works the Contractor must submit the material data reports for acceptance.
label | de81ec8a-0f25-5a4b-b4fc-0b875f30c820 |  | note | Acceptance criteria for the designated material must align with Table 5-1 and 5-2 from Cl 5.6.2 of the AECOMs Technical Specification.
label | b9570e41-1362-59bf-9649-fce2ec8ca9e6 |  | note | Reference Documents - AECOM MAPMP 2.0 DP1 Spec. Cl 5.6.2 & VicRoads Section 204
label | d426388f-bd93-5c2f-ae0a-8ea35a67efe0 |  | note | Inspection / Test Method - Verify
label | 6fa6c42f-6153-585a-868c-1877777ba40c |  | note | Record of Conformity - Aconex Reference / Test Reports
label | 5e98f823-0d7c-54d2-8f88-e4581d043ef1 |  | note | HP*
label | ca4355a9-f5f2-58e0-a2c3-90c8749bb966 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.7 - Production Testing
label | d28cae4f-fee7-5e38-9970-1fc094604f7c |  | note | Frequency - Prior to commencing works
label | 71ba49e0-d754-5832-9bdd-af6c23afb3ce |  | note | Acceptance Criteria - Supply information with respect to production testing. Production testing is to be undertaken at a frequency of that specified in Table 5-7 of AECOM’s specification.
label | 6302cab1-d3cb-520d-99cd-bb5bbcb82de1 |  | note | Reference Documents - AECOM-MAPMP 2.0 DP1 Spec. Cl 5.13.2.2
label | 2172d54b-d11a-5a06-8918-2709882e67eb |  | note | Inspection / Test Method - Verify
label | d4af00b5-dc0c-56bb-bc94-27e0e9877d1f |  | note | Record of Conformity - Approved production testing results
label | 83102d07-2bee-5520-8955-9a5e137ebed0 |  | note | TP
label | 36bcacc1-a428-57e0-aa61-f19bfa0815a4 |  | note | Responsibility - Project Engineer / Contract Administrator / Principal’s Design Consultant
checkpoint-group |  |  | section | 2.0 Subgrade Preparation – Expedient Works
checkpoint-status |  |  | checkpoint | 2.1 - Excavation to Design Subgrade Level
label | b37779c7-18db-5126-a62b-bcc81979e070 |  | note | Frequency - Each Lot
label | a965124c-490b-5be2-a555-3896fec7b905 |  | note | Acceptance Criteria - All in-situ material encountered within the extent of works, below the stripped surface level and existing pavements must be excavated as indicated on the drawings.
label | 2f5b154c-840b-57da-989e-cb637baefd62 |  | note | The Contractor must preserve the existing pavement that is not to be demolished.
label | cfec1770-b66e-585d-8153-d50101763261 |  | note | Reference Documents - AECOM-MAPMP 2.0 DP1 Spec. Cl 5.9 5.10.3.2 & 5.10.4
label | 0c6b8a55-12f3-5fcc-9aef-ddcb7d8149b8 |  | note | Inspection / Test Method - Visual Inspection
label | a413268b-46ca-5b10-ae53-87e12d30283d |  | note | Record of Conformity - This ITP signed
label | 47014bf6-4af6-5953-8827-bb2a91495358 |  | note | HP*
label | 2f915c70-128a-539e-894d-d02b9040e64c |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Subgrade Compaction and Proof Roll
label | ba6f44eb-07d9-599e-b0f1-59762f0cf456 |  | note | Frequency - Each Lot
label | ff714230-32f0-5060-a3e0-f95be54105dc |  | note | Acceptance Criteria - The compaction and proof rolling for expedient works have been combined as per the WMS.
label | e5188645-aa67-5736-92e3-2ecba79ad9be |  | note | Proof roll shall be conducted in a systematic manner that covers the entire area uniformly. A total of 2 static passes with a 12T smooth drum roller at a speed not greater than 6km/hr is to be carried out on the subgrade layer in the presence of the Principals Design Consultant. Proof rolling passes if it leaves no significant indentation marks on the surface and does not produce any visible permanent deformation in the in-situ material surface. Compaction is verified through the proof roll in lieu of compaction testing.
label | 0f36bdf8-09a6-596b-a192-3d13dcac33d7 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.10.2 & Cl 5.10.3
label | a479832e-84af-56e6-9f23-b3191a3e8b16 |  | note | Inspection / Test Method - Visual
label | b8be660a-4183-5f70-adb4-54880a5047f1 |  | note | Record of Conformity - This ITP signed
label | 0bb53d1f-4628-5087-8301-1a6fdeb8b188 |  | note | WP
label | cff09d88-cc6b-5884-b13f-2e129e0fba68 |  | note | Responsibility - Project Engineer / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 2.3 - Proof Roll Report
label | eb3f6bcc-cbc5-5b32-8670-15bb3b250b4d |  | note | Frequency - Each Lot
label | 9458d9a4-5b16-50de-b30c-e1620f0f56e3 |  | note | Acceptance Criteria - A Proof roll report must be submitted to the Contract Administrator and Principal’s Design Consultant within 24 hours after completion of proof rolling.
label | b18392f6-3f8a-5ea2-8e38-93c490dfb6bd |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.10.3.3
label | f7b7ef3e-3d40-52e4-ab4d-67240808f117 |  | note | Inspection / Test Method - Aconex
label | b6320071-b29f-5fbf-8fea-7d56d117da07 |  | note | Record of Conformity - Proof Roll Report
label | 1948eeb6-d75c-5ee5-a3a0-098e7bfca89f |  | note | HP*
label | 67699d18-eba4-5eb9-a7c0-ad1e8d004489 |  | note | Responsibility - Project Engineer / Contract Administrator / Principal’s Design
checkpoint-status |  |  | checkpoint | 2.4 - Proof Roll Failure
label | 4ebac1b4-8e4c-5b3e-819c-3e58e12ffa51 |  | note | Frequency - Each Lot
label | c0dfae91-cfc5-5f18-b040-e801d20c1d92 |  | note | Acceptance Criteria - Should any area of the subgrade layer comply with the failure criteria in Table 5-5 or fail the proof roll, the Contractor must identify and record the extent of the failed area prior to proceeding with subsequent pavement layers.
label | 45092f5d-5d12-557a-a039-b08987cb4434 |  | note | AECOM-MAPMP 2.0 Spec. Cl. 5.10.3.2
label | 2a19cd82-ef80-5213-a002-712c767ee3ff |  | note | Verify
label | 2600abad-10e0-582c-8c8e-e82baccd0f6c |  | note | This ITP Signed
label | 1d2009a9-621d-5630-8992-98b90d918861 |  | note | Reference Documents - HP*
label | 644042e0-9be4-52a5-b0c8-5fda61ceeae3 |  | note | Inspection / Test Method - Project Engineer / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 2.5 - Spot levels on Subgrade
label | f4b4d8bb-1c38-597f-8fc8-a580dbb077f3 |  | note | Frequency - Each Lot
label | 26e93328-e6ef-51e7-906a-e10bc40ffc7e |  | note | Acceptance Criteria - The Contractor must take an as-built survey of the finished subgrade surface for the inclusion of the final as-built submission.
label | 380e84be-7fc1-507d-bc71-4b346df93002 |  | note | Upon completion of the sub-grade preparation, the Contractor shall obtain spot levels on the prepared surface in a 5m by 5m grid and including breaks in grading and edge of pavement areas. The spot levels shall be provided on a drawing showing the pavement outline, the prepared subgrade levels and indicate any potential levels that are out of the tolerance given tolerances -30mm,+0mm.
label | 82287a45-f6a2-5ccb-a1e7-5677ce618680 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.12.1 Cl 5.12.4 Cl 5.12.5 & Cl 5.13.5
label | 914c7e6f-9f59-52f3-b3d5-bc3bb13e1f71 |  | note | Inspection / Test Method - Survey Report
label | 2bfdc3ce-4e7e-5746-9342-ec1781392c60 |  | note | Record of Conformity - This ITP Signed / Survey Report
label | 507290f9-1aeb-5214-a22c-b3141784aa2f |  | note | IP / SCP
label | b0f8d4c5-3448-5b2f-a942-37411d57acf9 |  | note | Responsibility - Project Engineer
checkpoint-group |  |  | section | 3.0 Capping Layer Preparation – Expedient Works
checkpoint-status |  |  | checkpoint | 3.1 - Subgrade Preparation
label | d2859c63-79b8-5f00-a310-aec16fb6e91e |  | note | Frequency - Each Lot
label | 8dd9e0f7-2574-57ff-815b-6b6807c17e40 |  | note | Acceptance Criteria - The surface of the prepared in-situ material must be free from loose material, cobbles and boulders protruding and restored to design level where required.
label | e035fc4b-23e2-5ed5-abe2-ed6851c4e167 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.12.1
label | 32ff6d3f-aed0-5263-aa59-4f48322ba253 |  | note | Inspection / Test Method - Verify
label | 63d9382a-e5fb-5dcb-b088-db56d508db8f |  | note | Record of Conformity - This signed ITP
label | a9cbcb05-e96e-5946-8405-d8244da2e8fc |  | note | HP*
label | eca8341c-4432-58ec-a834-0132992df50d |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 3.2 - Compaction and Proof Roll
label | 6ace916c-1811-575a-bb3b-e3b6aab73411 |  | note | Frequency - Each Lot
label | 83e467f1-5650-59b1-b8fb-ee3a630fe87a |  | note | Acceptance Criteria - Compaction of the capping layer is verified through the completion of proof rolling as detailed in the WMS.
label | 31f89895-a9df-5978-89ec-4445c9290d8f |  | note | No compaction testing required to be undertaken.The compaction process and proof rolling is to occur simultaneously in the presence of the Principals Design Consultant.
label | 40159325-e2fd-5f67-994f-dabfee7f2f1a |  | note | Proof rolling configuration as follows:
label | b9ad953a-582c-51ea-bbc4-f7d6b96a1f6c |  | note | • 2-4 passes by 12T smooth drum roller on heavy vibration setting
label | 7c81f515-7a4b-55c4-ad40-dced7354cce0 |  | note | • 1-2 passes by 12T smooth drum roller on light vibration setting.
label | d38ac3c9-b389-577a-94ab-5e269f9e937b |  | note | • 1-2 passes by 27T multi wheel roller.
label | ee8eaf7d-aa31-5793-a325-71b8bcdc5ee9 |  | note | Proof rolling passes if it leaves no significant indentation marks on the surface and does not produce any visible permanent deformation in the in-situ material surface.
label | 73f384d5-da1e-5b63-bb93-b5f078af016f |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.10.2 & 5.10.3
label | 1b975a74-00b9-5134-9e83-fcd1c5e92b62 |  | note | Inspection / Test Method - Visual
label | ca22ee3e-ec80-5213-8dfa-368df9f4d787 |  | note | Record of Conformity - This ITP signed
label | c0c8f0eb-603b-5886-be74-d8ff1c58fc8d |  | note | WP
label | 590cf82d-8016-5b89-9490-34ba91cf719d |  | note | Responsibility - Project Engineer / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 3.3 - Proof Roll Report
label | 83d34f11-8093-537d-9932-c9e5bb190e82 |  | note | Frequency - Each Lot
label | 0e2a36fa-728b-5aa5-9030-549c4a3ef3e4 |  | note | Acceptance Criteria - A Proof roll report must be submitted to the Contract Administrator and Principal’s Design Consultant within 24 hours after completion of proof rolling.
label | ad367eb9-5bf5-5393-8937-074c3df730a3 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.10.3.3
label | cf8f68c1-3271-51e1-975c-fb4d327b5aa3 |  | note | Inspection / Test Method - Aconex
label | 93ca7461-b828-5120-890c-bd5bea834f9e |  | note | Record of Conformity - Proof Roll Report
label | 7cfcabb6-c220-51b0-aeef-2189251d3ef3 |  | note | HP*
label | ebf5354e-e265-5d35-9768-80ae819500d6 |  | note | Responsibility - Project Engineer / Contract Administrator / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 3.4 - Proof Roll Failure
label | 5e0259d0-8b70-502b-90a0-dfbf22bbfda2 |  | note | Frequency - Each Lot
label | 1f27d52d-3f90-5d8f-b96b-b02433700b8c |  | note | Acceptance Criteria - Should any area of the capping layer comply with the failure criteria in Table 5-5 the Contractor must identify and record the extent of the failed area prior to proceeding with subsequent pavement layers.
label | f876ed37-2d8a-5912-a9fa-0884c9326217 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.10.3.2
label | 84440ea2-f31f-5637-8bc8-427280b2a396 |  | note | Inspection / Test Method - Verify
label | 75c38c29-9fe0-5f2d-b178-3aa8ca46be1f |  | note | Record of Conformity - This ITP Signed
label | a0806855-65cc-5462-a803-2680b54adccc |  | note | HP*
label | 72fb7ea0-4d92-530c-a57d-f633589a2d9a |  | note | Responsibility - Project Engineer / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 3.5 - Spot levels on Capping Layer
label | e5261844-3254-5893-91d0-66965cca2c81 |  | note | Frequency - Each Lot
label | dc81b072-0e18-5e1a-8ac1-c7512831da17 |  | note | Acceptance Criteria - Upon completion of the capping layer, the Contractor shall obtain spot levels on the prepared surface in a 5 m by 5 m grid and including breaks in grading and edge of pavement areas.
label | ee7a35d3-f9c1-5b33-87e0-70a66438cf74 |  | note | The spot levels shall be provided on a drawing showing the pavement outline, the prepared subgrade levels and indicate any potential levels that are out of the tolerance given tolerances -25mm,+0mm.
label | 18348793-984c-51f5-bea7-a60795e76cb8 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.12.1 & Table 6-2 in Cl 6.5.2.5
label | 4d1031ef-1aa9-528e-83a8-7f9a52f809d5 |  | note | Inspection / Test Method - Survey Report
label | be55496b-7f2b-5554-b2c4-bbaeb6a98014 |  | note | Record of Conformity - This ITP Signed / Survey Report
label | 3470d87a-f89f-54dd-96d2-358676ef37fb |  | note | IP / SCP
label | 2e33a492-63ab-541a-acff-05701e985ab9 |  | note | Responsibility - Project Engineer
checkpoint-group |  |  | section | 4.0 Subgrade Preparation – Day Works
checkpoint-status |  |  | checkpoint | 4.1 - Excavation to Design Subgrade Level
label | 8be4dac7-62d0-5582-a526-70f3ec59f62d |  | note | Frequency - Each Lot
label | af5b3de4-afb1-541e-92bd-06f864b35aac |  | note | Acceptance Criteria - All in-situ material encountered within the extent of works, below the stripped surface level and existing pavements must be excavated as indicated on the drawings.
label | 79a92a1f-cec7-5238-ae00-597004cbf020 |  | note | The Contractor must preserve the existing pavement that is not to be demolished.
label | faf51d50-e5fc-5b64-9acd-f5ea02b5d5c5 |  | note | Reference Documents - AECOM-MAPMP 2.0 DP1 Spec. Cl 5.9
label | 6eb5c647-e98c-583a-901e-e47c466f170f |  | note | Inspection / Test Method - Visual Inspection
label | b9866821-f313-5b30-94b8-ccdaa0f05002 |  | note | Record of Conformity - This ITP signed
label | 0aaafd50-8569-5b3e-a35a-8ae1fde27951 |  | note | HP*
label | 779b9161-b86f-52e1-8aff-d190d792fa2a |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 4.2 - Proof Roll
label | b558eb67-f450-586b-96a6-3ed7ff1262bc |  | note | Frequency - Each Lot
label | ccd70c37-7911-59b6-9c8c-db6619eb7f01 |  | note | Acceptance Criteria - Proof rolling will commence upon completion of compaction.
label | 75c8bcb7-d30f-5cc1-89f1-99d4d891fde0 |  | note | Proof roll is to be conducted in a systematic manner that ensures uniform coverage across the entire area at a speed no greater than 6km/hr.
label | aa556594-e69f-5719-a777-4cd10c30ba88 |  | note | The proof roll will be conducted with a 12T smooth drum roller or a water cart and in the presence of the Principal’s Design Representative.
label | b1455e1a-2ebf-5c67-8271-991ac13bdb01 |  | note | Proof rolling passes if it leaves no significant indentation marks on the surface and does not produce any visible permanent deformation in the in-situ material surface.
label | 4ea4b836-3f0c-5e40-9de4-5094618acd5e |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.11.3
label | abb16318-cf9f-5d92-86b1-a428f04dcbc9 |  | note | Inspection / Test Method - Visual
label | b02dfc7e-e292-571d-a7b2-8398fb2b03d0 |  | note | Record of Conformity - This ITP signed
label | 8b4ca729-bedd-5e44-844a-2c66ecdc10d2 |  | note | WP
label | e21e0ec1-831f-5602-9055-bd38bc0ef78c |  | note | Responsibility - Project Engineer / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 4.3 - Proof Roll Report
label | c30a5c7a-cf0d-5871-a3f8-d5b7a9ca77e2 |  | note | Frequency - Each Lot
label | 77ba6092-f2e8-526d-912a-ed5a11b95d14 |  | note | Acceptance Criteria - A Proof roll report must be submitted to the Contract Administrator and Principal’s Design Consultant.
label | 361ae12e-126f-5bde-aff1-c4618221ce56 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.11.3.2 & 5.11.3.3
label | c83df08e-1097-594c-a3d8-62c1f3eab9ee |  | note | Inspection / Test Method - Aconex
label | ec710338-341d-5e0b-ae4e-0d546aa9dfbc |  | note | Record of Conformity - Proof Roll Report
label | 8dc091d0-651f-5eb6-9126-621136552d5e |  | note | HP
label | a9f72b1c-d1cf-5928-9df7-0ba54a03ca00 |  | note | Responsibility - Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Proof Roll Failure
label | bc43f9ac-3ab7-5b8b-8255-276289992581 |  | note | Frequency - Each Lot
label | fd45413d-64e0-5e8b-9084-ae96b446dcb8 |  | note | Acceptance Criteria - Should any area of the subgrade layer comply with the failure criteria in Table 5-5 the Contractor must identify and record the extent of the failed area. In-situ material that fails proof rolling must be removed and replaced with up to 300mm of capping layer material.
label | 649bce02-f39f-5a1a-b682-e1e52f47bf3d |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl. 5.11.4
label | 45479b82-2b96-50f9-94bc-16eb32920d46 |  | note | Inspection / Test Method - Verify
label | 1494a65e-02db-5e6b-8f48-6d357e67ff75 |  | note | Record of Conformity - This ITP Signed
label | ed3c1123-88a2-5b3b-a73f-c91d037a5022 |  | note | HP*
label | f615dc68-0c88-5c13-923a-434fbd994092 |  | note | Responsibility - Project Engineer / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 4.5 - Compaction Testing
label | 49931b89-1ea8-5e04-a560-43d63906ea6e |  | note | Frequency - Each Lot
label | 07d939e6-e39d-5242-9207-b6da056bd892 |  | note | Acceptance Criteria - The in-situ material must be compacted to;
label | da61c5cd-18e2-5b80-8f7f-d6798913a298 |  | note | • Characteristic density ratio ≥ 98% MDD (standard) compaction up to 300mm below design subgrade level
label | 0e1ee171-92d2-5a87-9164-c13412dc0108 |  | note | • Characteristic density ratio ≥ 98% MDD (standard) compaction for capping layer material used to replace unsuitable in-situ material
label | ac97829c-51c6-5807-917e-7271d0de9557 |  | note | The minimum testing frequency is as follows:
label | d7efa743-e024-5bd1-a219-b27389c882c2 |  | note | Up to 800m2 – 4 tests
label | 8aa1a59f-4520-52f9-b4e8-67d91316c45d |  | note | 800 – 3000m2 – 6 tests
label | 2ea3edc2-210e-58d5-88c0-0dfef29743b4 |  | note | Greater than 3000m2 – 1 test per 500m2
label | 2628faba-a43a-5b07-9f4c-75ccb7a3c9b9 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. cl 5.11.2.2 & cl.5.13.3.2
label | a3b3e6bd-3122-542a-bb50-73e82101b8e2 |  | note | Inspection / Test Method - Testing
label | 55cd74bc-1ce7-5394-9a83-c3f6357b057a |  | note | Record of Conformity - Test Results
label | aff15e0a-4e60-59b3-9f11-ea28735f278a |  | note | TP
label | 2b934be1-81ed-5499-9169-8b942463b1be |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 4.6 - Spot levels on Subgrade
label | 955bdf37-1c1e-5613-86b6-e395ac5ef68e |  | note | Frequency - Each Lot
label | 1433b412-6696-542a-9c4b-5e3389c90867 |  | note | Acceptance Criteria - The Contractor must take an as-built survey of the finished subgrade surface for the inclusion of the final as-built submission.
label | 38a07126-f415-511d-a488-320933bdc9f2 |  | note | Upon completion of the sub-grade preparation, the Contractor shall obtain spot levels on the prepared surface in a 5 m by 5 m grid and including breaks in grading and edge of pavement areas. The spot levels shall be provided on a drawing showing the pavement outline, the prepared subgrade levels and indicate any potential levels that are out of the tolerance given tolerances -30mm +0mm.
label | 58cda734-e5a8-513b-95cb-3f42997f14dc |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.12.1 Cl 5.12.4 Cl 5.12.5 & Cl 5.13.5
label | 6caabacb-803e-5cfd-9f02-897ad17beacb |  | note | Inspection / Test Method - Survey Report
label | 97ee29f8-0a7f-5a97-967a-da29385af61e |  | note | Record of Conformity - This ITP Signed / Survey Report
label | a1d1fe66-fbec-5a38-a999-6a25e7e67518 |  | note | IP / SCP
label | 836c8c12-c63d-5e52-b374-ec5936718aab |  | note | Responsibility - Project Engineer
checkpoint-group |  |  | section | 5.0 Capping Layer Preparation – Day Works
checkpoint-status |  |  | checkpoint | 5.1 - Subgrade Preparation
label | 3c5e8473-3c0f-562e-ac20-488bcda1dfcf |  | note | Frequency - Each Lot
label | 4db6f566-93f2-5c6f-8438-a95b49b88259 |  | note | Acceptance Criteria - The surface of the prepared in-situ material must be free from loose material, cobbles and boulders protruding and restore to design level where required.
label | 018dcb03-9143-553a-8b0a-f87851a82aa1 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.12.1
label | 60319266-372b-5e7c-8358-72e6318474fe |  | note | Inspection / Test Method - Verify
label | e88f22b2-5f7d-5ff8-aa67-d16a5e26ef95 |  | note | Record of Conformity - This signed ITP
label | 72a991ad-08ee-5485-8f77-8d6d39f54fdf |  | note | HP*
label | c82fa996-fd86-5253-9714-eeefdeda3621 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 5.2 - Proof Roll
label | 449241cb-ee68-589f-b2fa-899f609640ff |  | note | Frequency - Each Lot
label | 4b491053-1100-59c1-a148-cc5fbb732c4a |  | note | Acceptance Criteria - Proof rolling will commence upon completion of compaction.
label | e2a5da28-1290-5e33-884c-1945571b2445 |  | note | Proof roll is to be conducted in a systematic manner that ensures uniform coverage across the entire area at a speed no greater than 6km/hr.
label | c23b9da6-2013-5674-a93b-1b85fbd7b157 |  | note | The proof roll will be conducted with a 12T smooth drum roller or a water cart and in the presence of the Principal’s Design Representative.
label | a7f38ea7-3a6d-5e9e-bbc0-daa8463b077b |  | note | Proof rolling passes if it leaves no significant indentation marks on the surface and does not produce any visible permanent deformation in the in-situ material surface.
label | 00c7c99d-072c-5d25-99d7-78aee9b837b2 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.11.3
label | 5174db1f-4317-5191-b95b-b1b19c6d001e |  | note | Inspection / Test Method - Visual
label | 3d04b3fc-ec77-54e0-a6e0-7f5496d5f207 |  | note | Record of Conformity - This ITP signed
label | 582a1ede-49e2-5bac-9c2f-3a4292eb8866 |  | note | WP
label | 5fe2ada1-5141-57da-8d9e-621ed2a52bfe |  | note | Responsibility - Project Engineer / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 5.3 - Proof Roll Report
label | 4f8f9b0b-23e2-58fb-aacb-6c40fa66b5b9 |  | note | Frequency - Each Lot
label | ac889420-031e-5f14-ae45-e38cad71d6fb |  | note | Acceptance Criteria - A Proof roll report must be submitted to the Contract Administrator and Principal’s Design Consultant.
label | ca8e383d-67c7-5f67-b7aa-6f29df91ba87 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.11.3.2 & 5.11.3.3
label | 0986efd1-21df-5c95-b83d-a76aca051dca |  | note | Inspection / Test Method - Aconex
label | ccfa8c23-b278-589d-ac4d-900a7a6d2af4 |  | note | Record of Conformity - Proof Roll Report
label | 537b541d-22fc-5aa5-9ae2-1bc17d45c12e |  | note | HP
label | ebaf64b9-5fc8-50e3-b897-5811d38f1df9 |  | note | Responsibility - Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Proof Roll Failure
label | 9e23d773-7eac-5030-9ce5-16c0b255ffd7 |  | note | Frequency - Each Lot
label | ac0cf063-569f-55e6-b309-79529ef2d3f9 |  | note | Acceptance Criteria - Should any area of the capping layer comply with the failure criteria in Table 5-5 the Contractor must identify and record the extent of the failed area. Capping layer material that fails proof rolling must be removed and replaced.
label | b12ef0e2-73a4-5900-a781-f0e0992d5716 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. 5.10.3.2 & 5.11.4
label | 817dba25-be58-5780-a6f2-dcc972b3705c |  | note | Inspection / Test Method - Verify
label | 4c82bfd2-533a-5afe-b806-b3ff86659605 |  | note | Record of Conformity - This ITP Signed
label | 3345a408-6bb8-5588-8a21-57d5c86c98f5 |  | note | HP*
label | deaeb08b-86bf-55ac-8a9c-32b5f865ff57 |  | note | Responsibility - Project Engineer / Principal’s Design Consultant
checkpoint-status |  |  | checkpoint | 5.5 - Compaction Testing
label | 18de6a6d-59f1-53c4-9086-cd6e17435cc5 |  | note | Frequency - Each Lot
label | da77bade-eeb4-5290-9163-41aa337518da |  | note | Acceptance Criteria - The capping layer must be compacted to characteristic density ratio ≥ 98% MDD (standard compaction). The minimum testing frequency is as follows:
label | 4eea408c-04b5-5c19-af48-eed4fb606609 |  | note | Up to 800m2 – 4 tests
label | 1069e019-2fe0-58c3-bfdc-50b83f8b053a |  | note | 800 – 3000m2 – 6 tests
label | 811c84ec-eb2e-5d04-ab1c-d7100d9152b3 |  | note | Greater than 3000m2 – 1 per 500m2
label | 589491ec-54b8-514c-accc-9bacfeed82f4 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.11.2.3 & cl.15.13.3.2
label | 7b47fd1e-2b0a-59f4-865e-2b9f5189f871 |  | note | Inspection / Test Method - Testing
label | 3f8633d1-d5f2-5b23-9e8a-b8a8b4727719 |  | note | Record of Conformity - Test Results
label | 64ff3733-b643-5722-8c48-209b69e032fd |  | note | TP
label | ae3ab464-e33c-5a7f-b44f-575fa6180b1f |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 5.6 - Spot levels on Capping Layer
label | b86f4611-ea59-52b0-a5f9-8f5f3e959da1 |  | note | Frequency - Each Lot
label | b4a90637-e5df-5ebb-a400-73667fec0405 |  | note | Acceptance Criteria - Upon completion of the capping layer, the Contractor shall obtain spot levels on the prepared surface in a 5 m by 5 m grid and including breaks in grading and edge of pavement areas. The spot levels shall be provided on a drawing showing the pavement outline, the prepared subgrade levels and indicate any potential levels that are out of the tolerance given tolerances -25mm,+0mm.
label | 228f372b-202e-52d3-8cd0-1cb04f148771 |  | note | Reference Documents - AECOM-MAPMP 2.0 Spec. Cl 5.12.1 & Table 6-2 in Cl 6.5.2.5
label | 8c9465e1-2f51-58aa-bd1f-116c0c12b840 |  | note | Inspection / Test Method - Survey Report
label | 6fb9b62b-361b-5ac2-a588-7d7e1ffe0231 |  | note | Record of Conformity - This ITP Signed / Survey Report
label | 04f967b3-3c5a-5ab4-a1e5-dccc943c065b |  | note | IP / SCP
label | d990bf3e-e758-56b3-95d0-81e7f91bdb60 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 82bfbc2a-db7f-56a9-b49d-87bbd86e4345 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 57362fd8-2e36-5a65-9a82-fde4c9a6852e |  | textbox | Name:
text | 6cd9a6de-ca8a-5901-8b7c-1a8bf1764a8d |  | textbox | Position:
date | a5af3c84-623a-5116-b239-6cba5a3b41e2 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP022 – Native Grass Protection | itp |  |  |  | Yes | ITP022 – Native Grass Protection | bee085c5-ea93-43a1-80dd-a3e7f7dcecc7
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 97a5077d-1543-5714-b6d8-fe7d285c8a47 |  | note | Frequency - Prior to site establishment
label | 07900bea-ee78-50ea-8b27-5e033d9007b2 |  | note | Acceptance Criteria - Review whether a preliminary report has been completed for the project which will outline where the Significant native grasses are and what protection has been specified.
label | a83d0e72-23d5-57e1-b64b-1ef276cb719f |  | note | Reference Documents - Consultant reports
label | 2633dbae-6842-555b-b148-d5b68900c4e8 |  | note | Inspection/ Test Method - Visual inspection
label | 605a4a9b-4eae-5a3f-8f24-a9df901dcb15 |  | note | Record of conformity - This Signed ITP
label | 0cf75c13-b335-5146-bbd6-9dba0347d4b3 |  | note | HP*
label | d3376edf-d6d5-51ef-8a11-751a1841ecec |  | note | Responsibility - FH Project Engineer
label | 3ee6d271-1927-534d-bccb-515962c2b977 |  | note | Checked By
text | 104a7a08-16bb-5cc6-a6f9-ae6ffd73ff4b |  | textbox | Name
text | 292f60e4-046a-50c0-84db-04917ee3ad9d |  | textbox | Position
date | 7537d677-ddb1-5c8d-8283-00862dcee57d |  | date | Date
checkpoint-status |  |  | checkpoint | 1.2 - Check the Google Earth Mapping
label | 0c52afe2-1015-5eae-a74d-beb1efd09914 |  | note | Frequency - During site establishment
label | 9b2812b2-d002-5587-a28d-8247b328c9e7 |  | note | Acceptance Criteria - Review the Google Earth mapping which outlines the boundary of the native grasses at the time they were mapped.
label | 52bbb6b0-d7dc-52e9-85c5-47e684efcc15 |  | note | Reference Documents - Google Earth Mapping
label | bff35185-70ad-5d1e-813c-6c717c9e9e7a |  | note | Inspection/ Test Method - Visual inspection
label | 7c924f7a-330b-58ae-8607-5047bf331a52 |  | note | Record of conformity - This Signed ITP
label | dfbbccf8-448b-5071-9747-798658616f3c |  | note | HP*
label | 54475a94-532f-53ca-8ed7-3a4e758d1dc1 |  | note | Responsibility - FH Project Engineer
label | 73678c61-a0eb-51fe-b4b9-74de734f890b |  | note | Checked By
text | 7f2db4f6-71d3-5df8-9696-cf642447f6d1 |  | textbox | Name
text | 5870e086-ef0d-5088-b88d-4393a838866e |  | textbox | Position
date | cad23399-5222-5b97-865d-8ef8e60fed76 |  | date | Date
checkpoint-group |  |  | section | 3. Implementation of Controls to Protect the Native Grasses
checkpoint-status |  |  | checkpoint | 3.1 - Mark out the exact Significant Native Grass Boundary area
label | cad67f38-b0c5-56bd-9ca5-79539c289fad |  | note | Frequency - Prior to commencing any activity
label | 6df58813-4677-5544-a37f-426a50266bf1 |  | note | Acceptance Criteria - Work with the surveyor to mark out the Significant Native grass boundary. FH Project Engineer must verify the set out survey data file matches the ECP. Signage will be placed onto the bollards stating ‘Native Grass Boundary Area.’ NTGVVP Nationally Significant Grasses to protect within this area.
label | 2bdd86c0-705b-5967-a0a6-9feadba81641 |  | note | Reference Documents - CEMP & ECP
label | c1e2613f-408a-5bac-998a-09733ac1226e |  | note | Inspection/ Test Method - Inspect
label | 557c8d9d-cb38-5a96-a8fc-a019e71c05e3 |  | note | Record of conformity - This Signed ITP
label | 9dfd0a68-a3e0-5b7a-8cd8-e08a02ba5c62 |  | note | HP*
label | a533efbb-aaf6-5b19-9582-8196307e9fab |  | note | Responsibility - FH Project Engineer
label | 14f8c1b1-b43e-5ed2-a119-af3d073ec3e7 |  | note | Checked By
text | 2a9799f7-c5a1-5dfe-bb5f-ffa196183d7a |  | textbox | Name
text | 5e4fe02c-40d6-5a3a-a493-0db09100f466 |  | textbox | Position
date | 1fccc880-f7e5-594c-9ef3-e87f2b5021a1 |  | date | Date
checkpoint-status |  |  | checkpoint | 3.2 - Use temporary fencing and signage to block access to the Significant native grasses where we are working in close proximity.
label | 402a7e03-1ada-51fa-a19f-cc599cc2fc95 |  | note | Frequency - Prior to commencing any activity
label | 54f9a3cc-55d5-514e-b4be-280539a6ff37 |  | note | Acceptance Criteria - For works in close proximity to the native grasses, delineate the native grass boundary using temporary fencing or t-top bollards with signage stating, “Vegetation Protection – No Go Zone.” Where possible this fencing will be installed at a distance away from the actual native grass boundary to act as a ‘buffer zone’.
label | feb7c8a2-bb26-5788-a76f-6b58b681e8cc |  | note | Reference Documents - CEMP & ECP
label | 877326f5-590c-522e-b22e-6f4b1b86e942 |  | note | Inspection/ Test Method - Inspect
label | 77642930-b12d-5741-a462-4e2597d60101 |  | note | Record of conformity - This Signed ITP
label | bf7bc1d0-9ddd-5987-98cb-b5a77a8e17d7 |  | note | HP*
label | abbddda1-5441-5e46-8227-163635c06630 |  | note | Responsibility - FH Project Engineer
label | 12940442-87e3-5da2-821b-9977401e6a04 |  | note | Checked By
text | 47de9c16-ee36-5c1d-b78a-cbd2baeae213 |  | textbox | Name
text | c672030c-3a10-5351-b18f-a645385a7c2e |  | textbox | Position
date | fa4f8ae6-4b7d-58a7-8e5f-da098959bdd6 |  | date | Date
checkpoint-status |  |  | checkpoint | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area
label | d8587498-b935-5adf-a4a6-052dea72e5de |  | note | Frequency - Prior to commencing any activity
label | 02a853ee-bf64-52a0-84f7-8ab88e75bb56 |  | note | Acceptance Criteria - Project Engineer and Superintendent / Foreman to confirm the ECP requirements of native grass delineation have been met; and verify the delineation has been set up correctly using a GPS Rover.
label | b58c14e2-7c11-504b-8347-bddc87bc70dd |  | note | Reference Documents - CEMP & EMP
label | ac312a57-c49c-52d2-ae6e-6c2af4b0c432 |  | note | Inspection/ Test Method - Inspect
label | d7de184b-a5e4-53b2-b7c4-52ce75de9922 |  | note | Record of conformity - This signed ITP
label | 2545beab-33e9-5b63-8154-f9115b97fe25 |  | note | HP
label | 5582e6eb-21ea-5781-a463-bf962aaa363f |  | note | Responsibility - FH Project Engineer
label | 705e8d28-701e-5481-852f-83ef000cd273 |  | note | Checked By
text | 8dc47b1c-62f7-5b5e-85fd-f4a1e3a3bad8 |  | textbox | Name
text | 4ef76219-73bd-5e92-9747-f1337acc2ae4 |  | textbox | Position
date | abee31b2-fab1-59d1-8ec7-6aed144d180e |  | date | Date
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area
label | e71c5b37-8d23-5843-85da-5a753a2cccd4 |  | note | Frequency - Prior to commencing any activity
label | 5e658ff3-9e5d-56d3-92ad-3bf7e9d55784 |  | note | Reference Documents - CEMP & EMP
label | 57a14d08-493a-5616-bb9c-befe5e249be7 |  | note | Inspection/ Test Method - Inspect
label | c068ce28-1000-59e8-bb5d-c10a644dc496 |  | note | Record of conformity - This signed ITP
label | 2b6b532f-77cf-5daa-aae7-701203ec2c55 |  | note | HP
label | 4940bb04-68dd-5f9e-b340-ee979eb6e38d |  | note | Responsibility - Superintendent / Foreman
label | c8c023c0-2e08-503e-8cda-d611860b02f5 |  | note | Checked By
text | 21595c30-dd2e-515f-ab6f-481f77f9c67f |  | textbox | Name
text | ae022b2c-1d92-58c8-b9a9-5b0379ba3445 |  | textbox | Position
date | f0c8cedc-4314-586e-a571-3fa3df4bd8e8 |  | date | Date
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | 4. APAM Hold Point Release - Second Inspection
checkpoint-status |  |  | checkpoint | 4.1 - Release of Hold Point for Native grass Protection
label | 09bf67c7-6ef4-5b24-a209-5b24bc588072 |  | note | Frequency - Prior to commencing construction
label | d033f7bb-eb5f-50ec-b879-ab8348e7d63a |  | note | Acceptance Criteria - Arrange an APAM inspection to confirm that the native grasses are protected with the required temporary fencing or bollards and correct signage where required. All parties are to sign off on this Hold Point Release document
label | 70203a1d-25d4-5b0d-bfb5-118ad7e25306 |  | note | Reference Documents - CEMP and ECP
label | 2d23acaf-5f9c-504d-9113-5cf1b3c46364 |  | note | Inspection/ Test Method - Visual
label | 4be8b80d-2d41-509e-b055-a98fc65b1618 |  | note | Record of conformity - This Signed ITP
label | 81087161-28f4-5372-9cfc-743448975d13 |  | note | HP
label | cc81507c-68a1-51d6-b176-6c13f0a35326 |  | note | Responsibility - APAM Fulton Hogan Environmental Manager or Project Manager
label | 1e9068e1-ec65-5913-b662-c8bb64daa910 |  | note | Checked By
text | baa74f55-8e61-554c-8793-0df345478405 |  | textbox | FH Name
text | d2fe5c16-666c-518b-9193-df8b847dc406 |  | textbox | Position
date | d554d2f2-33fa-50fb-8fde-84079cd6a9ef |  | date | Date
label | 7bce95d3-9a68-54fa-9cf6-716562e74236 |  | note | Checked By
text | cc05224d-d160-5ad7-81f0-03ddf828ee38 |  | textbox | APAM Name
text | 02831059-8bce-5bc6-b7d6-6dfd7ea70cec |  | textbox | Position
date | 856af1c4-2f3b-57c3-a3ac-c4d1616523fe |  | date | Date
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | b5f14223-83af-5988-bce0-d2787254b3cb |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed above have been reviewed and implemented in accordance with the Construction Environmental Management Plan and conform in all respects with the requirements of the Contract.
label | 5667f712-4d35-5f56-91af-9cb8bd315874 |  | note | FH Environmental Team
label | cb65dbfa-783e-502d-a5cd-37d4090117d1 |  | note | Name: Tirrell Slaney
label | 06cd603c-7231-524f-8a38-6facc10e3546 |  | note | Position: Environment and Sustainability Advisor
date | 7806662f-c172-53cc-ac4c-d4c3352005b3 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7a0ecfb6-d6b4-55e1-ad9b-901c3b4be952 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed above have been reviewed and implemented in accordance with the Construction Environmental Management Plan and conform in all respects with the requirements of the Contract.
label | 11c383dd-47f0-53c0-9b48-eca5100071be |  | note | FH Environmental Team
label | 35255392-be4a-5269-9652-39a895f1334d |  | note | Name: Kevin Gatt
label | cde55f7d-26bc-5612-9275-cf00f9193c77 |  | note | Position: Project Manager
date | 4b6b9a95-0e7f-5210-b797-c28f85fe6836 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP004C – Asphalt Production (SP1 Patching Mix) | itp |  |  |  | Yes | ITP004C – Asphalt Production (SP1 Patching Mix) | c807ef7f-e7cd-40e8-bc04-6c7030035107
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - Submission of Production Plan
label | 81625cfd-0f82-53fc-9250-9e487648538a |  | note | Frequency - Prior to commencing works
label | 5f9c6f17-9879-5ddb-8df3-55e8a4a4ae23 |  | note | Acceptance Criteria - The production plan must demonstrate that the production capacity and the hot storage capacity of the mixing plant is sufficient to supply asphalt to complete the work undertaken within any work period on time.
label | df9dc1ef-f9ed-5b65-9776-488768d6e360 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.1
label | 009c6ee9-15d8-59cc-a71f-ebd1413f0801 |  | note | Inspection / Test Method - Verify
label | 66eb68f6-23bf-51b0-87af-ce1a76021905 |  | note | Record of conformity - Aconex Correspondence
label | 02f9b8ce-c407-5c5c-b3d7-52f2fbebdb0d |  | note | HP
label | c350fc8f-e001-5e6c-91a0-34d909b22324 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Checking of Weighting Devices and Certificates
label | d102802c-e938-58dd-b8d8-e719a324fd69 |  | note | Frequency - Prior to commencing works
label | d59fdb17-1bd8-5991-a5bb-a56e42155903 |  | note | Acceptance Criteria - The Contractor must supply details of current certification of weighing equipment including belt weighers and weighbridges to the Contract Administrator.
label | 7e328f6b-61ee-52ca-a35c-1a5dc53fef16 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.6
label | bed7bbaa-a89c-571d-841b-68641012a0ca |  | note | Inspection / Test Method - Verify
label | 47e1e790-dfa2-59e1-a795-e79f9de33b28 |  | note | Record of conformity - Aconex Correspondence
label | c5b80c9d-de34-5c0f-b628-90c73909aec3 |  | note | WP
label | 993bcda7-6d14-5976-af60-e81eba480d3b |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | 29575440-f6ce-5bdf-9360-6d08cc1656ae |  | note | Checked by: WP released as per DCWC Mgt- GCOR-001444
checkpoint-status |  |  | checkpoint | 1.3 - Calibration of the mixing plant
label | eefccf8d-fd77-56c4-b70f-e6debdbf1651 |  | note | Frequency - Prior to commencing works
label | e637bb73-7210-5cbf-8503-9226737ac2d9 |  | note | Acceptance Criteria - Calibrating all necessary devices and parameters at the mixing plant to achieve the “Job Mix”. Established plants must provide historical records of the asphalt production over the previous one (1) month to verify consistency.
label | 82bd95e9-103b-5e03-a21b-3b0f14503eaf |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.11
label | 76c9ac3e-1c0b-5f20-b66f-0255211c57bd |  | note | Inspection / Test Method - Verify
label | 0957a35a-2860-58ba-824d-85f98057c3c9 |  | note | Record of conformity - Historical records of asphalt production, This ITP signed
label | 72940f2c-745b-5814-a0ff-ad5f565d6fc9 |  | note | WP
label | d531ebcd-ff01-5eeb-8123-e09266187180 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | 37f268fe-e902-5f7b-b8af-0dff7fe2e55c |  | note | Checked by: WP released as per DCWC Mgt- GCOR-001444
checkpoint-status |  |  | checkpoint | 1.4 - Aggregate Reference Samples
label | a94c8c0c-352e-58ee-b08c-1c3c0ab817ae |  | note | Frequency - Prior to commencing works
label | a1a64dcc-4ae5-52ff-91e1-ea56bab10956 |  | note | Acceptance Criteria - The Reference Samples must be divided into two representative portions, with one being held by the Contractor and the second portion by the Principal’s Design Consultant until completion of the Works.
label | a4aeca05-7c6f-58ef-99b4-f921dc0b10a0 |  | note | Minimum quantities for each aggregate fraction:
label | 844be67a-2642-5e1d-a220-91cb8e0eda87 |  | note | ○ 14mm: 50kg 10mm: 40kg 7mm: 30kg Dust: 20kg
label | ea815897-c733-596d-8767-fdae4cdf9b92 |  | note | ○ Sand: 20kg
label | 868c03ea-a28d-5509-bfa2-1623b5448980 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.16.2, Table 14-17
label | 1e49f0d2-5e63-5f59-b20a-a3b90329418d |  | note | Inspection / Test Method - Verify
label | 404f9cca-f22d-5ef5-9a1c-9640a6c5b43e |  | note | Record of conformity - Aconex Correspondence
label | 86dab30d-ae2f-5c7c-afc8-d52ae163063d |  | note | HP
label | 2481402e-8f6c-5f11-9784-ab0765c09690 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Submission and review of mix design
label | f02a9045-eb87-579f-b334-375927a91b4d |  | note | Frequency - Prior to commencing works
label | 1b4c95e5-e001-55f2-8033-c327d3dc3c7e |  | note | Acceptance Criteria - Submission and review of a mix design report detailing the mix which meets the requirements of the specification.
label | 1d36d694-3490-540d-b245-281ef64f9544 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.11.4
label | cfc2f66d-f2ec-5d37-bd3e-cec76bfdf5e7 |  | note | Inspection / Test Method - Verify
label | f2cac99e-f259-5609-b924-cf3ecb1d25fa |  | note | Record of conformity - Aconex Correspondence
label | 4d402c3c-ec89-5b1a-aef6-77ddee61785e |  | note | HP
label | 25ae4ba6-fa9f-57c0-afbd-6db9b962a140 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | e162b2be-6481-5a09-96fd-10d521bcf6e8 |  | note | Checked by: HP released as per DCWC Mgt- GCOR-001429
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Production Trial
label | b60542bb-53ac-5f0c-a1c6-9e9249999f65 |  | note | Frequency - Prior to commencing construction trial
label | f36a3fc2-a3bd-5b58-978f-fc1d98b7e73d |  | note | Acceptance Criteria - Successful trial of asphalt production with the mixing plant where the asphalt produced shows that the mix complies to the specification requirements.
label | 27e2509f-c564-57ce-a51d-274996974811 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.12.1
label | 3ed01ce4-6b6d-50d2-97a6-e3a734b982f3 |  | note | Inspection / Test Method - Verify
label | 563d29e1-78dd-5a11-91ea-69bdbd650c83 |  | note | Record of conformity - Aconex Correspondence
label | 29e895f2-89e4-526c-b35d-bfaa3755e537 |  | note | HP
label | 9a632e6f-1c6f-5cee-9abc-cac546a2c91e |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | 50c33d44-00f8-5e3f-a084-8141cf672392 |  | note | HP released as per DCWC Mgt- GCOR-001429
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Construction Trial
label | b059e4eb-791c-5bf6-ba23-43e73aee6ebb |  | note | Frequency - Prior to commencing works
label | 31b0ae67-06d1-566c-8923-e3a28e6207df |  | note | Acceptance Criteria - The Contractor must subject all the placing, compaction and finishing equipment and operating and supervisory personnel proposed for use on the Works to a trial using the construction procedures proposed for the Work.
label | 1ef80d53-02bc-5b74-b975-1fc8318c48eb |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.12.3
label | 1e3e3a9d-b996-55f2-8c5b-4b831ec8e7e1 |  | note | Inspection / Test Method - Verify
label | c6219779-1005-5844-86d3-4d171c2c0f1b |  | note | Record of conformity - Aconex Correspondence
label | 8a74a5f6-3a65-5d6f-b91c-04fa14fb0f36 |  | note | HP
label | 88b4ff53-6436-513e-b8db-1bc0c96a41e9 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | 403ec2f3-d27c-56ef-ad35-796fa2f8ed23 |  | note | Checked by: HP released as per DCWC Mgt- GCOR-001429
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Production and Construction Trial Report
label | 0bf6d083-87eb-5d6b-a8ee-74b56d614835 |  | note | Frequency - Prior to commencing works
label | 6e5ad208-f326-5d5b-9b41-80233bae743f |  | note | Acceptance Criteria - The Contractor must provide the Contract Administrator with a Production and Construction Trial Report detailing the results of both production and construction trials as well as all compliance testing.
label | 60d15a85-7fc8-5d87-8ea6-e144e2bcf0a8 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.12.5
label | e9dd361c-f98f-5606-ad10-a58aad80aead |  | note | Inspection / Test Method - Verify
label | 57835a80-1cb7-5665-8a71-23ecb5053145 |  | note | Record of conformity - Aconex Correspondence
label | beeb46d3-2089-5380-a4ba-c0fff900eaee |  | note | HP
label | 5757db06-3aca-52e0-aa04-73c167b64882 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | 2a324bc0-7b06-501f-ac76-e0a35114c248 |  | note | Checked by: HP released as per DCWC Mgt- GCOR-001429
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.9 - Nomination of Job Mix
label | 2d4c1dda-7075-5fed-9c5f-16b3a8aced0a |  | note | Frequency - Prior to commencing works
label | 9d99c8c7-4748-57d1-8985-361994a510ba |  | note | Acceptance Criteria - The Contractor must issue an updated asphalt mix design report with the details of the Job Mixture within 3 working days after completion of the construction trial.
label | ec9e5157-b8bd-5545-8b7b-933c5329ebd0 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.11.6
label | c1534b67-dbd2-506a-81a3-ba8b913ef506 |  | note | Inspection / Test Method - Verify
label | 5198340e-e02d-5644-b241-ae083d841973 |  | note | Record of conformity - Aconex Correspondence
label | 36874eb8-b99e-5cda-a499-f6cef4a2df2c |  | note | HP
label | 9cb7ab85-ed9b-5e03-a558-6587e19a08ff |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
label | 3f3f62a3-f155-57fb-ac9e-e4d9a94fdbc9 |  | note | Checked by: HP released as per DCWC Mgt- GCOR-001429
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Coarse Aggregates Material Properties – Initial Testing
checkpoint-status |  |  | checkpoint | 2.1 - Particle Density
label | 9763e131-ecaa-5cce-881a-345197185440 |  | note | Frequency - Initial
label | 43725630-ec7f-59e3-b44c-2ed4ad416bc7 |  | note | Acceptance Criteria - Not less than 2300 kg/m3
label | eb38b3d0-be48-56f9-96a7-44a463ba0323 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | 470a5249-0a91-5af2-9035-ae00055cfb2b |  | note | Inspection / Test Method - AS 1141.6.1
label | 197e6bc1-2e93-5fc9-966f-a928a2b37860 |  | note | Record of conformity - NATA - accredited test certificate
label | 191842b2-09df-5334-860c-93576756f67d |  | note | TP
label | 41d0eeb3-6f6f-54c8-8766-ca8dca17a198 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.2 - Water Absorption
label | f91b4e74-0b9f-5c80-9af0-ad2d96c34010 |  | note | Frequency - Initial
label | e723ece7-8330-598d-9f63-282edb9cdd7c |  | note | Acceptance Criteria - Not more than 2.0%
label | c86b2414-160d-507c-9dd4-597f05d59069 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | b528807f-fdc5-51a8-a96a-d04458ed690a |  | note | Inspection / Test Method - AS 1141.6.1
label | 17c4fada-31da-5cf2-8655-630ee24fe74a |  | note | Record of conformity - NATA - accredited test certificate
label | ed6c61f9-3453-57fd-8478-36fa1de59b20 |  | note | TP
label | 787a0d7d-9db7-5761-af99-44312fa54212 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.3 - Material Finer than 0.075mm in Aggregates (by washing)
label | 2bdf3923-9a42-5dba-bdfd-a2da6a7dd722 |  | note | Frequency - Initial
label | bc5213c9-ee60-5184-8fe4-21c85232b930 |  | note | Acceptance Criteria - Not more than 2.0%
label | d6fa123b-8c31-59e8-834d-98965ce537bf |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | 917c995d-436a-5667-9239-18710b5c89cb |  | note | Inspection / Test Method - AS1141.11.1
label | f16039ad-5e7f-5354-8b74-a2ca491fabbc |  | note | Record of conformity - NATA - accredited test certificate
label | b3a98f3b-009b-534d-9fd6-3477cbe9b215 |  | note | TP
label | cac39947-abbd-52aa-aaed-986fd599ee52 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.4 - Particle Shape by Proportional Calliper (using a 3:1 ratio)
label | 2daa90a2-b98c-5ef8-b53e-92bd217ed0cf |  | note | Frequency - Initial
label | cc9a2f00-395f-5e24-be94-e395b7ab8ed6 |  | note | Acceptance Criteria - Not more than 5.0% of misshapen particles
label | f03d6069-63db-580a-83f4-5cecdc180bac |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | df77fde9-437a-59fe-91ff-d3ca1b237db4 |  | note | Inspection / Test Method - AS1141.14
label | 28784802-6355-5e4d-9461-9883087bcd09 |  | note | Record of conformity - NATA - accredited test certificate
label | 0db12345-16e6-576b-bdcd-fb8c1d7476bf |  | note | TP
label | e09081f5-8463-5590-8da1-0e83965d2e1e |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.5 - Flakiness Index (nominal 10 mm and larger aggregate)
label | 21e615b9-bde6-5677-b494-c11287a74d47 |  | note | Frequency - Initial
label | b062c654-d8e7-5b58-8022-a33c9cee70e5 |  | note | Acceptance Criteria - Maximum 25%
label | 66818a73-b861-5a94-9295-05b213ec9127 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | 86c4d63e-2060-593f-bccd-e1bec00b0032 |  | note | Inspection / Test Method - AS 1141.15
label | d2771960-ee67-5e71-9ba7-9ed06e132cd8 |  | note | Record of conformity - NATA - accredited test certificate
label | 07170e4a-88f5-543d-9e81-fd2a94522f69 |  | note | TP
label | 31577226-d489-5975-8013-336b50d3b140 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.6 - Los Angeles Abrasion
label | c4ee085b-136c-5a4a-b5e4-01c4dd33ce92 |  | note | Frequency - Initial
label | 485acf76-8b4d-53ce-bf83-6c13a5365653 |  | note | Acceptance Criteria - Not more than 25% loss (B or K Test Grading)
label | 8619a19d-9f74-565a-9c34-047263e3f421 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | d71158ee-923c-58c5-bc2d-ca4d431f6b29 |  | note | Inspection / Test Method - AS 1141.23
label | bf0dce15-2861-5e52-8202-9139df9bec0e |  | note | Record of conformity - NATA - accredited test certificate
label | 52247e2f-43d5-576f-91b8-b8964bd32bc4 |  | note | TP
label | c8bed744-a1dd-5f30-98a8-f776cde6d2e0 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.7 - Soundness (using Sodium Sulphate)
label | e739a7e9-4b92-5f1d-9537-89f9db17b235 |  | note | Frequency - Initial
label | a24d4ea6-2f49-5b0c-b7e0-185a9195d577 |  | note | Acceptance Criteria - Not more than 3% weighted loss
label | 856e918a-83db-5ab0-a577-993bf3bac3dd |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | 0ecf6ba7-ce69-51be-a208-12cb9c58bc16 |  | note | Inspection / Test Method - AS 1141.24
label | c69a56de-26e4-5d5a-bad5-e37ccf9ba13a |  | note | Record of conformity - NATA - accredited test certificate
label | f1ef3c04-070b-59f8-bdba-06d6f4a3a6a8 |  | note | TP
label | 183df11f-7fec-5fe7-9786-5aa7dc00e942 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.8 - Wet Strength
label | 1bab3295-af15-567e-96d9-fdacdb24a849 |  | note | Frequency - Initial
label | fb6cfc11-0496-5d64-aaf6-c927db16df11 |  | note | Acceptance Criteria - Not less than 180kN
label | 4ce97459-1920-5f9e-85a1-690fec985d45 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | 42eb4e38-2ef7-583b-9932-f57dddba5eaf |  | note | Inspection / Test Method - AS 1141.22
label | dcdd3b39-7a51-5333-9d92-797214d42156 |  | note | Record of conformity - NATA - accredited test certificate
label | 2ee943e6-c8e8-5918-8776-68014230fede |  | note | TP
label | 30fae827-f6dd-5736-82d9-659080269b12 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.9 - Wet / Dry Strength Variation
label | 863d6e37-2b54-5a05-b6aa-00eedec21b04 |  | note | Frequency - Initial
label | 02222fc3-98d8-528f-b4af-895a399e9aff |  | note | Acceptance Criteria - Not more than 25%
label | b34c2a02-25d0-5747-9534-8bf6d182f8e5 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | afa88abe-36c7-5d1b-a55b-f0e99111992e |  | note | Inspection / Test Method - AS 1141.22
label | 2448bf5b-a66c-5008-b25f-f1920e1bed22 |  | note | Record of conformity - NATA - accredited test certificate
label | 9dd98517-b38c-5ec8-a9d5-1736c2e3e548 |  | note | TP
label | 73e6d8ad-b51c-5fc6-b02a-2f83f054fad9 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.10 - Secondary Mineral Content
label | 59b16a92-73db-5f22-bc16-259b94f19fa0 |  | note | Frequency - Initial
label | d879006c-9069-55d8-b968-c809b541656e |  | note | Acceptance Criteria - Not more than 20% (Basic rock types only)
label | 6523fc22-8bb5-5844-84d9-56319770dca3 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | b6041dc3-6028-57e5-bb29-b5b27603f5b5 |  | note | Inspection / Test Method - AS 1141.26
label | fc6421aa-a4d5-5a0b-9fee-3dd39cfb437d |  | note | Record of conformity - NATA - accredited test certificate
label | aa1aa2ed-9e19-58a2-8864-68e99c542770 |  | note | TP
label | efd59815-278c-5fc3-927a-ef866fadf028 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.11 - Friable particles
label | 075572e3-78fc-5dbf-a364-d97b0405362a |  | note | Frequency - Initial
label | 31739797-8776-5c8a-9213-e9db740f7d0e |  | note | Acceptance Criteria - Not more than 0.2%
label | eeff57d7-408b-5f49-9225-4df98cdd35c2 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | 0b88183b-de3e-5278-a6a4-0db56a412d99 |  | note | Inspection / Test Method - AS 1141.32
label | 63f1cd33-2ce3-5b9b-be17-d34fd0c3bab6 |  | note | Record of conformity - NATA - accredited test certificate
label | f6a0244d-2eca-5b26-811d-1388a2521529 |  | note | TP
label | a7ef456d-04e0-5800-ad3f-b92b3c355ff6 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 2.12 - Polished Aggregate Friction Value
label | 93c9f4e1-32ef-5b07-9434-da30e4d38e5f |  | note | Frequency - Initial
label | 3a5199a6-faf9-5e44-bc59-ea2c763e0de4 |  | note | Acceptance Criteria - Not less than 48
label | 78d02086-7ea5-552b-81ad-aa863d28fc96 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.2, Table 14-1
label | 186d6672-92ed-500f-a808-cc3bd3400eda |  | note | Inspection / Test Method - AS 1141.41
label | 1266f417-923a-5102-be45-6558ac7a98a2 |  | note | Record of conformity - VicRoads Assigned Value
label | c2f68744-10ba-5317-9d98-00086c8b4b6d |  | note | TP
label | 67e9de6a-f57b-5b3e-8625-2d36e6ce7180 |  | note | Responsibility - Laboratory Technician
checkpoint-group |  |  | section | 3. Coarse Aggregates Material Properties – Ongoing Production Testing
checkpoint-status |  |  | checkpoint | 3.1 - Particle Size Distribution
label | 89062ddf-0db9-529e-b6fd-6bdcc79f3c64 |  | note | Frequency - 1 per 500 tonnes aggregate
label | 352daf02-47ba-5c86-a381-958836f3036c |  | note | Acceptance Criteria - To be reported
label | 619db517-cbb6-5ca5-b46e-3b80db0d447b |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | 7e5be1aa-4f5c-54e5-9de0-88587bd14b36 |  | note | Inspection / Test Method - AS1141.11.1
label | f356500d-a9ca-5cce-b02a-76556fd993b7 |  | note | Record of conformity - NATA - accredited test certificate
label | ab95205f-c9b4-5814-8fb4-bca02bbe2ffc |  | note | TP
label | f8078b5b-509c-5c7e-bd5b-72a75ff4711c |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 3.2 - Apparent Particle Density
label | 06a3cb45-6a72-529e-9a6b-8e6cbe402b6f |  | note | Frequency - 1 per 2000 tonnes aggregate
label | 5f90c6d1-f97f-5827-9d16-c5c7b4db4455 |  | note | Acceptance Criteria - Not less than 2300 kg/m3
label | 3b46b035-6351-5f0b-a4cf-68f96de4c63a |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | 2007d2ec-4f2d-5c03-ae02-3f8a6018f664 |  | note | Inspection / Test Method - AS 1141.6.1
label | 9c1701da-2a2d-5cb3-b6be-fc48785fba83 |  | note | Record of conformity - NATA - accredited test certificate
label | 26713ec5-a2b4-5f70-bf04-6afa629b0d40 |  | note | TP
label | 2ee6c8ba-4810-5802-b9d1-63def9fce091 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 3.3 - Flakiness Index (nominal 10 mm and larger aggregate)
label | b1085ed0-cbc2-58ed-baa5-8660cffd66bf |  | note | Frequency - 1 per 1000 tonnes aggregate
label | d310664a-748e-5e53-bc9d-53222935c349 |  | note | Acceptance Criteria - Maximum 25%
label | 3ff0e8c9-f872-5af9-8553-030034b4a93f |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | 47d7a23c-9e32-5df8-84cc-27307e1b3904 |  | note | Inspection / Test Method - AS 1141.15
label | 801b40ee-178f-5a0c-8c4f-60d22bb1c010 |  | note | Record of conformity - NATA - accredited test certificate
label | f12a69a2-110c-5679-a3c0-2ea8e98ffd4b |  | note | TP
label | 9cce7f77-02ed-5503-9202-24db69f7b431 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 3.4 - Wet Strength
label | 8bccf511-0d9c-520a-9c84-1af4951c7998 |  | note | Frequency - 1 per 2500 tonnes aggregate
label | d6407c5f-79bc-59f5-9155-0d3930d08275 |  | note | Acceptance Criteria - Not less than 180kN
label | 1877dae6-c865-5130-a1c3-e0c0f236c463 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | dc8386f1-5833-5f1f-bb20-1f28ae1ee638 |  | note | Inspection / Test Method - AS 1141.22
label | a03131ec-83d5-5204-b791-8310184e655d |  | note | Record of conformity - NATA - accredited test certificate
label | 6e78763a-6263-51ea-b4f4-929d95d0b389 |  | note | TP
label | ba316cd1-3e3a-5126-b112-f1b4d7ee5c2b |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 3.5 - Weak/Friable particles
label | 6546661e-e61e-5b1d-b33c-32f9587a9ed2 |  | note | Frequency - 1 per 1000 tonnes aggregate
label | 74817d27-5e34-557f-88a8-89cbb8bea401 |  | note | Acceptance Criteria - Not more than 0.2%
label | 7ae80681-f726-5084-88cd-10902bc503d9 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | e3b89b4e-7e5e-5b92-8bcc-795618edf6b9 |  | note | Inspection / Test Method - AS 1141.32
label | 4f789d9f-f5c4-5551-b8ce-46593b44f8fc |  | note | Record of conformity - NATA - accredited test certificate
label | 0e59248d-0d5a-59ac-839b-9702eed27e5b |  | note | TP
label | aa5395b3-22cc-50bd-abf1-1e2e6b344021 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 3.6 - Unsound Stone Content by Visual Assessment
label | c8ec9720-16ba-539e-9223-0b12e18be594 |  | note | Frequency - 1 per 5000 tonnes aggregate
label | 39170db1-a150-5175-8110-cc6b36c97bc5 |  | note | Acceptance Criteria - To be reported
label | 7664311d-ecea-5014-92d6-62f5801cfef4 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.1 Table 14-18
label | 5e9e30c3-1bf1-555d-93e1-8fd7ac51c046 |  | note | Inspection / Test Method - RC 372.01
label | a52e63a7-94ab-5d15-b4dd-6af6b6935248 |  | note | Record of conformity - NATA - accredited test certificate
label | 333ea42e-1f0f-522e-809f-9fb2350ad700 |  | note | TP
label | 537f70aa-0ef0-52fa-9fb6-13953884e366 |  | note | Responsibility - Laboratory Technician
checkpoint-group |  |  | section | 4. Fine Aggregates Material Properties – Initial Testing
checkpoint-status |  |  | checkpoint | 4.1 - Particle Density
label | 17cf9fbd-cb37-5aa9-8408-5d5067da5455 |  | note | Frequency - Initial
label | fe398978-468c-521c-bcfe-35e7a213cbab |  | note | Acceptance Criteria - Not less than 2300kg/m3
label | a3c8451a-ee9a-5731-a83c-86b6b3c598e8 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | 967bae69-ce9f-58f9-9289-211ede9941ac |  | note | Inspection / Test Method - AS 1141.5
label | e8bed7d8-c5ae-59e6-a588-00e645c1c162 |  | note | Record of conformity - NATA - accredited test certificate
label | 4bc9e57d-15d8-5eab-8ad2-a9f0c855f57b |  | note | TP
label | 2d910e30-ae24-5b0b-9b81-8cd0be7eb798 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 4.2 - Water Absorption
label | ec9b57ac-fbec-5a7a-9360-8138b6ac83ca |  | note | Frequency - Initial
label | 0deee4b6-7750-58db-866e-2d8e804f2e6d |  | note | Acceptance Criteria - Not more than 2.5% (crushed aggregate), Not more than 2.0% (uncrushed aggregate)
label | 9194a2cb-0ac2-5cb4-86f4-ccd1249baa0a |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | 926e1683-c8fa-5064-b59b-7851c2ec8f96 |  | note | Inspection / Test Method - AS 1141.5
label | 4633db98-3c1c-5a40-9793-4fdb385ceef3 |  | note | Record of conformity - NATA - accredited test certificate
label | b07da71d-dc68-540f-8b9c-53a94600fecc |  | note | TP
label | 65e1b78d-0a46-5c03-b983-5efbcadca2a9 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 4.3 - Soundness (using Sodium Sulphate)
label | d0b0488b-46f4-5731-9797-e76dcb91ad4c |  | note | Frequency - Initial
label | ffb2bb78-e765-543b-9405-f4b32d174aa7 |  | note | Acceptance Criteria - Not more than 3% for any fraction
label | 0311d71a-8956-57dc-9ed2-16d4ce392960 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | effa9361-be31-5d76-ae2b-59901c7d43d8 |  | note | Inspection / Test Method - AS 1141.24
label | 21dca40f-b97e-5f1c-9a95-7c8d2d38f0a6 |  | note | Record of conformity - NATA - accredited test certificate
label | 0aa348d0-dd80-5d37-a515-8b32e383442b |  | note | TP
label | 73025155-2210-50bc-a5c7-0f52b3b5375f |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 4.4 - Degradation Factor (Note: only applicable to dust)
label | 8aa46df3-32a6-57a5-8f93-7c06ec075023 |  | note | Frequency - Initial
label | 71fca59b-c875-5f1a-9096-c8c6c7508275 |  | note | Acceptance Criteria - Not less than 60
label | 829a4b0a-7c59-5075-b3d0-7c9a6179f645 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | 5fb0a8e3-a244-553d-b12a-c3a4c72bd302 |  | note | Inspection / Test Method - AS 1141.25.3
label | 47cf2107-89c0-5279-90ce-9323d7e24034 |  | note | Record of conformity - NATA - accredited test certificate
label | b83e3b72-1236-5998-a640-c2081c9c25df |  | note | TP
label | 9f9bc54a-d9eb-5280-8d49-e5fa6402ca0e |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 4.5 - Plasticity Index
label | d0958992-d614-58d7-9b15-cbf6bdb45c9b |  | note | Frequency - Initial
label | 03ee6a7c-5bc5-5e34-b69b-0a85674999a4 |  | note | Acceptance Criteria - Non-Plastic
label | f341bc7b-3832-5975-9f23-dd0e4b439bed |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | 430ec56c-ca3c-5ce6-aa00-02ec2d67a390 |  | note | Inspection / Test Method - AS 1289.3.3.1 (wet preparation)
label | 0c3ad9ef-2d24-598a-918a-06920426a319 |  | note | Record of conformity - NATA - accredited test certificate
label | 030cbd8d-a0bd-550f-9392-1acd9882d449 |  | note | TP
label | 4ce8c683-d32b-5408-a1b7-563a7a91d6d7 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 4.6 - Linear Shrinkage
label | e45d6b9b-3af7-560e-aeea-6ff5adbd3b0a |  | note | Frequency - Initial
label | a8ec4a67-1f97-5e44-a67b-bc18c3722f77 |  | note | Acceptance Criteria - Not more than 1%
label | a9feea11-a535-5814-b159-6e3fb94c246f |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | 498c71f1-9a3c-5adb-a3d8-ef42b766affe |  | note | Inspection / Test Method - AS 1289.3.4.1 (wet preparation)
label | 9088857a-235b-5d06-a798-98e89dc03422 |  | note | Record of conformity - NATA - accredited test certificate
label | e477ce0c-2834-59ab-8682-89fc24ac9151 |  | note | TP
label | e781271a-a364-52ea-ad2d-923c812a9fef |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 4.7 - Methylene Blue Value (Crushed aggregate only)
label | efa1d95a-969d-5325-bda1-aefc1feb3d57 |  | note | Frequency - Initial
label | 9b2c1cbd-dfe5-5193-8474-484e9d8b5481 |  | note | Acceptance Criteria - Not more than 5mg/gram
label | b8be2c21-4327-5c61-8a57-73bb13eb38b3 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | 9f74794e-f3fd-5aa9-8ddc-f56e12d98428 |  | note | Inspection / Test Method - AS 1141.66
label | 5ba96400-7dd1-543b-93e9-d653ee26ad82 |  | note | Record of conformity - NATA - accredited test certificate
label | b9b44657-4e7f-5957-9062-bb74101c6f6f |  | note | TP
label | 7ec83377-4d73-58c4-b3d9-fb2e3a84e492 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 4.8 - Sand Equivalent (natural sands)
label | 66a0789f-c5de-5d47-bed4-9ad54a84f401 |  | note | Frequency - Initial
label | 53376e59-e625-591c-8f39-6b4d5e65d87e |  | note | Acceptance Criteria - Not less than 45
label | fcc690b4-7928-5446-9d12-3bd53661674d |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | 78c37647-e1e4-5e91-86b2-239a283b8a9b |  | note | Inspection / Test Method - AS 1289.3.7.1
label | cc3ce48a-87d8-5ef7-be69-9fa981cc586d |  | note | Record of conformity - NATA - accredited test certificate
label | 2be10b61-0e32-5237-9897-940028b64229 |  | note | TP
label | eb294a80-221d-55f1-a580-836d8af01c44 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 4.9 - Material Finer than 0.075mm in Aggregates
label | aedec981-70d3-55a4-8747-5aff186afc00 |  | note | Frequency - Initial
label | 97c2ffa4-ef51-52bb-bab3-64019772d6eb |  | note | Acceptance Criteria - Not more than 20%
label | 93eb1229-3de8-5eac-99dd-0cd53f8e2c2d |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-2
label | 031fa203-d24b-581c-b086-a9138de3c106 |  | note | Inspection / Test Method - AS 1141.11.1
label | 6871dcae-bdde-5dc7-b78c-c70285ec5e9a |  | note | Record of conformity - NATA - accredited test certificate
label | 9f1b705f-2134-57c0-b930-d6371b3579f0 |  | note | TP
label | d29104bc-1361-5b3d-bf8f-b31e3dd80f6e |  | note | Responsibility - Laboratory Technician
checkpoint-group |  |  | section | 5. Fine Aggregates Material Properties – Ongoing Production Testing
checkpoint-status |  |  | checkpoint | 5.1 - Particle Size Distribution
label | 510f1d6e-f4e5-5be3-ad38-62d4ef4c41c9 |  | note | Frequency - 1 per 500 tonnes aggregate
label | c2e6db8e-5ec4-590a-82b6-0368f3666756 |  | note | Acceptance Criteria - To be reported
label | b4de9b28-efd3-569b-82ea-41680fc9b356 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-19
label | dd7ede4f-6822-54cc-8ab5-98502831b1da |  | note | Inspection / Test Method - AS1141.11.1
label | e1f49612-f868-5e2b-b6d6-8422b9eb48ec |  | note | Record of conformity - NATA - accredited test certificate
label | 4aa257bf-f315-52f0-920c-f7265a1174e5 |  | note | TP
label | 903d1310-9c0c-5c40-a468-e1ce4a23ea12 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 5.2 - Plasticity Index
label | 1be43c25-da30-56a8-8d97-1b5137e0e4b5 |  | note | Frequency - 1 per 1000 tonnes aggregate
label | 8b2bf1a8-d223-5006-9031-e7ed71b7dc53 |  | note | Acceptance Criteria - Non-Plastic
label | 6386b908-64ff-519f-a2cd-286886cef69c |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-19
label | ae5fa2df-d66c-5cbc-98b8-85079c628f17 |  | note | Inspection / Test Method - AS 1289.3.3.1 (wet preparation)
label | a6f6b89e-9e78-5d28-832f-130424554898 |  | note | Record of conformity - NATA - accredited test certificate
label | ed5e4953-8379-504d-b282-602d372cc1b0 |  | note | TP
label | cee6db75-baef-599a-a992-99aa07a4faff |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 5.3 - Linear Shrinkage
label | c766008e-b51f-5523-88ff-0c33ca12c165 |  | note | Frequency - 1 per 1000 tonnes aggregate
label | 0ffb89da-a3b8-5fb2-b78f-5697d46cca74 |  | note | Acceptance Criteria - Not more than 1%
label | 1f20b127-f2fa-584c-a0d4-efd791ad3acc |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-19
label | c9d1453c-a028-5470-a217-e8becc87bc38 |  | note | Inspection / Test Method - AS 1289.3.4.1 (wet preparation)
label | 998013a3-aa0b-5fbe-9d09-6532b7bb20c8 |  | note | Record of conformity - NATA - accredited test certificate
label | 0cb21eee-5657-530c-bfe9-f15b0a60eaec |  | note | TP
label | 08a6bf58-a60a-5558-bae1-38d1a85a156f |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 5.4 - Methylene Blue Value (Crushed aggregate only)
label | 78e9286c-5e68-5e54-a929-4be3706546e5 |  | note | Frequency - 1 per 2000 tonnes aggregate
label | 9329a835-7940-558d-af54-14f839b09fe5 |  | note | Acceptance Criteria - Not more than 5mg/gram
label | 0902197f-2d15-5596-a4da-cc4c6c63f9a3 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.5.3, Table 14-19
label | 9209b2a5-9d42-5cbe-9915-6f1f735cc3bf |  | note | Inspection / Test Method - AS 1141.66
label | eb213f1a-732c-5b70-8e4c-524dc4995a2c |  | note | Record of conformity - NATA - accredited test certificate
label | 76fde515-f38b-5a94-a093-05c9eeb9f5ae |  | note | TP
label | 90a3e60d-1dc8-5fbf-8b94-f9bfc452bc43 |  | note | Responsibility - Laboratory Technician
checkpoint-group |  |  | section | 6. Binder Testing – Jetbind E (PMB)
checkpoint-status |  |  | checkpoint | 6.1 - Bituminous Binder Sampling and Submission
label | b2d4a564-7f67-5cc3-9aaf-e1334cf81860 |  | note | Frequency - Every delivery of bitumen to the mixing plant
label | aa218d75-7c6e-537e-b24d-891562a2089b |  | note | Acceptance Criteria - All samples of bitumen must be obtained in accordance with Appendix B of AS 2008.
label | 46fcb93f-2457-5b63-9a93-767c86d0e6d0 |  | note | ○ The samples shall consist of two (2) 0.5 litre (minimum) sealed containers labelled appropriately identifying the relevant lot and traceability to the source.
label | 3967cf22-ec62-5a04-bb06-54e2d2f16b4f |  | note | ○ These samples to be submitted to the Contract Administrator / Principal’s Design Consultant.
label | 7dea16dc-143f-5836-a037-734f32a3a1a4 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.5
label | e3cfdb2a-e1b6-5db1-af67-0b56d6707ee2 |  | note | Inspection / Test Method - AS 2008 Appendix B Verify
label | 5207eb86-53cd-5240-af8c-d6e1faef1125 |  | note | Record of conformity - This ITP signed / Aconex Correspondence
label | bfc2a5a3-6c56-5812-88f7-19b5fb4ff114 |  | note | HP
label | 739fb472-c0cd-5674-a485-b67ccc167ca6 |  | note | Responsibility - Laboratory Technician / FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - Viscosity at 165ºC
label | 2107844d-13c3-5030-a5dc-2b74e7859a25 |  | note | Frequency - 1 test per manufactured batch of binder (minimum 1 test per 250T of bitumen used)
label | d27c9f9f-9067-504f-90d2-5c7cea517ab9 |  | note | Acceptance Criteria - To be reported
label | 555807ce-b82d-5090-8826-2e3e508997e0 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.7
label | 9265eaaf-3d28-5102-9a16-d63000378e81 |  | note | Inspection / Test Method - AG:PT/T111
label | d4d64d69-a294-5f9a-95ef-ea4477fdc648 |  | note | Record of conformity - NATA - accredited test certificate
label | 0cd21470-e6a3-5cbf-97d0-3165f7e768df |  | note | TP
label | 91f26a4f-244b-5119-9984-eec43f9f8d91 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 6.3 - Torsional recovery at 25ºC, 30 s
label | 4442d97e-0af6-5e9f-9e43-281620f5f510 |  | note | Frequency - 1 test per manufactured batch of binder (minimum 1 test per 250T of bitumen used)
label | 05a37dae-efbf-53e8-b401-4929557627fb |  | note | Acceptance Criteria - To be reported
label | ace90f64-9720-5a40-94dd-d093666f4f16 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.7
label | e8161c3d-a8fd-59bc-a780-09f1fec9fa46 |  | note | Inspection / Test Method - AG:PT/T122
label | b70119c7-715a-5877-8f0b-5b136a77109a |  | note | Record of conformity - NATA - accredited test certificate
label | 922468c5-60a7-57f5-b22f-950757937ba8 |  | note | TP
label | 71178e7a-e3a1-5fb4-b248-1bd0625d663b |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 6.4 - Softening point
label | bde23d15-bbb8-5d7b-9f26-b8f9b1a9a4bd |  | note | Frequency - 1 test per manufactured batch of binder
label | e0947489-c003-52e0-bf25-36ea4f9cd425 |  | note | Acceptance Criteria - To be reported
label | 3a90a3d3-6a1f-57cb-b8c1-2e99193acf75 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.7
label | 06036ee7-a202-562c-b31b-b3fd1e175f82 |  | note | Inspection / Test Method - AG:PT/T131
label | e28b9755-5ef2-5d9f-8d00-3d40c428c647 |  | note | Record of conformity - NATA - accredited test certificate
label | d79ec9b5-31ea-5caa-a0cd-9487e1588f84 |  | note | TP
label | 5b05ad1a-dd43-5e4a-ae98-c96755b2ca41 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 6.5 - Submission of binder test results
label | 35293dfb-0242-51ee-8c8b-72bc146a90bd |  | note | Frequency - 1 test per manufactured batch of binder
label | 6d9973c8-c991-5091-8d2a-dc55f583a2c6 |  | note | Acceptance Criteria - Completion of the specified set of tests on the binder and submission of the test results to the Contract Administrator / Principal’s Design Consultant.
label | 16589d71-57b3-5aaa-9d29-4c8af94ad469 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.7
label | 2479e10f-2325-557d-a641-59defdc6cae4 |  | note | Inspection / Test Method - Verify
label | c3f8697c-993f-572e-8221-8e88e63f827d |  | note | Record of conformity - NATA - accredited test certificate
label | 4479930b-f7fd-5c64-ab4d-f88dec17bb33 |  | note | HP
label | 59388297-4394-5818-812d-1d9b9213268a |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7. Asphalt Production Testing
checkpoint-status |  |  | checkpoint | 7.1 - Sampling
label | 4787e9e1-1942-506c-9d35-6ed9f57f9fdb |  | note | Frequency - Up to 100T: 1 test per work period / shift; 100T to 200T:
label | 9020187a-a659-58d7-bbf0-c2e23d85d2f8 |  | note | ○ 2 tests per work period / shift;
label | 802f0978-8164-54d2-98a8-15a2b8e336ff |  | note | ○ Above 200T: 3 tests per work period / shift.
label | a588503e-49d7-515b-a9ed-a5ddf20be510 |  | note | ○ Note: AECOM can request additional testing if any concerns are raised with the asphalt material during the works.
label | 8262f311-bc1f-5b7c-83d9-23eb265b243f |  | note | Acceptance Criteria - Mix to be sampled from asphalt delivery trucks.
label | cbc65b6f-c5cf-53fe-84a8-99777ff01c3e |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.11, Table 14-21 Frequency amended as per DCWC Mgt-RTRFI- 000069
label | d47e5c9a-b63b-5aa7-8eba-7b6def4b5b27 |  | note | Inspection / Test Method - AS 2891.1.1
label | 7c8f1df1-45f2-5e4f-98c5-5ae37ba6ee9f |  | note | Record of conformity - NATA - accredited test certificate
label | 6a051c80-c587-5a7a-b570-719b331dcab0 |  | note | TP
label | 0f7868c5-5d05-5445-8909-0a574429a8d1 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.2 - Asphalt mix temperature
label | 180d9be5-34ab-534e-9dea-0e0b858c3c21 |  | note | Frequency - Once per sample obtained as per Item 7.1 of this document
label | 83b17803-8472-59e2-8f01-704ce202037b |  | note | Acceptance Criteria - The temperature of the mix immediately following discharge from the mixer shall be within 10ºC of that nominated by the Contractor but shall not be greater than 175ºC (for polymer modified bitumen).
label | d147fbaf-4458-5432-912f-6b8e49fde45c |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.1
label | f3757301-2818-5f5f-8e82-122df588a1a4 |  | note | Inspection / Test Method - Verify
label | 6f91bfe6-cb75-5388-8ed9-d50aa8170e52 |  | note | Record of conformity - NATA - accredited test certificate
label | f1b83fff-5848-514e-bd6d-1d45cba100cd |  | note | TP
label | 216f59b4-40a3-5438-a3d4-de0f29fa36f3 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.3 - Moisture content
label | 65675cbd-6a40-5131-bad3-6eecf8951754 |  | note | Frequency - Once per sample obtained as per Item 7.1 of this document
label | 3df54c3a-6984-5d7d-8bb4-ff67b63c9527 |  | note | Acceptance Criteria - To be reported
label | 34574233-0ba6-50e8-ba24-3bc2e1f21428 |  | note | Reference Documents - FH Internal
label | 576a0cb8-1ce8-5c86-af96-13d29bbab547 |  | note | Inspection / Test Method - RC 211.01
label | b5512910-678b-59d4-9a9a-5b1a128673e2 |  | note | Record of conformity - NATA - accredited test certificate
label | 58bc5a93-350a-51a2-ab81-981ba6924e17 |  | note | TP
label | 47996c12-c1a4-5c28-9d50-cde4f9c0f39a |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.4 - Combined aggregate grading
label | d8483088-b4f3-5dd7-a602-5ecc63e04a71 |  | note | Frequency - Once per sample obtained as per Item 7.1 of this document
label | e0540364-1712-573b-abb7-61b48a1b303a |  | note | Acceptance Criteria - Grading to be within the “job mix” envelope grading:
label | bd5624a0-4630-5b08-a537-96eebf1aa655 |  | note | – – – – – – – – – – – – – –
label | 4789c3f7-ea1b-5568-994a-54fe43d67c6f |  | note | Sieve Size (mm) ¦¦ Job Mix ¦¦ Job Mix Envelope
label | 6da97687-a150-5dfd-8d93-17040fa55a97 |  | note | – – – – – – – – – – – – – –
label | 89b5775d-a384-5c7d-a70c-4bcbed1765e4 |  | note | 13.2 ¦¦ 100 ¦¦ 94 - 100
label | d6d44bb3-1883-543d-93c6-447da21f8d46 |  | note | 9.5 ¦¦ 85 ¦¦ 79 - 91
label | e57e7900-e38d-5a62-8a76-56cb6b72693b |  | note | 6.7 ¦¦ 72 ¦¦ 66 - 78
label | cfbe4513-1844-5ea7-8bc8-bd72086b82b5 |  | note | 4.75 ¦¦ 59 ¦¦ 54 - 64
label | 3cd26549-b81b-571e-8122-3f5a665fb74a |  | note | 2.36 ¦¦ 45 ¦¦ 40 - 50
label | 44e36964-284f-55c1-882b-09db66f2453e |  | note | 1.18 ¦¦ 35 ¦¦ 31 - 39
label | 4c9b9e1d-63b0-5612-991b-ae20dda5a802 |  | note | 0.600 ¦¦ 26 ¦¦ 23 - 29
label | bd66bdc8-bf39-58ac-a99e-23e698bce6eb |  | note | 0.300 ¦¦ 17 ¦¦ 15 - 19
label | 9bbdb289-25f0-5c11-bdb4-5496037c91b7 |  | note | 0.150 ¦¦ 10.3 ¦¦ 8.3 - 12.3
label | 0b4ca05d-b0fe-5b91-97d2-a8c23211dbf1 |  | note | 0.075 ¦¦ 5.5 ¦¦ 4.0 - 7.0
label | 8dde0ed3-7e01-5728-80b5-0deda8787f2c |  | note | – – – – – – – – – – – – – –
label | a914c616-74e1-521a-90fd-ec364efeb402 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-14 Job Mix Formula as submitted in FHPL- GCOR- 000464
label | 3034fa71-7ceb-54c9-b200-8f016aa81204 |  | note | Inspection / Test Method - AS 2891.3.3
label | 735fa6b6-7e4d-5229-98b3-0406422dd17f |  | note | Record of conformity - NATA - accredited test certificate
label | 62890606-83ad-527c-af13-d613b81c47d9 |  | note | TP
label | 18dc16ec-873e-5245-bd37-6f2e439250c0 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.5 - Average Added Filler Content
label | bac0ad9c-06d8-5188-a703-adcd69e5218d |  | note | Frequency - At the end of each production shift
label | 0bc3bf22-112e-5a63-a885-e1fe73c004f8 |  | note | Acceptance Criteria - Average added filler content to be within ± 0.2% of the “job mix” target.
label | d90fd574-c668-571e-aa06-a530b7a00804 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-14
label | 0277a487-8293-5efd-ab4c-4e9d7dea269b |  | note | Inspection / Test Method - Verify
label | bf454c0b-5b3a-517f-9ee3-330360b8b5be |  | note | Record of conformity - Batch Records
label | 7040b2f8-4b6d-5930-917d-6c7074aa9796 |  | note | TP
label | 0073113d-c346-5bde-83c0-8c7fd41af55f |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.6 - Bitumen content
label | fcdae11b-54bf-5ece-a6a0-783bddc557d6 |  | note | Frequency - Once per sample obtained as per Item 7.1 of this document
label | 1794f8dc-2f12-5287-9806-ef41a1786831 |  | note | Acceptance Criteria - Within ± 0.3% of the “job mix” bitumen content by mass. From JMF: Within 5.2% - 5.8%
label | a39831ef-ef95-5daf-9d45-515cfe8d0ffb |  | note | Reference Documents - DP1 Spec. Cl 14.14.8, Table 14-14 Job Mix Formula as submitted in FHPL-GCOR-464
label | 4da8c5cb-acac-5cfa-9ea5-8a408b4b31dc |  | note | Inspection / Test Method - AS 2891.3.3
label | 5f316b91-be4c-5fc3-823c-fe4e9d53b848 |  | note | Record of conformity - NATA - accredited test certificate
label | 76890843-4658-5e0f-981b-a21a73306a0d |  | note | TP
label | 733b4c81-8eda-5804-a1c0-b326ac19e800 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.7 - Average bitumen content
label | 6504c34c-481c-5b11-aac0-0a2bae48c067 |  | note | Frequency - At the end of each production shift
label | c6860ad2-5b1e-54f8-b68a-e6c5d38b5944 |  | note | Acceptance Criteria - The Contractor shall determine the average bitumen content of each size of asphalt produced during each continuous mixing period or shift based on the total quantity of bitumen used and total asphalt produced.
label | cc24a030-feb5-51ae-9032-178867ebfa70 |  | note | ○ Average bitumen content must be not less than the bitumen content of the “job mix” (Job Mix Bitumen Content is 5.5%).
label | 41bada6c-7ce1-5795-ae05-f0f093376fba |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.13.15.7, 14.14.8, Table 14-14 Job Mix Formula as submitted in FHPL- GCOR- 000464
label | c1e7d188-9b77-5f2e-b08d-9ea448d21af3 |  | note | Inspection / Test Method - Verify
label | 24904f82-e029-5e43-a3dc-0f20807f8b47 |  | note | Record of conformity - Batch Records
label | 4323d617-067f-5de7-ad16-237774b25088 |  | note | TP
label | 99230c28-327a-511a-b677-d6ee74121239 |  | note | Responsibility - Laboratory Technician / FH Project Engineer
checkpoint-status |  |  | checkpoint | 7.8 - Maximum density
label | 692a0e98-427d-5db7-abcf-45010a94014a |  | note | Frequency - Once per sample obtained as per Item 7.1 of this document
label | 05490ea5-5c52-5fa1-b281-e1f51714901f |  | note | Acceptance Criteria - To be reported
label | b6663a61-8f30-5e9f-8e65-36fbbab18729 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.11
label | 4a5658a4-f23a-5d03-9428-5a2e8b71d752 |  | note | Inspection / Test Method - AS 2891.7.1
label | a9afdc26-f46b-5579-83ea-22391feef3bb |  | note | Record of conformity - NATA - accredited test certificate
label | ef9adf73-5807-545f-9e9d-7c3f65a3e19f |  | note | TP
label | ae333a0c-b779-5cc3-8700-daafa2081758 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.9 - Bulk density
label | c277f277-3e4f-526a-b0d0-1f4f1acc9987 |  | note | Frequency - Once per sample obtained as per Item 7.1 of this document
label | 7a7e1eae-67ec-5178-940f-b3f096054938 |  | note | Acceptance Criteria - To be reported
label | 604527be-9b94-5fe9-90a6-3273aa99c00a |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.17.11
label | 888a406b-49ac-50a3-b048-65bee41be868 |  | note | Inspection / Test Method - AS 2891.7.1
label | 98d9cf9f-72a8-56ec-8597-a84de0107809 |  | note | Record of conformity - NATA - accredited test certificate
label | 5ee8bd1f-3693-577b-8288-af0fea64b4b6 |  | note | TP
label | bc837102-c321-5627-ab0e-702f203194c0 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.10 - Voids in mineral aggregate (VMA)
label | f47e82ab-1e3d-52b7-b1fa-7f9461d3867d |  | note | Frequency - Once per sample obtained as per Item 6.1 of this document
label | 1ac49a42-080a-55db-920f-3551d814ed49 |  | note | Acceptance Criteria - 15% minimum
label | 7bb004c9-5b1a-5578-bbb1-2dd8b6f8c53a |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-13
label | 0758014a-3b9e-58b0-b09f-e743b73db8cc |  | note | Inspection / Test Method - AS 2891.8
label | c99e4593-0911-5369-931e-2b569dc8447f |  | note | Record of conformity - NATA - accredited test certificate
label | 4ea6f048-a140-509c-99c3-7ed43a37d87b |  | note | TP
label | 1550d9d7-8b28-5438-b289-3cf609815bc1 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.11 - Voids filled with bitumen (VFB)
label | cfdab5c8-6c1b-5d98-9e74-f5b0e79613b1 |  | note | Frequency - Once per sample obtained as per Item 6.1 of this document
label | edbe213a-4060-51e9-8e46-ad035db3368b |  | note | Acceptance Criteria - 70% minimum to 80% maximum
label | 07ad2aee-0a20-51e7-86c0-d249d1b29a34 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-13
label | 98b7ac92-a21a-5aa1-8f7d-62e4ffd2e0af |  | note | Inspection / Test Method - AS 2891.8
label | 90def9a2-c3a7-52cf-9728-521d992bd83d |  | note | Record of conformity - NATA - accredited test certificate
label | 7dc482f5-0b77-5600-ac75-70ee7defcab4 |  | note | TP
label | 43ec88b1-9d79-5aff-a282-7899110842a2 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.12 - Marshall Air Voids
label | 172c85f8-d8fd-5e6e-82a2-44ad600c2289 |  | note | Frequency - Once per sample obtained as per Item 6.1 of this document
label | b430631b-820f-549a-8f29-541cd9f9cde1 |  | note | Acceptance Criteria - 2.5% minimum to 4.5% maximum
label | 17531974-f927-5387-a57c-fb073ee8fb45 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-13 Job Mix Formula as submitted in FHPL- GCOR- 000464
label | 8c0a8b32-1f94-50cd-85b6-6d613ae42945 |  | note | Inspection / Test Method - AS 2891.8
label | 4a0be370-1d3c-52fd-816f-14c503dc805b |  | note | Record of conformity - NATA - accredited test certificate
label | 8ee97d00-d41c-5049-b0c9-69443c4916d6 |  | note | TP
label | ad690142-d7d6-59b5-9d3c-c471b62d3517 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.13 - Marshall stability
label | 89844e6e-09cd-506c-8669-347914de5ed8 |  | note | Frequency - Once per sample obtained as per Item 6.1 of this document
label | 324362bf-233e-50e5-80c1-4816da380125 |  | note | Acceptance Criteria - 10kN minimum
label | ef84684f-7ecd-5c70-82dd-ed010f7f63a6 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-13
label | 7c7ea0a7-d42d-5a42-a0ad-5c18e6bd5204 |  | note | Inspection / Test Method - AS 2891.8
label | 633ddc3d-64f8-50cb-8a5d-6ad9bd4e4c37 |  | note | Record of conformity - NATA - accredited test certificate
label | 931b6d88-8ae5-5e45-982e-09a815b788fa |  | note | TP
label | db2198ec-d0a5-526b-9fb3-f25b02de33d5 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | 7.14 - Marshall flow
label | ede56d0a-e521-59c6-8772-cce579641dda |  | note | Frequency - Once per sample obtained as per Item 6.1 of this document
label | 599bb6ee-1bdf-5c4a-8266-3f163d1480e8 |  | note | Acceptance Criteria - Report only
label | a726af1f-6264-5fbe-aa08-b2f5a4550238 |  | note | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 14.14.8, Table 14-13
label | 6fd43e50-e428-5e04-92bf-6a4e8135cd1c |  | note | Inspection / Test Method - AS 2891.8
label | 660468e6-29a0-50bd-8c93-86526d81b5b9 |  | note | Record of conformity - NATA - accredited test certificate
label | 8b780ca6-f498-5b1c-9f3a-13db1d53abaf |  | note | TP
label | 7edaa46f-69da-5db5-b73e-d4152429cca0 |  | note | Responsibility - Laboratory Technician
checkpoint-status |  |  | checkpoint | Final Inspection
label | 699ef112-b661-5039-9ced-453339907ae5 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
text | af40121c-c6df-5957-a903-1d7fe7c90a2b |  | textbox | Name:
text | 869fc70b-9844-59b5-970a-8cb093eaf476 |  | textbox | Position:
date | a491f6f3-7e9e-57d7-a045-229e3638ab87 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP021-3 – Reinstallation of Shallow Base Canister | itp |  |  |  | Yes | ITP021-3 – Reinstallation of Shallow Base Canister | feabcd3f-5409-406b-a4dd-590a79fc3119
checkpoint-group |  |  | section | 1. Installation of Shallow Base Canister
checkpoint-status |  |  | checkpoint | 1.1 - Preparation for the Works to be Undertaken
label | 4907c43f-3f77-5a82-838a-de7f57acb114 |  | note | Frequency - Prior to Start
label | 561e1a6a-433d-585d-969a-9767a439b515 |  | note | Acceptance Criteria - Ensure survey set out is undergone, excavation permit obtained and (if required) services in work(s) area isolated. Lights, slot cuts, and aiming points marked out.
label | 0a5242c1-947c-59b7-8632-5e415d724536 |  | note | Reference Documents - Drawing sets:
label | 262ea9b3-5371-5ca2-b8af-d38c344819ec |  | note | • 60692389- SHT-01_1-10
label | 820881fb-f86a-5af6-afb7-800e5e5d2580 |  | note | • 60692389- SHT-01_2-10
label | 194695d0-13a4-50e9-883d-534544320317 |  | note | Inspection/ Test Method - Verify
label | 36f2f895-4ffc-5817-b1e4-ad9888817bd3 |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | e44f46f7-4e3c-54af-bbb5-57a8ab630b1f |  | note | HP*
label | 1cc682c4-e1b1-57de-b34c-5c1f73ad448d |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.2 - Core and Cut
label | e7b522f2-d6e7-5e65-a0d3-9e407dbacc30 |  | note | Frequency - Each Lot
label | 97364cd0-56eb-568e-9f03-62079e31a43c |  | note | Acceptance Criteria - Light base cored into pavement and slot from base cut to pavement edge/expansion joint
label | 39ec9bfc-a073-53b4-9f62-19a6f4b49ba2 |  | note | Reference Documents - Drawing sets:
label | cfbf2990-0724-593f-9c80-b4ae336ec5a2 |  | note | • 60692389- SHT-01_1-10
label | ca075061-8e8e-5f5c-bdf6-c9615a56dad9 |  | note | • 60692389- SHT-01_2-10
label | 883313c6-0148-5dab-82e1-0a70096010f8 |  | note | Inspection/ Test Method - Verify
label | f928b76b-a498-5077-bdb6-95816329ef9c |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | a7ccb6e0-b506-53c8-9255-9226ae1ad93f |  | note | IP
label | f14d3e05-9f8b-59b9-89c1-a7eafbb56018 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.3 - Base positioning
label | c964830c-e6e9-5978-bdb6-eda110caafe6 |  | note | Frequency - Each Lot
label | 6217fd18-2e7a-57a5-b82e-cacf239f7d15 |  | note | Acceptance Criteria - Light base positioned and epoxy poured to secure. Installation of jig.
label | 4bdf2dcd-8eff-5f18-88e6-5df976845e71 |  | note | Reference Documents - Drawing sets:
label | 6693bde4-0969-5c83-aafe-daa2efe0061c |  | note | • 60692389- SHT-01_1- 10
label | cfcec325-2c74-58bd-8ba6-b05271454c66 |  | note | • 60692389- SHT-01_2- 10
label | def57218-157c-5a3b-a225-853c8c4f533c |  | note | Inspection/ Test Method - Verify
label | e008d92b-5386-525d-b3c8-2470b46d212c |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | a6efac68-fabc-5909-95a3-5d6a2da9b8de |  | note | IP
label | 1f6eb286-9989-5b2d-bb02-64f82cb53871 |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.4 - Cabling
label | ce7216bf-7d10-56cb-8dc5-e21ba27ce016 |  | note | Frequency - Each Lot
label | cf0712b9-fc7f-563b-a937-878179e1a599 |  | note | Acceptance Criteria - Cables ran and connected from new base via joints/slots/conduits to SIT pit.
label | f9cda923-2679-52ba-8c9a-275682ac5ad9 |  | note | Reference Documents - Drawing sets:
label | 2cc6f89e-5cce-51d3-8163-c7f1b10b68bf |  | note | • 60692389- SHT-01_1-10
label | cfc9202d-2ec4-5e29-a370-ed7d9dc14431 |  | note | • 60692389- SHT-01_2-10
label | 04b29a9d-4297-5143-8aa3-21713bcd8bff |  | note | Inspection/ Test Method - Verify
label | 463160bd-c785-56f7-b304-3877fa310cba |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | 0a08da2e-b411-5132-8233-a4108be149a4 |  | note | IP
label | 4c1e2f85-3ef3-5736-82e9-5f53da08dc6c |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.5 - Sealing
label | 45f8e260-fa8c-537d-8c74-dc78abcc2f54 |  | note | Frequency - Each Lot
label | 4d5e2928-cac8-596f-a5c6-7d9784605c3d |  | note | Acceptance Criteria - Once cables installed, backing rod placed and expansion joints sealed with approved product.
label | bcf4ffe0-3001-573c-8bb8-c6c92baec0ff |  | note | Reference Documents - Drawing sets:
label | 64bf2db7-df8d-5242-a827-ea19e54d590c |  | note | • 60692389- SHT-01_1-10
label | f9d29101-fbd5-505b-b799-df063364e6ae |  | note | • 60692389- SHT-01_2-10
label | e8eb90cc-3ff0-5950-9960-d023b871a272 |  | note | Inspection/ Test Method - Verify
label | fd8da8cb-a927-5a93-81fa-136de870059d |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | 60e0f6b8-7501-53a1-a010-0c2c872f7784 |  | note | IP
label | d9ab2582-177a-513d-af8d-3d787f4403bc |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | 1.6 - Finishing, Testing, Demobilisation
label | 71dcccae-c1c3-5adc-b7a4-92a6f2866adf |  | note | Frequency - Each Lot
label | 32ba47cf-0e31-5c37-97db-e5f8cee925cd |  | note | Acceptance Criteria - Gasket positioned on light top, light plugged and positioned to current orientation. Light tested and area cleaned before demobilisation.
label | db2686ac-06ec-5157-869b-d218cf73434f |  | note | Reference Documents - Drawing sets:
label | 82dc948c-0eba-54df-958f-3c3b83d728b0 |  | note | • 60692389- SHT-01_1-10
label | 50d41268-8af7-5fbf-b2b4-7f83a283d693 |  | note | • 60692389- SHT-01_2-10
label | 543bee0b-3ac8-5bfe-b2cd-de51915ba494 |  | note | Inspection/ Test Method - Verify
label | cee19f35-f6c4-55b6-9953-9c912a3664cc |  | note | Record of conformity - This ITP Signed / Avionics CL003
label | 131e1fd6-b636-504c-91e2-9a067d008c78 |  | note | IP
label | ef849b5d-ac6e-56d4-a098-fc5bf517c9ee |  | note | Responsibility - Project Engineer/Avionics
checkpoint-status |  |  | checkpoint | Final Inspection
label | 4e7a1d7f-b14a-5c76-b9b8-e460f999d611 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 9f62b790-a3d9-5fcb-8683-c4c0821040f9 |  | textbox | Name:
text | 0bfe2038-7295-5750-b649-824aa128ee1f |  | textbox | Position:
date | 9e97f880-2f10-5c02-9360-174a08581030 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP003 - Plant Mixed Foamed Bitumen Stabilised Pavements | itp |  |  |  | Yes | ITP003 - Plant Mixed Foamed Bitumen Stabilised Pavements | fed39c4a-7156-44be-bc9c-89ef599284e3
checkpoint-group |  |  | section | 1.0 Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | 64454f23-3da8-5612-8aa6-62f829d87698 |  | note | Frequency - Prior to commencing works
label | eb547904-0c73-5c92-b306-ad385c55810d |  | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current revision to be obtained via Aconex
label | e9e29e0a-6e3d-5d9e-a1a1-656f6b451edc |  | note | Reference Documents - Aconex
label | adf58cfb-d47f-5e23-ad5f-29570694701f |  | note | Inspection / Test Method - Verify
label | 5a338c15-26bd-5502-bdf8-3fee131f8fb6 |  | note | Record of Conformity - This signed ITP
label | 927b8642-c936-55fd-b3f1-133a2278e107 |  | note | HP*
label | 1c1bb7ec-af9c-5be6-863c-52096ff57893 |  | note | Responsibility - Fulton Hogan
checkpoint-status |  |  | checkpoint | 1.2 - Work Method Statement
label | 99ed5ad0-d85f-5322-988b-3906dbcb54c1 |  | note | Frequency - Prior to commencing works
label | d20eb9b1-0a0b-509e-8488-c435178b9173 |  | note | Acceptance Criteria - No stabilisation works shall be commenced until the construction procedure for the stabilisation works including all required compliance test results is acceptable to, and approved by, the Administrator.
label | 954538e7-993f-53fb-855a-d259f65a4228 |  | note | Reference Documents - MRTS09 cl.5.2
label | b0fbe795-cb0e-509d-8b2c-6915bfdb9519 |  | note | Inspection / Test Method - Verify
label | edd8537b-7914-540c-b21d-47eb5fa3ba8f |  | note | Record of Conformity - Approved Work Method Statement
label | 17da4e9a-91f3-54de-9365-9d64f374afd5 |  | note | HP
label | e0fc586d-5122-5d59-a6d6-77438b500605 |  | note | Responsibility - Fulton Hogan / AECOM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Material Compliance
label | 0120ffa5-9ecf-5a21-a7ea-7d6d40abcce6 |  | note | Frequency - Prior to commencing works
label | cf40ea59-4cfa-5bab-a31a-2a2094b2a498 |  | note | Acceptance Criteria - No material shall be incorporated into the works unless it has been demonstrated to the Administrator’s satisfaction that all the material to be used comply with all the requirements of the Technical Specification. Compliant test results noted below to be submitted to contract administrator: • Aggregates [Class 2 Crushed Rock (ex Fulton Hogan Tylden Quarry), Class 1 Crushed Rock (ex Holcim Oaklands Junction Quarry) and RAP (ex Melbourne Airport)] – Compliant with VicRoads Section 812. Coarse Aggregate compliant with 10-1 and fine aggregate compliant with 10-2.
label | ba68cb21-4563-53c4-b9c0-205d1800b05c |  | note | Reclaimed Asphalt Pavement (RAP) – Use of up to 15% by mass of the aggregate
label | 5827d761-c5f5-5b62-ab9e-d461bbba53f9 |  | note | Primary Binder – Class 170 bitumen and penetration grade 70/100 complying with AS 2008. Minimum content is 2.5% of the dry mass density. Compliant with Table 10-3: o Expansion Ratio ≥10 o Half Life ≥20 seconds
label | 61d81f63-62f4-5aa3-9612-c31cc45db969 |  | note | Secondary Binder – GP Cement compliant with AS3972. Maximum cement content in is 2% by mass of dry mix Foaming Agent – Compliant with MRTS09 Water – Compliant with 10.5.6: o Total Soluble Salts ≤1,000mg/l o Chloride Ion ≤600mg/l o ≤ 400 parts per million of sulphate ion o ≤1% by mass of undissolved solids
label | 70552646-ee6c-57e3-9e80-4a0abc43e147 |  | note | Reference Documents - MRTS09 cl.7.1 & AECOM - MAP MP2.0 Spec. cl. 10.5
label | 69d9774a-6189-5437-a178-f2eafc9b698a |  | note | Inspection / Test Method - Verify / Test Results
label | 00a48823-24aa-5610-bc25-d83e9bc44ad7 |  | note | Record of Conformity - Approved materials and material sources
label | 9d403660-51d9-5a16-8ebf-0aa5d1206bd3 |  | note | HP
label | d3ee759e-0098-5a53-b768-5a676826d2e9 |  | note | Responsibility - Fulton Hogan / AECOM
label | df9f9ea7-2014-50c8-a9e2-856ab73f5034 |  | note | Hold Point sign off Aconex reference: DCWC Mgt-GCOR-001825
label | 411e03be-8726-5e34-a6c7-498631acbc2c |  | note | Date: 19/07/2023
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Production Testing
label | 99b5c02c-5b84-5d88-8078-9d83051738b2 |  | note | Frequency - Prior to commencing works
label | a557e6d8-3382-5cde-ae42-78224c27ea5f |  | note | Acceptance Criteria - Supply information with respect to production testing of the unbound granular material utilised for the FBB mix.
label | a5de88dd-ee5b-53d9-9d47-748e6cca42ae |  | note | Reference Documents - Cl.4 VicRoads Section 812 & AECOM - MAP MP2.0 Spec. cl. 10.5.1
label | d2c503ed-88b2-5307-8f62-7d073b226fbd |  | note | Inspection / Test Method - TP
label | 920f3df5-d25a-51b7-9ab3-e869c5a1c399 |  | note | Record of Conformity - Approved Production Testing Results
label | 19af4d67-24dc-5575-b83e-f4720179166d |  | note | TP
label | e2b45095-1007-5844-8893-a3380200f888 |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-status |  |  | checkpoint | 1.5 - Mix Compliance
label | ee693e57-11cc-5c89-9516-e69aff18f975 |  | note | Frequency - Prior to commencing works
label | 1a0f8c65-88f8-5371-88db-57616ca1d36c |  | note | Acceptance Criteria - The mix design report must be submitted to the Contract Administrator at least 7 days prior to the plant production trials for review. Approval of the mix design report prior to commencing the production trial is a HOLD POINT. The mix design report must include the requirements stated in cl 10.6.2 of the AECOM specification.
label | 545c3832-e475-5cb5-9384-4f29532fff4b |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.6.2
label | 85e32735-3670-58a4-8857-e1c71b7510bf |  | note | Inspection / Test Method - Verify / Test Results
label | e4ed6037-5862-5bbf-9a60-3813bb24c0a7 |  | note | Record of Conformity - Approved mixed design
label | 5bd3dc7a-0bf4-541c-8f54-13d4333f548b |  | note | HP
label | a278ec1c-83c2-5b2b-af51-bd3c52c55f4f |  | note | Responsibility - Fulton Hogan / AECOM
label | 398484a9-a435-552b-8c72-7b17b8fbe65a |  | note | Hold Point sign off Aconex reference: DCWC Mgt-GCOR-001825
label | a6e00f40-965b-52b0-8fb0-3e7ad742dff1 |  | note | Date: 19/07/2023
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Plant Production Trials
label | 3e17108b-1631-503e-8b8d-76b36527b76f |  | note | Frequency - Prior to commencing works
label | 04f1de27-c2ea-5253-bbe4-462f488bebae |  | note | Acceptance Criteria - The Contractor must undertake a production trial at their mixing plant to validate the approved Laboratory Design Mixture and to confirm the mix meets the requirements of the Specifications detailed in Table 10-5. The Contractor must issue an updated mix design report with the details of the Job Mixture (Laboratory Design Mixture modified) within 3 working days after completion of the production trial. Resilient Modulus: 1 test per mix design for plant production – Table 10-5 Requirements:
label | a4b5f7b3-8580-5406-8550-f45306e5c615 |  | note | • 3-day-curing Resilient Modulus ≥1,000 • Soaked after 7-day curing Resilient Modulus ≥1,500 • Soaked after 14-day curing Resilient Modulus ≥1,800
label | b403d995-812e-5a25-af81-f377db2bc802 |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.6.1 Table 10-5 & 10.6.3
label | db0d0e2a-b8d3-574d-8a5e-af9a77c4422f |  | note | Inspection / Test Method - Verify / Test Results
label | b0435833-62ea-590c-a63a-2e7f265ecfa3 |  | note | Record of Conformity - Approved mixed design
label | bcbf2a26-7677-5a7c-96f7-3c214b5f96e9 |  | note | HP
label | 91df4def-fc5e-5798-b8ad-bdd45134f17b |  | note | Responsibility - Fulton Hogan / AECOM
label | fa9f0213-5227-537e-9137-c90fc38d3550 |  | note | Hold Point sign off Aconex reference: DCWC Mgt-GCOR-001825
label | 73a59eb2-cb47-507a-bca1-ed18cdf0d051 |  | note | Date: 19/07/2023
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Construction Trial
label | 4ec0dbe8-7d2e-5c9e-b605-9dccf250b71d |  | note | Frequency - Prior to commencing works
label | d1b4b8c6-f6b3-5c26-8a0f-318a8b2a9622 |  | note | Acceptance Criteria - A trial section shall be constructed using the same construction plant, processes and methodology that it is proposed to be used for the remainder of the works. The trial section must be compliant with all testing requirements within the specification.
label | 35dfff1c-a848-5c45-839e-aa01500cb92e |  | note | Reference Documents - MRTS09 cl.8.1.2.4 & cl.8.7.2.1
label | 6bc759df-6a39-54a1-8df6-dca386d1bfd3 |  | note | Inspection / Test Method - Verify / Test Results
label | f6b6d8f7-5492-5a4d-b0aa-b1fcaf05dfb6 |  | note | Record of Conformity - This signed ITP
label | a435aa63-9e64-5aa7-bf45-0ae2fa4b2548 |  | note | HP
label | f4f0c031-a2a8-5468-bd57-fa8fd23db9e7 |  | note | Responsibility - Fulton Hogan / AECOM
label | cd1f7a8a-8e31-58b9-b049-6f70bea2f718 |  | note | Hold Point sign off Aconex reference: DCWC Mgt-GCOR-001825
label | 668d099a-d886-518b-a3e5-2c78a758b5f8 |  | note | Date: 19/07/2023
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Foamed Bitumen Properties
label | c3132ed3-7731-54ca-bf50-211c9c083af2 |  | note | Frequency - Prior to commencing works
label | ef886adf-25a7-5270-9a1c-3a0a86a08a1e |  | note | Acceptance Criteria - The bituminous stabilising agent shall not be incorporated into the material to be stabilised where the foaming properties of it do not comply with the requirements of the technical specification. The bitumen is to be tested at the start of each bitumen tanker and every 400T of production for the following parameters: Expansion ratio greater than 10 Half-Life greater than 20 seconds
label | 94921cdf-6baa-51a3-a3dd-bf975e604ad0 |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.5.3 & MRTS09 cl.8.8.5 Table 5.4
label | a9886c6f-3203-5a6a-94c3-290360059e35 |  | note | Inspection / Test Method - Verify / Test Results
label | ab586d5d-2095-5d72-b79f-f13915f06ea5 |  | note | Record of Conformity - Test Results
label | ffca5f3b-97e5-5652-8744-950eef2fe5d9 |  | note | HP
label | e66af499-3f7e-5f85-b0e7-3be3b3fdc0d1 |  | note | Responsibility - Fulton Hogan / AECOM
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.9 - Stockpiling of Materials
label | de3604bf-54d2-50e9-8183-ca37d2321fca |  | note | Acceptance Criteria - Stockpiles shall be located on clear, even, firm, well drained ground and in a location where they can be clearly identified. All stockpiles shall be separated from other stockpiles by at least two metres and shall not be more than four metres high. The feedstock lot size is defined as 2500T.
label | 25d2c48d-f71f-54c9-9320-a3104e249d90 |  | note | The Contractor can delineate individual stock piles by either of the following methods: A.) Separate stock pile formed for each lot B.) Material of the same mix to be added to a single stockpile incrementally. Prior to adding the next portion of material, the initial/existing stockpile must be compliant with the specifications No stockpile that, in the opinion of the Administrator, is excessively wet shall be used in the stabilisation works.
label | 60f8e42a-7228-5d6e-9201-23d281d836ac |  | note | Reference Documents - MRTS09 cl. 6.6 & MRTS05 cl. 7.7
label | 319444ef-8189-575f-9d51-6f607c1b6023 |  | note | Inspection / Test Method - Verify
label | cdce000e-395b-50cc-a338-01c18ac4ecb7 |  | note | Record of Conformity - This ITP signed
label | 4c70221e-a14a-550b-b7d0-e505b681b5a3 |  | note | WP
label | 1c49698f-9597-5acd-b026-f588c0ffc326 |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-status |  |  | checkpoint | 1.10' - Feed Stockpile Testing
label | ee33f3ae-791b-51ba-b7ef-ff7b40a61e75 |  | note | Frequency - Prior to commencing works
label | 459a84d7-6cf2-5ec8-9370-4e0c2487843c |  | note | Acceptance Criteria - The following items must be tested for in the feed stockpile: Relative Moisture Ratio of Feed Stockpile: 4 tests per feedstock lot. Particle size distribution: 1 test per 1250T and a minimum of 2 tests per feedstock lot Fines Ratio: 1 test per 1250T and a minimum of 2 tests per feedstock lot Liquid Limit: 1 test per 1250T and a minimum of 2 tests per feedstock lot Linear Shrinkage: 1 test per 1250T and a minimum of 2 tests per feedstock lot Sulfate Content (water): 1 test per water source
label | 2dc3cc75-4750-5b1a-a40b-1bbdbee9b6e8 |  | note | Reference Documents - MRTS09 Cl. 8.8.6 & Table A2(c) & A3 AECOM - MAP MP2.0 Spec. cl. 10.5.6
label | 0a6b9917-3fdc-5a79-8264-e8f85eab3028 |  | note | Inspection / Test Method - Verify / Test Results
label | 6a7d3619-b313-58c5-b64e-bb963c859347 |  | note | Record of Conformity - Test Results
label | fafb294f-f945-5011-ad2b-c5b6af164cd0 |  | note | TP
label | 4182f1e0-0163-5fe7-ba10-31a028f9faf5 |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-group |  |  | section | 2.0 Construction Process
checkpoint-status |  |  | checkpoint | 2.1 - Testing of FBB Material for Stabilising Agent Contents and Resilient Modulus
label | 3088f96c-505a-5c07-97b1-e877d02407e1 |  | note | Frequency - Each Lot
label | 513e025c-cf39-51da-b630-4416bc41af1f |  | note | Acceptance Criteria - Bituminous stabilising agent content: Recorded at least once per 100T with a minimum if one recording in any production shift. Secondary stabilising agent: Recorded once per 100T with a minimum of one recording in any production shift. Resilient Modulus: 0 to 5000T: 1 Test 5000 to 15000T: 1 Test 15000 to 30000T: 1 Test Beyond 30000T: 1 Test per 20000T
label | bb7112cc-116e-55f6-91c0-395e59237b54 |  | note | Reference Documents - MRTS09 Table A3
label | 6ab60d3b-6881-54eb-82b0-53e3c94f42ef |  | note | Inspection / Test Method - Verify / Test Results
label | 77c7befb-d57e-51cc-afcf-7f15d1b5c94f |  | note | Record of Conformity - Test Results
label | 92e0ee48-30a0-531c-ad57-e027ad3a76f6 |  | note | TP
label | ee2d18a7-a3d6-5986-9e58-ed662d2eb655 |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-status |  |  | checkpoint | 2.2 - Surface Preparation
label | cb95e7fd-ad05-5053-96ba-504f029b81c4 |  | note | Frequency - Each Lot
label | 63b7b9ed-67fd-5250-8ca0-1cc7b4ad22bd |  | note | Acceptance Criteria - For all surfaces, preparation shall include the removal of all foreign and loose material. The Contractor shall ensure the surface onto which a stabilised layer is to be constructed is well compacted, trimmed and prepared before material for the overlying stabilised layer is placed.
label | c34eee8d-94d6-55d6-816e-322cb9d68fe8 |  | note | Reference Documents - MRTS09 cl. 8.8.9.1 & 8.8.9.3
label | 5417054c-840f-5b28-8a3c-2eb7d69a2f58 |  | note | Inspection / Test Method - Verify
label | ae865458-3f5f-5290-903c-475c0b13dd23 |  | note | Record of Conformity - This ITP signed
label | 61250ffc-2902-50a6-a854-67173b016a16 |  | note | WP
label | cb50ff48-9880-5e7f-85b5-28a7bcb494ab |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-status |  |  | checkpoint | 2.3 - Placement of FBB
label | aab920aa-237b-548a-aab5-05d0842a1294 |  | note | Frequency - Each Lot
label | 78573e7c-ef95-5673-a859-b2adbd302c0a |  | note | Acceptance Criteria - The FBB is to be placed in a single layer. The maximum compacted thickness of an individual layer is 300mm. The minimum compacted thickness should be equal to the design thickness stated on the drawings. The surface level at the topmost FBB layer shall not deviate from design level at the specified points by 0mm,-10mm. Surface Levels to be picked up following profiling, and prior to placement of Asphalt.
label | 07578853-4afa-5d6b-96a2-5157cf2dd00a |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.7 & Table 6-3 MRTS09 cl. 8.9.5.2.2 & 8.9.5.3.1
label | 7a1116ed-4a5b-578d-b973-f9b656c699bd |  | note | Inspection / Test Method - Visual Inspection
label | 13d4d6a7-d50a-54e8-a2d8-62b34c774bcc |  | note | Record of Conformity - Survey Report and Visual Inspection
label | 0466b8d0-a767-55dd-bec7-6a7e929a5b1b |  | note | HP*
label | 8dbb297c-e531-5114-affb-f0437fbd9d9c |  | note | Responsibility - Fulton Hogan
checkpoint-status |  |  | checkpoint | 2.4 - Proof Rolling
label | 41aa90da-ee8f-5cf9-9b94-4ccc9da4661c |  | note | Frequency - Each Lot
label | a75efb0b-6f5c-5488-8255-0d6a5fc321fb |  | note | Acceptance Criteria - Proof rolling of the completed layer must be undertaken at least 24 hours after the completion of the bitumen stabilised layer. The area must be uniformly covered with a minimum of 8 passes with either a pneumatic tyred roller or water cart not exceeding 6km/h.
label | a8f1bc6e-aab4-5cfe-9449-99ba42e6218e |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.8.3
label | 703d3a78-8fb7-524a-a77f-e23b0f4b0eb4 |  | note | Inspection / Test Method - Verify
label | 795a8eb0-1aa7-5e5d-96e8-eeb5e79f3870 |  | note | Record of Conformity - This ITP signed
label | b5d2d25c-be92-5640-adda-0f83a15ede50 |  | note | WP
label | a96795da-65ac-5e62-b039-1fcc0fbf7f3d |  | note | Responsibility - Fulton Hogan / AECOM
checkpoint-status |  |  | checkpoint | 2.5 - Proof Rolling Report
label | 45d0b942-e79b-5e66-9bb9-cb038e48ba04 |  | note | Frequency - Each Lot
label | c4bf2725-c590-55a8-bb75-8823876c3b18 |  | note | Acceptance Criteria - Proof roll report must be submitted to the Contract Administrator and Principal’s Design Consultant as soon as practical after completion of proof rolling.
label | 9054c34c-04bd-5973-94b0-26c8b22658df |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.8.7.2
label | 7a351e93-002c-5064-882b-735bb943ce6c |  | note | Inspection / Test Method - Verify / Proof Rolling Report
label | 250eecd9-fe20-5bba-86b9-cdc247f9a8ea |  | note | Record of Conformity - Aconex
label | fa179187-800a-518c-a4f4-5b39097c4489 |  | note | HP
label | 07f71408-3cec-5516-9b62-462067178a59 |  | note | Responsibility - Fulton Hogan / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Proof Roll Failure
label | f60b0e32-7fd3-5cba-af02-0fca547d3ebc |  | note | Frequency - Each Lot
label | 8dd1f2bd-5c21-5e56-a851-de2f95a60f17 |  | note | Acceptance Criteria - In the event of a failed proof roll the contractor must rectify the stabilised material to the extent and methodology identified in the proof rolling report. Area and depth of replacement to be agreed with CA prior to replacing.
label | ca472317-7617-57f9-8ff6-60b742ec4b33 |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 10.8.7.3
label | fd091ded-523c-585d-a93a-f793396e70ed |  | note | Inspection / Test Method - Verify
label | 039a7f56-e489-5cad-af6d-33d7f0d2c606 |  | note | Record of Conformity - This signed ITP
label | ae1ad443-2814-5002-86ab-ece576df77bc |  | note | HP*
label | 0d4d30bd-bcb7-5d91-9f46-59de0ffb9055 |  | note | Responsibility - Fulton Hogan
checkpoint-status |  |  | checkpoint | 2.7 - Testing Requirements
label | 07b04610-2db0-56cc-8277-705cb31b020f |  | note | Frequency - Each Lot
label | f3817d06-bd79-5696-8b5c-154d38775b54 |  | note | Acceptance Criteria - The foamed bitumen basecourse must be compacted to characteristic dry density ratio ≥98% modified compaction and a minimum of 4 test points per lot must be undertaken. Lots that contain in-situ material that failed the proof roll at subgrade level must be compaction tested in the location of the failed proof roll.
label | a78b9512-b8e8-53ff-99a0-5aa701a5b4d5 |  | note | Characteristic Construction Moisture Content to be within the limits of 60 – 80% and a minimum of 4 test points per lot must be undertaken.
label | 106dfb49-6edb-5bfe-8a7c-b89904a817d8 |  | note | Reference Documents - AECOM - MAP MP2.0 Spec. cl. 5.10.3.2, 10.8.3, 10.8.4 & MRTS09 Table A3
label | 7fa23245-3a0d-5e0d-8cb7-1abaac9ae5a9 |  | note | Inspection / Test Method - Verify / Test Results
label | 4dcae702-72a4-57b3-9ee6-9de614c7ca0b |  | note | Record of Conformity - This ITP signed
label | f3409ffe-86de-5994-8919-287a6b26d7b6 |  | note | TP
label | 39e9db59-98cc-56f2-8478-622f4df28fec |  | note | Responsibility - Fulton Hogan
checkpoint-status |  |  | checkpoint | Final Inspection
label | 2f37ae5f-1513-519c-82f0-c85775281321 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 2dd1505b-7eef-589a-91d3-625530856022 |  | textbox | Name:
text | c48350af-d506-5bd3-baf6-d70e74b111fc |  | textbox | Position:
date | 1485ce09-6a28-542a-8933-5fb9e58ff24b |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP