## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-093-Rail-CAMMS-Pedestrian Crossing Removal & Spot Tamping
ITP Description: |  | CAMMS-Pedestrian Crossing Removal & Spot Tamping
Document Number (in Teambinder):
Discipline (e.g. CIV/STR/RAIL: |  | 093-Rail
Revision Number: |  | 0
Revision Date: |  | 2023-09-04
ITP created by: |  | Jake Argentaro
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Camms Road
Inspection & Test Plan - Pedestrian Crossing Removal & Spot Tamping
|  |  | Document No: MRP-000-MRPA-CAM-ITP-0000 | 0 |  |  |  |  | Revision: | 0
[9 empty] | Date: | 2023-09-04
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.01 | Non Dependent | L1-CHE-SPE-316 Concrete Sleepers | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.02 | Non Dependent | L1-CHE-SPE-003 Heavy Rail Construction Tolerances | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.03 | Non Dependent | L1-CHE-SPE-064 Ballast Supply | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.04 | Non Dependent | L1-CHE-STD-039 MTST 000002-01 Track Design and Construction | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.05 | Non Dependent | PTC Heavy Rail Track Construction Standards Drawing F598 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.06 | Non Dependent | Camms Road Package 52 Design Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries
2.01 | Obtain and submit Material Certificate of Compliance for Track Materials; -Track Jewellery -Ballast 60mm Aggregate | IFC Drawing Track Construction Site Mudmap Bill of Materials | Units to be free from damage, total and types of units for full set validated No signs of discoloration Attatch: Manufactuer Certificates of Compliance | Review Document | Once | HP | Track Supervisor Project Engineer | ConQA Hold Point Release
2.02 | Submit Asphalt Cutting Plan | Track Construction Site Mudmap Asphalt Cutting Plan | Plant to detail cutting pattern for asphalt required for removal. Asphalt to be cut to 150mm depth to provide clearance between cutting disc and concrete sleepers/rail jewellery | Review Document | Once | HP | Track Supervisor Project Engineer | ConQA Hold Point Release
2.03 | Inspect supplied items upon delivery | IFC Drawing | No damage or rust on components Validate total number and type of components matches drawing Attatch: Photos on site; -Track Jewellery -Ballast 60mm Aggregate | Visual Measure | Per delivery | IP | Track Supervisor Project Engineer | Material Inspection Report
3 | Construction / Installation Activities
3.01 | Cut and remove asphalt Clean track structure of loose asphalt and debris, remove contaminated asphalt as required | Asphalt cutting plan | Cut asphalt as per cutting plan, asphalt to be cut at depth of 150mm so as to avoid damage to rail and sleepers. Remove asphalt material, clean debris off rail and ballast, remove contaminated ballast as requried. | Visual Measure | Once | IP | Track Surveyor Track Supervisor Site/Project Engineer | This ITP
3.02 | Fastening replacement as required | L1-CHE-STD-039 MTST 000002-01 Track Design and Construction | All rail sitting within Sleeper footing with correct sleeper insulators All rail fastenings installed Attatch Site Photo: -Installed sleepers & fastenings | Visual Measure | Once | IP | Track Supervisor Site/Project Engineer | This ITP
3.03 | Track Tamping | Track tamping alignment as per existing | Track Excavator Tamped, Ensures Track Geometry Tolerances are not breached; Gauge +3 / -3 Gauge Variation in 2m 4 Line (10m Chord) +4 / -4 Twist (3.5m Chord) +2 / -2 Top (10m Chord) +5 / -5 Cant +5 / -5 General Alignment +15/ -15 (note, partial resleeper only requries track to be tamped to conform with local geometry, no survey requirement) A minimum horizontal clearance of 3.0m from track centreline to structure. Height and Stagger readings of overhead wire to ensure minimum clearance of 4.61m is not breached Attatch; -Tamping Geometry Recording Attatch Site Photos: -Tamping Activity -Overhead measuring Activity -Structual Offset Measurement | Visual Measure | Once | HP | Tamping Operator Track Surveyor Overhead Engineer Track Supervisor Site/Project Engineer | This ITP
3.04 | Regualting and Ballast Profile | L1-CHE-STD-039 MTST 000002-01 Track Design and Construction | Ballast has 400m width from outer edge of kerbstone with 1:5 crossfall thereafter No Ballast to be on top surface of sleepers or aorund rail Fastenings Attatch Site Photos: -Ballast Shoulder Measurement -Rubber Panels free of ballast materials | Visual Measure | Once | IP | Regualtor Operator Works Supervisor Site/Project Engineer | This ITP
4 | Post-construction / Post-installation Activities
4.01 | Track Certification | MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B | Attach : -Track Geometry Conformance Certificate -Track System and Component Attatch Site Photos: -Before/After Photo of worksite | Visual Measure Doument Reivew | Once when all occupation works complete | HP | Nominated Authority (MTM Infrastructure Track Certifier) | ConQA Hold Point Release
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /