## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-093-Rail-CAMMS-Pedestrian Crossing Removal & Spot Tamping | itp |  |  |  |  | ITP-093-Rail-CAMMS-Pedestrian Crossing Removal & Spot Tamping Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-093-Rail-CAMMS-Pedestrian Crossing Removal & Spot Tamping
label | ITP Description: CAMMS-Pedestrian Crossing Removal & Spot Tamping
label | ITP number:
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 093-Rail
label | Revision Number: 0
label | Revision Date: 4/09/2023
label | ITP created by: Jake Argentaro
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: L1-CHE-SPE-316 Concrete Sleepers
label | 1.2 Non Dependent
label | Reference: L1-CHE-SPE-003 Heavy Rail Construction Tolerances
label | 1.3 Non Dependent
label | Reference: L1-CHE-SPE-064 Ballast Supply
label | 1.4 Non Dependent
label | Reference: L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
label | 1.5 Non Dependent
label | Reference: PTC Heavy Rail Track Construction Standards Drawing F598
label | 1.6 Non Dependent
label | Reference: Camms Road Package 52 Design Drawings
section | Preliminaries
checkpoint | 2.01 Obtain and submit Material Certificate of Compliance for Track Materials; Track Jewellery / Ballast 60mm Aggregate
label | REFERENCE: IFC Drawing, Track Construction Site Mudmap, Bill of Materials
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration
label | Attach: Manufactuer Certificates of Compliance
label | – – – – – – – – – – – – – – – – –
label | METHOD: Review Document
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Track Supervisor, Project Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.02 Submit Asphalt Cutting Plan
label | REFERENCE: Track Construction Site Mudmap, Asphalt Cutting Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Plant to detail cutting pattern for asphalt required for removal.
label | ○ Asphalt to be cut to 150mm depth to provide clearance between cutting disc and concrete sleepers/rail jewellery
label | – – – – – – – – – – – – – – – – –
label | METHOD: Review Document
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Track Supervisor, Project Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.03 Inspect supplied items upon delivery
label | REFERENCE: IFC Drawing
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: No damage or rust on components
label | ○ Validate total number and type of components matches drawing
label | Attach: Photos on site;
label | – Track Jewellery
label | – Ballast 60mm Aggregate
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per delivery
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Track Supervisor, Project Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material Inspection Report
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 3.01 Cut and remove asphalt, Clean track structure of loose asphalt and debris, remove contaminated asphalt as required
label | REFERENCE: Asphalt cutting plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Cut asphalt as per cutting plan, asphalt to be cut at depth of 150mm so as to avoid damage to rail and sleepers.
label | ○ Remove asphalt material, clean debris off rail and ballast, remove contaminated ballast as requried.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Track Surveyor, Track Supervisor, Site/Project Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.02 Fastening replacement as required
label | REFERENCE: L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All rail sitting within Sleeper footing with correct sleeper insulators
label | ○ All rail fastenings installed
label | Attach Site Photo:
label | – Installed sleepers & fastenings
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.03 Track Tamping
label | REFERENCE: Track tamping alignment as per existing
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Track Excavator Tamped, Ensures Track Geometry Tolerances are not breached;
label | ○ Gauge +3 / -3
label | ○ Gauge Variation in 2m 4
label | ○ Line (10m Chord) +4 / -4
label | ○ Twist (3.5m Chord) +2 / -2
label | ○ Top (10m Chord) +5 / -5
label | ○ Cant +5 / -5
label | ○ General Alignment +15/ -15 (note, partial resleeper only requries track to be tamped to conform with local geometry, no survey requirement)
label | ○ A minimum horizontal clearance of 3.0m from track centreline to structure.
label | ○ Height and Stagger readings of overhead wire to ensure minimum clearance of 4.61m is not breached
label | Attach;
label | – Tamping Geometry Recording
label | Attach Site Photos:
label | – Tamping Activity
label | – Overhead measuring Activity
label | – Structual Offset Measurement
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Tamping Operator, Track Surveyor, Overhead Engineer, Track Supervisor, Site/Project Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.04 Regualting and Ballast Profile
label | REFERENCE: L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ballast has 400m width from outer edge of kerbstone with 1:5 crossfall thereafter
label | ○ No Ballast to be on top surface of sleepers or aorund rail Fastenings
label | Attach Site Photos:
label | – Ballast Shoulder Measurement
label | – Rubber Panels free of ballast materials
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Regulator Operator, Works Supervisor, Site/Project Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 4.01 Track Certification
label | REFERENCE: MTMF020000-1 – Track Form A T, MTMF020000-2 – Track Form B
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | Attach:
label | – Track Geometry Conformance Certificate
label | – Track System and Component
label | Attach Site Photos:
label | – Before/After Photo of worksite
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Measure, Document Reivew
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once when all occupation works complete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP