## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Balcony Waterproofing |  | Balcony | 156fdd2b-63ee-4e55-a5a6-ce75f8a865de
| section | Details
| checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
8f30ca43-cdc2-526b-94f4-d5b563a69aba | note | Attach relevant photos
| checkpoint | WP details listed at architectural drawings for clarifications are followed.
0211ebc7-0c19-5501-972e-fbc69d62d70d | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
70c9fcdb-b295-50cd-8c7d-bb08336e7b8e | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
ae273fda-b0cc-511b-b9bd-821095f0464f | tickbox | Ensure no high points or crevices are in the substrate
e5f38f69-6812-58ff-ab85-96b40dbe8105 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
d96cf244-03fc-5e76-8c59-8fff102a4956 | note | Attach relevant photos
| checkpoint | Prime substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
7b104534-8083-5323-af76-463a645058c5 | note | Attach relevant photos
| checkpoint | Seal all corners, joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant - Apply selected sealant as per datasheet & application guidelines
458e573e-c9de-556d-b1b9-3c48f09763f9 | note | Attach relevant photos
| checkpoint | Balustrade base i.e shoe base or angle base installed & grouted with structural grout (as required)
97686a27-8c67-5352-a50c-9908766b3cc8 | note | Joint between bttom of base & substrate to be no greater than 10mm with continuous bead of caulking
| checkpoint | Overflow at the ends of balustrades in place
4ae24b8a-5d65-5df7-b3ab-41c180858761 | note | Approximate width of over floor to be 50mm
0e1fc875-2be0-521a-9cae-7b3dfe52ca90 | note | Height of overflow must be lower than the bttom of subsill
dec58cca-c7d4-5906-bf9b-96e8eb91add8 | note | Angle to be installed between end of base & wall with top of angle to be at FFL
| checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
| checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
0e4d9cd3-5e30-55bc-b546-79b8075a41a1 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
| checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
e9a960db-2f10-5451-9e84-d05b22cfb486 | note | Attach relevant photos
| checkpoint | Dry day for second coat (if required).
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
85d40d9f-b50d-56b1-a809-6cb0b8ca38c8 | note | Attach relevant photos
| checkpoint | Attatch photos for the drainage conduit.
0868cc1f-5151-5b8a-bc9e-500487045da5 | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
eb212c15-9b93-5fa4-8058-7227436a7511 | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
435c1fba-39cb-5a36-ac5c-321e0ffe018c | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Fire Sprinkler Tanks Waterproofing |  | Fire Sprinkler Tanks Waterproofing | 56dd32dc-20cb-431e-94e6-8c8a5b2d71ef
| section | Details
| checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
d24edc66-a80d-58f5-8c22-4a1dff967986 | note | Attach relevant photos
ea2950f9-4df7-510e-8d43-162532fd6aab | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
f3a589ef-1cb7-556e-85c2-015de825d567 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
55c0eeaf-b781-5e07-9780-79b64c7383b1 | tickbox | Ensure no high points or crevices are in the substrate
38677e2e-e488-5577-b65b-4a2b6d64ce4c | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Fatra Fatrafol 807 PVC membrane to be used. - Apply selected membrane as per datasheet & application guidelines
b4a270aa-470b-5598-a4e1-b0dab803f2d0 | note | Attach relevant photos
| checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
15a0621d-2e6b-53a7-b732-fa0d36337895 | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
57c62713-bdc8-55a2-a8a5-2a793d20fe23 | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
e13fa481-5eee-5316-a6b9-7cc4079c7aa0 | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
db5bef4e-b9ab-5a09-9e8f-572721854c87 | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Fire Sprinkler Tanks Waterproofing (Balconies) |  | Fire Sprinkler Tanks Waterproofing (Balconies) | 8a26b082-dcb4-4af7-8c61-6194b326cbe9
| section | Details
| checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
0ac6f7e8-d164-50c0-af3d-2908b97e6c81 | note | Attach relevant photos
f22f11d2-d7ad-5315-8303-66a6edbef0ee | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
9cb01dfa-e0ef-5c2d-8ed2-79818ae5bc0b | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
a066f137-dc7f-5ed2-8fbf-6e389e2f80e8 | tickbox | Ensure no high points or crevices are in the substrate
88c19551-e8fd-5413-90ad-691b6b539bc6 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Fatra Fatrafol 807 PVC membrane to be used. - Apply selected membrane as per datasheet & application guidelines
ff520158-ddba-5d1a-9ec3-0fb349a4e057 | note | Attach relevant photos
| checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
4b2f798a-223c-5393-a1c7-0d18ba30a806 | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
30c54f7f-ac94-5ea5-b19d-f022c2184d5c | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
4834bb65-8f43-5685-b1c9-72d47ea09452 | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
fdfe9571-6e7b-551a-b1fe-b7641de41bab | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Garbage Chutes Waterproofing |  | Garbage Chutes Waterproofing | 97d5c3a0-3a9f-425a-9694-95d6b9fd1e96
| section | Details
| checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
48dc8b54-626a-5de2-848b-a8ce416d62ab | note | Attach relevant photos
fe0bc858-9573-5d5c-882f-942df732be29 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
b29e8cc5-e824-56ed-9d4b-0905dfcadaa6 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
48ede63f-aa2b-5758-9039-454d9814d696 | tickbox | Ensure no high points or crevices are in the substrate
38a6294d-6c25-5c00-9d72-cda2fe995bc3 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
ce76267e-e289-5288-abbc-dc8680e717b9 | note | Attach relevant photos
| checkpoint | Primer substrate (walls and floors) with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
f262cd46-58f4-5333-b32d-e1d5cb523e71 | note | Attach relevant photos
| checkpoint | Apply angles to builders FFL as required.
0ffb11da-0261-59c8-83e9-e0ee65728251 | note | Attach relevant photos
| checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
4046954c-f167-502f-baa7-fb0b8e8ada55 | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
be68d5d4-52fd-5b6c-ae09-db6c7209c17e | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
81236fe3-0311-59b7-b72e-e9949ef59c07 | note | Attach relevant photos
| checkpoint | Dry day for second coat (if required).
ae52270f-cad3-5a40-a97d-59fa9ef92c88 | note | Attach relevant photos
| checkpoint | Apply 2 coats of Polybit Hybrid 150 waterbased polyurethane membrane on walls as required. - Apply selected membrane at a rate of 1.0 litres/m2 per coat as per datasheet & application guidelines
d2df26a6-1913-596b-b40f-e1ad15f68b7d | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
158729e2-1289-59a8-8da3-3a2c11b08261 | note | Attach relevant photos
| checkpoint | Conduct a flood test to garbage chute area.
bfaecfe8-781d-5cbe-9a95-221059021a2e | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
493ff51b-14f3-5059-8257-1cbe4e5fc202 | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
693349a0-ce7a-5658-aa24-3f700ff6af25 | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Garbage Rooms Waterproofing |  | Garbage Rooms Waterproofing | f71d3536-e1cf-4cbd-8382-269aa6afc679
| section | Details
| checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
bb7e639a-9ccb-5394-88cb-ee9b8aefba26 | note | Attach relevant photos
b4b31905-9aaf-502e-8b9c-e4af3625b692 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
d284d911-caf2-5868-929f-13a4f0a9a7df | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
4e0312ca-afe4-5423-887e-35f613ed8676 | tickbox | Ensure no high points or crevices are in the substrate
6cec7286-960e-5b98-b2df-7ea6dfa086e6 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Apply 1st coat of Duromix Hibuild WBE epoxy primer to walls and floors - Apply selected primer at a rate of 1.5m2/L as per datasheet & application guidelines
73485c2d-6acb-5edc-b992-213a47faade7 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Duromix Hibuild WBE epoxy primer to walls and floors - Apply selected primer at a rate of 1.5m2/L as per datasheet & application guidelines
5bdc7fa1-2522-5575-bb15-79dcf05aa8bc | note | Attach relevant photos
| checkpoint | Apply 1st coat of Duropoxy SLR100 epoxy top coat to walls and floors - Apply selected top coat a a rate of 6.6m2/L as per datasheet & application guidelines
b0508fab-33dd-5e4e-92ad-9ea59d086c29 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Duropoxy SLR100 epoxy top coat to walls and floors - Apply selected top coat a a rate of 6.6m2/L as per datasheet & application guidelines
348370d9-79e6-55dc-b50d-be7c3677d023 | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
be458bc4-d1d3-56ef-abb7-267b54595bb3 | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
88d2d2a0-74c8-5006-8d36-2abbb3a419cd | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
51593efb-81b9-5168-82ef-b18b9a31c83e | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Hobs |  | Hobs | a704504d-6e54-4c3e-af69-4416718f0f9d
| section | Details
| checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
3a0f08f6-855b-5eab-9fb7-d80d40565afd | note | Attach relevant photos
3a06efef-d3a2-53e1-a5f4-ee08b1bb4f22 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
9a600b77-243b-562a-b439-2c3d93568608 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
| checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
1dcccf95-1125-523f-ab48-06e5e21197b7 | note | Attach relevant photos
| checkpoint | Primer substrate with Polybit Hydrapoxy/polyprime - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
da2469d9-4a9c-53d9-9cd7-df202dbced17 | note | Attach relevant photos
| checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
a3cbe7f5-de46-5eef-99d3-abd29f8fdf16 | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydraguard - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
d8437c89-915b-5a1b-8f31-62d8a1161b4c | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydraguard - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
8e5970e7-0bbb-5875-9f7b-2632961acd37 | note | Attach relevant photos
| checkpoint | Dry day for second coat (if required).
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
df7e4c52-0e28-5e04-be8e-2bf17e527764 | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
6b164808-b590-53dc-9f63-96c62edc0d10 | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Internal Wet Area (Bathrooms & Laundries) Waterproofing |  | Internal Wet Area (Bathrooms & Laundries) Waterproofing | 2d56763e-4efa-47bc-a139-ed4e375143da
| section | Details
| checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
3eb114c9-450b-529b-aecb-1e7f35eeb36b | note | Attach relevant photos
5c89a9ac-d214-5bcb-869b-9ba7c4de85d0 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
568918be-5ccd-53a2-bbc0-680a544847ad | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
86bf8a76-42fd-592c-8049-c2b993d3953f | tickbox | Ensure no high points or crevices are in the substrate
b49d317a-ad9a-5ea7-8a3c-2fa2bce3b72c | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
80529d74-0fd6-5462-9483-37fcb2ba435a | note | Attach relevant photos
2d28e828-1e8e-5882-963e-a64ad6571064 | tickbox | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations
e375b127-b8c5-5d25-8d25-4b13784fba7b | tickbox | Shower Angles in correct position & level
1533ec7a-188f-561a-9d2c-5f284700c936 | tickbox | Door Angle is in correct position & level
a4cd9738-688e-59d5-96c3-a49c097ad416 | tickbox | Door & Shower Angle are 3mm guage aluminium
c964414d-a1ac-5854-b3b7-de7d1dc187d9 | tickbox | Ensure humidity, temperature & moisture are in accordance with manufactuer's recommendations
| checkpoint | Primer substrate (walls and floors) with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
c4d5d224-eba2-5b37-8096-8311db5ffe15 | note | Attach relevant photos
| checkpoint | Apply angles to builders FFL as required.
12e04272-ebf3-5a6d-8b19-72aa7ae32f19 | note | Attach relevant photos
| checkpoint | Seal all joints and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
52212da9-5e32-5b1e-81e5-4dd5be79b213 | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
a6880ded-5997-5092-800d-7d104b443615 | note | All floor wastes membranes to be turned down into floor waste
| checkpoint | Waterproof walls of shower section up to ceiling. Seal taps & the like. 2x coats required.
cd6442d2-c612-5a12-850d-24872ecf4293 | tickbox | Min 150mm kicker has been waterproofed (do width of roller 230mm)
0bef27fe-5e4e-5e7e-a7a5-eea1d24419f9 | tickbox | Min 1500mm past shower screen has been waterproofed.
f7bb8638-c1de-522d-bc81-9383e6b6b1e9 | tickbox | Waterproof all shower & adjacent walls
26d664d3-a3e7-547e-a019-844cfb6d5dcf | tickbox | Ensure humidity, temperature & moisture are in accordance with manufactuer's recommendations
458e1d7e-bec5-5c0b-9d78-7bd4a68d5670 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 250mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
3eb0f684-1659-52c2-8fa5-eae8396e593e | note | Attach relevant photos
| checkpoint | Dry day for second coat (if required).
7870cb6e-763e-528b-827f-37ea8360bb06 | note | Attach relevant photos
| checkpoint | Apply 2 coats of Polybit Hybrid 150 waterbased polyurethane membrane on walls as required. - Apply selected membrane at a rate of 1.0 litres/m2 per coat as per datasheet & application guidelines
a71fc85c-3ad7-5b81-91df-808f946c4ff5 | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
9511062d-08bc-5298-84cb-3bd7bf6b22e5 | note | Attach relevant photos
| checkpoint | Conduct a flood test to internal wet area.
2b61f13a-e0f2-5de2-a3e5-ae9c7bcbeeeb | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
7aca3548-f89f-58a8-bd75-136e3483eb17 | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
0ede30f2-f2b5-5ecf-ada2-b2dd12f2a0fc | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Internal Wet Areas |  | Internal Wet Areas | e77b2444-69db-47e6-a209-6237f6574681
| section | Details
| checkpoint | Area barricaded off to allow no access to internal wet areas with signs posted/ visible to include date of application, "No access waterproofing work in progress"
855450b8-a33e-504a-97c8-98414cc21bdb | note | Attach relevant photos
7706d53a-0ccc-5f1e-b2fc-ca1762d82ab9 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
8940d2dd-f031-55ea-9f5f-fd78aef2c868 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
28ee416b-4b9f-5388-9c86-232ede3e7f9a | tickbox | Ensure no high points or crevices are in the substrate
7eb98cee-c4ff-5669-92ab-f793cf6b8879 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
ae662bd7-4a3f-52b1-8eee-625bebd2c614 | note | Attach relevant photos
| checkpoint | Primer substrate with Polybit Hydrapoxy/polyprime - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
| checkpoint | Install alluminium waterstops to door entries and showers as per builder's FFL.
2e24527b-e0b0-5089-8275-15dd8803acc5 | note | Attach relevant photos
| checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
18277d32-229d-5817-85b4-02528211b635 | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydraguard on floors - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
5dadc5b0-82b7-5561-ad2a-94c585b62c93 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydraguard on floors - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
481ef313-8eaa-588e-b7dd-cb0e67ea197f | note | Attach relevant photos
| checkpoint | Dry day for second coat (if required).
e4f24016-1ae9-567f-bd04-2cc71ae2a902 | note | Apply Polybit Hybrid 150 to walls where required as per data sheet and application guidelines.
| checkpoint | Flood test for a minimum of 24 hours.
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
99fff5d8-b493-59fb-b58e-874147381e3f | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
f2d75a1e-c4c0-5f3a-b215-7978d6b616a7 | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Lift Pits Waterproofing |  | Lift Pits Waterproofing | 441a258c-0971-483e-bec9-2b3d38250b9a
| section | Details
| checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
42b54ecb-f91b-5e26-a735-70d8f376b5be | note | Attach relevant photos
a72cfe36-6907-5903-9620-f13d1e828a28 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
37ac07bb-5bc4-56e2-b8cd-24b24b3a5c9d | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
49c715b8-76e0-570c-bac9-663e6e206f15 | tickbox | Ensure no high points or crevices are in the substrate
87431705-599e-58cf-a373-55ce79cde696 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Dampen the surface to ensure the highest level of adhesion
1203dbc0-4707-51cb-8ee4-a40b53247a5a | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
2bda8f9f-d38d-590d-a73a-566711cda847 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
3eb06577-78c8-5540-820b-0a25c6f159ee | note | Attach relevant photos
| checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
2e2b237d-4d07-56a0-90e2-54fd6d184885 | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
a2132747-b892-56bc-bdce-be68ff0277bb | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
ee1e4d29-ad04-56f5-8781-e69a7573826d | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
71d937ae-11e5-50d9-8aaf-ec41f36c4307 | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Lift Pits Waterproofing (Balconies) |  | Lift Pits Waterproofing (Balconies) | 0315abe7-b63e-4994-9c20-3e6c213376b7
| section | Details
| checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
089e6bdd-18ad-5c0c-a3f2-418b15559b1d | note | Attach relevant photos
e819781a-49cb-5204-ba2b-153b069d3ff5 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
6c412b52-6848-5953-9bfe-adf671609969 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
5ba172f7-756b-55d3-a658-b52f32297131 | tickbox | Ensure no high points or crevices are in the substrate
d2c3f05f-b618-5daf-a35f-a74c1d8eb575 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Dampen the surface to ensure the highest level of adhesion
cad7f57d-ba20-5194-8648-bc13a6c8a434 | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
e85a4cb8-0cf5-5359-ad05-a504f506b994 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
eab4b519-7c89-5a18-80c0-138437fcb185 | note | Attach relevant photos
| checkpoint | Inspect for any remaining leaks and treat with HydraPlug - Apply selected sealant as per datasheet & application guidelines
b7001740-ee74-5c20-a582-ea34ff98db46 | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
bf0cfc6f-1814-57a8-8420-fc5f716bb6ad | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
5b399be4-7ef3-5fce-92d2-c30f898ce2de | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
134450e8-cec3-5107-8fc1-6bf751f04a06 | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Planter Box Waterproofing |  | Planter Box Waterproofing | 67cf97d0-2ba4-4f7b-b347-de8db318f1fa
| section | Details
| checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
203209c8-0fa5-57d3-9330-a089b78583a1 | note | Attach relevant photos
| checkpoint | WP details listed at architectural drawings for clarifications are followed.
| checkpoint | All floor should be with proper falls towards the floor waste with a min. 1:100 slope.
d2074225-92cd-5f2c-9854-2f5d6e037aac | note | Attach relevant photos
aa382870-f202-5661-b79d-277904413369 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
b69c1b1d-79d5-5cd2-8fef-ce51234e3070 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
90df72cf-bd0b-5dab-b605-fd8797dfeba9 | tickbox | Ensure no high points or crevices are in the substrate
f7f0add0-9364-58c2-a57c-fec633ddc522 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
0d8982e3-c07a-578e-98e0-419b90f64153 | note | Attach relevant photos
| checkpoint | Primer substrate with Polybit Hydrapoxy - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
daef92ea-63b5-503d-b88e-598c92cd8771 | note | Attach relevant photos
| checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
7952990a-f0a5-5988-ba28-8b1d2bfb5871 | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydraguard AR100 on floors and walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
66d38e67-77f0-5e10-8062-b4e9b46c2900 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydraguard AR100 on floors and walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
2a4d08ed-ce62-5c63-a43c-e665c41c8f03 | note | Attach relevant photos
| checkpoint | Dry day for second coat (if required).
| checkpoint | Attatch photos for the drainage conduit.
d0bd1746-582e-58e8-b104-829c92caf003 | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
7f4bd273-9b39-5957-a9d4-b6e337807093 | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
03d0b704-8063-55f1-93f4-a76407088ab8 | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Roof & Awnings ITP |  | Roof & Awnings ITP | a1cdfcee-b39d-48c4-b34a-01bdcd5ea150
| section | Details
| checkpoint | Area barricaded off to allow no access to roofs with signs posted/ visible to include date of application
| checkpoint | Ensure "No access waterproofing work in progress"
| checkpoint | Membrane system and methodology checked off against ALAND standard details and MSDS and guidelines
| checkpoint | Surface Preparation as per Application Guide
| checkpoint | Substrate clean, dry and free from dust.
| checkpoint | Ensure substrate is structurally sound and ready to receive membrane
| signoff | Ensure Humidity, temperature and moisture are in accordance with manufacturer's recommendations prior to primer - have signed by Aland - Do not proceed if above has not been signed off
| checkpoint | Apply Primer (Polyprime or Hydrapoxy)
| checkpoint | Ensure all floor wastes and pipes have been primed in accordance with manufacturer's recommendations (PVC prime & Metal prime)
| checkpoint | All corners have polyurethane bond breaker (hydraflex) installed with min 12mm radios
| checkpoint | Ensure Humidity, temperature and moisture are in accordance with manufacturer's recommendations prior to first coat
| checkpoint | Apply first coat of membrane (Hydraguard)
| checkpoint | Apply final coat of membrane (Hydraguard)
| checkpoint | Allow curing in accordance with manufacturers specification 24-48 hours min
| checkpoint | Apply top coat (polyguard) in accordance with manufacturers specifications.
| checkpoint | Carry out dry film thickness test using Positector coating thickness inspection instrument - a total dry film thickness of 1.2mm (1200 microns) in two finished coats.
| checkpoint | Ensure all work is completed as per ITP
| checklist | Roof, Terraces & Walkways Waterproofing |  | Roof, Terraces & Walkways Waterproofing | 0165bc3f-d9ce-47a3-b147-64d74f81445e
| section | Details
| checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
9e33bb43-5638-5d5d-92bb-d2e9655e366c | note | Attach relevant photos
| checkpoint | WP details listed at architectural drawings for clarifications are followed.
| checkpoint | All floor should be with proper falls towards the floor waste with a min. 1:100 slope.
0a5c805b-2b49-5ca5-a65d-8ef118be7569 | note | Attach relevant photos
| checkpoint | WPM must be applied around the linear drains (grated drains) before adding the leveling screed.
769b8a2d-77f3-59c4-961b-3baa3306a90e | note | Attach relevant photos
a0451640-494e-541e-8e1f-3c5de91c1946 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
2cf1aa36-3c1e-5ba5-8103-75a0bf27e474 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
4fc73ded-d7a2-57af-ae9e-e404e9dba155 | tickbox | Ensure no high points or crevices are in the substrate
33d3051f-50d4-5da0-b115-67b9e8c5d12e | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
b573c42c-ded7-5f55-93fb-13b6b5122e16 | note | Attach relevant photos
| checkpoint | Primer substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
aae7566e-0d03-5d4a-9ade-0105345f7604 | note | Attach relevant photos
| checkpoint | Seal all joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
ee8ddbcb-376f-5c45-8e34-e169babcbc4f | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup up and over external hobs. - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
4bb7e586-9baa-576b-b8e6-17f24db4b542 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup up and over external hobs - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
7d9dc148-7db0-5988-8388-e357b40f5ebe | note | Attach relevant photos
| checkpoint | Dry day for second coat (if required).
a5843674-9040-5f2e-b4e7-fccd8dd1479d | note | Attach relevant photos
| checkpoint | Apply PolyGuard protective UV top coat. - Apply selected top coat at a rate of 0.2-0.6 kg/m2 in one or two coats, depending on traffic conditions as per datasheet & application guidelines
| checkpoint | the WPM must be terminated at the specified height outlined in the wind classification report Via saw cut reglet or other WPM termination method specified at AS 4654.2, or can be overlap by approved elastomeric weather-resist coating by min. 150mm.
b685ba95-9cc8-5943-9478-5a48cd3c5806 | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
fe345553-24de-5844-9ad4-86f54789954a | note | Attach relevant photos
| checkpoint | Attatch photos for the drainage conduit.
1f0b116a-c4bc-5a10-a7b6-06d6a5969ef5 | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
fb81802f-fa09-5b80-abc8-c583fb725bb1 | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
e1e3f009-6196-5d37-9bbb-3d6d127b8651 | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Slab Edges Waterproofing |  | Slab Edge | ec230b87-b242-4e5f-9543-1b913ed9858e
| section | Details
| checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
4dbb977d-0260-5b42-97a1-1dcac9871432 | note | Attach relevant photos
97c427f3-d174-5efd-a60e-5b84d5cf9a97 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
2328207f-5f7e-5bfb-82cb-09c3e8b00a83 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
44b7a295-31c5-5648-9db1-1e02fa04cd59 | tickbox | Ensure no high points or crevices are in the substrate
4c5dc9e6-4223-553d-9289-a910b16b9e8b | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Dampen the surface to ensure the highest level of adhesion as required
8bc775a4-64e7-50b1-9ce5-225a104e3527 | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines & ensure WPM to be extened and terminated inside the drip groove.
e0dbcd86-8397-5509-b9b8-494eded87006 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines & ensure WPM to be extened and terminated inside the drip groove.
fbae3823-4716-55b7-b5e4-b1f35b7770b1 | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
d0a05505-9be4-59a1-a0ba-a2e4a0c9fe04 | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
bb4ac5d0-995b-5b94-9d05-9669562e9ae4 | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
31183314-6d8c-5b17-bab6-956ed1f8c6be | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Stormwater Tanks Waterproofing |  | Stormwater Tanks Waterproofing | 65c46244-3f19-4a3e-b320-85e39bb351dc
| section | Details
| checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
0cef2f40-61c7-5580-b4c9-dae715e25d23 | note | Attach relevant photos
1ea90a79-8bcd-51a1-a4cf-ab70f89f4652 | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
9bb95195-ace5-5e1e-9759-947e78f08422 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
3154c880-9a57-5f3c-94ac-b20ec8e2a72c | tickbox | Ensure no high points or crevices are in the substrate
5b9bbd35-eed3-5a6b-b926-f1b3d8e51597 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
1aff74a9-dc1d-569a-a131-0ac0b7b33106 | note | Attach relevant photos
| checkpoint | Seal all joints and penetrations with Polybit HydraFlex FC polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
fa4d5621-b4b8-5fe0-872d-df25b17f119e | note | Attach relevant photos
| checkpoint | Dampen the surface to ensure the highest level of adhesion as required
9021b1a8-4b1b-5364-a105-1eb7b89926d2 | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
7fca46d1-fe4a-5859-8fca-ccb7e4f5a404 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
6e53ce0f-e089-542a-ae27-51bfdd17a7ce | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
8330bf8e-28e9-5eb3-ba77-327169cd3cba | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
2c3bd4d9-a396-542e-b864-44d1564327d5 | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
49593adb-6422-57f3-8f03-2b33b4797d6b | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Stormwater Tanks Waterproofing (Balconies) |  | Stormwater Tanks Waterproofing (Balconies) | dbd66734-c5ab-4349-88f9-cdd6aa1267e5
| section | Details
| checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
558a9c82-3410-5dce-b5b0-f318d1d3f649 | note | Attach relevant photos
538c46ef-a714-5e14-af50-6b07859b94bd | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
b79fdaa9-572b-5e16-b33d-917d8eea01e6 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
0e02122a-47bd-53b7-8be0-018c0042994e | tickbox | Ensure no high points or crevices are in the substrate
5ad7c678-4a7e-5dd6-9e92-a9b891693628 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
| checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
2ff9b500-5848-50e1-a693-d2df84d4dfe6 | note | Attach relevant photos
| checkpoint | Seal all joints and penetrations with Polybit HydraFlex FC polurethane sealant. - Apply selected sealant as per datasheet & application guidelines
df33966a-2328-57c6-a4e8-65b4d427e8d5 | note | Attach relevant photos
| checkpoint | Dampen the surface to ensure the highest level of adhesion as required
752b472e-437e-5202-b71d-f57adeb6fcad | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
1f229d8e-334b-5ffe-9d9b-b9261e177ae9 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydralastic Flex 2K on walls and floors - Apply selected membrane at a rate of 1.6kg/m2 for 1.0-2.0mm thickness as per datasheet & application guidelines
a9f7bfc9-5abc-58d6-aebe-e3960ebef0b1 | note | Attach relevant photos
| checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
cb9df272-3229-525f-a454-0594297bf450 | note | Attach relevant photos
| checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
91b698c0-30e3-5c2c-8528-89f739717f8f | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
bae8e237-6fbf-5417-8e0f-8aa820e4500f | note | HOLDPOINT - Once all above items have been signed off work may proceed
| checklist | Waste/Bin Rooms |  | Waste/Bin Rooms | e8dd6025-ae0e-4cba-b64f-05545c612c3f
| section | Details
| checkpoint | Area barricaded off to allow no access with signs posted/ visible to include date of application, "No access waterproofing work in progress"
d7c6b71b-1196-5d57-a63e-ae16e67fcaa1 | note | Attach relevant photos
f4e0a084-d584-549d-97c7-9dc3137a252c | tickbox | Membrane system & methodology checked off against Aland standard waterproofing details & MSDS
69f28ae3-264a-5494-adee-29e113b41471 | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
| checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
ffc8b2cb-2b0a-559a-b021-ccebe3a0f97e | note | Attach relevant photos
| checkpoint | Primer substrate with Polybit Hydrapoxy- Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
0434ba03-4121-542c-a84b-d4dcaef1415f | note | Attach relevant photos
cedcd477-c544-5be0-9c91-ba8f064e6536 | note | Attach relevant photos
| checkpoint | Apply 1st coat of Polybit Hydrapoxy flooring on floors and walls as per datasheet & application guidelines
2a638111-8fab-5987-ae27-a08718a8d553 | note | Attach relevant photos
| checkpoint | Apply 2nd coat of Polybit Hydrapoxy flooring on walls and floors - Apply selected membrane as per datasheet & application guidelines
9e631876-b50f-5e53-aeb2-f07da74cb563 | note | Attach relevant photos
| checkpoint | Dry day for second coat (if required).
484fe4c5-4f50-5b5d-a20f-5cc06517ada1 | note | Attach relevant photos
| checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
680de115-9433-5bbb-9948-49deb05bffa7 | note | HOLDPOINT - Once all above items have been signed off work may proceed