## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Roof & Awnings ITP
section | Details
checkpoint | Area barricaded off to allow no access to roofs with signs posted/ visible to include date of application
checkpoint | Ensure "No access waterproofing work in progress"
checkpoint | Membrane system and methodology checked off against standard details and MSDS and guidelines
checkpoint | Surface Preparation as per Application Guide
checkpoint | Substrate clean, dry and free from dust.
checkpoint | Ensure substrate is structurally sound and ready to receive membrane
signoff | Ensure Humidity, temperature and moisture are in accordance with manufacturer's recommendations prior to primer - have signed by Aland - Do not proceed if above has not been signed off
checkpoint | Apply Primer (Polyprime or Hydrapoxy)
checkpoint | Ensure all floor wastes and pipes have been primed in accordance with manufacturer's recommendations (PVC prime & Metal prime)
checkpoint | All corners have polyurethane bond breaker (hydraflex) installed with min 12mm radios
checkpoint | Ensure Humidity, temperature and moisture are in accordance with manufacturer's recommendations prior to first coat
checkpoint | Apply first coat of membrane (Hydraguard)
checkpoint | Apply final coat of membrane (Hydraguard)
checkpoint | Allow curing in accordance with manufacturers specification 24-48 hours min
checkpoint | Apply top coat (polyguard) in accordance with manufacturers specifications.
checkpoint | Carry out dry film thickness test using Positector coating thickness inspection instrument - a total dry film thickness of 1.2mm (1200 microns) in two finished coats.
checkpoint | Ensure all work is completed as per ITP
checklist | Roof & Awnings ITP (No 3rd)
section | Details
checkpoint | Area barricaded off to allow no access to roofs with signs posted/ visible to include date of application
checkpoint | Ensure "No access waterproofing work in progress"
checkpoint | Surface Preparation as per Application Guide
checkpoint | Substrate clean, dry and free from dust.
checkpoint | Ensure substrate is structurally sound and ready to receive membrane
signoff | Ensure Humidity, temperature and moisture are in accordance with manufacturer's recommendations prior to primer - have signed by Aland - Do not proceed if above has not been signed off
checkpoint | Apply Primer (Polyprime or Hydrapoxy)
checkpoint | Ensure all floor wastes and pipes have been primed in accordance with manufacturer's recommendations (PVC prime & Metal prime)
checkpoint | All corners have polyurethane bond breaker (hydraflex) installed with min 12mm radios
checkpoint | Ensure Humidity, temperature and moisture are in accordance with manufacturer's recommendations prior to first coat
checkpoint | Apply first coat of membrane (Hydraguard)
checkpoint | Apply final coat of membrane (Hydraguard)
checkpoint | Allow curing in accordance with manufacturers specification 24-48 hours min
checkpoint | Apply top coat (polyguard) in accordance with manufacturers specifications.
checkpoint | Carry out dry film thickness test using Positector coating thickness inspection instrument - a total dry film thickness of 1.2mm (1200 microns) in two finished coats.
checkpoint | Ensure all work is completed as per ITP