## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Roof & Awnings ITP |  | Roof & Awnings ITP |  | a1cdfcee-b39d-48c4-b34a-01bdcd5ea150
| section | Details
| checkpoint | Area barricaded off to allow no access to roofs with signs posted/ visible to include date of application
| checkpoint | Ensure "No access waterproofing work in progress"
| checkpoint | Surface Preparation as per Application Guide
| checkpoint | Substrate clean, dry and free from dust.
| checkpoint | Ensure substrate is structurally sound and ready to receive membrane
| signoff | Ensure Humidity, temperature and moisture are in accordance with manufacturer's recommendations prior to primer - have signed by Aland - Do not proceed if above has not been signed off
| checkpoint | Apply Primer (Polyprime or Hydrapoxy)
| checkpoint | Ensure all floor wastes and pipes have been primed in accordance with manufacturer's recommendations (PVC prime & Metal prime)
| checkpoint | All corners have polyurethane bond breaker (hydraflex) installed with min 12mm radios
| checkpoint | Ensure Humidity, temperature and moisture are in accordance with manufacturer's recommendations prior to first coat
| checkpoint | Apply first coat of membrane (Hydraguard)
| checkpoint | Apply final coat of membrane (Hydraguard)
| checkpoint | Allow curing in accordance with manufacturers specification 24-48 hours min
| checkpoint | Apply top coat (polyguard) in accordance with manufacturers specifications.
| checkpoint | Carry out dry film thickness test using Positector coating thickness inspection instrument - a total dry film thickness of 1.2mm (1200 microns) in two finished coats.
| checkpoint | Ensure all work is completed as per ITP