## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
53a1aaa9-0b97-4702-a1cf-38c711d133c5 | checklist | Roof & Awnings ITP |  | Roof & Awnings ITP
897d9cc1-45b1-4a91-8337-b887ba99cf8d | section | Details
3e3ff858-2e7f-4de8-9e27-d7839e470868 | checkpoint | Area barricaded off to allow no access to roofs with signs posted/ visible to include date of application
6c9f9eeb-fdd9-4ac0-955a-f60490d2f020 | checkpoint | Ensure "No access waterproofing work in progress"
de94c55c-f6b8-4482-9de6-d3e3f28116c1 | checkpoint | Surface Preparation as per Application Guide
9a384acb-c1ce-4251-9d42-a153fb0ba69f | checkpoint | Substrate clean, dry and free from dust.
44faf237-41dd-4040-9332-906b1cdff4ad | checkpoint | Ensure substrate is structurally sound and ready to receive membrane
5737a37e-4518-428b-9b1a-bf29e0791dc8 | signoff | Ensure Humidity, temperature and moisture are in accordance with manufacturer's recommendations prior to primer - have signed by Aland - Do not proceed if above has not been signed off
84f9670d-93bd-46e2-9485-ac79fe4e5565 | checkpoint | Apply Primer (Polyprime or Hydrapoxy)
c0118938-b36c-46f8-a15f-0b15d7aa3be0 | checkpoint | Ensure all floor wastes and pipes have been primed in accordance with manufacturer's recommendations (PVC prime & Metal prime)
0cd0362f-868c-4a4d-a143-5c646a273796 | checkpoint | All corners have polyurethane bond breaker (hydraflex) installed with min 12mm radios
9cd5f75d-1e2a-4883-9d65-869684485fce | checkpoint | Ensure Humidity, temperature and moisture are in accordance with manufacturer's recommendations prior to first coat
2ee55920-aa24-43ad-a447-a5b988f3a80a | checkpoint | Apply first coat of membrane (Hydraguard)
2ff7f244-52f4-4639-8077-5deb16b57cb3 | checkpoint | Apply final coat of membrane (Hydraguard)
071b879a-f0a9-48cc-bf0c-1e90c732e32d | checkpoint | Allow curing in accordance with manufacturers specification 24-48 hours min
2a2a1868-74d1-4103-89d7-340c662e4c1d | checkpoint | Apply top coat (polyguard) in accordance with manufacturers specifications.
77320b7e-ba76-45a2-95d8-3cd652e6f607 | checkpoint | Carry out dry film thickness test using Positector coating thickness inspection instrument - a total dry film thickness of 1.2mm (1200 microns) in two finished coats.
45fcd0b9-ae6f-4769-ad4c-880fdcc3a9a1 | checkpoint | Ensure all work is completed as per ITP