## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Site Establishment and Safety Checklist
section | Details
checkpoint | Delivery and goods lift location
checkpoint | Delivery requirements i.e. booking process
checkpoint | On site storage / office location
checkpoint | Site specific restrictions i.e. noise / starting times
checklist | Ductwork Checklist
section | Ductwork
checkpoint | Rectangular duct installed as per latest drawing
checkpoint | Duct flanges firmly bolted and sealed where required
checkpoint | Cleats installed as required
checkpoint | Correct hanger spacing / supports installed
checkpoint | DW insulated where required and damage free
checkpoint | Ductwork restrained for wind/seismic where required
checkpoint | Any required ductwork leakage testing
checkpoint | Pops & flex installed as per latest drawing
checkpoint | Correct hanger spacing / supports installed for flex
checkpoint | Free from support off other services
checkpoint | Flexible duct connections completed correctly
checkpoint | Blade dampers installed as documented and left in the open position
checkpoint | BD pop access panel coordinated and marked
checkpoint | Cushion boxes installed as per latest drawing
checkpoint | Balancing dampers installed as documented and left in the open position
checkpoint | Location of register coordinted with other services and marked on plan or floor
checkpoint | Photos of ductwork correctly sealed through smoke wall & smoke damper
checklist | Pipework Checklist
section | Pipework
checkpoint | Pipework installed as per latest drawings
checkpoint | Pipework installed level and free of damage
checkpoint | All joins welded / crimped as per manufacturer's instructions
checkpoint | Air bleeds installed in pipework where required
checkpoint | Riser or area branch valve access panel coordinated and marked
checkpoint | Correct hanger spacing / supports installed for pipe runs
checkpoint | No other services suspended from pipework
checkpoint | Pipework lagged where required and correct thickness
checkpoint | Pipework labelled
checkpoint | Pipework secitons though fire walls lagged as per test report
checkpoint | Correct hanger spacing / fall
checkpoint | Drain tested
checkpoint | Drain pump installed level and tested
checkpoint | Drain terminates at a tundish
checkpoint | Drains, pump and tundish access for maintenance.
checklist | Indoor Equipment Checklist
section | Indoor Equipment
checkpoint | Indoor Unit (IDU) correctly supported as per project engineering requirements
checkpoint | Correct IDU installed as per latest drawing
checkpoint | Flexible connections installed and sealed
checkpoint | Access to filter bank / filters installed
checkpoint | Access to all relevant controls and isolators
checkpoint | IDU access panel coordinated and marked
checkpoint | Ventilation fan correctly supported as per project engineering requirements
checkpoint | Correct fan installed as per latest drawing
checkpoint | Fan connections secured and sealed
checkpoint | Access to fan and isolator
checkpoint | Ventilation fan access panel coordinated and marked
checkpoint | Correct VAV installed as per latest drawing
checkpoint | Access to VAV and controls
checkpoint | VAV access panel coordinated and marked
checklist | Grille Fit-Off Checklist
section | Grille Fit-Off
checkpoint | Grilles installed in correct location as per latest duct layout / RCP
checkpoint | Correct grille type installed
checkpoint | Grille installed flush and square
checkpoint | Are all grilles installed correctly? Air leaks, vibration or failure
checkpoint | Grille color as per schedule
checkpoint | Grille left clean of fingerprints and caps installed where required
checkpoint | Grille fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | Refrigeration Pipe Checklist
section | Refrigeration Pipe
checkpoint | Correct IDU & ODU installed as per latest drawing & schedule
checkpoint | Installed as per latest drawings
checkpoint | No other services suspended from pipe work (Attach Photos below)
checkpoint | Installation damage free (Any Issues comment/attach Photos below)
checkpoint | Correct supports used and support spacing
checkpoint | Pipe labelled after insulation - provide photo evidence
checkpoint | Pipe mains installation completed to drawings/specification
checkpoint | Pipework system pressure tested
checkpoint | Area left clean and tidy - photos of cleanliness or issues
checklist | All Subbie Rough-in Progression Checklist
section | All Subbie Rough-in Progression
checkpoint | All work in zone completed and appear compliant
label | Pass once all work complete
checklist | All Subbie Fit off & Testing Progression Checklist
section | All Subbie Fit off & Testing Progression
checkpoint | All work in zone completed and appear compliant
label | Pass once all work complete
checklist | As Builts Checklist
section | As Builts
checkpoint | Update As-Built's of any known changes
checklist | Fan Checklist
section | Fan
checkpoint | Fan installed as per latest drawing
checkpoint | Inspect the fan. Record and report for any issues
checkpoint | Fan is labelled clearly
checkpoint | Confirm ductwork connections to the fans are correct and include flexible connections
checkpoint | Confirm VSD is installed
checkpoint | Confirm test points, sensors and gauges have been provided and installed as documented
checkpoint | Confirm correct eletrical connections to the fan
checkpoint | Adequate maintenance clearance maintained
checkpoint | Unit complete with acoustic wrapping as per documented
checkpoint | Installed as per manufacturer's requirements. Refer to specific equipment schedule for detail.
checklist | Plantroom Equipment Checklist
section | Plantroom Equipment
checkpoint | Coil correctly supported as per project engineering requirements
checkpoint | Pipework installed as per latest drawings
checkpoint | Pipework installed level and free of damage
checkpoint | All joins welded / crimped as per manufacturer's instructions
checkpoint | Air bleeds installed in pipework where required