## Project Structure
Folder Structures | Work Item | Level | Tag ID No & Panel No | Checklists
Site QA
Prefab
Basement 3
|  |  | 26520 542-B3-01 | Prefab ITP
|  |  | 26521 542-B3-02 | Prefab ITP
|  |  | 26522 542-B3-03 | Prefab ITP
|  |  | 26523 542-B3-04 | Prefab ITP
|  |  | 26524 542-B3-05 | Prefab ITP
|  |  | 26525 542-B3-06 | Prefab ITP
|  |  | 26526 542-B3-07 | Prefab ITP
|  |  | 26527 542-B3-08 | Prefab ITP
|  |  | 26528 542-B3-09 | Prefab ITP
|  |  | 26529 542-B3-10 | Prefab ITP
Manufacture
Basement 3
|  |  | 26520 542-B3-01 | Manufacture ITP
|  |  | 26521 542-B3-02 | Manufacture ITP
|  |  | 26522 542-B3-03 | Manufacture ITP
|  |  | 26523 542-B3-04 | Manufacture ITP
|  |  | 26524 542-B3-05 | Manufacture ITP
|  |  | 26525 542-B3-06 | Manufacture ITP
|  |  | 26526 542-B3-07 | Manufacture ITP
|  |  | 26527 542-B3-08 | Manufacture ITP
|  |  | 26528 542-B3-09 | Manufacture ITP
|  |  | 26529 542-B3-10 | Manufacture ITP

## Checklists
type | name | values
checklists | Manufacture ITP
section | Formwork Set Out
checkpoint | Internal set out - Rebates
checkpoint | Internal set out - Far Side Ferrules
checkpoint | Internal set out - Vertical Joint
checkpoint | Internal set out - Horizontal Joint
checkpoint | Internal set out - Penos
checkpoint | Panel ID Tag fitted
section | Pre-Pour Inspection
checkpoint | Formwork
text | Dimensions
text | Stability
checkpoint | Panel edge
text | Details
text | Penetrations
checkpoint | Reinforcement
text | Sizes
text | Location
text | Fixing
checkpoint | Lifters
text | Type
text | Location
checkpoint | Grout Tubes
text | Type
text | Location
checkpoint | Connectors
text | Type
text | Location
checkpoint | Other ferrules
text | Type
text | Location
checkpoint | Other Inserts
text | Type
text | Location
checkpoint | Cover Check
section | Pour
checkpoint | Test
text | Date:
text | Time:
text | Air Temp:
text | Water:
text | Docket No:
text | Placed By:
text | Finished By:
checkpoint | Panel Stripped - Grout tubes cleared
checkpoint | Panel Stripped - Lifters cleared & clutch tested
section | Removed from mould
checkpoint | Attach any relevant documents or photos
select | Crane or Forklift | Crane, Forklift
section | As Built Panel Inspection
checkpoint | All perimeter dimensions
checkpoint | Square check
checkpoint | All penetration dimensions
checkpoint | Rebates
checkpoint | Top lifters
checkpoint | Side lifters
checkpoint | Propoints
checkpoint | Grout tube location
checkpoint | Ferrules checked
checkpoint | Ferrules cleared with tap & spray
checkpoint | All arisis rubbed smooth
checkpoint | Grout tube fill points cleared
checkpoint | Panel Racked
text | Rack No.
bool | Crane
bool | Forklift
checkpoint | Completed
signoff | Signed By
checklists | Prefab ITP
section | Set Out
checkpoint | Attach any relevant documents or photos
text | Panel/ Draw No:
text | Panel ID:
text | Concrete:
text | Drawing Rev No: IFA
text | Drawing Rev No: IFC
text | Panel Thickness:
text | Length:
text | Height:
text | Weight
section | Prefab
checkpoint | U Bars Top
select | Bar Type | N10, N12, N16, N20
text | Bar Type
checkpoint | U Bars Bottom
select | Bar Type | N10, N12, N16, N20
text | Bar Type
checkpoint | Sides
select | Bar Type | N10, N12, N16, N20
text | Bar Type
checkpoint | Trimmer/ Corner Bar Near Side
select | Bar Type | N10, N12, N16
text | Bar Type
checkpoint | Central
select | Bar Type | N10, N12, N16
text | Bar Type
checkpoint | Far Side
select | Bar Type | N10, N12, N16
text | Bar Type
checkpoint | Bar
text | A Layer
text | B Layer
text | C Layer
text | D Layer
checkpoint | Mesh
select | A Layer | SL81, SL82, SL92, SL102,
text | A Layer
select | B Layer | SL81, SL82, SL92, SL102,
text | B Layer
select | Mid Layer | SL81, SL82, SL92, SL102,
text | Mid Layer
checkpoint | Penos
checkpoint | Rebates Near
checkpoint | Rebates Far
checkpoint | Propoints Near
text | No Of:
checkpoint | Propoints Far
text | No Of:
checkpoint | Correct Heights for Panel Thickness
checkpoint | Grout Tubes - Top
select | Diameter | 50mm, 65mm, 80mm
text | Diameter
text | No of Lengths
checkpoint | Grout Tubes - Bottom
select | Diameter | 50mm, 65mm, 80mm
text | Diameter
text | No of Lengths
checkpoint | Spouts - Near
checkpoint | Spouts - Far
checkpoint | Structural Connections
checkpoint | M16
text | No Of.
checkpoint | M20
text | No Of.
checkpoint | Cast Plate
text | No Of.
checkpoint | Correct Heights for Panel Thickness
checkpoint | Slab Connections
text | Type
text | No Of.
text | Top
text | Centre
text | Bottom
checkpoint | Lifters: GAL Top
text | No Of.
select | SWL | 8T, 10T
text | SWL
checkpoint | Lifters: GAL Side
text | No Of.
select | SWL | 8T, 10T
text | SWL
checkpoint | Lifters: GAL Face
text | No Of.
select | SWL | 7T
text | SWL
checkpoint | Prefab Built By
signoff | Checked By