## Checklists
Type | Name | Values | Prefix | Postfix | Usage Count | User Addable | Template Name
checklist | Boxing to footing | [5 empty] | QA - Internal Frames Checklist
section | Wall
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm cut ground hieghts
checkpoint | Boxing mark off grid
checkpoint | Shutter to hieght or over size
checkpoint | Site concrete in place and 80 mm thick
checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint | Concrete hieght bead in place
checkpoint | Botls to bottom place every 600 mm
checkpoint | Braces in place - every 600
checkpoint | Strong back in place if required
Checkpoint | Area stripped
checklist | Boxing Pad
section | Pad
Checkpoint | Has area been handed over by W & H
checkpoint | Boxing mark off grid
checkpoint | Shutter to hieght or over size
checkpoint | Site concrete in place and 80 mm thick
checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint | Concrete hieght bead in place
checkpoint | Botls to bottom place every 600 mm
checkpoint | Braces in place - every 600
checkpoint | Strong back in place if required
Checkpoint | Area stripped
checklist | Uppper floor slab
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm hieghts
checkpoint | Boxing mark off grid
checkpoint | Shutter to hieght or over size
checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint | Concrete hieght bead in place if required
checkpoint | Botls to bottom place every 600 mm
checkpoint | Braces in place - every 600
checkpoint | Strong back in place if required
Checkpoint | Area stripped
Checkpoint | Shower rabate in place
Check point | Bathroom rabate in place
checklist | Ground floor slab
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm hieghts
checkpoint | Boxing mark off grid
checkpoint | Shutter to hieght or over size
checkpoint | rebate in place
checkpoint | rebate type correct
checklist | Precast install
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm location
checkpoint | Grid marked / survey point given
checkpoint | shims in place at base
checkpoint | Gap maintained between panels
checkpoint | starters in place
checkpoint | props installed as per plan
checklist | Precast install - flat slabs
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm location
checkpoint | Grid marked / survey point given
checkpoint | back propping in place and at hieght
checkpoint | layout confirmed
checkpoint | glav angle in place
checklist | Precast install - Balcony
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm location
checkpoint | Grid marked / survey point given
checkpoint | back propping in place and at hieght
checkpoint | Front front level
checkpoint | Side level
checklist | Window door Opening / Framing
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm hieghts of datum
checkpoint | Is rebate correct
checkpoint | Framing bolted as requied
checkpoint | DPC installed
checkpoint | Correct framing Members
checkpoint | Is wall plumb
checkpoint | is opening square
checklist | Framing to steel beam
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm location
checkpoint | Are services installed
checkpoint | All bolts installed
checkpoint | DPC installed where required
checklist | GIB Weatherline
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Framing inspected to be covered
checkpoint | Screw patten achieve
checkpoint | All joints taped
checkpoint | Window area taped
checkpoint | Rebates taped
Checklist | Balcony soffit framing
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Framing inspected to be covered
checkpoint | DPC in place
checkpoint | are bolts installed
checkpoint | Set out correct
checklist | Roof framing
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Is steel complete
checkpoint | Steel beams packed
checkpoint | All bolts installed to bearers
checkpoint | DPC installed where required
checkpoint | trusses installed
checkpoint | Hip trusse nogged
checkpoint | Ridge nogged
checkpoint | hardware install
checkpoint | Lintel bolts and brackets

## b & 6
B 5 & ^
Level | area on floor / Grid | lists required
Footings Ground | [5 empty] | Ground Floor framing
| Grid 1 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 2 | Pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 |  |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | pad | footing | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 20 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | pad | footing | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  |  |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid b | Pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c |  |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid d |  |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid e | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
Level 1 Slab | [7 empty] | Ground Floor framing
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony |  |  |  |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs
|  | Balcony install |  | Precast install - Balcony |  |  |  |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline | Balcony soffit framing
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
Level 2 Slab | [6 empty] | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab | footing | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
Level 3 Slab | [8 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | [5 empty] | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
Level 4 Slab | [8 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab | footing | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
Level 5 Slab | [8 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  |  |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
Level 6 Slab | [8 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  |  |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing