## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Excavation (EX) | itp |  |  |  |  | ITP - Excavation (EX)
section | Details
checkpoint | 1 - Underlying Lots conform (if applicable)
label | Inspection / Test Method / Standard / Specification - Lot Register, Relevant Lots
label | Stage or Frequency of Sampling - Prior to commencement of works
label | Acceptance Criteria - Works cannot commence until underlying lots are conforming
label | Method - QBC QA Records
label | Level of Inspection - Inspection
label | Verification By - CQR
label | Record - Verification Checklist Sheet EX
checkpoint | 2 - Services identified and protected
label | Inspection / Test Method / Standard / Specification - DBYD
label | Stage or Frequency of Sampling - Prior to commencement of works at each location
label | Acceptance Criteria - Check DBYD Plans to ensure all services have been located.
label | ○ Locate underground services with a qualified locator and mark with survey pegs or marker paint to identify services with close proximity to the works
label | Method - Visual Check
label | Level of Inspection - Inspection
label | Verification By - CQR
label | Record - Verification Checklist Sheet EX, DBYD Plans
checkpoint | 3 - Cultural Heritage Monitor (if required)
label | Inspection / Test Method / Standard / Specification - MRTS51.1 CL3.1
label | Stage or Frequency of Sampling - As required
label | Acceptance Criteria - MRTS51.1 Clause 3.2 notes that No known Indigenous Cultural Heritage within and adjacent to the site were identified.
label | ○ In case of an unexpected heritage find, then prior to commencing ground disturbing activities, the Contractor shall ensure that all staff involved in, or supervising, these activities, have attended the Principal’s Cultural Heritage Induction or an alternative Cultural Heritage Induction course deemed suitable by the Administrator. This includes, as a minimum, all Site management staff, employees and subcontractors working on activities which disturb the natural ground surface. The Principal’s Cultural Heritage Induction shall be arranged through the Administrator.
label | ○ This shall be communicated at Pre-start/ tool-box meetings.
label | Method - QBC Environmental Strategies
label | Level of Inspection - Inspection
label | Verification By - CQR
label | Record - Verification Checklist Sheet EX
checkpoint | 4 - Erosion and Sediment controls in place
label | Inspection / Test Method / Standard / Specification - MRTS52 CL6.1 HOLD POINT 1
label | ○ MRTS52 CL6.2
label | ○ MRTS52 CL7 HOLD POINT 2
label | Stage or Frequency of Sampling - Submit Erosion and Sediment Control design to Administrator prior to undertaking work
label | Acceptance Criteria - The Contractor shall be responsible for the installation of measures for the control of erosion and sediment throughout the worksite to ensure construction works do not result in erosion and sedimentation that cause environmental nuisance or harm outside the worksite.
label | The Contractor shall consider at least the following erosion and sediment control strategies:
label | – Minimise clearing.
label | – Minimise the extent and duration of soil exposure.
label | – Divert clean waters from areas of disturbance.
label | – Early installation of all drainage, erosion and sediment control measures
label | – Protect exposed soil surfaces from erosion.
label | – On-site capture of sediment
label | – Manage topsoil.
label | – Progressive stabilisation and revegetation of disturbed areas
label | ○ Prior to the natural surface is disturbed on a section of the Works, the Contractor shall submit an Erosion and Sediment Control Plan (ESCP) for that section. Clearing and grubbing shall not start until the ESCP has been assessed as suitable by the Administrator.
label | ○ MRTS52 Cl 6.1 – HOLD POINT 1
label | Erosion and sediment control measures shall comply with the following requirements:
label | – Early installation of all drainage erosion and sediment control measures
label | – All erosion and sediment control measures shall be installed and maintained in good working order
label | – Any runoff from the site shall comply with the provisions of the Environmental Protection (Water) Policy 1997
label | – There shall be no erosion resulting from construction practices unless there are provisions within worksite to manage resulting sediment.
label | ○ As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the works, the Contractor must install erosion and sediment controls (including sediment traps, catch banks and diversion drains) associated with drainage paths flowing through the works area. The completion of these activities will be a Hold Point for any further earthworks.
label | ○ MRTS52 CL7 – HOLD POINT 2
label | Method - QBC QA Records, Receipt of Notice to Contractor confirming approval of Erosion and Sediment Control Plan, Administrator Surveillance On-Site
label | Level of Inspection - Hold Point
label | Verification By - CQR Administrator
label | Record - Notice to Contractor, Verification Checklist Sheet EX, Hold Point Release
holdpoint | HOLD POINT
checkpoint | 5 - Dust control measures in place
label | Inspection / Test Method / Standard / Specification - MRTS51 CL8.7.1, MRTS51 CL8.7.2
label | Stage or Frequency of Sampling - Works generating dust
label | Acceptance Criteria - The Contractor shall be responsible for managing work under the Contract to avoid and minimise Environmental Harm on air quality including from dust, smoke and offensive odours and other air pollutants.
label | ○ Where specified in Clause 6.3 of Annexure MRTS51.1, the Contractor shall assess and manage construction related air quality in accordance with Chapter 6 of the Road Traffic Air Quality Management Manual. Construction related air quality complaints shall be managed in accordance with Chapter 7 of the Road Traffic Air Quality Management Manual
label | The Contractor shall consider at least the following air quality management strategies:
label | – Regular watering or temporary sealing of the site and access roads
label | – Avoiding works (e.g., stripping, excavation, etc) during dry and windy conditions
label | – Fitting equipment with dust collection/suppression devices
label | – Stabilising/covering all materials stockpiled for longer than 1 month (excluding pavement materials & screenings) by grassing, erosion blanketing, emulsion spray or other approved method.
label | – Covering loads
label | – Maintaining clean roadways to and from worksite
label | Method - QBC QA Records, QBC Environmental Strategies
label | Level of Inspection - Inspection
label | Verification By - CQR
label | Record - Verification Checklist Sheet EX
checkpoint | 6 - Level control in place
label | Inspection / Test Method / Standard / Specification - Contract Documents, Project Drawings, MRTS04 CL6.3.1
label | Stage or Frequency of Sampling - Entire excavation process
label | Acceptance Criteria - Adequate level control being utilised by contractor to ensure excavation dimensions are being monitored.
label | ○ The heights of earthworks measured anywhere on a layer surface shall not vary from those shown on the drawings, or calculated in accordance with Clause 6.1, by more than the tolerance stated in Table 6.3.1 unless specified otherwise. MRTS04 CL6.3.1
label | Method - QBC QA Records
label | Level of Inspection - Inspection
label | Verification By - CQR
label | Record - Verification Checklist Sheet EX
checkpoint | 7 - Superintendent advised of unsuitable material
label | Inspection / Test Method / Standard / Specification - MRTS04 CL 9.2
label | ○ MRTS04 CL9.4 HOLD POINT 4
label | ○ MRTS04.1 CL5
label | Stage or Frequency of Sampling - Each location of unsuitable material
label | Acceptance Criteria - Unsuitable Material shall include:
label | a) Material from swamps, marshes, and bogs
label | b) Logs, stumps, and perishable materials
label | c) Material susceptible to spontaneous combustion
label | d) Excavated material that has a WPI greater than 4000 or a pi greater than 50 as stated in clause 14.2.
label | e) Dry or wet material to a depth of 300mm or the depth of subgrade treatment, whichever is greater, which in the opinion of the administrator cannot be reasonably worked or conditioned to achieve specified requirements.
label | f) All material removed, where the material below the depth defined in clause 9.2(e) is, in the opinion of the administrator, unsuitable for compacting subsequent layers.
label | g) Material forming the foundation for a structure which has an allowable bearing pressure less than that nominated on the drawings.
label | h) Material forming the foundation for an embankment which has an allowable bearing pressure or CBR less than that stated in clause 4 of annexure MRTS04.1 or, where not so stated, a CBR less than 3 based on dynamic cone penetrometer using test method Q114B.
label | i) Material containing noxious weeds and other matter which may adversely affect the local environment, except where these are treated in an appropriate manner.
label | j) Acid sulfate soils from within the site which cannot be treated or managed in accordance with CL 10
label | k) Stripped topsoil which is deemed not suitable as planting media and is not suitable for use elsewhere in the works.
label | l) Building rubble including concrete, asphalt and other materials, except where broken down or otherwise treated and proved to be suitable for use, and
label | m) Abandoned Public Utility Plant and any associated material.
label | ○ It shall be the sole responsibility of the Contractor to prove that material is Unsuitable Material as defined in Clause 9.2. Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator.
label | ○ Where spoiling of excess and unsuitable material is to occur, the Contractor require to nominate the Stockpile locations and approved by the Administrator. The Administrator is not obliged to approve any stockpile location within the road reserve. MRTS04.1 CL5
label | ○ Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator, and provide any test results required to justify such a claim. MRTS04 CL9.4 HOLD POINT 4
label | Method - QBC QA Records
label | Level of Inspection - Hold Point
label | Verification By - CQR Administrator
label | Record - Verification Checklist Sheet EX
holdpoint | HOLD POINT
checkpoint | 8 - Bottom of excavation (subgrade)
label | Inspection / Test Method / Standard / Specification - MRTS04 CL13.3.2.1
label | ○ MRTS04 CL18.3.3.1
label | ○ MRTS04.1 CL12.3, 12.4
label | Stage or Frequency of Sampling - Notification to Administrator once excavation is complete
label | Acceptance Criteria - When the level of excavation has reached subgrade level plus a nominal allowance determined by the Contractor, the Contractor shall cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3. Hold Point 6
label | Method - QBC QA Records
label | Level of Inspection - Hold Point
label | Verification By - CQR Administrator
label | Record - Verification Checklist Sheet EX
holdpoint | HOLD POINT
checkpoint | 9 - Bottom of excavation (Other than subgrade)
label | Inspection / Test Method / Standard / Specification - MRTS04 CL13.3.1
label | ○ MRTS04 CL13.3.3
label | ○ MRTS04 CL13.3.4
label | Stage or Frequency of Sampling - Notification to Administrator once excavation is complete
label | Acceptance Criteria - The bottom of excavations shall be trimmed to the tolerances specified in Clause 6 and any loose material removed from the surface.
label | ○ Excavations shall be constructed to the shapes, lines, dimensions, and other requirements shown on the drawings.
label | ○ All permanent excavation batters shall be finished in accordance with Clause 16.
label | ○ The bottom of excavations shall be trimmed to the tolerances specified in Clause 6 and any loose material removed from the surface.
label | Confined Excavations: MRTS04 CL13.3.3
label | – Trench excavations and excavations for structures shall be carried out to the dimensions shown on the drawings or, where not so shown, to the minimum dimensions necessary to construct the Works accurately and safely under the Contract.
label | ○ Prior to any excavation Works or trench excavations, an assessment is to be undertaken to identify cadastral marks that may need protecting as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
label | ○ The material in the bottom of Confined Excavations shall comply with the density requirements of Clause 15. Where the insitu material does not comply, it shall be compacted to a depth of at least 150 mm in accordance with the requirements of Clause 15.
label | Excavation for structure foundations: MRTS04 CL 13.3.4
label | – Excavation for foundations of structures shall be carried out to the dimensions and depths shown on the drawings. All excavations for foundations shall be drained.
label | ○ When competent material has been reached at or below the depth shown on the drawings, the Foundation Surface shall be trimmed to a generally horizontal plane or to generally horizontal steps as appropriate, completely dewatered and presented for final inspection by the Contractor’s Registered Professional Engineers of Queensland (RPEQ) geotechnical engineer. No work which will cover the surface of the foundation shall proceed until the foundation has been inspected and approved by the Contractor’s RPEQ geotechnical engineer and approved by the Administrator. Hold Point 7 The Contractor shall give the Administrator three days' notice of such inspection. Witness Point 1
label | ○ If the Foundation Surface has deteriorated since the time the foundation was approved and before blinding concrete or Backfill material has been placed, additional material shall be removed until competent material is reached as described above and then Hold Point 7 shall be re-released.
label | ○ No further work to cover the Foundation Surface shall proceed until the As Constructed Survey of the excavated area have been met as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
label | Method - QBC QA Records
label | Level of Inspection - Hold Point
label | Verification By - CQR
label | Record - Verification Checklist Sheet EX
holdpoint | HOLD POINT
checkpoint | 10 - Site Cleaned up
label | Inspection / Test Method / Standard / Specification - Applicable Standards (MRTS)
label | Stage or Frequency of Sampling - At completion of works
label | Acceptance Criteria - Site is cleaned and free from potential hazards. Finished works are as per drawings/specifications.
label | Method - Visual Check
label | Level of Inspection - Inspection
label | Verification By - CQR
label | Record - Verification Checklist Sheet EX
checkpoint | 11 - Lot Closed
label | Inspection / Test Method / Standard / Specification - MRTS50 CL10.1, 11
label | Stage or Frequency of Sampling - For this lot
label | Acceptance Criteria - Lot records conform to relevant specifications. Any NCRs have been actioned and closed.
label | Final conformance requirements:
label | ○ Verification Checklist Sheet EX
label | ○ Compaction – min requirements as per MRTS04 Appendix A
label | ○ Survey – including quantities (Volume, area, perimeter) as required.
label | ○ Hold points released – where required
label | Method - Review
label | Level of Inspection - Review
label | Verification By - CQR
label | Record - Verification Checklist Sheet EX