## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-014-CIV-CAMMS-Footpaths & Shared User Paths | itp |  |  |  |  | ITP-014-CIV-CAMMS-Footpaths & Shared User Paths Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-014-CIV-CAMMS-Footpaths & Shared User Paths
note | ITP Description: CAMMS-Footpaths & Shared User Paths Scale C- 1 (Set-out & Bedding)
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): CIV
note | Revision Number: 0
note | Revision Date:
note | ITP created by: Victor Mira
note | ITP approved for use by: Victor Mira
note | 1.1 Non Dependent
note | Reference: VicRoads Section 304 August 2013
note | 1.2 Non Dependent
note | Reference: VicRoads Section 703 April 2019
note | 1.3 Non Dependent
note | Reference: Council EDCM 401
note | 1.4 Non Dependent
note | Reference: Council EDCM 501
note | 1.5 Non Dependent
note | Reference: Council EDCM 502
note | 1.6 Non Dependent
note | Reference: Council EDCM 503
note | 1.7 Non Dependent
note | Reference: AS 1379-2007
note | 1.8 Non Dependent
note | Reference: VicRoads Section 812 July 2016
section | Preliminaries - Materials
checkpoint | 2.1 Bedding Material Placement & Compaction
note | REFERENCE: IFC Drawings:
note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
note | • 812.04, 703.21
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
note | • SUP: SIZE 40mm CLASS 3 CRUSHED ROCK
note | • Material is registered with VicRoads in accordance with Code of Practice RC500.02.
textbox | • Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED HOLDPOINT AUTHORITY
checkpoint | 2.2 Concrete Mix
note | REFERENCE: IFC Drawings:
note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
note | • 703.05 (a), 703.07
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
note | — Footpaths, Residential driveways and Median islands infills: 25Mpa
note | — Industrial Crossovers: VR330/32 to be registered by Vicroads
note | — Traffic Islands: 32 Mpa
note | — SUP: VR330/32
note | • No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
textbox | • Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED HOLDPOINT AUTHORITY
checkpoint | 2.3 Reinforcement
note | REFERENCE: IFC Drawings:
note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
note | • 703.16
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
note | • Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
note | • Following steel mesh requirements shall apply as per IFC Drawings:
note | — Footpaths, Residential driveways and Median islands infills: SL72
note | — Industrial Crossovers: SL82
note | — Traffic Islands: SL72
note | — SUP: SL82
textbox | • Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED HOLDPOINT AUTHORITY
checkpoint | 2.4 Evaporative Retardant
note | REFERENCE: 703.09
note | 610.17 (f)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
textbox | • Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, for each product, prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED HOLDPOINT AUTHORITY
checkpoint | 2.5 Curing Compound
note | REFERENCE: 703.10 (a)
note | 610.23 (d)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
note | • Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, for each product, prior to placement of concrete
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED HOLDPOINT AUTHORITY
section | Preliminaries - Documents
checkpoint | 3.1 Survey Set-out
note | REFERENCE: IFC Drawings
note | 703.17
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
note | • The Nominated Authority will review and confirm the set out.
note | • Attach: Survey Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review, Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED HOLDPOINT AUTHORITY
checkpoint | 3.2 Lot Map
note | REFERENCE: MRPA Lot Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Attach Marked drawing indicating the location of this Lot
note | • Attach: Lot Map
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Attached Lot Map
textbox | Date Completed:
section | Pre-Construction Activities
checkpoint | 4.1 Site Clearing & Grubbing
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: If not completed during the site establishment, the work area needs to be cleared and grubbed.
note | • Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.2
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.2 IFC Drawings
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
note | — Using the correct and complete set of drawings
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to starting Works and at regular intervals
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Construction Activities
checkpoint | 5.1 Excavation
note | REFERENCE: 703.20
note | IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
note | • Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
note | • Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.2 Excavation-Pavement Thickness Increases for Crossings
note | REFERENCE: IFC Drawings:
note | MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
note | Relevant Council drawings:
note | • EDCM 501
note | • EDCM 502
note | • EDCM 503
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
note | • Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.3 Bedding Material Placement & Compaction
note | REFERENCE: 703.21 IFC Drawings
note | IFC Drawings:
note | MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
note | Relevant Council drawings:
note | • EDCM 501
note | • EDCM 502
note | • EDCM 503
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings:
note | • Footpath: Bedding shall 100 mm compacted thickness
note | • SUP: Bedding shall be 150 mm compacted thickness
note | • Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
note | • The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
note | • All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
note | • Attach: Bedding Material Delivery Dockets
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.4 Shared User Path - Compaction Testing
note | REFERENCE: 703.21
note | 304.08 (a) & (b)
note | 304.11 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Compaction shall meet the following requirements:
note | • Scale of Surface Level Measurement = Scale C
note | • Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
note | • Mean Value of Density Ratio % (3 tests) not less than 100%
note | • Attach: Moisture Content Test Results
note | • Attach: Mean Value of Density Ratio
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.5 Shared User Path - Proof-rolling
note | REFERENCE: 703.21
note | 304.08 (b)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Bedding material to be compacted and proof rolled before any construction.
note | • Withstands Test rolling without visible deformation or springing.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED HOLDPOINT AUTHORITY
checkpoint | 5.6 Formwork Construction & Placement
note | REFERENCE: IFC Drawings
note | 703.12
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
note | • Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
note | • Joints in formwork shall be constructed such that loss of mortar is prevented.
note | • Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.7 Construction Joints & Matching Existing Surfaces
note | REFERENCE: IFC Drawings 703.24
note | Relevant Council Standard DrawingsRelevant Council drawings:
note | • EDSM 401
note | • EDCM 501
note | • EDCM 502
note | • EDCM 503
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
note | • Consult the relevant Council Standard drawings for the joint detail, these may require:
note | i. Concrete cutting of a shear-key
note | ii. Surface roughening
note | iii. Drilling and insertion of dowel bars (may also be galvanised)
note | iv. Cutting a groove for sealant
note | • Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
note | • Transitions between different profiles shall be made in accordance with the drawings.
note | • Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.8 Isolation Joints
note | REFERENCE: IFC Drawings 703.26 (c)
note | Relevant Council Standard Drawings
note | • EDSM 401
note | • EDCM 501
note | • EDCM 502
note | • EDCM 503
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
note | ii. at any location marked on the drawings
note | • The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.9 Expansion Joints
note | REFERENCE: IFC Drawings 703.26 (a) (ii) & (b) (i)
note | Relevant Council Standard Drawings
note | • EDSM 401
note | • EDCM 501
note | • EDCM 502
note | • EDCM 503
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Where applicable, expansion joints shall be placed:
note | i. on either side of vehicle crossings
note | ii. at junctions with existing footpaths and shared use paths
note | iii. at junctions with bridges
note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
note | • The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
note | • Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
note | • Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.10 Reinforcement Placement
note | REFERENCE: IFC Drawings 703.13
note | • EDSM 401
note | • EDCM 501
note | • EDCM 502
note | • EDCM 503
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
note | — Footpaths, Residential driveways and Median islands infills: SL72
note | — Industrial Crossovers: SL82
note | — Traffic Islands: SL72
note | — SUP: SL82
note | • Minimum cover of 50mm at edges has been achieved (including tie wire locations).
note | • Any splice lengths achieve the minimum length and are in contact for this length.
note | • The reinforcement surface condition is free from dirt, debris and damage.
note | • The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
note | • Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.11 Pre-pour Survey
note | REFERENCE: IFC Drawings 703.15
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
note | Erected formwork and base layer within the tolerances below:
note | • Departure from RL = ±10mm
note | • Departure from alignment = ±10mm
note | • Rate of change of deviation from RL or alignment = 10mm in 10m
note | • Irregularities in alignment = 5mm in 3m
note | • Section dimensions = ±5mm
note | • Section dimensions (less than 25mm) = ±3mm
note | • Width of pavement = -5mm, +15mm
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.12 Pre-pour Inspection
note | REFERENCE: Section 703.09
note | Section 703.21
note | Section 610.17a), b) & c)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
note | • Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.13 Weather Conditions & Evaporation Limits
note | REFERENCE: 703.09
note | 610.17 (a - f)
note | Table 610.171
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
note | • Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.14 Concrete Testing - Sampling Frequencies-Footpath
note | REFERENCE: 703.11
note | AS 1379-2007 Clause 6.2
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
note | • Correct quantity of cylinders manufactured per sample.
note | • Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.15 Concrete Testing - Sampling Frequencies-SUP
note | REFERENCE: 703.11
note | 610.16 (b)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
note | Shared User Path:
note | • 0m3 to 10m3 = 1 sample
note | • 10m3 to 25m3 = 2 samples
note | • 25m3 to 50m3 = 3 samples
note | • 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
note | • For each additional 50m3 and additional sample shall be taken.
note | • Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
note | Footpaths:
note | • 0m3 to 50m3 = 1 sample
note | • Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
note | • Compressive strength cylinders = 2 no. 28 day strength.
note | • Correct quantity of cylinders manufactured per sample.
note | Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.16 Concrete Testing - Slump
note | REFERENCE: 703.11
note | 610.16 (c)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Slump testing tolerances =
note | <60mm = ±10mm
note | ≥60mm to ≤80mm = ±15mm
note | >80mm to ≤110mm = ±20mm
note | >110mm to ≤150mm = ±30mm
note | >150mm = ±40mm
note | Record: Required information on the Concrete Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each sample
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Concrete Tester
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.17 Placement & Compaction
note | REFERENCE: 703.08
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • All concrete batches are traceable.
note | • Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
note | • Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
note | • Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
note | • Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
note | • Vibration continued at each point until air bubbles cease to emerge from the concrete.
note | • Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
note | Record: Required information on the Concrete Pour Record.
note | Attach: Concrete Pour Record
note | Attach: Concrete Dockets
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each load
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: SP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 5.18 Surface Finishes
note | REFERENCE: IFC Drawings
note | Relevant Council Drawings
note | 703.25
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top.
note | • It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
note | • After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
note | • Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
note | • All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.19 Footpaths - Crack-control Joints / Weaken Plane Joints
note | REFERENCE: IFC Drawings
note | Relevant Council Drawings
note | 703.26 (b) (ii)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.20 Curing
note | REFERENCE: 703.10
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
note | • The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
note | • Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
note | • The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
note | • Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
note | • Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Post-construction Activities
checkpoint | 6.1
note | REFERENCE:
note
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note
note
note | METHOD:
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY:
note | – – – – – – – – – – – – – – – – –
note | CATEGORY:
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
textbox | Date Completed:
checkpoint | 6.2
note | REFERENCE:
note
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note
note
note | METHOD:
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY:
note | – – – – – – – – – – – – – – – – –
note | CATEGORY:
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
textbox | Date Completed:
checkpoint | 6.3
note | REFERENCE:
note
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note
note
note | METHOD:
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY:
note | – – – – – – – – – – – – – – – – –
note | CATEGORY:
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
textbox | Date Completed:
checkpoint | 6.4
note | REFERENCE:
note
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note
note
note | METHOD:
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY:
note | – – – – – – – – – – – – – – – – –
note | CATEGORY:
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
textbox | Date Completed:
checkpoint | 6.5
note | REFERENCE:
note
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note
note
note | METHOD:
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY:
note | – – – – – – – – – – – – – – – – –
note | CATEGORY:
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
textbox | Date Completed:
checkpoint | 6.6
note | REFERENCE:
note
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note
note
note | METHOD:
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY:
note | – – – – – – – – – – – – – – – – –
note | CATEGORY:
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
textbox | Date Completed:
checkpoint | 6.7
note | REFERENCE:
note
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note
note
note | METHOD:
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY:
note | – – – – – – – – – – – – – – – – –
note | CATEGORY:
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
textbox | Date Completed:
checkpoint | 6.8
note | REFERENCE:
note
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note
note
note | METHOD:
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY:
note | – – – – – – – – – – – – – – – – –
note | CATEGORY:
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
textbox | Date Completed:
checkpoint | 6.9
note | REFERENCE:
note
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note
note
note | METHOD:
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY:
note | – – – – – – – – – – – – – – – – –
note | CATEGORY:
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY:
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS:
textbox | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP