## Project Structure
Folder Structure |  |  |  | Checklists | #NAME?
Site QA
Switchboard's
|  |  | MSB / DB-B | Switchboards
|  |  | DB1 | Switchboards
|  |  | DBM | Switchboards
|  |  | DB2 | Switchboards
Cable Tray
|  |  | Basement | Cable Tray
|  |  | Ground Floor | Cable Tray
|  |  | First Floor | Cable Tray
|  |  | Second Floor | Cable Tray
First Fix
Basement
|  |  | Carpark | First Fix Electrical
|  |  | Ramp | First Fix Electrical
|  |  | Generator Room | First Fix Electrical
|  |  | Lift A Pit | First Fix Electrical
|  |  | Lift Lobby | First Fix Electrical
|  |  | Stairwell | First Fix Electrical
Ground Floor
|  |  | Truck Loading Bay | First Fix Electrical
|  |  | Double Stacked Carpark Area | First Fix Electrical
|  |  | Courier Pick Up G.05 | First Fix Electrical
|  |  | Mobile Setup Room G.04 | First Fix Electrical
|  |  | Breakout G.02 | First Fix Electrical
|  |  | Recruitment Store G.03 | First Fix Electrical
|  |  | Prayer Room G.01 | First Fix Electrical
|  |  | Dispatch G.06 | First Fix Electrical
|  |  | Cool Store G.07 | First Fix Electrical
|  |  | Warehouse G.10 | First Fix Electrical
|  |  | Storeoom G.13 | First Fix Electrical
|  |  | QC & Order Received G.11 | First Fix Electrical
|  |  | Share Office G.12 | First Fix Electrical
|  |  | Pallet Quarantine G.14 | First Fix Electrical
|  |  | Hall GF.05 | First Fix Electrical
|  |  | Drying Room GF.16 | First Fix Electrical
|  |  | Shower GF.15 | First Fix Electrical
|  |  | Shower GF.14 | First Fix Electrical
|  |  | DB Cupboard GF.13 | First Fix Electrical
|  |  | Toilet Shower GF.09 | First Fix Electrical
|  |  | Storage GF.08 | First Fix Electrical
|  |  | WC GF.06 | First Fix Electrical
|  |  | WC GF.07 | First Fix Electrical
|  |  | Store GF.08 | First Fix Electrical
|  |  | Sprinkler Room GF.10 | First Fix Electrical
|  |  | Stairs GF.12 | First Fix Electrical
|  |  | Entry GF.01 | First Fix Electrical
|  |  | Service Cupboard GF.04 | First Fix Electrical
|  |  | Lift B Pit | First Fix Electrical
Level 1
|  |  | Café 1.07 | First Fix Electrical
|  |  | Kitchen 1.08 | First Fix Electrical
|  |  | Store 1.09 | First Fix Electrical
|  |  | Training Room 1.06 | First Fix Electrical
|  |  | Meeting Room 1.05 | First Fix Electrical
|  |  | Recruitment Office 1.03 | First Fix Electrical
|  |  | DR Office 1.02 | First Fix Electrical
|  |  | Quiet 1.11 | First Fix Electrical
|  |  | Quiet 1.10 | First Fix Electrical
|  |  | Meeting 1.12 | First Fix Electrical
|  |  | Ther Apheresis 1.21 | First Fix Electrical
|  |  | ACC WC 1.22 | First Fix Electrical
|  |  | Ther Office 1.23 | First Fix Electrical
|  |  | Sluice 1.24 | First Fix Electrical
|  |  | Ther Apheresis 1.20 | First Fix Electrical
|  |  | ACC 1.19 | First Fix Electrical
|  |  | Ther Apheresis 1.18 | First Fix Electrical
|  |  | Waiting 1.16 | First Fix Electrical
|  |  | HR Office 1.14 | First Fix Electrical
|  |  | National Office / Open Plan 1.15 | First Fix Electrical
|  |  | Office Hallway / Corridor Areas | First Fix Electrical
|  |  | Hall FF.04 | First Fix Electrical
|  |  | Lobby FF.14 | First Fix Electrical
|  |  | Cleaner FF.13 | First Fix Electrical
|  |  | WC FF.11 | First Fix Electrical
|  |  | Hall FF.09 | First Fix Electrical
|  |  | Elec Cupboard FF.12 | First Fix Electrical
|  |  | WC FF.05 | First Fix Electrical
|  |  | Acc WC FF.06 | First Fix Electrical
|  |  | Services Cupboard FF.07 | First Fix Electrical
|  |  | Egress Hallway to External Stairs | First Fix Electrical
|  |  | Stairwell FF.10 | First Fix Electrical
Level 2
|  |  | Plasma Donors 2.04 | First Fix Electrical
|  |  | Waiting 2.03 | First Fix Electrical
|  |  | Reception 2.02 | First Fix Electrical
|  |  | Whole Blood Donors 2.05 | First Fix Electrical
|  |  | Refreshment Space 2.06 | First Fix Electrical
|  |  | Interview 2.08 | First Fix Electrical
|  |  | Interview 2.09 | First Fix Electrical
|  |  | Interview 2.10 | First Fix Electrical
|  |  | Interview 2.11 | First Fix Electrical
|  |  | Interview 2.12 | First Fix Electrical
|  |  | Admin Office 2.21 | First Fix Electrical
|  |  | Admin Storage 2.19 | First Fix Electrical
|  |  | Machine Storage 2.18 | First Fix Electrical
|  |  | Consumable Storage 2.17 | First Fix Electrical
|  |  | Consignment 2.16 | First Fix Electrical
|  |  | Quiet / Study 2.15 | First Fix Electrical
|  |  | Nurses Station 2.13 | First Fix Electrical
|  |  | Managers 2.14 | First Fix Electrical
|  |  | Comms 2.20 | First Fix Electrical
|  |  | BOH Hallway / Corridor Areas | First Fix Electrical
|  |  | Lift B | First Fix Electrical
|  |  | Lift A | First Fix Electrical
|  |  | Service Cupboard SF.03 | First Fix Electrical
|  |  | ACC WC SF.04 | First Fix Electrical
|  |  | Lobby SF.05 | First Fix Electrical
|  |  | WC SF.06 | First Fix Electrical
|  |  | WC SF.07 | First Fix Electrical
|  |  | WC SF.08 | First Fix Electrical
|  |  | Cleaner SF.09 | First Fix Electrical
|  |  | WC SF.10 | First Fix Electrical
|  |  | WC SF.11 | First Fix Electrical
|  |  | Lobby SF.012 | First Fix Electrical
|  |  | Service Cupboard SF.14 | First Fix Electrical
|  |  | HWC Cupboard SF.13 | First Fix Electrical
|  |  | Service Room SF.15 | First Fix Electrical
|  |  | DB Cupboard SF.16 | First Fix Electrical
|  |  | Stairwell SF.17 | First Fix Electrical
|  |  | Lift Lobby SF.01 | First Fix Electrical
Second Fix
Basement
|  |  | Carpark | Second Fix
|  |  | Ramp | Second Fix
|  |  | Generator Room | Second Fix
|  |  | Lift A Pit | Second Fix
|  |  | Lift Lobby | Second Fix
|  |  | Stairwell | Second Fix
Ground Floor
|  |  | Truck Loading Bay | Second Fix
|  |  | Double Stacked Carpark Area | Second Fix
|  |  | Courier Pick Up G.05 | Second Fix
|  |  | Mobile Setup Room G.04 | Second Fix
|  |  | Breakout G.02 | Second Fix
|  |  | Recruitment Store G.03 | Second Fix
|  |  | Prayer Room G.01 | Second Fix
|  |  | Dispatch G.06 | Second Fix
|  |  | Cool Store G.07 | Second Fix
|  |  | Warehouse G.10 | Second Fix
|  |  | Storeoom G.13 | Second Fix
|  |  | QC & Order Received G.11 | Second Fix
|  |  | Share Office G.12 | Second Fix
|  |  | Pallet Quarantine G.14 | Second Fix
|  |  | Hall GF.05 | Second Fix
|  |  | Drying Room GF.16 | Second Fix
|  |  | Shower GF.15 | Second Fix
|  |  | Shower GF.14 | Second Fix
|  |  | DB Cupboard GF.13 | Second Fix
|  |  | Toilet Shower GF.09 | Second Fix
|  |  | Storage GF.08 | Second Fix
|  |  | WC GF.06 | Second Fix
|  |  | WC GF.07 | Second Fix
|  |  | Store GF.08 | Second Fix
|  |  | Sprinkler Room GF.10 | Second Fix
|  |  | Stairs GF.12 | Second Fix
|  |  | Entry GF.01 | Second Fix
|  |  | Service Cupboard GF.04 | Second Fix
|  |  | Lift B Pit | Second Fix
Level 1
|  |  | Café 1.07 | Second Fix
|  |  | Kitchen 1.08 | Second Fix
|  |  | Store 1.09 | Second Fix
|  |  | Training Room 1.06 | Second Fix
|  |  | Meeting Room 1.05 | Second Fix
|  |  | Recruitment Office 1.03 | Second Fix
|  |  | DR Office 1.02 | Second Fix
|  |  | Quiet 1.11 | Second Fix
|  |  | Quiet 1.10 | Second Fix
|  |  | Meeting 1.12 | Second Fix
|  |  | Ther Apheresis 1.21 | Second Fix
|  |  | ACC WC 1.22 | Second Fix
|  |  | Ther Office 1.23 | Second Fix
|  |  | Sluice 1.24 | Second Fix
|  |  | Ther Apheresis 1.20 | Second Fix
|  |  | ACC 1.19 | Second Fix
|  |  | Ther Apheresis 1.18 | Second Fix
|  |  | Waiting 1.16 | Second Fix
|  |  | HR Office 1.14 | Second Fix
|  |  | National Office / Open Plan 1.15 | Second Fix
|  |  | Office Hallway / Corridor Areas | Second Fix
|  |  | Hall FF.04 | Second Fix
|  |  | Lobby FF.14 | Second Fix
|  |  | Cleaner FF.13 | Second Fix
|  |  | WC FF.11 | Second Fix
|  |  | Hall FF.09 | Second Fix
|  |  | Elec Cupboard FF.12 | Second Fix
|  |  | WC FF.05 | Second Fix
|  |  | Acc WC FF.06 | Second Fix
|  |  | Services Cupboard FF.07 | Second Fix
|  |  | Egress Hallway to External Stairs | Second Fix
|  |  | Stairwell FF.10 | Second Fix
Level 2
|  |  | Plasma Donors 2.04 | Second Fix
|  |  | Waiting 2.03 | Second Fix
|  |  | Reception 2.02 | Second Fix
|  |  | Whole Blood Donors 2.05 | Second Fix
|  |  | Refreshment Space 2.06 | Second Fix
|  |  | Interview 2.08 | Second Fix
|  |  | Interview 2.09 | Second Fix
|  |  | Interview 2.10 | Second Fix
|  |  | Interview 2.11 | Second Fix
|  |  | Interview 2.12 | Second Fix
|  |  | Admin Office 2.21 | Second Fix
|  |  | Admin Storage 2.19 | Second Fix
|  |  | Machine Storage 2.18 | Second Fix
|  |  | Consumable Storage 2.17 | Second Fix
|  |  | Consignment 2.16 | Second Fix
|  |  | Quiet / Study 2.15 | Second Fix
|  |  | Nurses Station 2.13 | Second Fix
|  |  | Managers 2.14 | Second Fix
|  |  | Comms 2.20 | Second Fix
|  |  | BOH Hallway / Corridor Areas | Second Fix
|  |  | Lift B | Second Fix
|  |  | Lift A | Second Fix
|  |  | Service Cupboard SF.03 | Second Fix
|  |  | ACC WC SF.04 | Second Fix
|  |  | Lobby SF.05 | Second Fix
|  |  | WC SF.06 | Second Fix
|  |  | WC SF.07 | Second Fix
|  |  | WC SF.08 | Second Fix
|  |  | Cleaner SF.09 | Second Fix
|  |  | WC SF.10 | Second Fix
|  |  | WC SF.11 | Second Fix
|  |  | Lobby SF.012 | Second Fix
|  |  | Service Cupboard SF.14 | Second Fix
|  |  | HWC Cupboard SF.13 | Second Fix
|  |  | Service Room SF.15 | Second Fix
|  |  | DB Cupboard SF.16 | Second Fix
|  |  | Stairwell SF.17 | Second Fix
|  |  | Lift Lobby SF.01 | Second Fix
Completion
Completion
FEL SM Weekly Site Checklist
| 2022-11-21 |  |  | FEL SM Weekly Site Checklist
| 2022-11-28 |  |  | FEL SM Weekly Site Checklist
| 2022-12-05 |  |  | FEL SM Weekly Site Checklist
| 2022-12-12 |  |  | FEL SM Weekly Site Checklist
| 2022-12-19 |  |  | FEL SM Weekly Site Checklist
| 2023-01-09 |  |  | FEL SM Weekly Site Checklist
| 2023-01-16 |  |  | FEL SM Weekly Site Checklist
| 2023-01-23 |  |  | FEL SM Weekly Site Checklist
| 2023-01-30 |  |  | FEL SM Weekly Site Checklist
| 2023-02-06 |  |  | FEL SM Weekly Site Checklist
| 2023-02-13 |  |  | FEL SM Weekly Site Checklist
| 2023-02-20 |  |  | FEL SM Weekly Site Checklist
| 2023-02-27 |  |  | FEL SM Weekly Site Checklist
| 2023-03-06 |  |  | FEL SM Weekly Site Checklist
| 2023-03-13 |  |  | FEL SM Weekly Site Checklist
| 2023-03-20 |  |  | FEL SM Weekly Site Checklist
| 2023-03-27 |  |  | FEL SM Weekly Site Checklist
| 2023-04-03 |  |  | FEL SM Weekly Site Checklist
| 2023-04-10 |  |  | FEL SM Weekly Site Checklist
| 2023-04-17 |  |  | FEL SM Weekly Site Checklist
| 2023-04-24 |  |  | FEL SM Weekly Site Checklist
| 2023-05-01 |  |  | FEL SM Weekly Site Checklist
| 2023-05-08 |  |  | FEL SM Weekly Site Checklist
| 2023-05-15 |  |  | FEL SM Weekly Site Checklist
| 2023-05-22 |  |  | FEL SM Weekly Site Checklist
| 2023-05-29 |  |  | FEL SM Weekly Site Checklist
| 2023-06-05 |  |  | FEL SM Weekly Site Checklist
| 2023-06-12 |  |  | FEL SM Weekly Site Checklist
| 2023-06-19 |  |  | FEL SM Weekly Site Checklist
| 2023-06-26 |  |  | FEL SM Weekly Site Checklist
| 2023-07-03 |  |  | FEL SM Weekly Site Checklist
| 2023-07-10 |  |  | FEL SM Weekly Site Checklist
| 2023-07-17 |  |  | FEL SM Weekly Site Checklist
| 2023-07-24 |  |  | FEL SM Weekly Site Checklist
| 2023-07-31 |  |  | FEL SM Weekly Site Checklist
| 2023-08-07 |  |  | FEL SM Weekly Site Checklist
| 2023-08-14 |  |  | FEL SM Weekly Site Checklist
| 2023-08-21 |  |  | FEL SM Weekly Site Checklist
| 2023-08-28 |  |  | FEL SM Weekly Site Checklist
| 2023-09-04 |  |  | FEL SM Weekly Site Checklist

## First Fix Electrical
type | name
checklist | QA - First Fix
section | Flush Boxes
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Fire rated boxes installed where necessary
checkpoint | Acoustic boxes installed where necessary
section | Cabling
checkpoint | Power cables installed correctly
checkpoint | Lighting cables installed correctly
checkpoint | Power cables wired from correct RCD location
checkpoint | Power circuits comply with medical regulations
checkpoint | Circuits clearly labelled
checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint | All cables secured via cable ties with ends cut
section | Cable Tray
checkpoint | Minimum 25% spare capacity left on cable tray
section | QA - Lights
checkpoint | Setout Correct
checkpoint | Cabling in correct location
checkpoint | Emergency/ Exit Lighting
checkpoint | Nogging installed for Electrical Services
section | Photos

## Cable Tray
Section | Cable Tray
Checkpoint | Unistrutt Filed & Painted
Checkpoint | Hangers Spaced as Specified
Checkpoint | Correct Size Ladder Installed
Checkpoint | Tray Joined Correctly
Checkpoint | Hangers Sceismicly Restrained as per Design
Checkpoint | Tray Fastened to Hangers
Checkpoint | Correct Anchors used fixing to Ceiling / Walls
Checkpoint | Cable Tray Bonded
section | Photos

## Switchboards
section | Switchboard
checkpoint | Spatial certificate signed if required
checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint | All clearances sighted to ensure location is compliant
checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint | Cables neatly dressed
checkpoint | Phase tabs on chassy covered
checkpoint | All earths and neutrals labelled to match phase numbers
checkpoint | Switchboard is clean on the inside and outside
checkpoint | Masking blanks installed
checkpoint | DB legend installed
checkpoint | Feisst label on the door installed
section | Photos

## Second Fix Electrical
type | name | values
checklist | QA - Second fix
section | Power Outlets
checkpoint | Correct type installed ( to comply with medical regulations)
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Outlet Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Switches
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Light switch Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Fixtures
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Tested for operation
checkpoint | Correctly installed with stainless screws & 90 / 45 angle
section | Photos

## Completion
type | name
checklist | QA - Completion
checkpoint | All Areas Defected by SM & Feisst Team prior to PC
checkpoint | All DBs Tested, results uploaded to Drive on iPad and sent to Project Admin
checkpoint | PS3 Completed & Signed for Emergency Lighting
checkpoint | PS3 Completed & Signed for Seismic Bracing of Electrical Fixtures
checkpoint | All COCs completed and Submitted to Julia
checkpoint | "Clean" As Built Set of Drawings Completed and Submitted to Julia
checkpoint | All excess material removed from site and returned to wholesalers
checkpoint | All assets accounted for and removed from site

## SM Weekly Checklist
type | name
checklist | FEL SM Weekly Site Checklist
section | Monday
checkpoint | Prestart Meeting with Team
checkpoint | Health Check
checkpoint | Review Tasks for the week
checkpoint | Identify Targets Including Hours
checkpoint | Approve hours by 9AM for previous week
checkpoint | Sign off Subcontractor Hours & Submit
checkpoint | Review SWMS
checkpoint | Site Toolbox Meeting
checkpoint | SSSP in Order
section | Tuesday
checkpoint | Follow up outstanding RFI's with PM
section | Wednesday
checkpoint | Review Roadblocks & Follow Up if still unresolved
checkpoint | QAs up to date
section | Thursday
checkpoint | Weekly planner filled out for week ahead
checkpoint | Roadblocks identified and actioned
checkpoint | Materials organized for week ahead
checkpoint | Plans printed with any relevant notes added
section | Friday
checkpoint | Submit Toolbox minutes to main contractor and FEL office
checkpoint | Job Cards up to date and submitted
checkpoint | Team tasks for week ahead filled out on whiteboard