## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | QA - Speedwall |  |  |  |  | Yes | QA - Speedwall | 184657a8-2685-4890-9b9d-51ca631275fb
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status |  |  | checkpoint | Area ready for Speedwall install
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Bottom track correctly installed (size, location and fixings)
checkpoint-status |  |  | checkpoint | Top track correctly installed (size, location and fixings)
checkpoint-status |  |  | checkpoint | 30mm minimum gap at head
checkpoint-status |  |  | checkpoint | Install C track Fixings @ 400crs with M6.5 x 32 Mushroom head spikes into concrete
checkpoint-status |  |  | checkpoint | Fixings Hilti X-ENP-19 L15MX fixings 400crs in into steel
checkpoint-status |  |  | checkpoint | 10 x 16 fixings on C-Track to (horizontal panel - vertical C-Track 250crs, horizontal C-Track 400crs) (vertical panel - vertical C-Track 400crs, horizontal C-Track 250crs)
checkpoint-status |  |  | checkpoint | Fire sealant installed correctly and photographed
checkpoint-status |  |  | checkpoint | All joints sealed correctly as per specification
checkpoint-status |  |  | checkpoint | Speedwall installed straight and level
checkpoint-status |  |  | checkpoint | Openings installed for services as per drawings
checkpoint-status |  |  | checkpoint | Speedwall completed within specified tolerance, checked and approved
checkpoint-status |  |  | checkpoint | Speedwall report sent through to client
checklist-flat | 2dc772e3-f8a2-40bc-ae25-1f0e32937a07 |  | checklist | GIB Lining |  |  |  |  | Yes | GIB Lining | 1ba94284-14ef-437f-b4d7-3f938467c70e
checkpoint-status | 9fd0eeea-01a3-4f99-82dc-ab12ab5aa8d7 |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status | 2272a0be-2d68-4156-9a17-adc2fb45e459 |  | checkpoint | Area ready for GIB install
checkpoint-status | e5b864fc-0f23-4733-a923-ccd0ecd2b567 |  | checkpoint | Insulation installed
checkpoint-status | 7aa46461-3f38-411b-b593-0358b52de006 |  | checkpoint | General photos, comments and observations during install
checkpoint-status | adbf1d5b-dbb7-48f3-9bde-2fc35f8709bf |  | checkpoint | Correct lining checked and approved and area specifics checked
checkpoint-status | fd676076-01b2-4643-925e-08062a26c5ef |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | db368c12-fac9-425f-8612-60cf52b3890e |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | 89d10454-7595-4845-8868-a3a439a8f3c2 |  | checkpoint | GIB Lining completed correctly within specified tolerance, checked and approved
checkpoint-status | 6a81160f-3a7a-4e36-883b-7441d5bfe6ea |  | checkpoint | GIB Lining report sent through to client
checklist-flat | c14630ab-4e13-4551-a841-b365be03907d |  | checklist | Internal Steel Stud Walls Checklist |  |  |  |  | Yes | Internal Steel Stud Walls Checklist | 56b05456-168a-4560-885b-401d1e125754
checkpoint-status | 129e813d-58ae-49ac-b15e-37bc75c9309c |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
text | dd7d9ec5-8ae3-52fa-bf05-e75f756dbfd5 |  | textbox | Drawing no.
checkpoint-status | 2ea2051a-4e4a-4cb8-8345-a0acf7bd8df9 |  | checkpoint | Dimensions / locations checked and accurate
checkpoint-status | 38522dff-0def-4871-a6a5-4d177bc97128 |  | checkpoint | All frames are square
checkpoint-status | d5a3d5bb-d13d-482c-ac97-86fac4308359 |  | checkpoint | Frames are straight and level
checkpoint-status | cd10f631-2cdb-4787-9ecc-a8db86627e51 |  | checkpoint | Fixings are correct
checkpoint-status | e286dcb2-9868-404b-bfb8-6057ef3ace24 |  | checkpoint | Any bracing requirements installed
checkpoint-status | e8bc6af9-e49b-459b-a8ba-668b33bedb0c |  | checkpoint | Doors and openings installed as per spec
checkpoint-status | 6a8cda60-0ede-490f-b900-3f93c3a068e4 |  | checkpoint | Nogs / service nogs installed correctly as per plan
checkpoint-status | 199431c6-1a45-43b3-bab5-3a06c9b637fa |  | checkpoint | Any additional photos, comments and observations
checkpoint-status | 7f4121c4-030f-45f2-8178-3a6fc6b8569f |  | checkpoint | All steel stud completed correctly within tolerance in respective area
checkpoint-status | f2a20dc7-f82f-4bf1-a4d7-d0f4331820b6 |  | checkpoint | Report sent through to client
checklist-flat | d53f08f4-4aad-4fdc-af51-c18af63b186f |  | checklist | Villaboard |  |  |  |  | Yes | Villaboard Checklist | 70b79b6f-dd8a-4af2-8ec1-efc5ea749085
checkpoint-status | 3856fc07-569d-459e-b0a3-05911f8d2ec5 |  | checkpoint | Framing set out (ie;stud and nog spacing)
checkpoint-status | 806babef-4a65-4362-b360-1ec60f5ba852 |  | checkpoint | Gib Lining base are secured and flush with each other with no protruding fixings.
checkpoint-status | ba256ed8-7b9e-4d78-9599-9a22ad679a28 |  | checkpoint | Gap between Villaboard edges/joints are at 1-2mm maximum
checkpoint-status | de42766f-3d79-4b06-8e2e-e68599cc9b05 |  | checkpoint | 6mm gap between floor and bottom edge of sheet. 6mm gap between ceiling and top of sheet.
checkpoint-status | 2665285d-5d9d-4c26-ad15-afc739aef4c0 |  | checkpoint | Villaboard must be installed dry.
checkpoint-status | 7b1f6135-d8db-462b-9c66-1232b42fed7e |  | checkpoint | Correct fixings used and installed at correct centres.
checkpoint-status | d8f65752-16ad-4132-81f8-471ac4d399c2 |  | checkpoint | Villaboard report sent through to client.
checklist-flat | bd2c6a4f-e387-4e77-93ef-0e19cdf46363 |  | checklist | Doors |  |  |  |  | Yes | Doors Checklist | c86745f3-5799-40ad-bff6-b0bd9a71cc6a
checkpoint-status | e82604c7-51d3-4d75-8260-ebdfda7f67d1 |  | checkpoint | Installer details input
checkpoint-status | a46c7a0f-b814-4aa7-b691-4ecd3ef80ee3 |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status | 817a0cd8-53b0-4740-a0ae-24ece219a933 |  | checkpoint | Door opening checked and correct
checkpoint-status | 7e76d0d7-6c87-4af0-b252-194592b770d2 |  | checkpoint | Direction of door correct
checkpoint-status | af105858-17d0-424d-834c-51bcc279ab78 |  | checkpoint | Number of screws and hardware location correct
checkpoint-status | b70a7bc9-9003-4f9b-97fd-afa5fedc29eb |  | checkpoint | Door hinges installed in place with correct screws
checkpoint-status | eeaddeb8-8a13-4f3d-98de-c39c90ed0cfd |  | checkpoint | Floor clearance correct
checkpoint-status | 47fec660-9dba-449a-81cc-a9eae362f4bc |  | checkpoint | Undercoat on door surface
checkpoint-status | c79c2bbf-37c3-406c-9405-308181a8a249 |  | checkpoint | Fireseal around door installed as per spec
checkpoint-status | fe9a8af7-30e3-4330-9ad7-2d8ee5fafa20 |  | checkpoint | Door is fully operational after installation
checkpoint-status | e71e5850-202f-4f39-9cbb-8d2504cc01ed |  | checkpoint | Door jambs are plumn and level
checkpoint-status | dbaa0fab-022f-4ed0-a0ed-a7079ad74608 |  | checkpoint | Door gap around door leaf within tolerance
checkpoint-status | a1f58017-b428-4574-b2b5-7e392a3fe884 |  | checkpoint | Door report sent through to client