## ChecklistsITCs
Delete rows that aren't applicable to the project, then create the project breakdown and send to CONQA
type | name | values | prefix | postfix
checklist | Site Establishment and Safety Checklist | Pass, Fail
checkpoint | Delivery and goods lift location
checkpoint | Delivery requirements i.e. booking process
checkpoint | On site storage / office location
checkpoint | Site specific restrictions i.e. noise / starting times
checklist | Ductwork Checklist | Pass, Fail
checkpoint | Rectangular duct installed as per latest drawing | Yes, No
checkpoint | Duct flanges firmly bolted and sealed where required | Yes, No
checkpoint | Cleats installed as required | Yes, No
checkpoint | Correct hanger spacing / supports installed | Yes, No
checkpoint | DW insulated where required and damage free | Yes, No
checkpoint | Ductwork restrained for wind/seismic where required | Yes, No, N/A
checkpoint | Any required ductwork leakage testing | Pass, Fail
checkpoint | Spiral installed as per latest drawing | Yes, No
checkpoint | Spiral joins sealed correctly | Yes, No
checkpoint | Correct hanger spacing / supports installed for spiral | Yes, No
checkpoint | Spiral insulated where required and damage free | Yes, No, N/A
checkpoint | Additional taping/sealing to medium/high pressure spiral | Yes, No, N/A
checkpoint | Pops & flex installed as per latest drawing | Yes, No
checkpoint | Correct hanger spacing / supports installed for flex | Yes, No
checkpoint | Free from support off other services | Yes, No
checkpoint | Flexible duct connections completed correctly | Yes, No
checkpoint | Blade dampers installed as documented and left in the open position | Yes, No
checkpoint | BD pop access panel coordinated and marked | Yes, No, N/A
checkpoint | Cushion boxes installed as per latest drawing | Yes, No
checkpoint | Balancing dampers installed as documented and left in the open position | Yes, No, N/A
checkpoint | Location of register coordinted with other services and marked on plan or floor | Yes, No
checkpoint | Volume Control Dampers installed as per latest drawing | Yes, No
checkpoint | Motorised dampers installed as per latest drawing / actuator fit off | Yes, No, N/A
checkpoint | Smoke dampers installed as per latest drawing / actuator fit off | Yes, No, N/A
checkpoint | Damper access panels coordinated and marked | Yes, No
Checklist | Fire Damper | Pass, Fail
checkpoint | Fire damper installed as per latest drawing | Yes, No
checkpoint | Fire damper installed as per manufacturer's installation guide | Yes, No
checkpoint | Fire Damper labelled with Mechonik's sticker | Yes, No
checkpoint | Damper access installed in duct | Yes, No
checkpoint | Access panel installed on RCP for maintenance/ inspection access | Yes, No
Checklist | Pipework | Pass, Fail
checkpoint | Drain trapped where required | Yes, No
checkpoint | Correct hanger spacing / fall | Yes, No
checkpoint | Drain tested | Pass, Fail
checkpoint | Drain pump installed level and tested | Yes, No
checkpoint | Drain terminates at a tundish | Yes, No
checkpoint | Drains, pump and tundish access for maintenance. | Yes, No
checklist | Indoor Equipment - FCU | Pass, Fail
checkpoint | Indoor Unit (IDU) correctly supported as per project engineering requirements | Yes, No
checkpoint | Correct IDU installed as per latest drawing | Yes, No
checkpoint | Flexible connections installed and sealed | Yes, No
checkpoint | Access to filter bank / filters installed | Yes, No, N/A
checkpoint | Access to all relevant controls and isolators | Yes, No
checkpoint | IDU access panel coordinated and marked | Yes, No
checklist | Indoor Equipment - Fan | Pass, Fail
checkpoint | Ventilation fan correctly supported as per project engineering requirements | Yes, No
checkpoint | Correct fan installed as per latest drawing | Yes, No
checkpoint | Fan connections secured and sealed | Yes, No
checkpoint | Access to fan and isolator | Yes, No
checkpoint | Access to filter bank / filters installed | Yes, No
checkpoint | Ventilation fan access panel coordinated and marked | Yes, No
checklist | Plantroom / Outdoor Equipment | Pass, Fail
checkpoint | AHU correctly supported as per project engineering requirements | Yes, No, N/A
checkpoint | Correct AHU installed as per latest drawing | Yes, No, N/A
checkpoint | Access to filter bank / filters installed | Yes, No, N/A
checkpoint | Access to all relevant controls, isolators and maintenance items | Yes, No, N/A
checkpoint | Floor or Platform Mounted Thermal Plant correctly supported as per project engineering requirements | Yes, No, N/A
checkpoint | Maintenance and ventilation clearance maintained as per manufacturer's specs | Yes, No, N/A
checkpoint | All manufacturer specific requirements have been provided in addition to project requirements | Yes, No, N/A
checklist | Grille Fit-Off Checklist | Pass, Fail, N/A
checkpoint | Grilles installed in correct location as per latest duct layout / RCP | Yes, No
checkpoint | Correct grille type installed | Yes, No
checkpoint | Grille installed flush and square | Yes, No
checkpoint | Are all grilles installed correctly? Air leaks, vibration or failure | Yes, No
checkpoint | Grille color as per schedule | Yes, No
checkpoint | Grille left clean of fingerprints and caps installed where required | Yes, No
checkpoint | Grille fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below) | Yes, No
checklist | Refrigeration Pipe Checklist | Pass, Fail, N/A
checkpoint | Correct IDU & ODU installed as per latest drawing & schedule | Yes, No
checkpoint | Installed as per latest drawings | Yes, No
checkpoint | No other services suspended from pipe work (Attach Photos below) | Yes, No
checkpoint | Installation damage free (Any Issues comment/attach Photos below) | Yes, No
checkpoint | Correct supports used and support spacing | Yes, No
checkpoint | Pipe labelled after insulation - provide photo evidence | Yes, No
checkpoint | Pipe mains installation completed to drawings/specification | Yes, No
checkpoint | Pipework system pressure tested | Pass, Fail, N/A
checkpoint | Area left clean and tidy - photos of cleanliness or issues | Yes, No
checklist | All Subbie Rough-in Progression Checklist | Complete, Incomplete
checkpoint | All work in zone completed and appear compliant | Yes, No
label | Pass once all work complete
checklist | All Subbie Fit off & Testing Progression Checklist | Complete, Incomplete
checkpoint | All work in zone completed and appear compliant | Yes, No
label | Pass once all work complete
checklist | As Builts Checklist | Complete, Incomplete
button | Update As-Built's of any known changes | Yes, No

## TO BUILD - FCU
Project Breakdown |  |  | Checklists
PROJECT NAME: WEST GATE TUNNEL PROJECT FCC OPERATIONS BUILDING
OHS |  |  | Site Establishment and Safety Checklist
| Ground Level | BLG2106-FCU01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU07
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU08
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-BB01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
| Level 1 | BLG2106-FCU09
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU10
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU11
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU12
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU13
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU14
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU15
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU16
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU17
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU18
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU19
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU20
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU21
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU22
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU23
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU24
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU25
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU26
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-BB02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
BLG2106-BB03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
BLG2106-BB04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
BLG2106-BB05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
| Roof Level / Plantroom | BLG2106-FCU27
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU28
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU29
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU30
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU31
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU32
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU33
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-FCU34
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
Grille Fit-Off Checklist
BLG2106-BB06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
BLG2106-BB07
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
BLG2106-CDU01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU07
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU08
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU09
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist

## TO BUILD - Fans
Project Breakdown |  |  | Checklists
PROJECT NAME: WEST GATE TUNNEL PROJECT FCC OPERATIONS BUILDING
OHS |  |  | Site Establishment and Safety Checklist
Site QA | Roof Level / Plantroom | BLG2106-EAF01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Indoor Equipment - Fan
Grille Fit-Off Checklist
BLG2106-EAF02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Indoor Equipment - Fan
Grille Fit-Off Checklist
BLG2106-EAF03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Indoor Equipment - Fan
Grille Fit-Off Checklist
BLG2106-EAF04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Indoor Equipment - Fan
Grille Fit-Off Checklist
BLG2106-EAF05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Indoor Equipment - Fan
Grille Fit-Off Checklist
BLG2106-EAF06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Indoor Equipment - Fan
Grille Fit-Off Checklist
BLG2106-SAF01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Indoor Equipment - Fan
Grille Fit-Off Checklist
BLG2106-SAF02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Indoor Equipment - Fan
Grille Fit-Off Checklist
BLG2106-RAF01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Indoor Equipment - Fan
Grille Fit-Off Checklist
BLG2106-RAF02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Indoor Equipment - Fan
Grille Fit-Off Checklist

## TO BUILD - CRAC
Project Breakdown |  |  | Checklists
PROJECT NAME: WEST GATE TUNNEL PROJECT FCC OPERATIONS BUILDING
OHS |  |  | Site Establishment and Safety Checklist
Site QA | Ground Level | BLG2106-CRC01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
BLG2106-CRC02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
BLG2106-CRC03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
BLG2106-CRC05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
BLG2106-CRC06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Pipework
Indoor Equipment - FCU
Refrigeration Pipe Checklist
| Roof Level / Plantroom | BLG2106-CDU10
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU11
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU12
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU14
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist
BLG2106-CDU15
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Ductwork Checklist
Pipework
Plantroom / Outdoor Equipment
Refrigeration Pipe Checklist

## TO BUILD - Fire Dampers
Project Breakdown |  |  | Checklists
PROJECT NAME: WEST GATE TUNNEL PROJECT FCC OPERATIONS BUILDING
OHS |  |  | Site Establishment and Safety Checklist
Site QA | Ground Level | FD-G.01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.07
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.08
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.09
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.10
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.11
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.12
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.13
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.14
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.15
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.16
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-G.17
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
| Level 1 | FD-1.01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.02
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.03
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.04
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.05
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.06
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.07
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.08
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.09
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.10
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.11
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.12
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.13
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.14
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.15
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.16
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
FD-1.17
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist
| Roof Level / Plantroom | FD-2.01
All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Fire Damper Checklist