## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | FM 03 - Formwork - Columns |  |  |  |  | Yes | FM 03 - Formwork - Columns | 070a5c50-cd26-49e2-b652-669392c5b959
checkpoint-group |  |  | section | Receipt of Materials
checkpoint-status |  |  | checkpoint | Receipt of Material
label | bed533c4-88b6-594c-abae-fe04487146e8 |  | note | TYPE OF INSPECTION - Visual
label | 4c95cec8-52f7-583c-956d-efd67ddd3c69 |  | note | ACCEPTANCE CRITERIA - Contract Drawings
label | aacca211-6d09-5552-85bb-2f1774253f0c |  | note | Shop Drawings
label | 1f2113fc-e33a-5223-a493-532a008d81a9 |  | note | Delivery Dockets
text | 01244195-f11a-5ba8-83e8-2bfafbbadcde |  | textbox | DATE:
button | e7810ab7-730d-5589-b135-7b682294008b |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-group |  |  | section | COLUMNS
checkpoint-status |  |  | checkpoint | Surface Finish
label | f65b4559-39b4-5bcb-bd3c-32b5d990f66b |  | note | TYPE OF INSPECTION - Visual
label | 0fca6189-e39f-55b6-b606-3c302c1dff7c |  | note | ACCEPTANCE CRITERIA - Class 2
label | f47279c7-2ec1-5b16-9c4d-449e2afaab53 |  | note | Structural Spec.
label | c62bec8f-2ba7-5a61-9001-98fcd8acf3a8 |  | note | AS3610-1995
button | 0ae12067-682f-525b-b85c-5d444182b8c3 |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | Dimension / Set Out
label | 3e66a0ef-d690-5069-988b-c5e30c964b90 |  | note | TYPE OF INSPECTION - Tape / Visual
label | 9220cb11-c10b-5529-a7e6-85ae87810bdd |  | note | ACCEPTANCE CRITERIA - Drawings
text | 81b5383c-b757-5b1f-b2f9-e6b109b43182 |  | textbox | DRG. No:
button | c3761dc3-98e6-56cc-9660-9c6699d7c26d |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | Profile / Plumb
label | c8c37734-dd1a-51b2-bb07-60c4ce141c90 |  | note | TYPE OF INSPECTION - Tape / Visual / Survey
label | e08ba652-d8e2-52c2-9437-05ccb8dd060b |  | note | ACCEPTANCE CRITERIA - Drawings
text | df98377c-3482-547a-9ad3-5aba0e4ae4a8 |  | textbox | DRG. No:
button | 9ae73996-9ac3-5c1e-b20e-cc43640f00c0 |  | button | INSPECTED BY - MITCON | Pass,Fail
holdpoint |  |  | signoff | INSPECTED BY - Eng/Surv.
checkpoint-status |  |  | checkpoint | Falsework
label | 5517b638-6261-51bd-a36b-3f7ce8162f96 |  | note | TYPE OF INSPECTION - Tape / Visual
label | 290b07d3-29b4-5ce8-86a7-8c8d272f0c12 |  | note | ACCEPTANCE CRITERIA - Pre-pour Insp.
label | 062c551d-da71-5823-af61-76e908380745 |  | note | AS3610-1995
button | 7092f62b-1db2-50fc-befc-017b87fb0ffd |  | button | INSPECTED BY - MITCON | Pass,Fail
holdpoint |  |  | signoff | INSPECTED BY - Eng/Surv.
checkpoint-status |  |  | checkpoint | Cast In Items
label | fbe9c9ab-e125-5af8-aba8-8be58f3acb8b |  | note | TYPE OF INSPECTION - Tape / Visual / Survey
label | 09a83b82-a57a-5ba7-8f3b-9d6047cb1bcb |  | note | ACCEPTANCE CRITERIA - Drawings
text | c1397679-3836-563b-bb66-e8446a48dd7f |  | textbox | DRG. No:
button | 54da5e6f-1b97-525e-8ba0-45a32285afd7 |  | button | INSPECTED BY - MITCON | Pass,Fail
holdpoint |  |  | signoff | INSPECTED BY - Eng/Surv.
checkpoint-status |  |  | checkpoint | Penos / Block Outs
label | 1a4d7c07-11d3-58ef-817e-7cbf70e16ff2 |  | note | TYPE OF INSPECTION - Tape / Visual
label | 91ea3b07-8c28-5dee-9641-edde00be2758 |  | note | ACCEPTANCE CRITERIA - Drawings
text | 32f63841-b235-51b6-a06a-5603b705c445 |  | textbox | DRG. No:
button | 09b71189-2f66-51eb-be49-8fa8dcfe5d94 |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-group |  |  | section | ASBUILT
checkpoint-status |  |  | checkpoint | ASBUILT
label | b202a43a-85a3-50f3-a976-b89055abd080 |  | note | TYPE OF INSPECTION - Survey
label | 1dcd38ba-108d-5787-84cc-762abb3fc8c8 |  | note | ACCEPTANCE CRITERIA - Drawings
text | ca932df2-a418-5b71-809b-280bd62cf10f |  | textbox | Survey Equipment Serial No.
text | f25bb05a-91f2-5c62-ad04-ded21dc2e015 |  | textbox | Setout
text | 79937090-afb5-57e3-b7e1-fcad4be02229 |  | textbox | Asbuilt
text | e03cc569-8295-5f7f-a5c8-55060dd778c8 |  | textbox | Comments:
checkpoint-group |  |  | section | BUILDER'S APPROVAL REQUIRED PRIOR TO CONCRETE PLACEMENT
checkpoint-no-status |  |  | checkpoint | BUILDER'S APPROVAL REQUIRED PRIOR TO CONCRETE PLACEMENT
select | a445db1b-a4ae-569f-9bcc-5ec27fee6452 |  | dropdown | AREA CONFORMS TO SPECIFICATIONS / CRITERIA ? | Yes,No
select | 2b91188d-8386-5a9d-98f0-125e02208c59 |  | dropdown | IS N.C.R. REQUIRED? | Yes,No
text | 75dbfc7c-46e7-511b-a79c-c4e06e80c777 |  | textbox | Inspected by (Builder):
text | 94a0f7f1-41d3-5949-8f9a-5ee61a6530f0 |  | textbox | Position:
checklist-flat |  |  | checklist | FM 06 - Pre Pour Inspection - (MEVA DECK) |  |  |  |  | Yes | FM 06 - Pre Pour Inspection - (MEVA DECK) | 17638346-5873-4dd6-a57a-fed4c0715217
checkpoint-status |  |  | checkpoint | Sole Boards
checkpoint-status |  |  | checkpoint | Prop spacing & capacity
checkpoint-status |  |  | checkpoint | Prop inclination
checkpoint-status |  |  | checkpoint | MD / ME prop locating pins
checkpoint-status |  |  | checkpoint | MEP Prop - SAS quick lowering system
checkpoint-status |  |  | checkpoint | MD drop heads in pos. & secure
checkpoint-status |  |  | checkpoint | MD prop heads in pos. & secure
checkpoint-status |  |  | checkpoint | Bracing bays correctly located
checkpoint-status |  |  | checkpoint | MEP brace frame - secure
checkpoint-status |  |  | checkpoint | Primary beams - secure
checkpoint-status |  |  | checkpoint | Primary beams - capacity, size, spacing
checkpoint-status |  |  | checkpoint | Secondary beams spacing
checkpoint-status |  |  | checkpoint | MD pans - condition
checkpoint-status |  |  | checkpoint | Infill strips
checkpoint-status |  |  | checkpoint | Forkheads
checkpoint-status |  |  | checkpoint | Cantilevering supports
checkpoint-status |  |  | checkpoint | MD beam stiffeners (cantilevered areas)
checkpoint-status |  |  | checkpoint | Safety chains
checkpoint-status |  |  | checkpoint | Compensation beams
checkpoint-status |  |  | checkpoint | MD assembly locks
checkpoint-status |  |  | checkpoint | Plywood condition
checkpoint-status |  |  | checkpoint | Timber condition
checkpoint-status |  |  | checkpoint | Equipment/System condition
checkpoint-status |  |  | checkpoint | Eccentric loading
holdpoint |  |  | signoff | SIGN OFF
checklist-flat |  |  | checklist | FM 04 - Pre Pour Inspection - (CONVENTIONAL SLABS) |  |  |  |  | Yes | FM 04 - Pre Pour Inspection - (CONVENTIONAL SLABS) | 1cb72e2b-c9e4-440d-a39a-18c3c691b576
checkpoint-status |  |  | checkpoint | Sole Boards
checkpoint-status |  |  | checkpoint | Base Plates
checkpoint-status |  |  | checkpoint | Frame spacing
checkpoint-status |  |  | checkpoint | Frame bracing
checkpoint-status |  |  | checkpoint | Frame extensions
checkpoint-status |  |  | checkpoint | Location pins (telescopic inner)
checkpoint-status |  |  | checkpoint | Bearer size & spacing
checkpoint-status |  |  | checkpoint | Joist size & spacing
checkpoint-status |  |  | checkpoint | Canter levering supports
checkpoint-status |  |  | checkpoint | Prop spacing
checkpoint-status |  |  | checkpoint | Prop bracing
checkpoint-status |  |  | checkpoint | Eccentric loading
checkpoint-status |  |  | checkpoint | Prop inclination
checkpoint-status |  |  | checkpoint | Timber condition
checkpoint-status |  |  | checkpoint | Steel condition
checkpoint-status |  |  | checkpoint | Nails in plates as req'd
checkpoint-status |  |  | checkpoint | Column framing
checkpoint-status |  |  | checkpoint | Column bracing
checkpoint-status |  |  | checkpoint | Plywood Condition
holdpoint |  |  | signoff | SIGN OFF
checklist-flat |  |  | checklist | FM 05 - Pre Pour Inspection - (CONVENTIONAL WALLS) |  |  |  |  | Yes | FM 05 - Pre Pour Inspection - (CONVENTIONAL WALLS) | 2207b22a-5932-4a10-83bf-61907571b115
checkpoint-status |  |  | checkpoint | LVL Whaler condition & spacing
checkpoint-status |  |  | checkpoint | LVL Soldier condition & spacing
checkpoint-status |  |  | checkpoint | Lap & lace of whaler timbers between soldiers Tie rods suitably located
checkpoint-status |  |  | checkpoint | Nuts & plates in pos. & secure
checkpoint-status |  |  | checkpoint | Stop ends suitably secured
checkpoint-status |  |  | checkpoint | Openings & voids suitably secured
checkpoint-status |  |  | checkpoint | Corners suitably secured
checkpoint-status |  |  | checkpoint | Concrete pour rate advised (Ref concrete type / notes)
checkpoint-status |  |  | checkpoint | Push pull props in pos. & secure
checkpoint-status |  |  | checkpoint | Sufficient bracing to support forms
checkpoint-status |  |  | checkpoint | Base of form suitably secured / braced Scaffold brackets correctly pos. & secure Guard rail post in pos. & secure
checkpoint-status |  |  | checkpoint | Pour platform in position and secure
checkpoint-status |  |  | checkpoint | Plywood condition
holdpoint |  |  | signoff | SIGN OFF
checklist-flat |  |  | checklist | F19A – PRE-POUR INSPECTION & TEST PLAN – PT |  |  |  |  | Yes | F19A – PRE-POUR INSPECTION & TEST PLAN – PT | 3ea62c39-dbd1-4d40-981f-3b0464076031
checkpoint-status |  |  | checkpoint | 1. Current Drawings and Revisions
text | d5715dab-1984-597c-8250-4db0acc4a31b |  | textbox | Drawing Number
text | fc485fbe-91d4-5d57-ab28-e9543f56e60c |  | textbox | Revision
select | f1a0da82-de8c-57c0-8e9a-3f4e4331e3cd |  | dropdown | Issued For Construction | Yes,No
checkpoint-status |  |  | checkpoint | 2. Are the Anchorages securely fixed and anti-burst installed?
checkpoint-status |  |  | checkpoint | 3. Is the duct placed in the correct position and alignment, with joints sealed?
checkpoint-status |  |  | checkpoint | 4a. Has the strand been installed with the correct number and type?
checkpoint-status |  |  | checkpoint | 4b. Strand Information
checkpoint-status |  |  | checkpoint | Strand Type
text | 0615914d-6d8e-5420-be37-ba8fdd170e95 |  | textbox | 12.7mm / 15.2mm
text | deea5eee-6c2b-5f8c-8b47-ebec1f71075d |  | textbox | Coil Number
text | d94f408d-25a5-5520-81cd-12a8c780a58e |  | textbox | 12.7mm / 15.2mm
text | 344a9839-9b5b-59d6-bfc4-e3c4124c56ab |  | textbox | Coil Number
text | a4d54ac1-e312-5d20-81c0-b4d007b52a6b |  | textbox | 12.7mm 15.2mm
text | 5870dfcf-d84c-5933-ad00-992a90dd5193 |  | textbox | Coil Number
text | 99b9b96f-e248-52bc-adaa-8b4e03682ee9 |  | textbox | 12.7mm 15.2mm
checkpoint-status |  |  | checkpoint | 5. Are the dead ends, including anti-burst installed (onion or swage)?
checkpoint-status |  |  | checkpoint | 6. Are tendons profiled correctly and supporting chairs secured?
checkpoint-status |  |  | checkpoint | 7. Are grout hoses installed with anchorages sealed?
checkpoint-status |  |  | checkpoint | 8. Has the post-tensioning system been inspected and signed off by an Engineer?
checkpoint-status |  |  | checkpoint | PRE-POUR SIGN OFF
text | bf92eb85-5e7d-50fe-bc71-0eca2a1df6e9 |  | textbox | AusPT LEADING HAND
text | 27e8a3c8-eccb-5514-aac6-bc9ee8273b87 |  | textbox | Date:
holdpoint |  |  | signoff | SIGN OFF
checklist-sectioned |  |  | checklist | FM 03 - Formwork - Beams / Slab |  |  |  |  | Yes | FM 03 - Formwork - Beams / Slab | 41dd5da3-3462-4267-8f17-a522df496d9c
checkpoint-group |  |  | section | Receipt of Materials
checkpoint-status |  |  | checkpoint | Receipt of Material
label | d78fca03-2d6e-53f1-b0b1-29bf1e19e324 |  | note | TYPE OF INSPECTION - Visual
label | 64dbab1e-5355-5c41-9258-63a5b4599991 |  | note | ACCEPTANCE CRITERIA - Contract Drawings
label | 936ac1b1-a974-586a-ad1e-269ad1981575 |  | note | Shop Drawings
label | 68592b9b-f2a6-5c8c-9da5-178d8eb62679 |  | note | Delivery Dockets
text | 98d0b179-ca61-5aba-8b60-bd5b09caf2aa |  | textbox | DATE:
button | a1d65e0d-ad96-5005-9470-6641d1102cea |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-group |  |  | section | BEAMS / SLAB
checkpoint-status |  |  | checkpoint | Surface Finish
label | b5a76712-9050-5af1-9dd1-1b61880bee01 |  | note | TYPE OF INSPECTION - Visual
label | 4583a6c4-a539-5773-bf8c-989184172b68 |  | note | ACCEPTANCE CRITERIA - Class 2
label | 01dc2bdb-e5ce-588e-88c5-87d928476a2c |  | note | Structural Spec.
label | 049d97e3-17c5-5d08-9fcb-a43f8de33e2b |  | note | AS3610-1995
button | 2c4deb45-3c67-56a8-8508-83df2832792a |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | RL's
label | 37b0f5a9-e1e9-5d15-b5e1-06c4453f842c |  | note | TYPE OF INSPECTION - Tape / Visual
label | d17d5e04-70c2-5563-bae3-6758dcd0d147 |  | note | ACCEPTANCE CRITERIA - Drawings
text | d4f369a8-e7c0-50ef-a9c7-aec22965888f |  | textbox | DRG. No:
button | d7acb589-9759-527c-bf65-959a1a858ce7 |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | Dimension / Set Out
label | e357fd7a-7df9-5a01-8402-3ce9ab14820e |  | note | TYPE OF INSPECTION - Tape / Visual
label | 96cbbe51-930d-5850-88a9-ae2ed5387a36 |  | note | ACCEPTANCE CRITERIA - Drawings
text | 0cfa9eb9-5301-52dc-a2df-fd9de24ac2e8 |  | textbox | DRG. No:
button | aefcbe32-b2f7-526b-9bed-dc99b2fb0be3 |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | Profile / Plumb
label | 922d8559-8d7e-5cfe-89c2-f72571082167 |  | note | TYPE OF INSPECTION - Tape / Visual
label | a0672cfd-7f9c-5969-9d33-b14dde6a6da4 |  | note | ACCEPTANCE CRITERIA - Drawings
text | 16c78eee-c0f5-520c-be2f-1ba6dccdd5d2 |  | textbox | DRG. No:
button | 5d09c3c6-cd7d-50dc-8809-b8cc39eaae18 |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | Falsework
label | 9314eed2-232e-5a59-8d2b-cdb70ba964d7 |  | note | TYPE OF INSPECTION - Visual / Engineer
label | 68f5914d-9d7a-515e-b57d-98ddd791eff3 |  | note | ACCEPTANCE CRITERIA - Pre-pour Insp. AS3610-1995
button | e7f37369-5d85-526a-bbce-1f478083e2c5 |  | button | INSPECTED BY - MITCON | Pass,Fail
holdpoint |  |  | signoff | INSPECTED BY - Eng/Surv.
checkpoint-status |  |  | checkpoint | Cast In Items
label | a935bad4-6e2e-5430-8c8a-5ecdef5c88e1 |  | note | TYPE OF INSPECTION - Tape / Visual / Survey
label | c20a6ea6-34f0-5dcf-87a9-9cef99ea44c7 |  | note | ACCEPTANCE CRITERIA - Drawings
text | 04e28a4f-5336-53aa-831a-bcd8f15bd968 |  | textbox | DRG. No:
button | 36754629-5406-5cd5-8951-c0f584fe0f06 |  | button | INSPECTED BY - MITCON | Pass,Fail
holdpoint |  |  | signoff | INSPECTED BY - Eng/Surv.
checkpoint-status |  |  | checkpoint | Penos / Block Outs
label | f8e9f561-dede-5ad4-87f3-90d39b13529d |  | note | TYPE OF INSPECTION - Tape / Visual
label | 30e4b42e-71b0-50df-bd35-c65783c61723 |  | note | ACCEPTANCE CRITERIA - Drawings
text | 08854e91-499e-522a-bff1-a6d5808666d0 |  | textbox | DRG. No:
button | 4746fb65-1f44-58f1-8b00-5efbc873f5d8 |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-group |  |  | section | ASBUILT
checkpoint-status |  |  | checkpoint | ASBUILT
label | 9c99bce1-f637-59f4-9f7f-9d4383c502a1 |  | note | TYPE OF INSPECTION - Survey
label | 6e166b86-32f6-5dce-8d90-46db925d20e8 |  | note | ACCEPTANCE CRITERIA - Drawings
text | 380d5492-418c-5374-aec7-ddd13a5d111e |  | textbox | Survey Equipment Serial No.
text | 3122d1eb-f046-5698-814a-5719ed503478 |  | textbox | Setout
text | 708be4f2-1b6a-5d4b-96d4-160d13397c8c |  | textbox | Asbuilt
text | eb78f4b5-4da8-5411-8586-b47de415b7a6 |  | textbox | Comments:
checkpoint-group |  |  | section | BUILDER'S APPROVAL REQUIRED PRIOR TO CONCRETE PLACEMENT
checkpoint-no-status |  |  | checkpoint | BUILDER'S APPROVAL REQUIRED PRIOR TO CONCRETE PLACEMENT
select | f8314224-02bf-511d-9d19-1c2d41e8afcf |  | dropdown | AREA CONFORMS TO SPECIFICATIONS / CRITERIA ? | Yes,No
select | 0e329ccf-8731-511e-97a9-b9e2c3db24d8 |  | dropdown | IS N.C.R. REQUIRED? | Yes,No
text | 611a6b70-2392-5e54-aa92-6100c1108cb7 |  | textbox | Inspected by (Builder):
text | fcc7f2c4-e747-544c-b5be-b5efeab12dec |  | textbox | Position:
checklist-flat |  |  | checklist | FM 13 - Pre Pour Inspection - (Easy Stair) |  |  |  |  | Yes | FM 13 - Pre Pour Inspection - (Easy Stair) | 53d0d910-27f0-49be-90e5-637100f1f1dc
checkpoint-status |  |  | checkpoint | Mid Landing Prop Spacing
checkpoint-status |  |  | checkpoint | Primary Bearer Spacing
checkpoint-status |  |  | checkpoint | Secondary Bearer Spacing
checkpoint-status |  |  | checkpoint | Top Landing Prop Spacing
checkpoint-status |  |  | checkpoint | Stair throat Prop Spacing
checkpoint-status |  |  | checkpoint | Ezy stairs fixed in position
checkpoint-status |  |  | checkpoint | Handrail attached
holdpoint |  |  | signoff | SIGN OFF
checklist-flat |  |  | checklist | F19B – POST-POUR INSPECTION & TEST PLAN – PT |  |  |  |  | Yes | F19B – POST-POUR INSPECTION & TEST PLAN – PT | 6bcb8014-4e9d-4f05-94aa-f4227cb39fa6
checkpoint-status |  |  | checkpoint | 1. Current Drawings and Revisions
text | 6ed55426-3d72-5aeb-99e7-38e5317cebcc |  | textbox | Drawing Number
text | e7348b10-b5f2-5028-b62d-f8d4109208ca |  | textbox | Revision
select | b2e17bf3-5a7a-5126-b002-cd2089489cd1 |  | dropdown | Issued For Construction | Yes,No
checkpoint-status |  |  | checkpoint | 2. Are the anchor blocks and wedges installed?
checkpoint-status |  |  | checkpoint | 3. Has an initial stress been carried out as per design requirements?
checkpoint-status |  |  | checkpoint | 4. Has AusPT sighted the concrete test report prior to commencement of full stress?
checkpoint-status |  |  | checkpoint | 5. Has the concrete test results reached minimum required strength as per Engineer’s requirements?
checkpoint-status |  |  | checkpoint | 6. Has a full stress been carried out as per the design requirements?
checkpoint-status |  |  | checkpoint | 7. Have the extensions been recorded and submitted?
checkpoint-status |  |  | checkpoint | 8. Have the extensions been approved and received?
checkpoint-status |  |  | checkpoint | 9. Have the tendons been cut & sealed?
checkpoint-status |  |  | checkpoint | 10. Have the tendons been grouted?
checklist-flat |  |  | checklist | Concrete Delivery Checklist |  |  |  |  | Yes | Concrete Delivery Checklist | 748b5392-54ee-4715-9b68-1f7c5a1a4cf0
checkpoint-status |  |  | checkpoint | Concrete Record
text | 23b13524-e188-53a9-81fa-3c21a7d5ee74 |  | textbox | LOCATION OF POUR:
text | e9fda373-9f7f-5550-9920-5a1e50e4c648 |  | textbox | SUPPLIER:
text | f792ac09-ab04-554f-8b1c-774f0b8cecf7 |  | textbox | OVERALL QUANTITY: |  |  | M3
text | 741b976f-a7e7-5276-b5c8-28ea801d99fc |  | textbox | CONCRETE STRENGTH: |  |  | Mpa
select | 6f032543-548e-5629-b47e-00ce36242197 |  | dropdown | DELIVERED TO LOCATION BY: | PUMP-LINE,MOBILE BOOM,TOWER BOOM,KIBBLE,Other
text | 00b530d5-5736-55b2-9edc-1e0d1bb38d7b |  | textbox | DOCKET NUMBERS:
select | 7331ab22-e467-57e7-a69d-e2990fd22622 |  | dropdown | ON SITE TESTING REQ'D: | Yes,No
checklist-sectioned |  |  | checklist | FM 03 - Formwork - Walls / Shafts |  |  |  |  | Yes | FM 03 - Formwork - Walls / Shafts | 96f6974a-b209-44b9-bccc-b4aa9addb6ae
checkpoint-group |  |  | section | Receipt of Materials
checkpoint-status |  |  | checkpoint | Receipt of Material
label | bd51afb3-28fa-5073-8f0d-9d5f311cbe1a |  | note | TYPE OF INSPECTION - Visual
label | 5283cc8a-3138-596c-94a8-414a2cfe1f4f |  | note | ACCEPTANCE CRITERIA - Contract Drawings
label | 99da0e05-9864-506b-8b30-6d46254ba57f |  | note | Shop Drawings
label | 41baf70b-aba5-5766-be44-3a5cd7ed3ac5 |  | note | Delivery Dockets
text | 46d88a35-b0d1-568e-8a7d-c45449c60f56 |  | textbox | DATE:
button | db7bb0a8-4ccc-5d6f-b07f-522aa4d96183 |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-group |  |  | section | WALLS / SHAFTS
checkpoint-status |  |  | checkpoint | Surface Finish
label | 5f942976-5396-5e35-9ce8-b5fabd67a98e |  | note | TYPE OF INSPECTION - Visual
label | b4530ac9-b1c0-52fb-a74a-89d8f161211d |  | note | ACCEPTANCE CRITERIA - Class 2
label | 520558a9-8a31-551d-87fa-44e5d38b4626 |  | note | Structural Spec.
label | 22bac868-bf95-5886-83b6-edcb29541187 |  | note | AS3610-1995
button | d3ee636e-8495-5727-a811-7ca7d722efad |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | Dimension / Set Out
label | bab28b63-ffed-5555-aaf9-a7b68e3d9a16 |  | note | TYPE OF INSPECTION - Tape / Visual / Survey
label | d534e04e-756a-572e-b312-a4041fea8b87 |  | note | ACCEPTANCE CRITERIA - Drawings
text | 69038ce9-9c08-5bd4-ae9c-2969b172fd61 |  | textbox | DRG. No:
button | 43b2689f-a0aa-5b72-a531-1f2b0cca7b94 |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | Profile / Plumb
label | b0356e41-c467-5aaf-bf59-e06f236861f2 |  | note | TYPE OF INSPECTION - Tape / Visual / Survey
label | b61879e8-a27d-55eb-8c68-c09697993b3a |  | note | ACCEPTANCE CRITERIA - Drawings
text | 91358f45-7518-5d0b-b6c7-2656c2357783 |  | textbox | DRG. No:
button | b6b4c761-f222-56c6-93e5-2ba83c69be95 |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | Falsework
label | d850ac6f-8856-519c-9018-3cdf4af51314 |  | note | TYPE OF INSPECTION - Visual / Engineer
label | 7a6b3eeb-34f3-5558-bed5-1922e40dccd8 |  | note | ACCEPTANCE CRITERIA - Pre-pour Insp. AS3610-1995
button | 2715aa5f-b3f1-5768-ae10-b77ff1c5a68c |  | button | INSPECTED BY - MITCON | Pass,Fail
holdpoint |  |  | signoff | INSPECTED BY - Eng/Surv.
checkpoint-status |  |  | checkpoint | Cast In Items
label | c9ffe94f-fd3c-5f84-9615-27ca5b564a5e |  | note | TYPE OF INSPECTION - Tape / Visual / Survey
label | e9788f95-666d-5256-ad86-e172051d5874 |  | note | ACCEPTANCE CRITERIA - Drawings
text | 4ff47774-0d9b-52d8-bdeb-255222e90080 |  | textbox | DRG. No:
button | da256d0f-b058-558c-ab90-39b41e972729 |  | button | INSPECTED BY - MITCON | Pass,Fail
holdpoint |  |  | signoff | INSPECTED BY - Eng/Surv.
checkpoint-status |  |  | checkpoint | Penos / Block Outs
label | 20eb0e60-549a-563a-bdba-df61ff045fc4 |  | note | TYPE OF INSPECTION - Tape / Visual
label | 3247dbc5-5b66-5102-b36f-17682b62809c |  | note | ACCEPTANCE CRITERIA - Drawings
text | e1697123-806b-54cb-a117-af2aee4310c1 |  | textbox | DRG. No:
button | 4bfe2929-3c0c-5422-b448-f321b11c926f |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-group |  |  | section | ASBUILT
checkpoint-status |  |  | checkpoint | ASBUILT
label | 73b1569b-62a9-5801-9bdc-dc9aa4b8fcb9 |  | note | TYPE OF INSPECTION - Survey
label | 640876d3-9e21-57a3-a373-57a4e6b699e2 |  | note | ACCEPTANCE CRITERIA - Drawings
text | 43ce9eb1-fa59-5c36-baec-fce2396085f5 |  | textbox | Survey Equipment Serial No.
text | 7ccace76-1111-5d89-bb7a-f3fc162cfdd3 |  | textbox | Setout
text | 3c7d3b2d-1e0c-58ae-948b-027880302e89 |  | textbox | Asbuilt
text | 8dad0d51-4a8f-500d-a7b3-f11abb9cdf2a |  | textbox | Comments:
checkpoint-group |  |  | section | BUILDER'S APPROVAL REQUIRED PRIOR TO CONCRETE PLACEMENT
checkpoint-no-status |  |  | checkpoint | BUILDER'S APPROVAL REQUIRED PRIOR TO CONCRETE PLACEMENT
select | e7d636e5-8bd1-56da-8387-fe2d53026d1b |  | dropdown | AREA CONFORMS TO SPECIFICATIONS / CRITERIA ? | Yes,No
select | 168d6474-05a4-5710-876d-c93934d207d6 |  | dropdown | IS N.C.R. REQUIRED? | Yes,No
text | ff056297-d525-5e25-bd12-58b852150170 |  | textbox | Inspected by (Builder):
text | 6ce94f48-f861-56fb-bf73-b4d2e9409c1d |  | textbox | Position:
checklist-flat |  |  | checklist | FM 07 - Pre Pour Inspection - (MEVA WALL FORMWORK) |  |  |  |  | Yes | FM 07 - Pre Pour Inspection - (MEVA WALL FORMWORK) | 984e9ac8-aabd-4667-9190-9f29ef6098e8
checkpoint-status |  |  | checkpoint | Startec panel condition
checkpoint-status |  |  | checkpoint | Alustar panel condition
checkpoint-status |  |  | checkpoint | Mammut panel condition
checkpoint-status |  |  | checkpoint | Alkus / Plywood surface condition
checkpoint-status |  |  | checkpoint | Shutter / panel configuration
checkpoint-status |  |  | checkpoint | Tie rods suitably located
checkpoint-status |  |  | checkpoint | Nuts & plates in pos. & secure
checkpoint-status |  |  | checkpoint | Assembly locks - correctly positioned
checkpoint-status |  |  | checkpoint | Uni assembly locks - correctly positioned
checkpoint-status |  |  | checkpoint | Alignment rails in pos. & secure
checkpoint-status |  |  | checkpoint | Stop ends suitably secured
checkpoint-status |  |  | checkpoint | Openings & voids suitably secured
checkpoint-status |  |  | checkpoint | Corners in pos, & secure
checkpoint-status |  |  | checkpoint | Hinged corners in pos. & secure
checkpoint-status |  |  | checkpoint | Infill strips suitably reinforced (Align. Rails!)
checkpoint-status |  |  | checkpoint | Flange screws - secure
checkpoint-status |  |  | checkpoint | Concrete pour rate advised (Ref concrete type / notes)
checkpoint-status |  |  | checkpoint | Push pull props in pos. & secure
checkpoint-status |  |  | checkpoint | Sufficient bracing to support forms
checkpoint-status |  |  | checkpoint | Scaffold brackets correctly pos. & secure
checkpoint-status |  |  | checkpoint | Guard rail post in pos. & secure
checkpoint-status |  |  | checkpoint | Pour platform in position and secure
checkpoint-status |  |  | checkpoint | Timber condition
checkpoint-status |  |  | checkpoint | Plywood condition
holdpoint |  |  | signoff | SIGN OFF
checklist-flat |  |  | checklist | FM 08 - Pre Pour Inspection - (METAL DECK KF57) p2 |  |  |  |  | Yes | FM 08 - Pre Pour Inspection - (METAL DECK KF57) p2 | ab4b8425-e8f1-44df-9c7d-dd7733d6aec5
checkpoint-status |  |  | checkpoint | Sole Boards
checkpoint-status |  |  | checkpoint | Base Plates
checkpoint-status |  |  | checkpoint | Frame spacing
checkpoint-status |  |  | checkpoint | Frame bracing
checkpoint-status |  |  | checkpoint | Frame extensions
checkpoint-status |  |  | checkpoint | Location pins (telescopic inner) Bearer size & spacing
checkpoint-status |  |  | checkpoint | Joist size & spacing Canter levering supports Prop spacing
checkpoint-status |  |  | checkpoint | Prop bracing
checkpoint-status |  |  | checkpoint | Eccentric loading
checkpoint-status |  |  | checkpoint | Prop inclination
checkpoint-status |  |  | checkpoint | Timber condition
checkpoint-status |  |  | checkpoint | Steel condition
checkpoint-status |  |  | checkpoint | Nails in plates as req'd
holdpoint |  |  | signoff | SIGN OFF
checklist-sectioned |  |  | checklist | FM 13 - ITP - Concrete |  |  |  |  | Yes | FM 13 - ITP - Concrete | b87615e5-0fc1-49d3-89c3-4b12cef2e737
checkpoint-group |  |  | section | Reo Pre-pour Check
checkpoint-status |  |  | checkpoint | Engineer's Inspection completed and approval/comments attached
checkpoint-group |  |  | section | Services, Builder to confirm (HOLD POINT)
checkpoint-status |  |  | checkpoint | Services
holdpoint |  |  | signoff | SIGN OFF
checkpoint-status |  |  | checkpoint | Plumbing inserts installed
checkpoint-status |  |  | checkpoint | Electrical conduits in place
checkpoint-status |  |  | checkpoint | Penetrations, setdowns and inserts installed
checkpoint-group |  |  | section | Concrete Pre-pour Inspections
checkpoint-status |  |  | checkpoint | Concrete Delivery Checklist Completed
label | 89e6f71a-9734-59d0-84be-f4f6c07268ca |  | note | Refer to Concrete Delivery Checklist
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Concrete dockets copied and attached
checkpoint-status |  |  | checkpoint | Work area is clean
checkpoint-status |  |  | checkpoint | Spot level checks performed
checkpoint-status |  |  | checkpoint | QA documents submitted to Builder
checkpoint-status |  |  | checkpoint | Test results to be forwarded once received
checklist-sectioned |  |  | checklist | Vesta Pre-pour Check |  |  |  |  | Yes | Vesta Pre-pour Check | f020b964-4a99-4772-b98d-7b692c1c45e3
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Steel has been inspected and has been installed as per the latest structural drawings. Eg. Ligatures and Bars positioned correctly
checkpoint-status |  |  | checkpoint | All Cast in Elements installed and to the correct locations. Eg. Threaded Couplers, and Cast in Items installed to correct spec and location, RL.
checkpoint-status |  |  | checkpoint | Provide adequate cover to beam, top and bottom reinforcement of slab.
label | 1ea3782b-53ef-5e58-8ba8-6792663a3cce |  | note | -Measure and check cover of reinforcement against formwork is as specified
label | 3bee0de5-7f6f-5c89-8120-0242f3cf0968 |  | note | -Minimum cover to elements as per point 9 of the concrete notes on drawing S001 Stage C.
checkpoint-status |  |  | checkpoint | Ensure reinforcement has been properly tied and structure is rigid as per specifications
label | 62eb6328-33bd-5142-8816-efc537712a16 |  | note | - Tie wire to be Annealed steel 1.25 mm diameter (minimum)
label | c050d52a-39d0-5ea2-ac8c-424fab07e762 |  | note | - Reinforcement Bar Correct Size
checkpoint-status |  |  | checkpoint | Steel surface condition free from thick rust, grease, mud etc.
checkpoint-status |  |  | checkpoint | Ensure reinforcement has been properly tied and the below lap lengths maintained.
checkpoint-status |  |  | checkpoint | Concrete pour area cleaned of steel fixers off-cuts and other steel fixers rubbish
holdpoint |  |  | signoff | SIGN OFF
checklist-flat |  |  | checklist | FM 14 - Pre Pour Inspection - (prefab column tubes). |  |  |  |  | Yes | FM 14 - Pre Pour Inspection - (prefab column tubes). | f6e49165-2e1b-4ce4-af34-8576dbe3fd3f
checkpoint-status |  |  | checkpoint | 1. Manufacturer recognised quality check is clearly visible on the external of the column tube
checkpoint-status |  |  | checkpoint | 2. Tube Damage - External liner
checkpoint-status |  |  | checkpoint | 3. Tube Damage - Internal liner
checkpoint-status |  |  | checkpoint | 4. Column end tape in position,secure and free from deterioration
checkpoint-status |  |  | checkpoint | 5. Stripping tape - long section to the top & short section at the base of the column
checkpoint-status |  |  | checkpoint | 6. Stripping tape orientation facing internal of the building (where possible - subject to architectural requirement!)
checkpoint-status |  |  | checkpoint | 7. Column base support / plywood yolks in position & secure - column tube captive
checkpoint-status |  |  | checkpoint | 8. Column top support / plywood yolks in position & secure - column tube captive
checkpoint-status |  |  | checkpoint | 9. Column Uplift restraints in position & secure - Timber secure through reo cage at top of column and fix with approved anchor to formwork deck
checkpoint-status |  |  | checkpoint | 10. Column Uplift restraints in position & secure - Nails at base through the tube
checkpoint-status |  |  | checkpoint | 11. Floor surface at base of column is level & even without gaps allowing leakage
checkpoint-status |  |  | checkpoint | 12. Concrete placement rate restrictions m/hr (if any) are discussed with concrete contractor
checkpoint-status |  |  | checkpoint | 13. Concrete discharge height limitations - refer to specification / minimise where possible
holdpoint |  |  | signoff | SIGN OFF
checklist-sectioned |  |  | checklist | FM 03 - Formwork - Stairs |  |  |  |  | Yes | FM 03 - Formwork - Stairs | f93f38db-0c47-4309-80c0-6ba306d3acf4
checkpoint-group |  |  | section | Receipt of Materials
checkpoint-status |  |  | checkpoint | Receipt of Material
label | cfa1c067-b796-5c71-858d-3ec1937c5860 |  | note | TYPE OF INSPECTION - Visual
label | 2b78d85a-5c3e-5dc4-8a57-712c62d99d91 |  | note | ACCEPTANCE CRITERIA - Contract Drawings
label | d9059a44-3616-5f3c-be06-30b8bde8fa30 |  | note | Shop Drawings
label | 3829f89d-1b5e-5780-ae50-1d17f5bc8f87 |  | note | Delivery Dockets
text | d1d2bae3-e7f2-543a-8e72-b7bbe4b18781 |  | textbox | DATE:
button | 3f0fa1eb-5adb-5a71-b1ad-53773960c705 |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-group |  |  | section | STAIRS
checkpoint-status |  |  | checkpoint | Surface Finish
label | 3b223829-4e95-58ab-bfef-a66ada9cc372 |  | note | TYPE OF INSPECTION - Visual
label | 4e0ec2a1-c1c9-50fa-8d49-3c2f0b7bb63f |  | note | ACCEPTANCE CRITERIA - Class 2
label | dc696882-91e4-56a5-99ee-b7c7092d6a54 |  | note | Structural Spec.
label | a6228173-3a20-55cd-ab23-38e44ea61172 |  | note | AS3610-1995
button | 9564ea60-53ba-5ccd-bb06-ab5a9634d5ed |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | Dimension / Set Out
label | a091b923-8564-5fa2-a6cd-409876e9064e |  | note | TYPE OF INSPECTION - Tape / Visual
label | 1499d2bd-6cb1-5f3e-bd53-de8b3da9b5b4 |  | note | ACCEPTANCE CRITERIA - Drawings
text | 14bbef27-945c-5736-b081-2676ce6813d0 |  | textbox | DRG. No:
button | 19b61feb-aace-554d-964a-1e908c90b83b |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | Profile / Plumb
label | bf0e3281-4dd7-5123-9103-6fb18993b28a |  | note | TYPE OF INSPECTION - Tape / Visual
label | 960e8ba6-a10b-5723-8849-0f5bb2630c8f |  | note | ACCEPTANCE CRITERIA - Drawings
text | 45817df8-3f9b-5a86-99dc-67c97b05e9df |  | textbox | DRG. No:
button | 22b44d3a-dd97-5cb2-87c5-fbd363c61b48 |  | button | INSPECTED BY - MITCON | Pass,Fail
checkpoint-status |  |  | checkpoint | Falsework
label | 91d7b065-43af-5b13-9f67-c20f6ce3ca9d |  | note | TYPE OF INSPECTION - Tape / Visual
label | ea2408cd-d3e3-50d7-bb17-3478d9ccabc9 |  | note | ACCEPTANCE CRITERIA - Pre-pour Insp.
label | 1246e045-02a3-5249-9857-53c39b057a94 |  | note | AS3610-1995
button | 45b4e0ed-b44c-59bf-9ab0-d452f1fccb93 |  | button | INSPECTED BY - MITCON | Pass,Fail
holdpoint |  |  | signoff | INSPECTED BY - Eng/Surv.
checkpoint-group |  |  | section | ASBUILT
checkpoint-status |  |  | checkpoint | ASBUILT
label | f72b63fa-adae-5b50-a18e-6eb55331d2c5 |  | note | TYPE OF INSPECTION - Survey
label | 7c3baeec-9871-526b-b28a-f98006bdf488 |  | note | ACCEPTANCE CRITERIA - Drawings
text | f97ddc97-2731-5952-99cf-abec6483f6a9 |  | textbox | Survey Equipment Serial No.
text | 40e2cda8-2ce1-596a-ac72-a6cbc3a4905d |  | textbox | Setout
text | fa0d182e-2925-5d41-9fbd-5717f3364ce7 |  | textbox | Asbuilt
text | abecfff8-3fbf-57eb-a512-7d28f8d667ac |  | textbox | Comments:
checkpoint-group |  |  | section | BUILDER'S APPROVAL REQUIRED PRIOR TO CONCRETE PLACEMENT
checkpoint-no-status |  |  | checkpoint | BUILDER'S APPROVAL REQUIRED PRIOR TO CONCRETE PLACEMENT
select | 5b40ad63-ec2f-52c4-8f85-6cf7e24a6f59 |  | dropdown | AREA CONFORMS TO SPECIFICATIONS / CRITERIA ? | Yes,No
select | 84761f47-ab12-5be7-84b9-3e6f0551c546 |  | dropdown | IS N.C.R. REQUIRED? | Yes,No
text | b909539c-0c35-5718-868c-82e0c0cf28ac |  | textbox | Inspected by (Builder):
text | 717f5e42-b84e-510f-a732-969cdf68090a |  | textbox | Position: